## Readme
Notes: This excel file presents in a different format part of the informations included in the appendix 1.1 of the TYNDP 2014 report. It includes two sheets, one focused on the list of projects of pan-European significance and their subsequents investments. The second sheet is focused on the CBA indicators of the TYNDP 2014 projects of pan-European significance. For a complete and detailed overview of each project, please always refer to the TYNDP 2014 report - appendix 1.1

## Investments
Project Index | Project name | Investment index | Substation 1 | Substation 2 | Description | Expected date of commissioning | Present status | Evolution since TYNDP 2012 | Evolution driver
1 | RES in north of Portugal
|  | 1 | V.Minho (PT) | Pedralva (PT) | Connection of the new 400kV substation V.Minho to Pedralva substation by means of two new 400kV lines(2x43)km. The realization of this two connections can take advantage of some already existing 150kV single lines, which will be reconstructed as double circuit lines 400+150kV line and partially sharing towers with those 400kV circuits. | 2015 | Under Construction | Delayed | Although the investment is already under construction some constraints regarding environmental issues led the commissioning date to delay
|  | 2 | Pedralva (PT) | Sobrado (PT) | New 47km double circuit Pedralva (PT) - Sobrado (PT) 400kV OHL, (only one circuit installed in a first step). | 2020 | Planning | Delayed | Due to the expected delay of the connection of new RES generation in North of Portugal, the commissioning date of this investment item is delayed
|  | 3 | Pedralva (PT) | V. Castelo (PT) | New 57,5km double circuit Pedralva - V. Castelo 400kV OHL (one circuit installed). | 2015 | Design & Permitting | Investment on time | Investment on time
|  | 4 | V.Minho (by Ribeira de Pena and Fridão) | Feira (by Ribeira de Pena and Fridão) | New 129km double-circuit 400kV OHL V.Minho (PT) - Ribeira de Pena (PT) - Fridão (PT) - Feira (PT) (one circuit operated at 220kV between V.P. Aguiar and Estarreja) with a new 400/60kV substation in Rib. Pena. In a first step, only the 139km section Rib. de Pena (PT) - Feira (PT) will be constructed and operated at 220kV as Vila Pouca Aguiar (PT) - Carrapatelo (PT) - Estarreja (PT). In a second step, one circuit of this line will be operated at 400kV. | 2018 | Design & Permitting | Delayed | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was delayed.
|  | 474 | Ribeira de Pena (PT) |  | New 400/60kV substation in Rib. Pena. | 2017 | Design & Permitting | Delayed | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was delayed.
|  | 476 | V. P. Aguiar (by Carrapatelo) | Estarreja (by Carrapatelo) | New 400+220kV double circuit OHL (initially only used at 220kV) Vila Pouca Aguiar - (Rib. Pena) - Carrapatelo - Estarreja . Total length of line: 2x(96+49)km. 220kV circuit. | 2017 | Design & Permitting | Delayed | Due to the expected delay of the connection of new RES generation in Portugal, the commissioning date of this investment item is delayed
|  | 941 | Fridão |  | New substation to connect a new hydro power plant. | 2017 | Planning | New Investment | No changes expected
2 | RES in center of Portugal
|  | 8 | Seia | Penela | New single circuit 400kV OHL Seia-Penela (90km). | 2016 | Design & Permitting | Investment on time | Project on time
|  | 9 | Fundão (PT) | Falagueira (PT) | New 400kV double circuit OHL Fundão (PT) -'Castelo Branco zone'-Falagueira (PT) | 2017 | Design & Permitting | Delayed | Adjustments resulting from the new date of renewables projects.
|  | 478 | Penela (PT) | Paraimo / Batalha (PT) | New double circuit 400kV OHL (15km) to connect Penela substation to Paraimo-Batalha line. | 2016 | Design & Permitting | Investment on time | design & permitting
|  | 481 | Penela (PT) |  | Expansion of the existing Penela substation to include 400kV facilities. | 2016 | Design & Permitting | Investment on time | Design & Permitting
|  | 484 | Fundão (PT) |  | New 400/220kV substations in Fundão. | 2017 | Design & Permitting | Delayed | Due to the expected delay on the connection of new RES generation in the centre of Portugal, the commissioning date of this investment item is delayed
4 | Interconnection Portugal-Spain
|  | 18 | Beariz (ES) | Fontefria (ES) | New northern interconnection. New double circuit 400kV OHL between Beariz (ES) - Fontefria (ES). | 2016 | Design & Permitting | Delayed | Delays in authorization process due to a change on the route and on the location of substations, induced by environmental concerns
|  | 496 | Fontefría (ES) | Vila do Conde (PT) (By Viana do Castelo) | New northern interconnection. New 400kV OHL Fontefría (ES) - Viana do Castelo (PT) - Vila do Conde (PT). | 2016 | Design & Permitting | Delayed | Delays in authorization process due to a change on the route and on the location of substations were induced by environmental concerns
|  | 497 | Vila do Conde (PT) | Recarei/Vermoim (PT) | New double circuit 400kV OHL between Vila do Conde (PT) - Recarei/Vermoim (PT). | 2015 | Design & Permitting | Delayed | Partial sections from the line found environmental problems in his original route. The problems are being solved with the identification of new routes, prompting a delay in the commissioning date.
|  | 498 | Fontefria (ES) |  | New northern interconnection. New 400kV substation Fontefria (ES), previously O Covelo. | 2016 | Design & Permitting | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 18
|  | 499 | Beariz (ES) |  | New northern interconnection. New 400kV substation Beariz (ES), previously Boboras | 2016 | Design & Permitting | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 18
|  | 500 | V. Castelo (PT) |  | New 400/150kV substation V.Castelo (PT). | 2016 | Design & Permitting | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 496.
|  | 501 | Vila do Conde (PT) |  | New 400kV substation Vila do Conde (PT). | 2015 | Design & Permitting | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 497.
5 | Eastern interconnection ES-FR
|  | 36 | Sta.Llogaia (ES) | Baixas (FR) | New HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors and converters in both ending points. | 2015 | Under Construction | Delayed | Answering all concerns expressed during the authorization process in Spain and environmental issues in France led to postponing the investment. Both issues are solved by now.
|  | 505 | Sta.Llogaia (ES) |  | Converter station of the new HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors. | 2015 | Under Construction | Delayed | Works completed in 2014; commercial operation expected after test period at the same time as the cable (investment 36).
|  | 506 | Baixas (FR) |  | Converter station of the new HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors. | 2015 | Under Construction | Delayed | Works completed in 2014; commercial operation expected after test period at the same time as the cable (investment 36).
13 | Baza project
|  | 31 | Caparacena (ES) | La Ribina (ES) | New double circuit Caparacena-Baza-La Ribina 400kV OHL. | 2025 | Under Consideration | Rescheduled | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress
|  | 569 | Baza (ES) |  | New 400kV substation in Baza | 2025 | Under Consideration | Rescheduled | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress
|  | 570 | La Ribina (ES) |  | New 400kV substation in La Ribina (will be connected as an input/output in Carril-Litoral 400kV line ). | 2025 | Under Consideration | Rescheduled | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress
16 | Western interconnection FR-ES
|  | 38 | Gatica (ES) | Aquitaine (FR) | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf. | 2023 | Planning | Investment on time | The technical consistency of the project progresses and the commissioning date is now defined more accurately.
21 | Italy-France
|  | 55 | Grande Ile (FR) | Piossasco (IT) | "Savoie - Piémont" Project : New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 600MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and also along the existing motorways' right-of-way. | 2019 | Under Construction | Delayed | After some delay in the works of the Frejus service gallery of the motorway, in which the cables will be installed, the project timeline has been updated. Works are already in progress.
|  | 922 | Rondissone (IT) | Trino (IT) | Removing limitations on the existing 380 kV Rondissone-Trino | 2019 | Planning | New Investment | The item contributes to get the full advantage of the new HVDC cables was planned for the first time in the Italian National Development Plan 2013
|  | 923 | Lacchiarella(IT) | Chignolo Po(IT) | Removing limitations on the existing 380 kV Lacchiarella-Chignolo Po | 2019 | Planning | New Investment | The item contributes to get the full advantage of the new HVDC cables was planned for the first time in the Italian National Development Plan 2013
|  | 924 | Vado (IT) | La Spezia (IT) | Removing limitations on the existing 380 kV Vado-Vignole and Vignole-Spezia | 2019 | Planning | New Investment | The item contributes to get the full advantage of the new HVDC cables was planned for the first time in the Italian National Development Plan 2013
22 | Lake Geneva West
|  | 57 | Genissiat (FR) | Verbois (CH) | Reconductoring of the existing 225kV double circuit line Genissiat-Verbois with high temperature conductors. | 2020 | Planning | Investment on time | -
23 | France-Belgium Phase 1
|  | 60 | Avelin/Mastaing (FR) | Horta (new 400-kV substation) (BE) | Replacement of the current conductors on the axis Avelin/Mastaing - Avelgem - Horta with high performance conductors (HTLS = High Temperature Low Sag) | 2021 | Planning | Rescheduled | Investment was at conceptual stage in TYNDP2012; on-going feasibility studies lead to a more accurate commissioning date.
24 | Belgian North Border
|  | 445 | Zandvliet (BE) | Lillo (BE) | Brabo: part Zandvliet-Lillo: Brabo allows to realize the intended market capacity increase on the North Border in a more robust way (greater scenario independence compared to PST 4 only) , and reinforces the network to facilitate increased demand and connection of possible new generation around Antwerp Harbour area. It consists of constructing a new 380kV circuit Zandvliet-Lillo(new substation)-Mercator, in addition to the existing Zandvliet - Mercator connection. This investment item concerns the part between Zandvliet and Lillo substations. | 2018 | Design & Permitting | Delayed | Permitting procedure for adaptation of land use (GRUP) had to be reinitiated, in order to comply with the demand of investigating alternative solutions.
|  | 604 | Lillo (BE) | Mercator (BE) | Brabo: part Lillo-Mercator + restructuring 150kV. Brabo allows to realize the intended market capacity increase on the North Border in a more robust way (greater scenario independence compared to PST 4 only) , and reinforces the network to facilitate increased demand and connection of possible new generation around Antwerp Harbour area. It consists of constructing a new 380kV circuit Zandvliet-Lillo(new substation)-Mercator, in addition to the existing Zandvliet - Mercator connection. This investment item concerns the part between Lillo and Mercator substations, involving a restructuring of the adjacent 150kV network. | 2018 | Design & Permitting | Delayed | Permitting procedure for adaptation of land use (GRUP) had to be reinitiated, in order to comply with the demand of investigating alternative solutions.
|  | 605 | Lillo (BE) |  | Brabo - substation Lillo 380: Brabo allows to realize the intended market capacity increase on the North Border in a more robust way (greater scenario independence compared to PST 4 only) , and reinforces the network to facilitate increased demand and connection of possible new generation around Antwerp Harbour area. It consists of constructing a new 380kV circuit Zandvliet-Lillo(new substation)-Mercator, in addition to the existing Zandvliet - Mercator connection. This investment item concerns the erection of new 380kV substation Lillo. | 2018 | Design & Permitting | Delayed | Permitting procedure for adaptation of land use (GRUP) had to be reinitiated, in order to comply with the demand of investigating alternative solutions.
|  | 606 | Gramme (BE) | Van Eyck (BE) | Gramme-Van Eyck: second 380kV circuit First phase of reinforcement on the axis Gramme-Van Eyck, needed to facilitate connection of possible new central generation and to prepare for increasing transit fluxes whilst securing market capacity between BE & NL. This investment consist of creating a second 380kV line on the axis Gramme-Van Eyck - Section Van Eyck - Zutendaal (30 km): need to erect a new single circuit. Done with high performance conductors in order to be future proof (cfr. phase 2) - Section Gramme - Zutendaal (55km): reconfiguration of 150kV network so that an existing 150kV line can be operated at 380kV | 2015 | Under Construction | Delayed | Implementation of the project has been aligned with maintenance period of nuclear units ==> commissioning now foreseen in 2015 instead of end 2014
|  | 607 | Van Eyck (BE) |  | Gramme-Van Eyck: substation Van Eyck 380 First phase of reinforcement on the axis Gramme-Van Eyck, needed to facilitate connection of possible new central generation and to prepare for increasing transit fluxes whilst securing market capacity between BE & NL. This investment item consists of construction a 380kV substation named "Van Eyck", needed to integrate the second 380 kV line on the axis Gramme-Van Eyck. | 2015 | Under Construction | Delayed | Commissioning date of this inv. item aligned with implementation of inv. item 606 thus now 2015 instead of 2014
|  | 608 | Horta (BE) | Mercator (BE) | Horta-Mercator in HTLS The axis Horta-Mercator needs to be upgraded in order to transport the envisioned higher fluxes between France, Stevin & the Netherlands, and to facilitate connection of possible new generation (+-1000 MW) . Upgrade consists of replacing the current double circuit 380kV by high performance conductors allowing to double its transport capacity. The line currently passing Mercator going to Doel will be integrated into Mercator substation to obtain a better flux balance and avoid an upgrade between Mercator & Doel at this stage. | 2019 | Design & Permitting | Investment on time | The expected commissioning date of 2019 is based on the hypothesis of acquiring all necessary permits as planned, followed by the assessment of the final investment decision in 2016. Meanwhile the drivers behind this investment will be further monitored and its timing managed accordingly.
|  | 609 | Zandvliet (BE) |  | Horta-Mercator in HTLS The axis Horta-Mercator needs to be upgraded in order to transport the envisioned higher fluxes between France, Stevin & the Netherlands, and to facilitate connection of possible new generation (+-1000 MW) . Upgrade consists of replacing the current double circuit 380kV by high performance conductors allowing to double its transport capacity. The line currently passing Mercator going to Doel will be integrated into Mercator substation to obtain a better flux balance and avoid an upgrade between Mercator & Doel at this stage. | 2016 | Under construction | Investment on time | Installation of PST (plus upgrade of line Doel-Zandvliet) will be done as a first reinforcement in the Antwerp area. The PST has been ordered, as such the status of this investment is "under construction" with an expected commissioning date of 2016.
|  | 1050 | Gramme (BE) | Massenhoven (BE) | Conditional: Gramme-Van Eyck + Massenhoven-Meerhout-Van Eyck Envisions to double the transport capacity by upgrading the Gramme-Van Eyck axis to high-performance conductors, and by putting a second 380kV circuit on the Massenhoven-Meerhout-Van Eyck axis. The need to upgrade is conditional to the evolution of production in the LImburg-Liège area and to the evolution of the physical (transit)flux towards 2020-2025. This need will be further monitored. | 2020 | Planning | Investment on time | This investment is a split off from invest item 445a from in TYNDP 2012, and complemented with the Massenhoven-Meerhout-Van Eyck section. This investment is subject to further monitoring towards 2020-2025 given its dependency on production in the area in combination with evolution of the (transit)flux.
25 | IFA2
|  | 62 | Tourbe (FR) | Chilling (GB) | New subsea HVDC VSC link between the UK and France with a capacity around 1000 MW. PCI 1.7.2 (NSCOG corridor) | 2020 | Design & Permitting | Investment on time | Extensive feasibility studies (e.g. seabed surveys) have been conducted to determine the most suitable route; on the French side, the ministry of energy acknowledged the notification of the investment on 08/04/14.
26 | Austria - Italy
|  | 63 | Lienz (AT) | Veneto region (IT) | The project foresees the reconstruction of the existing 220kV-interconnection line as 380kV-line on an optimized route to minimize the environmental impact. Total length should be in the range of approx. 140km. | 2023 | Planning | Investment on time | Planning in progress co-ordinately between TERNA and APG
|  | 218 | Obersielach (AT) | Lienz (AT) | New 380kV OHL connecting the substations Lienz (AT) and Obersielach (AT) to close the Austrian 380kV-Security Ring in the southern grid area. Line length: 190km. | 2023 | Under Consideration | Investment on time | Progress as planned.
|  | 614 | Nauders (AT) | Glorenza (IT) | interconnector IT-AT (phase 1) | 2018 | Design & Permitting | Investment on time | -
|  | 1039 | Volpago (IT) |  | New 380/220/132 kV substation with related connections to 380 kV Sandrigo Cordignano and 220 KV Soverzene Scorzè where removing limitations are planned | 2020 | Planning | Delayed | The Volpago Substation was included in the TYNDP 2012 as part of the item 26.83 which had as commissioning date 2015. Permitting process delayed due to territorial constraint
|  | 1049 | tbd (IT) | tbd (AT) | interconnector IT-AT (phase 2) | 2023 | Under Consideration | New Investment | project progress
28 | 28
|  | 70 | Villanova (IT) | Lastva (ME) | New 1000MW HVDC interconnection line between Italy and Montenegro via 375km 500kV DC subsea cable and converter stations at both ending points. | 2017 | Under Construction | Delayed | rescheduling of work due to further secondary permitting during land rights acquisition and construction phase
|  | 621 | Villanova (IT) |  | Converter station of the new 1000MW HVDC interconnection line between Italy and Montenegro via 375km 500kV DC subsea cable. | 2017 | Under Construction | Delayed | rescheduling of work due to further secondary permitting during land rights acquisition and construction phase
|  | 622 | Lastva (ME) |  | Converter station in Montenegro of the new 1000MW HVDC sub-sea 500 kV cable between Italy and Montenegro. | 2017 | Under Construction | Delayed | rescheduling of work due to further secondary permitting during land rights acquisition and construction phase
|  | 624 | Lastva (ME) |  | New 400 kV substation Lastva in Montenegro will be connected to the existing line 400kV Podgorica 2(ME)-Trebinje(BA), with two transformers 2X300MVA 400/110kV. This substation will enable secure supply of the Montenegrin coastal network, and connection of the convertor station for the HVDC cable between Montenegro and Italy. | 2015 | Design & Permitting | Investment on time | on time
29 | Italy-North Africa
|  | 635 | Sicily Area (IT) | North Africa node | New interconnection between Italy and North Africa-new DC submarine cable | 2030 | Under Consideration | Investment on time | -
30 | 30
|  | 75 | Sorgente (IT) | Rizziconi (IT) | New 90km double circuit 400kV line, partly via subsea cable and partly via OHL. This line is part of a larger project that foresees the creation of the future 400kV grid of Sicily. | 2015 | Under Construction | Delayed | rescheduling of 6 months work due to technical issues during construction phase
31 | Italy-Switzerland
|  | 124 | Mettlen (CH) | Airolo (CH) | Upgrade of existing 225kV OHL into 400kV. Line length: 90km. | 2020 | Under Consideration | Investment on time | -
|  | 642 | Airolo (CH) | Pallanzeno(IT)-Baggio(IT) | New interconnection project between Italy and Switzerland; | 2022 | Design & Permitting | Investment on time | permitting process started on the Italian side since September 2012
|  | 914 | Cassano (IT) | Chiari (IT) | Upgrade to 380 kV of part of existing 220 kV Cassano Ric.Ovest | 2022 | Design & Permitting | New Investment | The interconnection scheme envisaged in TYNDP 2012 is now defined. The upgrade of Chiari-Cassano is identified as critical to get full advantage of the Giacomo project.
|  | 932 | Magenta(IT) |  | new 400 kV section in Magenta substation | 2020 | Design & Permitting | Investment on time | HVDC link between Pallanzeno and Baggio will be realized using existing 220 kV line connecting the Magenta 220/132 kV substation. Consequently, a new 400 kV section will be needed to reconnect the Magenta substation to the 400 kV line Turbigo – Baggio
33 | 33
|  | 90 | Calenzano (IT) | Colunga (IT) | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 2018 | Design & Permitting | Delayed | delay in the permitting process (EIA)
|  | 1041 | Villanova (IT) | S. Barbara (IT) | Removing limitations on existing 220 kV grid between Villanova e S.Barbara | 2020 | Planning | New Investment | The item 1041 has a significant effect on the grid transfer capacity
35 | North-South corridor
|  | 311 | Kocin (CZ) |  | Upgrade of the existing substation 400/110kV; upgrade transformers 2x350MVA. | 2024 | Design & Permitting | Delayed | Project commissioning date postponed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side
|  | 313 | Kocin (CZ) | Mirovka (CZ) | Connection of 2 existing 400kV substations with double circuit OHL having 120.5km length: and a capacity of 2X1700 MVA. | 2024 | Design & Permitting | Delayed | Project commissioning date postponed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side. Permitting procedure issues and wiring change.
|  | 315 | Kocin (CZ) | Prestice (CZ) | Adding second circuit to existing single circuit line OHL upgrade in length of 115.8km. Target capacity 2x1700 MVA. | 2028 | Design & Permitting | Delayed | Project commissioning date postponed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side. Wiring change to higher capacity.
|  | 316 | Mirovka (CZ) | Cebin (CZ) | Adding second circuit to existing single circuit line (88.5km, 2x1700 MVA). | 2028 | Design & Permitting | Delayed | Project is dependent on other investments which are delayed.
36 | Kriegers Flak CGS
|  | 141 | Ishøj / Bjæverskov (DK) | Bentwisch (DE) | Three offshore windfarms connected to shore combined with 400 MW interconnection between both countries | 2018 | Design & Permitting | Investment on time | Commissioning date must be achieved in order to ensure grid connection for further renewable energy.
37 | Southern Norway - Germany
|  | 142 | Tonstad (NO) | Wilster (DE) | A 514 km 500 kV HVDC subsea interconnector between southern Norway and northern Germany. | 2018 | Design & Permitting | Investment on time | Agreement between the two TSOs on commissioning date.
|  | 406 | (Southern part of Norway) (NO) | (Southern part of Norway)(NO) | Voltage uprating of existing 300 kV line Sauda/Saurdal - Lyse - Ertsmyra - Feda - 1&2, Feda - Kristiansand; Sauda-Samnanger in long term. Voltage upgrading of existing single circuit 400kV OHL Tonstad-Solhom-Arendal. Reactive power devices in 400kV substations. | 2020 | Design & Permitting | Delayed | Revised progress due to less flexible system operations in a running system (voltage upgrade of existing lines). Commissioning date expected 2019-2021.
39 | DKW-DE, step 3
|  | 144 | Audorf (DE) | Kassö (DK) | Step 3 in the Danish-German agreement to upgrade the Jutland-DE transfer capacity. It consists of a new 400kV route in Denmark and In Germany new 400kV line mainly in the trace of a existing 220kV line. | 2019 | Planning | Delayed | Planning ongoing - minor delay due to coordination with project 183.1018
40 | Luxembourg-Belgium Interco
|  | 446 | Schifflange (LU) |  | As a first interim step a PST is commissioned in 2016 in Schifflange and connected to an existing OH-line with an additional 3.5km cable between Biff(CREOS-LU) and Substation Bascharage (CREOS-LU). | 2015 | Under Construction | Investment on time | Studies for interim step are finalized, Investment decision expected by mid of 2014
|  | 447 | Heisdorf (LU) | Berchem (LU) | Erection of a new 20km 225kV double-circuit mixed (cable+OHL)line with 1000 MVA capacity in order to create a loop around Luxembourg city including substations for in feed in lower voltage levels. | 2017 | Design & Permitting | Investment on time | Substation Blooren is authorized and under construction, Authorization for line section is still pending
|  | 650 | Bascharage (LU) | Aubange (BE) | BELUX LT In a second step: new 220 kV interconnection with neighbour(s) between Creos grid in LU and ELIA grid in BE via a 16km double circuit 225kV underground cable with a capacity of 1000 MVA. | 2020 | Under Consideration | Investment on time | An ongoing network study investigates the robustness of the planned 220kV connection between LU and BE.
42 | OWP TenneT Northsea part 1
|  | 160 | Offshore- Wind park Nordergründe (DE) | Inhausen (DE) | New AC-cable connection with a total length of 32km. | 2016 | Under Construction | Delayed | Delay due delay of windfarms
|  | 163 | Cluster HelWin1 (DE) | Büttel (DE) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 133km. Line capacity: approx.. 576 MW. | 2014 | Under Construction | Investment on time
|  | 164 | Cluster SylWin1 (DE) | Büttel (DE) | New line consisting of underground +subsea cable with a total length of 206 km. Line capacity: aprox.864MW. | 2015 | Under Construction | Delayed
|  | 165 | Cluster DolWin1 (DE) | Dörpen/West (DE) | New line consisting of underground +subsea cable with a total length of 167 km. Line capacity: 800MW. | 2014 | Under Construction | Delayed
|  | 167 | Cluster BorWin2 (DE) | Diele (DE) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205km. Line capacity: 800MW. | 2015 | Under Construction | Delayed
|  | 654 | Cluster DolWin2 (DE) | Dörpen/West (DE) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 138 km. Line capacity: 900 MW | 2015 | Under Construction | Investment on time
|  | 655 | Cluster DolWin3 (DE) | Dörpen/West (DE) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 162 km. Line capacity: 900 MW | 2017 | Under Construction | Investment on time
|  | 657 | Cluster HelWin2 | Büttel (DE) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 133 km. Line capacity: 690 MW | 2015 | Under Construction | Investment on time
46 | Offshore Wind Baltic Sea
|  | 194 | OWF Cluster Baltic Sea East (DE) | Lüdershagen/Lubmin (DE) | Grid Connection of offshore wind farms ( using AC-technology). According to German law, the grid connection has to be constructed and operated by the TSO (50Hertz Transmission). | 2031 | Design & Permitting | Investment on time | The investment is split into different stages with different commissioning dates (starting in 2017) depending on the predicted installed capacity of offshore wind. For further information see the national "Offshore Grid Development Plan"
|  | 195 | wind farm cluster Baltic Sea West (DE) | Bentwisch/Lüdershagen (DE) | Grid Connection of offshore wind farms ( using AC-technology). According to German law, the grid connection has to be constructed and operated by the TSO (50Hertz Transmission). | 2032 | Design & Permitting | Investment on time | The investment is split into different stages with different commissioning dates (starting in 2026) depending on the predicted installed capacity of offshore wind. For further information see the national "Offshore Grid Development Plan"
47 | AT - DE
|  | 212 | Isar (DE) | St. Peter (AT) | New 400kV double circuit OHL Isar - St. Peter including new 400kV switchgears Altheim, Pirach, Simbach and St. Peter. Also including 4. circuit on line Ottenhofen - Isar. | 2018 | Design & Permitting | Delayed | delayed due to long permitting process
|  | 216 | St. Peter (AT) | Tauern (AT) | Completion of the 380kV-line St. Peter - Tauern. This contains an upgrade of the existing 380kV-line St. Peter - Salzburg from 220kV-operation to 380kV-operation and the erection of a new internal double circuit 380kV-line connecting the substations Salzburg and Tauern (replacement of existing 220kV-lines on optimized routes). Moreover the erection of the new substations Wagenham and Pongau and the integration of the substations Salzburg and Kaprun is planned. | 2020 | Design & Permitting | Investment on time | In Sept. 2012 the application for granting the permission (EIA) was submitted to the relevant authorities. According to the experience of similar projects the commissioning is expected for 2020.
|  | 219 | Westtirol (AT) | Zell-Ziller (AT) | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of an additional 220/380kV-Transformer. Line length: 105km. | 2021 | Planning | Investment on time | The upgrade of the line and substation Westtirol is currently in the planning process.
|  | 689 | Vöhringen (DE) | Westtirol (AT) | Upgrade of an existing over head line to 380 kV, extension of existing and errection of new 380-kV-substations including 380/110-kV-transformers. Transmission route Vöhringen (DE) -Westtirol (AT). This project will increase the current power exchange capacity between the DE, AT. | 2020 | Planning | Investment on time | Progress as planned.
48 | New SK-HU intercon. - phase 1
|  | 214 | Gabcikovo (SK) | Gonyü area (HU) | New interconnection (new 2x400 kV tie-line) between SK and HU starting from Gabčíkovo substation (SK) to the Gőnyü substation on Hungarian side ( preliminary decision). Project also includes the erection of new switching station Gabčíkovo next to the existing one. | 2018 | Planning | Delayed | Expected commission date postponed on 2018 by reason of difficulties associated with finding the common national border crossing point.
|  | 695 | Rimavská Sobota (SK) | Sajóivánka (HU) | Connection of the two existing substations (R.Sobota (SK) - Sajoóivánka (HU)) by the new 2x400 kV line (preliminary armed only with one circuit). | 2018 | Planning | Delayed | Expected commission date postponed on 2018 by reason of difficulties associated with finding the common national border crossing point.
|  | 696 | Sajóivánka (HU) |  | 2x70 Mvar shunt reactors in station Sajóivánka (HU) | 2018 | Planning | Delayed | Expected commission date postponed to 2018 as a result of negotiations between SEPS and MAVIR.
|  | 697 | Sajóivánka (HU) |  | Second 400/120 kV transformer in station Sajóivánka (HU) | 2018 | Planning | Delayed | Expected commission date postponed to 2018 as a result of negotiations between SEPS and MAVIR.
|  | 698 | Gyor (HU) |  | 70 Mvar shunt reactor in station Győr (HU) | 2018 | Planning | Delayed | Investment rescheduled as a result of changes in planning input data (need delayed)
|  | 699 | Gyor (HU) |  | Third 400/120 kV transformer in station Győr (HU) | 2018 | Planning | Delayed | Investment rescheduled as a result of changes in planning input data (need delayed)
54 | New SK-HU intercon. - phase 2
|  | 720 | Velké Kapušany (SK) | tbd (HU) | Erection of new 2x400 line between SK and Hungary (substation on Hungarian side still to be defined). The Investment is under consideration. | 2021 | Under Consideration | Investment on time | No change.
55 | CZ West-east corridor (West)
|  | 302 | Vyskov (CZ) | Cechy stred (CZ) | New second circuit 400kV OHL; Target capacity 2x1730 MVA. | 2016 | Design & Permitting | Delayed | Delayed due to permitting procedure difficulty
|  | 303 | Babylon (CZ) | Bezdecin (CZ) | New second circuit 400kV OHL; 1385 MVA. | 2018 | Design & Permitting | Delayed | Delay caused by permitting process difficulty
|  | 304 | Babylon (CZ) | Vyskov (CZ) | New second circuit 400kV OHL; 1385 MVA. | 2021 | Design & Permitting | Delayed | Delayed due to permitting procedure difficulty
58 | GerPol Power Bridge
|  | 140 | Eisenhüttenstadt (DE) | Plewiska (PL) | Construction of new 400 kV double circuit line Plewiska (PL)-Eisenhüttenstadt (DE) creating an interconnector between Poland and Germany. | 2030 | Planning | Rescheduled | The investment in planning phase. Expected problems with the routing cause adoption of commissioning date.
|  | 353 | Krajnik (PL) | Baczyna (PL) | Construction of new 400 kV double circuit line Krajnik – Baczyna. | 2020 | Planning | Investment on time | Investment is in the tendering procedure.
|  | 355 | Mikulowa (PL) | Swiebodzice (PL) | Construction of new 400 kV double circuit line Mikułowa-Świebodzice in place of existing 220 kV line. | 2020 | Planning | Investment on time | Investment on time.
|  | 726 | Gubin (PL) |  | New 400 kV substation Gubin located near the PL-DE border. The substation will be connected by the new line Plewiska (PL)-Eisenhüttenstadt (DE). | 2030 | Planning | Rescheduled | Change of the commissioning date as the investment is correlated with the investment 140.
|  | 727 | Plewiska (PL) |  | Construction of new substation Plewiska Bis (PL) to connect the new line Plewiska (PL)-Eisenhüttenstadt (DE). | 2020 | Planning | Investment on time | The project is at the planning stage.
|  | 1035 | Baczyna |  | Construction of new 400/220 kV Substation Baczyna to connect the new line Krajnik-Baczyna. | 2018 | Planning | Investment on time | The investment was part of n°58.353 in TYNDP 2012 and is now presented stand alone. It is in the tendering procedure (design and build scheme).
59 | LitPol Link Stage 1
|  | 368 | Elk (PL) | PL-LT border | Construction of a new 400 kV interconnector line from Ełk to PL-LT border. | 2015 | Under Construction | Investment on time | Investment is under construction.
|  | 369 | Siedlce Ujrzanów (PL) | Milosna (PL) | Construction of new 400 kV line Siedlce Ujrzanów - Miłosna. | 2015 | Under Construction | Investment on time | The project is in the construction phase.
|  | 370 | Elk (PL) | Lomza (PL) | Construction of new 400 kV line Ełk-Łomża. | 2015 | Under Construction | Investment on time | The project is under construction.
|  | 371 | Ostroleka (PL) | Narew (PL) | Construction of new 400 kV line Ostroleka-Lomza-Narew + extension of substation Narew. | 2015 | Under Construction | Investment on time | The project is under construction.
|  | 376 | Alytus (LT) | PL-LT border | Construction of 500 MW Back-to-Back convertor station near Alytus 330kV substation. Construction of double circuit 400kV OHL between Alytus and PL-LT border (51 km). | 2015 | Under Construction | Investment on time | As planned.
|  | 379 | Kruonis (LT) | Alytus (LT) | New double circuit 330kV OHL Alytus–Kruonis(2x1080 MVA, 53km). | 2016 | Design & Permitting | Delayed | Several months delay due to difficulties with the acquisition of the land
|  | 728 | Lomza (PL) |  | Construction of new substation Łomża to connect the line Ełk-Łomża. | 2015 | Under Construction | Investment on time | The project is under construction.
|  | 729 | Ostroleka (PL) |  | A new 400 kV switchgear in existing substation Ostroleka (in two stages) with transformation 400/220kV 500 MVA and with transformation 400/110kV 400 MVA. | 2015 | Under Construction | Investment on time | The project is under construction.
|  | 730 | Stanislawów (PL) |  | New substation 400kV Stanisławów will be connected by splitting and extending existing line Miłosna-Narew and Miłosna-Siedlce. | 2015 | Under Construction | Expected earlier than planned previously | In TYNDP 2012 the building of the substation Stanisławów was reported as part of a line Ostrołęka-Stanisławów. The commissioning time has been aligned with the construction of the line Miłosna-Siedlce Ujrzanów which is expected in 2015.
|  | 1036 | Siedlce Ujrzanów |  | New Substation Siedlce Ujrzanów will be connected by new line Miłosna-Siedlce Ujrzanów and later by new line Kozienice-Siedlce Ujrzanów | 2015 | Under Construction | Investment on time | The investment was previously included in the investment no. 369 as "new 400 kV switchgear in existing Substation Siedlce". The concept has changed and there is a new substation in a different location.
|  | 1037 | Elk Bis |  | New 400/110 kV Substation Ełk Bis connected by two double 400 kV lines Łomża-Ełk and Ełk-Alytus creating an interconnector Poland-Lithuania. | 2015 | Under Construction | Investment on time | The inv. was part of inv. no 370 in TYNDP2012 as "new 400kV switchgear in existing Substation Ełk". The concept has changed, it is not possible to extend the existing substation and there is a new substation in a different location, expected in 2015.
60 | NordBalt phase 1
|  | 377 | Klaipeda (LT) | Telsiai (LT) | New single circuit 330kV OHL (943 MVA, 85km). | 2014 | Under Construction | Investment on time | -
|  | 383 | Klaipeda (LT) | Nybro (SE) | (NordBalt) A new 300kV HVDC VSC partly subsea and partly underground cable between Lithuania and Sweden | 2015 | Under Construction | Investment on time
|  | 385 | Grobina (LV) | Imanta (LV) | The reinforcement for Latvian grid project with the new 330kV OHL construction and connection to the Riga node. New 330kV OHL construction mainly instead of the existing 110kV double circuit line route, 110kV line will be renovated at the same time and both will be assembled on the same towers. Length 380km, Capacity 800MW | 2018 | Under Construction | Investment on time | The part of reinforcement for Kurzemes ring
62 | Estonia-Latvia 3rd IC
|  | 386 | Kilingi-Nomme (EE) | R-TEC2 (LV) | 330 kV AC OHL between Kilingi-Nõmme substation in Estonia and R-TEC2 substation in Latvia. New 330 kV power transmission line is planned to take route along already existing 110 kV power transmission lines, by constructing both 110 kV and 330 kV lines on the same towers. Under the framework of the project it is planned to reconstruct the open-air switchyard of the 330/110 kV substation „TEC-2” by constructing new open-air connection point for the 330 kV line „Kilingi Nomme-TEC-2”. | 2020 | Planning | Investment on time | Progress as planned.
|  | 735 | Harku (EE) | Sindi (EE) | New double circuit OHL with 2 different voltages 330 kV and 110 kV and with capacity 1200 MVA/240 MVA and a length 140 km. Major part of new internal connection will be established on existing right of way on the western part of Estonian mainland. | 2018 | Design & Permitting | Investment on time | Progress as planned.
64 | N-S Finland (P1) stage 1
|  | 739 | Ulvila (FI) | Kristinestad (FI) | Second line part of the four new single circuit 400kV OHL are part of project in upgrading Ostrobothnian 220kV system into 400kV, and strengthening the 400 kV grid in Northern Finland. total length of lines: 520 km. Total Expected capacity: 1850 MVA. | 2014 | Under Construction | Investment on time | Investment progresses as planned
|  | 740 | Hirvisuo (FI) | Pyhänselkä (FI) | Third line part of the four new single circuit 400kV OHL are part of project in upgrading Ostrobothnian 220kV system into 400kV, and strengthening the 400 kV grid in Northern Finland. total length of lines: 520 km. Total Expected capacity: 1850 MVA. | 2016 | Design & Permitting | Expected earlier than planned previously | Station name updated from Ventusneva to Hirvisuo. Investment decision has been made and schedule has been updated.
69 | East Anglia Cluster
|  | 747 | Bramford (GB) | Twinstead (GB) | Construction of a new transmission route from Bramford to the Twinstead Tee Point creating Bramford - Pelham and Bramford - Braintree - Rayleigh Main double circuits; the rebuild of Bramford substation and the installation of an MSC at Barking. | 2022 | Design & Permitting | Investment on time | Delay in project requirement due to generation going back.
71 | COBRA cable
|  | 427 | Endrup (DK) | Eemshaven (NL) | COBRA: New single circuit HVDC connection between Jutland and the Netherlands via 350km subsea cable; the DC voltage will be 320kV and the capacity 700MW. | 2019 | Design & Permitting | Delayed | Rescheduled to develop a solid regional business case (including additional project partners); and to account for the time needed for the acceptance by the authorities of a preferred route.
74 | Thames Estuary Cluster (NEMO)
|  | 443 | Richborough (GB) | Zeebrugge (BE) | Nemo Project: New DC sea link including 135km of 400kV (voltage level is subject to outcome of detailed engineering) DC subsea cable with 1000MW capacity | 2018 | Design & Permitting | Investment on time | Investment on time, with a technical commissioning planned end 2018 leading to commercial operation in 2019
|  | 449 | Richborough (GB) | Canterbury (GB) | New 400kV double circuit and new 400kV substation in Richborough connecting the new Belgium interconnector providing greater market coupling between the UK and the European mainland. | 2018 | Planning | Investment on time | Investment on time
|  | 450 | Sellindge (GB) | Dungeness (GB) | Reconductoring the existing circuit which runs from Sellindge - Dungeness with a higher rated conductor. This will facilitate the connection of more interconnectors on the South coast and prevent thermal overloading of this area. | 2015 | Design & Permitting | Investment on time | Investment on time
75 | Stevin (backbone)+BE offshore
|  | 444 | Zomergem (BE) | Zeebrugge (BE) | STEVIN The Stevin project envisions the extension of the 380kV backbone to the coastal area, via the construction of new +-50km (40km OHL; 10km cable) double-circuit (3000MVA for each circuit) between Zomergem and Zeebrugge., including the construction of a new substation in Zeebrugge. | 2018 | Design & Permitting | Delayed | Delay due to request of 3rd parties to examine more alternatives, and procedures launched , and due to appeals against the GRUP (land use act) by 3rd parties in States Council. Meanwile arrangements have been made, and the updated planning envisions end 2017/begin 2018 as new commissioning date.
|  | 752 | Offshore hub (BE) | Stevin (Zeebrugge) | Belgian Offshore Grid (BOG) The Belgian Offshore Grid investment consists of the eruption of an offshore hub connected to onshore AC grid (at Zeebrugge) via underground cables, including the necessary reactive compensation for the cables. Subject to result of ongoing design, legal, ownership & regulatory concertation with stakeholders. | 2018 | Design & Permitting | Delayed | 2018 is the earliest possible date: project is subject to outcome of ongoing design, legal, ownership & regulatory framework concertation with stakeholders.
76 | London Cluster
|  | 753 | Pelham (GB) | Waltham Cross (GB) | Reconductoring the existing circuit which runs from Pelham - Rye House - Waltham Cross with a higher rated conductor. | 2021 | Design & Permitting | Delayed | Postponed due to the slow build up of generation in the East Anglia area and also in demand within London.
|  | 754 | Hackney (GB) | Waltham Cross (GB) | Uprating and Reconductoring of the Hackney - Tottenham - Brimsdown - Waltham Cross double circuits. Construction of a new 400kV substation at Waltham Cross and modifications to the Tottenham substation and the installation of two new transformers at Brimsdown substation. | 2021 | Design & Permitting | Delayed | Postponed due to the build up of generation schemes in the East Anglia area and demand increases in London.
|  | 755 | Hackney (GB) | St. John's Wood (GB) | This is a new Hackney - St. John's Wood 400kV double circuit. It will replace an old asset rated at 275kV that has come to the end of its life. | 2018 | Under Construction | Investment on time | Investment on time
|  | 757 | St. John's Wood (GB) | Wimbledon (GB) | New St. John's Wood - Wimbledon 400kV double circuit. | 2018 | Design & Permitting | Investment on time | Investment on time
77 | Anglo-Scottish Cluster
|  | 452 | Hunterston (GB) | Deeside (GB) | A new 2.4GW (short term rating) submarine HVDC cable route from Hunterston to Deeside with associated AC network reinforcement works at both ends. | 2016 | Design & Permitting | Investment on time | Investment on time
|  | 453 | Peterhead (GB) | Hawthorn Pit (GB) | A new ~2GW submarine HVDC cable route from Peterhead to Hawthorn Pit with associated AC network reinforcement works at both ends with possible offshore HVDC integration in the Firth of Forth area. | 2020 | Under Consideration | Investment on time | Investment on time
78 | South West Cluster
|  | 458 | Hinkley Point (GB) | Seabank (GB) | New 400kV substation at Hinkley Point. New 400kV transmission route from Hinkley Point to Seabank. Reconstruction of Bridgewater substation for 400kV operation. Uprate Bridgewater - Melksham to 400kV. | 2019 | Design & Permitting | Investment on time | Based on current generation connection dates this investment is progressing on time.
79 | Wales Cluster
|  | 769 | Wylfa (GB) | Pembroke (GB) | A new ~2GW submarine HVDC cable route from Wylfa/Irish Sea to Pembroke with associated AC network reinforcement works at both ends. | 2025 | Planning | Rescheduled | Delayed due to anticipated changes in the local generation background.
81 | North South Interconnector
|  | 462 | Woodland (IE) | Turleenan (NI) | A new 140 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. | 2017 | Design & Permitting | Delayed | Further studies required before re-submission for planning consents
82 | RIDP I
|  | 463 | Srananagh (IE) | New substation in South Donegal (IE) | A new EHV overhead line from Srananagh in Co. Sligo to a new substation in south Co. Donegal | 2020 | Planning | Investment on time | The preferred scheme has been selected since the last TYNDP; this is one of the elements of the preferred scheme.
|  | 896 | South Donegal (IE) | Omagh South (NI) | A new 275 kV cross border link between a new substation in South Donegal in Ireland and a new substation established south of Omagh in Northern Ireland | 2024 | Planning | New Investment | Investment 82.463 of the previous TYNDP described the as then undefined scheme that was the subject of a joint study between NIE and EirGrid. That study has since been completed. This investment is one of a number emerging from the study.
|  | 897 | Omagh South | Turleenan | A new 275 kV overhead line from a new substation established south of Omagh to a new 400/275 kV substation, established at Turleenan by the North South Interconnection Development | 2020 | Planning | New Investment | Investment 82.463 of the previous TYNDP described the as then undefined scheme that was the subject of a joint study between NIE and EirGrid. That study has since been completed. This investment is one of a number emerging from the study.
85 | Integration of RES in Alentejo
|  | 779 | F. Alentejo (by Ourique) | Tavira (by Ourique) | New 122km double-circuit 400+150 kV OHL F. Alentejo-Ourique-Tavira. The realization of this connection can take advantage of some already existing 150kV single lines, which can be reconstructed as double circuit line 400+150kV, investments needs the investment which consist of the extension of existing Ourique substation to include 400 kV facilities. | 2025 | Planning | Rescheduled | Due to the expected delay on the connection of new RES in Portugal, the commissioning date of this project is delayed
|  | 780 | Ourique (PT) |  | Extension of existing Ourique substation to include 400 kV facilities. | 2025 | Planning | Rescheduled | Due to the expected delay on the connection of new RES in Portugal, the commissioning date of this project is delayed
86 | East Coast Cluster
|  | 781 | Under Consideration (GB) | Under Consideration (GB) | A very high level indication of the works required for GB East Coast. In detail the projects will consist of multiple offshore HVDC and AC circuits and connecting platforms joining to multiple onshore connection points with their own reinforcement requirements. It enables significant connection of offshore windfarms and provides alternative to onshore reinforcement at a cheaper overall cost. | 2023 | Under Consideration | Investment on time | Investment on time
|  | 782 | Under Consideration (GB) | Under Consideration (GB) | Connection of Triton Knoll, Doggerbank & Hornsea GB Wind Farms and all associated works. This is in the region of 11GW of offshore generation. | 2020 | Under Consideration | Investment on time | Investment on time
90 | Swiss Roof
|  | 129 | Beznau (CH) | Mettlen (CH) | Upgrade of the existing 65km double circuit 220kV OHL to 400kV. | 2020 | Design & Permitting | Delayed | long permitting procedure (comprising several phases). In this case, Federal Court decision for partial cabling.
|  | 130 | La Punt (CH) | Pradella / Ova Spin (CH) | Installation of the second circuit on existing towers of a double-circuit 400kV OHL (50km). | 2017 | Planning | Investment on time | none
|  | 133 | Bonaduz (CH) | Mettlen (CH) | Upgrade of the existing 180km double circuit 220kV OHL into 400kV. | 2020 | Under Consideration | Investment on time | none
|  | 134 | Bassecourt (CH) | Romanel (CH) | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines; total length: 140km. Construction of a new 400/220 kV substation in Mühleberg (= former investment 132 'Mühleberg Substation') | 2020 | Design & Permitting | Delayed | lines: long permitting procedure (comprising several phases)- Mühleberg substation: under construction
|  | 136 | Border area (DE-AT) | Rüthi (CH) | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 2022 | Planning | Investment on time | investment 136 now comprises the cross-border part of former investment 136, and investment 1099 is the Swiss part of former investment 136.
|  | 1099 | Rüthi | Bonaduz - Grynau | Rüthi - Grynau 2 x 380 kV Rüthi - Bonaduz 1 x 380 kV | 2022 | Planning | Investment on time | Investment 136 now comprises the cross-border part of former investment 136, and investment 1099 is the Swiss part of former investment 136.
91 | Swiss Ellipse
|  | 121 | Bickigen (CH) | Romanel (CH) | Construction of different new 400kV OHL sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 250km. | 2020 | Design & Permitting | Delayed | long permitting procedure (comprising several phases)
|  | 122 | Chippis (CH) | Lavorgo (CH) | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV. Total length: 120km. | 2020 | Design & Permitting | Delayed | long permitting procedure (comprising several phases)
|  | 123 | Mettlen (CH) | Ulrichen (CH) | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 90km. | 2019 | Planning | Investment on time | none
|  | 125 | Schwanden (CH) | Limmern (CH) | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. OHL part | 2015 | Under Construction | Investment on time | none
|  | 126 | Golbia (CH) | Robbia (CH) | New 2x 400kV cable connection between Golbia and the Bernina line double circuit. | 2019 | Under Consideration | Investment on time | none
|  | 127 | Magadino (CH) | Verzasca (CH) | Upgrade of existing 150kV line into 220kV line. | 2020 | Under Consideration | Investment on time | none
|  | 128 | Bâtiaz (CH) | Nant de Drance (CH) | New 400kV double circuit OHL between Bâtiaz and Châtelard. New 2x 400kV cable connection between Châtelard and Nant de Drance. Total length: 22km. | 2020 | Design & Permitting | Delayed | long permitting procedure (comprising several phases)
|  | 795 | Schwanden (CH) | Limmern (CH) | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. Underground cable part | 2015 | Under Construction | Investment on time | none
92 | ALEGrO
|  | 146 | Area of Oberzier - Aachen/Düren (DE) | Area of Lixhe - Liège (BE) | ALEGrO Connection between Germany and Belgium including new 100 km HVDC underground cable with convertor stations and extension of existing 380 kV substations. The assessment of the Final Investment Decision is planned in 2015. | 2019 | Design & Permitting | Delayed | BE: Several months delay due to authorisation procedure in Belgium longer than expected (modification of "Plan de secteur" in Wallonia). DE: Delay due to unclear permitting framework (legal framework for planning approval is presently under development
|  | 1045 | Lixhe | Herderen | AC BE Reinforcements Internal reinforcements in AC network in Belgium have started in the context of securing infeed from the 380kV network into the Limburg & Liège area. These reinforcements are also needed to facilitate the integration of ALEGrO into the Belgian grid. The reinforcements consist of - extension of an existing single 380 kV connection between Lixhe and Herderen by adding an additional circuit with high performance conductors (HTLS) - creation of 380kV substation in Lixhe, including a 380/150 transformator - creation of 380kV substation in Genk (André Dumont), including a 380/150 kV transformator | 2017 | Design & Permitting | Investment on time | This investment item is split off from the generic Alegro investment item which up to now included also the internal reinforcements
|  | 1048 | Lixhe | Herderen | Potentially additional AC BE Reinforcements Envisions the installation of a second 380 kV overhead line between Herderen to Lixhe. And the installation of a 2nd 380/150 transformator in Limburg area (probably substation André Dumont). These reinforcements are conditional to the evolution of production in the Limburg-Liège area and to the evolution of the physical (transit) flux towards 2020-2025. | 2020 | Under Consideration | New Investment | Evolution of generation in the Limburg-Liège must be accounted for in the perimeter of the Alegro project. This conditional project has a commissioning date set to 2020 as indication for further monitoring of the need.
94 | GerPol Improvements
|  | 139 | Vierraden (DE) | Krajnik (PL) | Upgrade of existing 220 kV line Vierraden-Krajnik to double circuit 400 kV OHL. | 2017 | Design & Permitting | Investment on time | A delay in the permit process for the line Neuenhagen-Bertikow-Vierraden (DE) as a prerequisite caused an adaptation in the time schedule for the line between Vierraden and Krajnik from to 2017.
|  | 796 | Krajnik (PL) |  | Upgrade of 400/220 kV switchgear in substation Krajnik (new 400/220 kV switchyard). | 2017 | Design & Permitting | Delayed | The commissioning time of the investment has been aligned with the schedule for the investment 139.
|  | 799 | Mikulowa (PL) |  | Installation of new Phase Shift Transformer in substation Mikułowa and the upgrade of substation Mikułowa for the purpose of PST installation. | 2015 | Design & Permitting | Delayed | Investment postponed because of prolongation of the tendering process. Due to complexity of the technical solutions more time is needed for the tendering procedure.
|  | 992 | Vierraden |  | Installation of new PSTs in Vierraden | 2016 | Planning | New Investment | Based on a common agreement between PSE and 50Hertz the investment was specified in more detail in close cooperation between PSE and 50Hertz. The common solution consists of PST in Vierraden (DE) and PST in Mikułowa (PL) Investment 799.
96 | Keminmaa-Pyhänselkä
|  | 801 | Keminmaa (FI) | Pyhänselkä (FI) | Integration of new generation + increased transmission capacity demand. | 2024 | Under Consideration | Rescheduled | Investment progresses as planned, rescheduled slightly since last TYNDP due to expected development on the drivers behind the investment.
103 | Reinforcements Ring NL
|  | 438 | Eemshaven (NL) | Diemen (NL) | New 175-200km AC overhead line with capacity of 2x2650 MVA of 380kV. In the first phase a connection between Eemshaven Oude Schip and Vierverlaten will be built as well as an upgrade of the existing line Diemen - Lelystad - Ens | 2018 | Design & Permitting | Investment on time | Changes in plans of thermal plants at Eemshaven offers the opportunity to phase the grid expansions. The a first phase consists of a new 380 kV connection between Eemshaven-Oudeschip and Vierverlaten and the upgrade the circuits form Diemen-Lelystad-Ens
|  | 439 | Borssele (NL) | Tilburg (NL) | New 100-130km double-circuit 380kV OHL with 2x2650 MVA capacity. | 2016 | Design & Permitting | Investment on time | With a 380 kV substation at Rilland, the Zuid-West 380 kV project can be taken into service in two parts. The first part consists of the Borssele - Rilland line including substation Rilland and the second part consist of the Rilland – Tilburg line.
|  | 440 | Maasvlakte (NL) | Beverwijk (NL) | New 380 kV double-circuit mixed project (OHL+ underground cable) including approximately 20km of underground cable for 2650 MVA. The cable sections are a pilot project. The total length of cable at 380kV is frozen until more experience is gained. | 2017 | Under Construction | Delayed | Permitting procedures took longer than expected. The part from Maasvlakte to Bleiswijk has been commissioned.
|  | 441 | Zwolle (NL) | Under analysis (BE) | BELUX INTERIM As a first interim step a PST will be integrated in Schifflange, and connected to an existing OH-line to control the transit flows from Germany to Belgium as from end 2015. | 2015 | Under construction | Investment on time | Studies for interim step are finalized; Investment decision has been taken mid-2014 and PST is planned to be operational end 2015.
106 | Ireland GB Interconnector
|  | 809 | Dunstown (IE) | Pentir (GB) | A new HVDC subsea connection between Ireland and Great Britain; this may be achieved by a direct link or by integrating an interconnector with a third party connection from Ireland to GB. | 2025 | Under Consideration | Investment on time | Joint studies between National Grid and EirGrid indicate a strong benefit for a second interconnector between Ireland and GB.
107 | Celtic Interconnector
|  | 810 | Great Island or Knockraha (IE) | La Martyre (FR) | A new HVDC subsea connection between Ireland and France | 2025 | Under Consideration | Investment on time | Feasibility studies are progressing
108 | 1000MW HPS Tarnita connection
|  | 811 | Tarnita (RO) | Mintia (RO) | New double circuit 400kV OHL Tarnita(RO)-Mintia(RO) 2x1380 MVA. | 2018 | Planning | Investment on time | The project shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending.
|  | 812 | Tarnita (RO) | Cluj E - Gadalin (RO) | New double circuit 400kV OHL Tarnita(RO)- Cluj E-Gadalin (RO) 2x1380 MVA. | 2018 | Planning | Investment on time | The project shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending.
|  | 813 | Tarnita (RO) |  | New 400kV substation connecting 1000 MW Hydro Pumped Storage Tarnita Lapustesti to the grid. | 2018 | Planning | Investment on time | The project shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending.
110 | Norway-Great Britain
|  | 424 | Kvilldal (NO) | Blythe (GB) | A 720 km long 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern England. | 2020 | Design & Permitting | Investment on time | On time
111 | 3rd AC Finland-Sweden north
|  | 396 | Finland North (FI) | Sweden bidding area SE1/SE2 | Third single circuit 400kV AC OHL between Sweden and Finland | 2025 | Under Consideration | Rescheduled | Rescheduled following a review of priorities and dependencies for all grid reinforcements in Sweden. Thanks to postponement of this investment, other internal investments will be commissioned on time
113 | Doetinchem - Niederrhein
|  | 145 | Niederrhein (DE) | Doetinchem (NL) | New 400kV line double circuit DE-NL interconnection line. Length:57km. | 2016 | Design & Permitting | Delayed | Permitting procedures take longer than expected
120 | 2nd Offshore-Onshore Corridor
|  | 933 | Offshore Hub OR Stevin - TBD | Izegem - TBD | Further connection to inland: phase 2 Preliminary analysis shows the need to reinforce the 380kV network with a second offshore-onshore corridor in order to evacuate up to 4 GW of offshore wind. The solutions under study consist of multiple investment items. This investment item envisions the possibility of an AC OR DC solution going from an offshore hub OR onshore substation Stevin in Zeebrugge towards a further inland location. The reference solution presented here is an AC corridor towards Izegem. To be confirmed by further detailed studies in the coming years. The cost estimation does not take into account the offshore part of the corridor. | 2030 | Under Consideration | New Investment | Additional offshore-onshore corridor needed in order to evacuate full potential of up to 4GW (compared to current target of 2,3 GW) of offshore wind in the Belgian part of the North Sea in visions 3 & 4.
|  | 1053 | Offshore Hub - TBD | Doel - TBD | 1 GW connection to inland: phase 1 Preliminary analysis shows the need to reinforce the 380kV network with a second offshore-onshore corridor in order to evacuate up to 4 GW of offshore wind. The solutions under study consist of multiple investment items. This investment item envisions the possibility of a 1 GW DC solution between an offshore hub towards an inland location (substation Doel or further inland could be a possible location). Subject to further studies. The cost estimate does not take into account the construction of an eventual offshore hub. | 2030 | Under Consideration | New Investment | Additional offshore-onshore corridor needed in order to evacuate full potential of up to 4GW (compared to current target of 2,3 GW) of offshore wind in the Belgian part of the North Sea in visions 3 & 4.
121 | 2nd Interco Belgium - UK (1GW)
|  | 934 | Kemsley (UK) for example - TBD | Doel/Zandvliet (BE) for example - TBD | NEMO 2: UK to BE 380kV inland This investment item envisions the possibility of a second 1GW HVDC connection, between UK (Kemsley) and a Belgian 380kV substation further inland in the Antwerp area (Doel, Zandvliet are indicative locations). Subject to further studies. | 2030 | Under Consideration | New Investment | Preliminary studies on vision 3&4 scenario's have indicated potential fur further regional welfare & RES integration increase by further increasing the interconnection capacity between Belgium & UK up to 2 GW.
123 | LitPol Link Stage 2
|  | 335 | Ostroleka (PL) | Olsztyn Matki (PL) | Construction of new 400 kV line Ostrołęka - Olsztyn Mątki after dismantling of 220kV line Ostrołęka - Olsztyn with one circuit from Ostrołęka to Olsztyn temporarily on 220 kV. | 2017 | Design & Permitting | Investment on time | The investment in on time.
|  | 373 | Ostroleka (PL) | Stanislawów (PL) | Construction of new 400 kV line Ostrołęka-Stanisławów. | 2020 | Design & Permitting | Investment on time | The project is at the design stage.
|  | 374 | Kozienice (PL) | Siedlce Ujrzanów (PL) | Construction of new 400 kV line Kozienice-Siedlce Ujrzanów. | 2019 | Design & Permitting | Expected earlier than planned previously | The commissioning date has been adjusted compared to the previous national plan and TYNDP.
|  | 1038 | Alytus |  | Construction of the second 500 MW back-to-Back converter station in Alytus | 2020 | Planning | New Investment | This investment was missing not explicitly mentioned in TYNDP 2012,but was already foreseen.
124 | NordBalt phase 2
|  | 378 | Panevezys (LT) | Musa (LT) | New single circuit 330kV OHL (1080 MVA, 80km). | 2022 | Planning | Rescheduled | Investment 60 is postponed in the new national transmission grid development plan. Construction of new NPP, which has impact to the necessity of this investment is unclear, so priority was taken to the other internal investments needed.
|  | 733 | Ekhyddan (SE) | Nybro/Hemsjö (SE) | New single circuit 400 kV OHL. A key investment to accomplish full utilization of the NordBalt cable between Lithuania and Sweden (project 60) at all times. | 2021 | Planning | Rescheduled | Thanks to postponement, other internal investments will be commissioned on time. Congestions due to the delay will be handled by investing in a temporary system protection scheme.
126 | SE North-south reinforcements
|  | 403 | Sweden bidding area SE1 | Sweden bidding area SE3 | Based on a joint Statnett & Svenska Kraftnät study for North-South reinforcements, this contains reinforcements in cut 1 and 2 in Sweden | 2025 | Under Consideration | Investment on time | The investment now combine new investments and the previous 399, 786, 787, 788 and 806. All of the old investments appear only in the list of cancelled investments in the regional plan
127 | 127
|  | 86 | Foggia (IT) | Villanova (IT) | New 178km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. | 2019 | Design & Permitting | Delayed | delay in the permitting process (EIA) concerning the part Foggia-Gissi still under authorization; the part Villanova Gissi is already authorized
|  | 91 | Foggia (IT) | Benevento II (IT) | Upgrade of the existing 85km Foggia-Benevento II 400kV OHL. | 2014 | Under Construction | Investment on time | No changes
|  | 96 | Deliceto (IT) | Bisaccia (IT) | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area. | 2017 | Design & Permitting | Delayed | delay in the permitting process (EIA)
|  | 645 | Laino (IT) | Altomonte (IT) | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria. | 2017 | Design & Permitting | Delayed | delay in the permitting process (EIA)
129 | OWP Northsea TenneT Part 4
|  | 943 | NOR-9-1 | Cloppenburg | Connection of new offshore wind park. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 255 km. Line capacity: 900 MW | 2028 | Under Consideration | New Investment | new investment
|  | 945 | NOR-10-1 | Cloppenburg | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 260km. Line capacity: 900 MW | 2029 | Under Consideration | New Investment | new investment
|  | 947 | NOR-11-2 | Wilhelmshafen | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 270km. Line capacity: 900 MW | 2031 | Under Consideration | New Investment | new investment
|  | 951 | NOR-13-2 | Kreis Segeberg | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 330km. Line capacity: 900 MW | 2030 | Under Consideration | New Investment | new investment
130 | N-S Eastern DE_section East
|  | 208 | Pulgar (DE) | Vieselbach (DE) | Construction of new 380kV double-circuit OHL in existing corridor Pulgar-Vieselbach (103 km). Support of RES and conventional generation integration, maintaining of security of supply and support of market development. | 2024 | Planning | Investment on time | The project is part of the results of the national grid development plan and included in the list of national interest (Bundesbedarfsplan). With in this process the commissioning dates of the included projects have been aligned with the current situation.
|  | 665 | Lauchstädt (DE) | Meitingen (DE) | New DC- lines to integrate new wind generation from control area 50Hertz especially Mecklenburg-Vorpommern, Brandenburg and Sachsen-Anhalt towards Central/south Europe for consumption and storage. | 2022 | Planning | Investment on time | Result from National Grid Development Plan
132 | N-S Western DE_section North_2
|  | 661 | Emden East (DE) | Osterath (DE) | New HVDC-lines from Emden to Osterath to integrate new wind generation especially from North Sea towards Central Germany for consumption. | 2022 | Planning | Investment on time | Progress as planned.
|  | 663 | Cloppenburg East (DE) | Merzen (DE) | New 380-kV double circuit over-head-line Cloppenburg East - Merzen with a total length of ca. 55 km. New errection of a 380-kV substation Merzen. | 2022 | Planning | Investment on time | Progress as planned.
|  | 666 | Conneforde (DE) | Cloppenburg (DE) | New 380-kV-line in existing OHL corridor for integration of on- and offshore Wind generation. Incl. new 380-kV-switchgear in Cloppenburg and new transformers in Cloppenburg | 2022 | Planning | Investment on time | TYDNP 2012 investment 43.A89 is divided in several parts
133 | Longterm German RES
|  | 956 | Schleswig-Hostein | Baden-Würtemberg / Bavaria | new DC- line in HVDC technology to integrate new wind generation from northern Germany toward southern Germany and southern Europe for consumption and storage. Connections points north: Brunsbüttel, Wilster, Kreis Segeberg, Stade, Alfsted. South: Großgartach, Goldshöfe, Raitersaich, Vöhringen | 2030 | Under Consideration | New Investment | new investment
|  | 958 | Güstrow (DE) | Meitingen (DE) | New DC- lines to integrate new wind generation from Baltic Sea and control area 50Hertz especially Mecklenburg-Vorpommern towards Central/south Europe for consumption and storage. | 2034 | Under Consideration | New Investment | New Investment
|  | 969 | lower saxony | NRW | New HVDC line to integrate new wind generation especially from North Sea towards Central Germany for consumption and storage. connections points north: Emden, Conneforde. South: Oberzier, Rommerskirchen | 2030 | Under Consideration | New Investment | new investment
|  | 970 | lower saxony | Hessen/Baden-Würtemberg | New HVDC line to integrate new wind generation especially from North Sea towards South Germany for consumption and storage. Connections points north: Cloppenburg, Elsfelth/West. South: Bürstadt, Philipsburg | 2030 | Under Consideration | New Investment | new investment
134 | N-S Western DE_section South
|  | 176 | Daxlanden (DE) | Eichstetten (DE) | This AC project is necessary in order to evacuate the energy arriving from HVDC corridors towards southern Germany and reinforce the interconnection capacity with Switzerland | 2020 | Under Consideration | Investment on time | No significant change
|  | 179 | Rommerskirchen (DE) | Weißenthurm (DE) | New380 kV overhead line in existing route. Extension and erection of substations incl. erection of 380/110kV-transformers. | 2017 | Under Construction | Delayed | The section Rommerskrichen to Sechtem is delayed because the permitting procedures take longer than planned. The 36 km section from Sechtem to Weißenturm is already commissioned.
|  | 660 | Osterath (DE) | Philippsburg (DE) | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North Sea towards Central-South Germany for consumption and storage. | 2019 | Design & Permitting | Investment on time | Progress as planned.
|  | 680 | Urberach (DE) | Daxlanden (DE) | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2021 | Planning | Investment on time | Progress as planned.
135 | N-S Western DE_parallel lines
|  | 188 | Kruckel (DE) | Dauersberg (DE) | New 380 kV over head lines in existing rout. Extension of existing and erection of several 380/110kV-substations. | 2020 | Design & Permitting | Investment on time | Progress as planned.
|  | 662 | Wehrendorf (DE) | Urberach (DE) | New lines in HVDC technology from Wehrendorf to Urberach to integrate new wind generation especially from North Sea towards Central-South Europe for consumption and storage. | 2022 | Under Consideration | Rescheduled | The need for this long-term investment was not confirmed by the regulatory authority within the national grid development plan 2012. Therefore further studies on this project are ongoing.
|  | 680 | Urberach (DE) | Daxlanden (DE) | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2021 | Planning | Investment on time | Progress as planned.
136 | CSE1
|  | 227 | Banja Luka (BA) | Lika (HR) | New 400kV interconnection line between BA and HR | 2021 | Under Consideration | Rescheduled | Feasibility study is expected to be launched.
|  | 617 | Lika(HR) | Brinje(HR) | New 55 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2020 | Planning | Investment on time | Feasibility study is expected to be launched.
|  | 618 | Lika(HR) | Velebit(HR) | New 60 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2020 | Planning | Investment on time | Feasibility study is expected to be launched.
|  | 619 | Lika (HR) |  | New 400/110 kV substation, 2x300 MVA | 2018 | Planning | Delayed | Feasibility study is expected to be launched.
|  | 620 | Brinje (HR) |  | New 400/220 kV substation, 1x400 MVA | 2020 | Planning | Investment on time | Feasibility study is expected to be launched.
|  | 633 | Konjsko(HR) | Velebit(HR) | New 100km single circuit 400 kV OHL replacing ageing 220 kV overhead line | 2020 | Planning | Investment on time | Feasibility study is expected to be launched.
138 | Black Sea Corridor
|  | 265 | Vidno (BG) | Svoboda (BG) | New 400kV double circuit OHL to accommodate 2000 MW RES generation in N-E Bulgaria (Dobruja region). Line length: 2x70km. | 2019 | Planning | Delayed | Delayed due to lack of funding.
|  | 273 | Cernavoda (RO) | Stalpu (RO) and Gura Ialomitei (RO) | Reinforcement of the cross-section between the Western coast of the Black Sea (Eastern Romania) and the rest of the system. New 400kV double circuit OHL between existing substations Cernavoda and Stalpu, with 1 circuit derivation in/out in 400 kV substation Gura Ialomitei,situated in the vicinity of the new line. Line length:159km.2x1380 MVA | 2019 | Design & Permitting | Delayed | Longer than expected delay regarding clarification of legal framework for right of land acquirement and regarding environment permitting procedure.
|  | 275 | Smardan(RO) | Gutinas(RO) | Reinforcement of the cross-section between the Western coast of the Black Sea (Dobrogea area) and the rest of the system. New 400kV double circuit OHL (one circuit wired)between existing substations. Line length:140km; 1380 MVA | 2020 | Design & Permitting | Investment on time | Rapid increase of wind generation connected in the area. Efforts to be made to speed construction.
|  | 276 | Suceava(RO) | Gadalin(RO) | Reinforcement of the cross-section between developing wind generation hub in Eastern Romania and the rest of the system. New 400kV simple circuit OHL between existing substations. Line length: 260km. 1204 MVA | 2021 | Design & Permitting | Investment on time | No change of status.
|  | 715 | Stalpu (RO) |  | To reinforce the cross-section between the Black Sea coast wind generation in Romania and Bulgaria and the consumption and storage centres to the West, the 220 kV OHL Stalpu-Teleajen-Brazi is upgraded to 400 kV, as a continuation of the 400 kV d.c. OHL Cernavoda-Stalpu. The 220/110 kV substation Stalpu is upgraded to 400/110kV (1x250MVA). | 2019 | Planning | Delayed | The investment was rescheduled in correlation with project 273.
|  | 800 | Dobrudja(BG) | Burgas (BG) | New 140km single circuit 400kV OHL in parallel to the existing one. | 2018 | Planning | Delayed | Delayed due to lack of funding.
|  | 1112 | Svoboda (BG) | splitting point | Construction of a new 400/110kV power line breaking up the existing 400kV Saedinenie OHL and connecting 400/110kV Svoboda substation. | 2019 | Planning | Delayed | Delayed due to lack of funding
141 | CSE3
|  | 223 | Cirkovce (SI) | Heviz (HU) Zerjavenec (HR) | The existing substation of Cirkovce(SI) will be connected to one circuit of the existing Heviz(HU) -Zerjavinec(HR) double circuit 400kV OHL by erecting a new 80km double circuit 400kV OHL in Slovenia. The project will result in two new cross-border circuits: Heviz(HU)-Cirkovce(SI) and Cirkovce (SI)-Žerjavenec (HR). | 2016 | Design & Permitting | Investment on time | Progresses as planned.
|  | 225 | Divaca (SI) | Cirkovce (SI) | Upgrading 220kV lines to 400kV in corridor Divaca-Klece-Bericevo-Podlog-Cirkovce. | 2020 | Design & Permitting | Investment on time | Progresses as planed.
142 | CSE4
|  | 256 | Maritsa East 1 (BG) | N.Santa (GR) | New interconnection line BG-GR by a 130km single circuit 400kV OHL. | 2021 | Design & Permitting | Delayed | Delayed due to lack of funding.
|  | 257 | Maritsa East 1 (BG) | Plovdiv (BG) | New 100km single circuit 400kV OHL in parallel to the existing one. | 2016 | Design & Permitting | Delayed | Delayed due to difficulties with the acquisition of the land
|  | 258 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | New 13km single circuit 400kV OHL in parallel to the existing one. | 2016 | Design & Permitting | Delayed | Delayed due to difficulties with the acquisition of the land
|  | 262 | Maritsa East 1 (BG) | Burgas (BG) | New 400kV OHL. Line length: 150km. | 2016 | Design & Permitting | Delayed | Delayed due to difficulties with the acquisition of the land
144 | Mid Continental East corridor
|  | 238 | Pancevo (RS) | Resita (RO) | New 131 km double circuit 400kV OHL between existing substation in Romania and Serbia (63 km on Romanian side and 68 km on Serbian side)2x1380 MVA. | 2017 | Design & Permitting | Investment on time | Activities are mostly synchronized on both sides. The main problem is right of land along the line path.
|  | 269 | Portile de Fier (RO) | Resita (RO) | New 116 km 400kV OHL between existing substation 400 kV Portile de Fier and new 400 kV substation Resita; 1380 MVA. | 2017 | Design & Permitting | Delayed | The investment was coordinated with investment 50.238. The main problems are right of land along the line path and permitting.
|  | 270 | Resita (RO) | Timisoara-Sacalaz-Arad (RO) | Upgrade of existing 220kV double circuit line Resita-Timisoara-Sacalaz-Arad to 400kV double circuit. Line length: approx.. 100 km d.c. + 74,6 km s.c.;2x1380 MVA; 1204 MVA the circuit between Sacalaz and C. Aradului | 2022 | Design & Permitting | Investment on time | Planned to start after investment 269 is finalized.
|  | 701 | Resita (RO) |  | New 400 kV substation Resita (T400/220 kV 400 MVA + T 400/110 kV 250 MVA), as development of the existing 220/110 kV substation. | 2017 | Design & Permitting | Investment on time | Investment has been split. It is expected that the substation will be commissioned in two stages. In TYNDP 2012, timing referred only to the adjacent lines.
|  | 705 | Timisoara (RO) |  | Replacement of 220 kV substation Timisoara with 400 kV substation (2x250 MVA 400/110 kV) | 2022 | Design & Permitting | Investment on time | Investments 269 and 701 have to be finalized first.
146 | CSE8 Transbalkan Corridor
|  | 625 | Lastva (ME) | Pljevlja (ME) | Reinforcement of the Montenegrin internal 400 kV transmission network with new 160 km double circuit 400kV AC OHL between existing substation Pljevlja and new substation Lastva. The investment will enable secure supply of Montenegrin power system and power transits directed to new HVDC link towards Italy. Also, this investment will enable connection of Renewable energy sources along its route. | 2016 | Design & Permitting | Investment on time | on time
|  | 1075 | Kragujevac | Kraljevo | New internal 400 kV OHL will connect existing SS Kragujevac with SS Kraljevo which is planned for upgrade to 400 kV voltage level. This investment will enhance the possibility of energy transits in direction north-east to south-west and east to west. | 2018 | Design & Permitting | Delayed | New axis for transits from East to the West, typically from Bulgaria to Bosnia and Montenegro, and further to the west.
|  | 1076 | Kraljevo |  | Upgrade of the existing 220/110kV substation Kraljevo 3 by constructing the 400 kV level. | 2017 | Design & Permitting | Delayed | This upgrade is required for the construction of new 400 kV OHL Kragujevac - Kraljevo which will increase local security of supply and power transfer from Eastern to Western part of region.
147 | CSE9
|  | 235 | Tirana(AL) | Pristina (RS) | New 238km 400kV OHL; on 78km the circuit will be installed on the same towers as the Tirana-Podgorica OHL currently in construction ; the rest will be built as single circuit line. | 2016 | Under Construction | Delayed | slight delay, due to procedural reasons. In particular the previous tender has been cancelled and a new one was launched. Currently the project is under construction
|  | 236 | Leskovac(RS) | Shtip (MK) | New 170km 400kV single circuit overhead interconnection between Serbia and FYR of Macedonia. | 2014 | Under Construction | Delayed | land acquisition
|  | 239 | Bitola (MK) | Elbasan (AL) | New 150km cross-border single circuit 400kV OHL between existing substation Bitola and Elbasan | 2017 | Design & Permitting | Delayed | additional investigation of feasibility
|  | 244 | Filippi(GR) | Lagadas (GR) | Connection of the new 400kV substation in Lagadas in Thessaloniki area to the existing substation of Filippi via a new 110km double circuit 400kV OHL. | 2016 | Design & Permitting | Delayed | Delays in the expropriation and permission process. These issues have been resolved.
|  | 708 | Lagadas (GR) |  | New 400kV substation in Lagadas in Thessaloniki area. | 2014 | Under Construction | Delayed | Delays due to environmental licensing process
148 | CCS new
|  | 68 | Okroglo (SI) | South Udine (IT) | New 120km double circuit 400kV OHL between Okroglo(SI) and future substation of South Udine (IT) with PST in Okroglo. The thermal rating will be 1870 MVA per circuit. | 2021 | Planning | Investment on time | There are some issues with social acceptance and territorial constraints. End of construction works are planned by the end of 2021.Full operation is expected by end of 2021(beginning of 2022).
|  | 92 | West Udine (IT) | Redipuglia (IT) | New 40km double circuit 400kV OHL between the existing substations of West Udine and Redipuglia, providing in and out connection to the future 400kV substation of South Udine. | 2016 | Under Construction | Delayed | permitting only recently completed (March 2013) and construction work had to be rescheduled accordingly. Note that the expected commissioning date for the project is December 2016
|  | 615 | Okroglo (SI) |  | Installation of a new 400kV PST in Okroglo which is a part of a double 400 kV OHL Okroglo(SI)-Udine(IT). | 2021 | Planning | Investment on time | End of construction works are planned by the end of 2021. Full operation is expected by end of 2021 (beginning of 2022).
150 | CCS new 10
|  | 616 | Slovenia (SI) | Salgareda (IT) | New HVDC link between Italy and Slovenia. | 2022 | Under Consideration | Investment on time | Project is under feasibility study.
151 | Asturian Ring
|  | 522 | Sama (ES) |  | New 400kV substation Sama in the new Asturias Ring with connection to Lada and a new reactance. | 2026 | Under Consideration | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by)
|  | 523 | Reboria (ES) |  | New 400kV substation Reboria in the Asturian ring with 2 transformers 400/220 kV | 2026 | Under Consideration | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by)
|  | 524 | Costa Verde (ES) |  | New 400kV substation Costa Verde in the Asturian Ring with 2 new transformer units 400/220 kV | 2026 | Under Consideration | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by)
|  | 928 | GOZON (ES) | SAMA (ES) | Asturian Ring. New double circuit Gozon-Reboria-Costa Verde-Sama 400 kV | 2026 | Under Consideration | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by)
152 | France Germany Interconnection
|  | 988 | Vigy | Ensdorf or further (tbd) | Upgrade of the existing Vigy Ensdorf (Uchtelfangen) 400 kV double circuit OHL to increase its capacity. | 2030 | Under Consideration | New Investment | Commissioning date will result from the on-going technical feasibility under investigation.
|  | 989 | Muhlbach | Eichstetten | Operation at 400 kV of the second circuit of a 400kV double circuit OHL currently operated at 225 kV ; some restructuration of the existing grid may be necessary in the area. | 2026 | Under Consideration | New Investment | Studies in progress showed the feasibility of upgrading the existing asset in order to provide mutual support to Alsace and Baden and some exchange capacity increase between France and Germany. The detailed timeline of the investment is under definition.
153 | France-Alderney-Britain
|  | 987 | Cotentin Nord | Exeter | France-Alderney-Britain (FAB) is a new 220km-long HVDC subsea interconnection between Exeter (UK) and Cotentin Nord (France) with VSC converter station at both ends. Expected rated capacity is 2*700 MW. | 2022 | Planning | New Investment | Studies conducted after TYNDP2012 release have shown the economic viability of this interconnection and lead to develop this investment. Feasibility studies (marine surveys)are starting to find a suitable subsea route.
157 | Aragón-Catalonia south
|  | 545 | Escatron (ES) | La Secuita (ES) | New single circuit Escatrón-Els Aubals-La Secuita 400kV OHL. | 2027 | Under Consideration | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by)
|  | 546 | Els Aubals (ES) |  | New 400kV substation in Els Aubals. | 2027 | Under Consideration | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by)
|  | 547 | La Secuita (ES) |  | New 400kV substation in La Secuita with 400/220kV transformer. | 2027 | Under Consideration | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by)
158 | Massif Central South
|  | 597 | La Gaudière (FR) | Rueyres (FR) | New 175-km 400kV double circuit OHL Gaudière-Rueyres substituting to the existing single circuit 400kV OHL | 2023 | Under Consideration | Investment on time | Studies conducted after TYNDP2012 release have led to better investment definition.
163 | BalticCorridor
|  | 1004 | Sindi | Paide | Reinforcement of existing 330 kV OHL between Paide and Sindi 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2030 | Planning | New Investment | -
|  | 1010 | Tartu | Valmiera | Reinforcement of existing 330 kV OHL with new towers and wires of 3x300 mm2 in phase. The thermal capacity of the line is planned 1000 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2030 | Under Consideration | New Investment | -
|  | 1011 | Tsirguliina | Valmiera | Reinforcement of existing 330 kV OHL with new towers and wires of 3x300 mm2 in phase. The thermal capacity of the line is planned 1000 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2030 | Under Consideration | New Investment | -
|  | 1012 | Balti | Tartu | Reinforcement of existing 330 kV OHL between Balti and Tartu 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2030 | Under Consideration | New Investment | -
|  | 1013 | Eesti | Tsirguliina | Reinforcement of existing 330 kV OHL between Eesti and Tsirguliina 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2030 | Under Consideration | New Investment | -
|  | 1062 | TEC2 | Salaspils | Internal reinforcement for Baltic Corridor 600 MW | 2030 | Under Consideration | New Investment | -
|  | 1063 | TEC1 | TEC2 | Investment is necessary to strenghtening internal grid in Latvia due to get transmission capacity of 600 MW via Latvia | 2030 | Under Consideration | New Investment | -
|  | 1064 | Viskali (LV) | Musa (LT) | To get 600 MW of capacity via Baltic States additionally. | 2030 | Under Consideration | New Investment | -
|  | 1065 | Aizkraukle (LV) | Panevežys (LT) | To increase transmission capacity by 600 MW via Baltic States | 2030 | Under Consideration | New Investment | -
164 | N-S Eastern DE_central section
|  | 149 | Dollern (DE) | Stade (DE) | New 380kV double circuit OHL Dollern - Stade including new 380kV switchgear in Stade. Length:14km. | 2022 | Design & Permitting | Delayed | The investment is delayed because of changes in the investment driver
|  | 157 | Wahle (DE) | Mecklar (DE) | New 380kV double circuit OHL Wahle - Mecklar including two new substations. Length: 210km. | 2018 | Design & Permitting | Delayed | delay due to long permitting process
|  | 177 | Goldshöfe (DE) | Bünzwangen (DE) | AC-extension of the "C corridor" at one ending point in Southern Germany towards the consumption areas allowing the existing grid to deal with the additionnal flows from DC-link | 2020 | Design & Permitting | Investment on time | Anticipation of design and permitting phase due to foreseen difficulties (protected area in the Swabian Alps)
|  | 664 | Brunsbüttel, Wilster, Kreis Segeberg | Großgartach, Goldshöfe, Grafenrheinfeld | New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. | 2022 | Planning | Investment on time | The expected commissioning date is 2017 - 2022
|  | 677 | Dollern (DE) | Landesbergen (DE) | New 380 kV line in existing OHL corridor Dollern-Sottrum-Wechold-Landesbergen (130 km) | 2022 | Planning | Investment on time
|  | 685 | Mecklar (DE) | Grafenrheinfeld (DE) | New double circuit OHL 400-kV-line (130 km) | 2022 | Planning | Investment on time
167 | Viking DKW-GB
|  | 436 | Idomlund (DK) | Endrup (DK) | New 74km single circuit 400kV line via cable with capacity of approx. 1200MW. | 2030 | Under Consideration | Rescheduled | In national plan route is replaced by different project, upgrading an existing route from Tjele to Idomlund (72.898). The known route (Endrup-Idomlund) from the TYNDP12 would additionally be necessary as soon as the interconnection to GB is built.
|  | 998 | Idomlund (DKW) | Stella West (GB) | 2x700 MW HVDC subsea link across the North Seas. | 2030 | Under Consideration | New Investment | New opportunity to integrate markets, new opportunity to exploit non correlated RES
168 | Spaak NL
|  | 894 | Sliedrecht area | Dodewaard | New Overhead line from Sliedrecht to Dodewaard of 2x2633 MVA in Wintrack, 65 km | 2025 | Under Consideration | New Investment | This new investment has been identified as a beneficial project in the NSCOGI study and is part of the national grid development plan
170 | Baltics synchro with CE
|  | 380 | Visaginas (LT) | Kruonis (LT) | New single circuit 330kV OHL (1080 MVA, 200km) for the internal grid reinforcement. | 2022 | Under Consideration | Rescheduled | Investment depending on Visaginas NPP construction time.
|  | 382 | Vilnius (LT) | Neris (LT) | New single circuit 330kV OHL (943 MVA, 50km). | 2022 | Planning | Rescheduled | Investment 61 is postponed in the new national transmission grid development plan. Construction of new NPPP is unclear, so priority was taken to the other internal investments needed.
|  | 1034 | Substation in Lithuania | State border | 400 kV interconnection line for synchronous interconnection of Baltics | 2023 | Under Consideration | New Investment | -
172 | ElecLink
|  | 1005 | Sellindge (UK) | Le Mandarins (FR) | Eleclink is a new FR – UK interconnection cable thought the channel Tunnel between Selindge (UK) and Mandarins (FR). Converter stations will be located on Eurotunnel concession at Folkestone and Coquelles. This HVDC interconnection is a PCI project (Project of common interest). It will increase by 1GW the interconnection capacity between UK and FR by 2016. | 2016 | Design & Permitting | New Investment
173 | FR-BE phase 2
|  | 1008 | tbd(FR) | tbd(BE) | The following (combination of) options are envisioned and will be further studied: - Lonny-Achène-Gramme (Reconductoring with High Temperature Low Sag conductors or HVDC) - Capelle-Courcelles (HVDC) - Warande-Zeebrugge/Alfa (HVDC) | 2030 | Under Consideration | New Investment | Preliminary analyses show the need for an additional reinforcement in visions 3 & 4 (2030) between France & Belgium , complementary to project # 23.
174 | Greenconnector
|  | 1014 | Verderio (I) | Sils (CH) | New +/- 400 kV DC cable and subsea link between Switzerland and Italy. Very short AC cable (380 kV) between the site of the converter station and the substation of Sils i.D. | 2018 | Design & Permitting | New Investment | Project application to TYNDP 2014.
175 | Great Belt II
|  | 1000 | Malling (DKW) | Kyndby (DKE) | 600 MW HVDC subsea link between both DK systems (2 synchr. areas, 2 market areas) | 2030 | Under Consideration | New Investment | in case of n expanded DKE-SE connection this link could be beneficial.
176 | Hansa PowerBridge
|  | 995 | Station SE4 | Station DE | New DC cable interconnector between Sweden and Germany. | 2025 | Under Consideration | New Investment | RGBS common investigations for TYNDP 2014
177 | PST Hradec
|  | 889 | Hradec |  | Construction of new PST in substation Hradec with target capacity 2x1700MVA | 2016 | Design & Permitting | Investment on time | Progress as planned
179 | DKE - DE
|  | 1016 | Bjæverskov (DK2) | Bentwisch (DE) | new 600 MW HVDC subsea cable connecting DK2 and DE | 2030 | Under Consideration | New Investment | RGBS common investigations for TYNDP14
182 | BRITIB (GB-FR-ES)
|  | 1111 | Gatica | Indian Queens | Interconnection project between Indian Queens (Great Britain), Cordemais (France) and Gatica (Spain) in a multiterminal HVDC configuration with 3 sections of 1000 MW each, and a submarine route from Spain to Great Britain along the French coast. | 2018 | Under Consideration | New Investment | Project application to TYNDP 2014.
183 | DKW-DE, Westcoast
|  | 1018 | Niebüll (DE) | Endrup (DKW) | new 380 kV cross border line DK1-DE for integration of RES and increase of NTC | 2022 | Planning | Investment on time | in TYNDP12 this investment was part of 43.A90
184 | PST Arkale
|  | 594 | Arkale (ES) |  | New PST in Arkale-Argia 220 kV interconnection line | 2016 | Planning | Investment on time | Draft NDP expected to be published during the preparation of TYNDP 2012 was not finally approved and published, so the investment is yet in a planning stage. If the new NDP is published by 2014, as expected, commissioning date would not be affected.
185 | Greenwire IE-GB
|  | 1020 | Dunstown | Pembroke | Greenwire Interconnector spur 1, enables additional 500MW of interconnection between UK and Irish market | 2018 | Planning | New Investment | Opportunity to connect Irish RES to GB market
|  | 1021 | Woodland | Pentir | Greenwire Interconnector spur 2, enables additional 1000MW of interconnection between UK and Irish market | 2017 | Planning | New Investment | Project application to TYNDP 2014.
186 | east of Austria
|  | 886 | tbd | tbd | To allow the grid integration of the planned renewable energy generation (mainly wind power) in the north-eastern part of Austria ("Weinviertel") and to cover the foreseen load growth in that region the transmission grid infrastructure has to be enforced and new substations for the connection need to be erected | 2021 | Planning | Rescheduled | The development of wind energy in Lower Austria was temporarily stopped by the federal state government to establish a concept for land use. Final concept was published in beginning of 2014 – project now continues with planned commissioning in 2021.
187 | St. Peter - Pleinting
|  | 997 | Pleinting (DE) | St. Peter (AT) | new 380-kV-line Pleinting (DE) - St. Peter (AT) on existing OHL corridor | 2022 | Under Consideration | New Investment | new investment
189 | Irish-Scottish Isles
|  | 1024 | Cruachan | Argyll hub | HVCD link between Cruachan (onshore) to Argyll offshore hub | 2030 | Under Consideration | New Investment | Project application to TYNDP 2014.
|  | 1025 | Argyll hub |  | A new dedicated offshore HVDC hub platform to allow connection of offshore renewable generation and interconnection capacity. | 2030 | Under Consideration | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI
|  | 1026 | Coleraine hub |  | A new dedicated offshore HVDC hub platform to allow connection of offshore renewable generation and interconnection capacity. | 2030 | Under Consideration | New Investment | Project application to TYNDP 2014.
|  | 1027 | Coolkeeragh hub |  | A new dedicated offshore HVDC hub platform to allow connection of offshore renewable generation and interconnection capacity. | 2030 | Under Consideration | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI
|  | 1028 | Argyll | Coleraine | HVCD link between Argyll offshore hub and Coleraine offshore hub | 2030 | Under Consideration | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI
|  | 1029 | Coolkeeragh | Coolkeeragh hub | HVCD link between Coolkeeragh onshore and Coolkeeragh offshore hub | 2030 | Under Consideration | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI
|  | 1030 | Coleraine | Coleraine hub | HVCD link between Colerain onshore and Coleraine offshore hub | 2030 | Under Consideration | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI
|  | 1031 | Coleraine hub | Coolkeeragh hub | HVCD link between Coleraine offshore hub and Coolkeeragh offshore hub | 2030 | Under Consideration | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI
|  | 1032 | Hunterston | Coleraine hub | HVCD link between Hunterston (onshore) to Argyll offshore hub | 2030 | Under Consideration | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI
190 | Norway-Great Britain
|  | 1033 | Sima | Peterhead | A 650 km long 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern Scotland. | 2020 | Design & Permitting | New Investment | Project application to TYNDP 2014.
191 | OWP TenneT Northsea Part 2
|  | 211 | Cluster DolWin 4 (NOR 3-2) | Unterweser | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 190km. Line capacity: 900 MW | 2020 | Under Consideration | Investment on time | on time
|  | 656 | Cluster BorWin3 | Emden/Ost (DE) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 160 km. Line capacity: 900 MW | 2018 | Design & Permitting | Investment on time
|  | 658 | Cluster BorWin4 (DE) | Emden/Ost (DE) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 172 km. Line capacity: 900 MW | 2019 | Design & Permitting | Investment on time
|  | 952 | Cluster DolWin 5 (NOR-1-1) | Halbemond | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 250 km. Line capacity: 900 MW | 2021 | Under Consideration | New Investment | new investment
|  | 953 | Cluster DolWin 6 (NOR-3-3) | Halbemond | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 60km. Line capacity: 900 MW | 2021 | Under Consideration | New Investment | new investment
|  | 954 | Cluster BorWin 5 (NOR-7-1) | Halbemond | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 260km. Line capacity: 900 MW | 2022 | Under Consideration | New Investment | new investment
192 | OWP Northsea TenneT Part 3
|  | 659 | Cluster SylWin2 (DE) | Büttel (DE) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205 km. Line capacity: 900 MW | 2023 | Under Consideration | Investment on time
|  | 946 | NOR-11-1 | Elsfleth/West | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 230km. Line capacity: 900 MW | 2026 | Under Consideration | New Investment | new investment
|  | 948 | NOR-12-1 | Wilhelmshafen | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 230km. Line capacity: 900 MW | 2027 | Under Consideration | New Investment | new investment
|  | 950 | NOR-13-1 | Kreis Segeberg | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 330km. Line capacity: 900 MW | 2025 | Under Consideration | New Investment | new investment
|  | 955 | Cluster BorWin6 (NOR-7-2) | Unterweser | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 180km. Line capacity: 900 MW | 2023 | Under Consideration | New Investment | new investment
193 | Godelleta-Morella/La Plana
|  | 927 | La Plana/Morella | Godelleta | New 400 kV axis Godelleta-Morella/La Plana (Spain) | 2023 | Under Consideration | Rescheduled | Investment rescheduled as a result of changes in planning data inputs.
194 | Cartuja
|  | 561 | Cartuja (ES) |  | New 400kV substation Cartuja with a 400/220kV transformer. | 2022 | Under Consideration | Rescheduled | Investment rescheduled as the associated new wind power plants have been postponed
|  | 929 | Cartuja | Arcos | New double circuit Cartuja-Arcos 400 kV | 2022 | Under Consideration | Rescheduled | Investment rescheduled as the associated new wind power plants have been postponed
197 | N-S Finland P1 stage 2
|  | 742 | Pyhänselkä (FI) | Petäjävesi (FI) | New single circuit 400 kV OHLs will be built from middle Finland to Oulujoki Area to increase the capacity between North and South Finland. Will replace existing 220 kV lines. | 2023 | Design & Permitting | Delayed | Rescheduled due to timing of system changes that trigger the investment. End station name updated.
198 | Area of Lake Constance
|  | 136 | Border area (DE-AT) | Rüthi (CH) | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 2022 | Planning | Investment on time | investment 136 now comprises the cross-border part of former investment 136, and investment 1099 is the Swiss part of former investment 136.
|  | 984 | Herbertingen | Tiengen | Herbertingen – Tiengen: Between the two substations Herbertingen and Tiengen a new line will be constructed in an existing corridor. Enhancement of the grid, which will increase transmission capacity noticeably, is needed at the substation Herbertingen. | 2020 | Planning | Investment on time | Progress as planned. This project is a concretion of TYNDP12 project 44.A77. Due to the ongoing planning stage, this section was developed and an own investment item was created.
|  | 985 | point Rommelsbach | Herbertingen | Rommelsbach – Herbertingen: Between point Rommelsbach and substation Herbertingen a new line will be constructed in an existing corridor. This will significantly increase transmission capacity (grid enhancement). | 2018 | Planning | Investment on time | Progress as planned. This project is a concretion of TYNDP12 project 44.A77. Due to the ongoing planning stage, this section was developed and an own investment item was created.
|  | 986 | point Wullenstetten (DE) | point Niederwangen (DE) | Point Wullenstetten – Point Niederwangen Between point Wullenstetten and point Niederwangen an upgrade of an existing 380-kV-line is necessary (grid enhancement). Thereby, a significantly higher transmission capacity is realized. The 380 kV substation station Dellmensingen is due to be extended (grid enhancement). | 2020 | Planning | Investment on time | This project is a concretion of TYNDP 2012 project 44.A77. Due to the ongoing planning stage, this section was developed and an own investment item was created.
|  | 1043 | Neuravensburg | border area (AT) | Point Neuravensburg – Point Austrian National border (AT) Between switching point Neuravensburg and Austrian National border (AT) a new line with a significantly higher transmission capacity will be constructed in an existing corridor (grid enhancement). | 2023 | Planning | Investment on time | This project is a concretion of TYNDP 2012 project 44.A77. This investment is caused by the investment 136 "Bodensee Studie". Due to the ongoing planning stage, this section was developed and an own investment item was created.
199 | Lake Geneva South
|  | 1051 | CORNIER (FR) | CHAVALON (CH) | Upgrade of the double circuit 225 kV line between Cornier (France) and Riddes and Saint Triphon (Switzerland) to a single circuit 400 kV line between Cornier and Chavalon (Switzerland). In order to take most benefit from this, the existing 400 kV Genissiat substation will be connected in/out to the existing line Cornier-Montagny. | 2025 | Under Consideration | New Investment | grid studies conducted after TYNDP2012 release allowed to define the investment
200 | North-South corridor
|  | 306 | Vitkov (CZ) |  | New 400/110kV substation equipped with transformers 2x350MVA. | 2020 | Design & Permitting | Delayed | Complication of permitting procedure
|  | 307 | Vernerov (CZ) |  | New 400/110kV substation equipped with transformers 2x350MVA. | 2017 | Design & Permitting | Delayed | Complication with permitting procedure.
|  | 308 | Vernerov (CZ) | Vitkov (CZ) | New 400kV double circuit OHL, 1385 MVA. | 2019 | Design & Permitting | Investment on time | As planned
|  | 309 | Vitkov (CZ) | Prestice (CZ) | New 400kV double circuit OHL, 2x1730 MVA. | 2021 | Design & Permitting | Investment on time | As planned
|  | 312 | Mirovka (CZ) |  | Upgrade of the existing substation 400/110kV with two transformers 2x350MVA. | 2020 | Design & Permitting | Delayed | Project delayed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side
|  | 314 | Mirovka (CZ) | V413 (CZ) | New double circuit OHL with a capacity of 2x1385 MVA and 26.5km length. | 2020 | Design & Permitting | Delayed | Project delayed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side
203 | Aragón-Castellón
|  | 537 | Mudejar (ES) |  | New 400kV substation Mudejar and connection to the axis Aragón-Teruel | 2016 | Design & Permitting | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP
|  | 538 | Morella (ES) | La Plana(ES) | Southern part of the new Cantabric-Mediterranean axis. New double circuit Morella-la Plana 400kV-OHL. | 2018 | Design & Permitting | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP
|  | 1069 | Mezquita | Morella | Mezquita-Morella 400 kV line | 2017 | Design & Permitting | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP
|  | 1070 | Mudejar | Morella | OHL 400kV AC Mudejar-Morella | 2017 | Design & Permitting | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP
204 | N-S transmission DE_par_line_2
|  | 686 | Schalkau / area of Altenfeld (DE) | area of Grafenrheinfeld (DE) | New double circuit OHL 380-kV-line (130 km) | 2024 | Under Consideration | Rescheduled | Delay due to missing confirmation by the regulator
205 | N-S transmission DE_par_line_1
|  | 153 | Redwitz (DE) | Grafenrheinfeld (DE) | Upgrade of 220kV connection Redwitz - Grafenrheinfeld to 380kV, including new 380kV switchgear Eltmann. Line length: 97km. | 2015 | Design & Permitting | Delayed | Delayed due to delayed of related investment 45.193 and unexpected long permitting process of the investment itself
|  | 193 | Vieselbach (DE) | Redwitz (DE) | New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see investment 153). The Section Lauchstädt-Vieselbach has already been commissioned. Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is right downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids. | 2015 | Design & Permitting | Delayed | Previously "mid term" is now updated to specific date. Partly under construction (section Vieselbach – Altenfeld). 3rd section (Altenfeld – Redwitz) in permitting process, long permitting process with strong public resistance.
206 | Reinforcement Southern DE
|  | 682 | Großgartach (DE) | Endersbach (DE) | AC-extension of the "C corridor" at one ending point in Southern Germany towards the consumption areas allowing the existing grid to deal with the additionnal flows from DC-link | 2019 | Planning | Investment on time | Standard processing 2018-2019
|  | 687 | Redwitz (DE) | Schwandorf (DE) | New double circuit OHL 380 kV line in existing OHL corridor Redwitz-Mechlenreuth-Etzenricht-Schwandorf (185 km) | 2020 | Planning | Investment on time
|  | 688 | Raitersaich (DE) | Isar (DE) | New 380 kV line in existing OHL corridor Raitersaich - Ludersheim - Sittling - Isar or Altheim (160 km) | 2024 | Under Consideration | Rescheduled | Delay due to missing confirmation by the regulator
|  | 990 | Grafenrheinfeld (DE) | Großgartach (DE) | AC-extension of the "C corridor" between two of its ending points in Southern Germany allowing the existing grid to deal with the additionnal flows from DC-link | 2019 | Planning | New Investment | Standard processing
207 | Reinforcement Northwestern DE
|  | 675 | Conneforde (DE) | Unterweser (DE) | Upgrade of 220-kV-circuit Unterweser-Conneforde to 380kV , Line length: 32 km. | 2024 | Under Consideration | Rescheduled | Delay due to missing confirmation by the regulator
|  | 676 | Dollern (DE) | Elsfleht/West (DE) | New 380 kV line in existing OHL corridor Dollern - Elsfleht/West Length:100 km | 2024 | Under Consideration | Rescheduled | Delay due to missing confirmation by the regulator
|  | 939 | Conneforde | Emden/Ost | New 380-kV-line in existing OHL corridor for integration of RES | 2019 | Planning | Delayed | In TYNDP 2012 part of investment 43.A89
|  | 940 | Emden/Ost | Halbemond | New 380-kV-line Emden - Halbemond for RES integration incl. new transformers in Halbemond | 2021 | Under Consideration | Rescheduled | In TYNDP 2012 part of investment 43.A89
208 | N-S Western DE_section North_1
|  | 150 | Conneforde (DE) | Fedderwarden (DE) | New 380kV double circuit (OHL, partly underground) Conneforde - Wilhelmshaven (Fedderwarden, former Maade) including new 400kV switchgear Fedderwarden. Length: 35 km. | 2018 | Design & Permitting | Investment on time
|  | 151 | Wehrendorf (DE) | Ganderkesee (DE) | New line (length: ca. 95km), extension of existing and erection of substations, erection of 380/110kV-transformers. | 2017 | Design & Permitting | Delayed | delay due to long permitting process
|  | 156 | Niederrhein (DE) | Dörpen/West (DE) | New 380 kV double circuit overhead line Dörpen - Niederrhein including extension of existing substations. | 2018 | Design & Permitting | Delayed | The project is delayed due to delays in public-law and civil-law licensing procedures.
209 | Reinforcement Northeastern DE
|  | 147 | Dollern (DE) | Hamburg/Nord (DE) | New 380kV double circuit OHL Dollern - Hamburg/Nord. Length:43km. First circuit 2015, second circuit 2017 | 2017 | Under Construction | Delayed | Delay due to long permitting process
|  | 148 | Audorf (DE) | Hamburg/Nord (DE) | New 380kV double circuit OHL Audorf - Hamburg/Nord including two new 380/220kV transformers in substation Audorf and new 380 kV Switchgear in Kummerfeld. Length: 65km. | 2017 | Design & Permitting | Delayed | delay due to long permitting process
|  | 667 | Brunsbüttel (DE) | Niebüll | About 135 km new 380-kV-lines and around 10 new transformers for integration of onshore Wind in Schleswig-Holstein and increase of NTC between DE and DK | 2018 | Planning | Delayed | The old investment 43.A90 is now divided in several parts.
|  | 935 | Kreis Segeberg | Göhl | New 380-kV-lineKreis Segeberg - Lübeck - Siems - Göhl, including five new transformers | 2021 | Under Consideration | Rescheduled | Investment was part of investment 43.A90 in TYNDP 2012. Now separately
|  | 937 | Audorf | Kiel | New 380-kV-line in existing OHL corridor including 4 new transformers and new 380-kV-switchgears in Kiel/West and Kiel/Süd | 2021 | Under Consideration | Rescheduled | In TYNDP 2012 this investment was part of investment 43.A90
210 | E15
|  | 1071 | Würmlach (AT) | Somplago (IT) | Würmlach - Somplago | 2017 | Design & Permitting | New Investment | Project application to TYNDP 2014.
213 | Santa Llogaia - Bescano
|  | 508 | Ramis (ES) |  | New 400kV substation in Ramis with two 400/220kV transformers; connection as input/output in Santa Llogaia - Bescano line | 2015 | Design & Permitting | Delayed | Answering all concerns expressed during the authorization process led to postponing the investment.
|  | 509 | Santa Llogaia (ES) |  | New 400kV substation Sta.Llogaia. | 2014 | Under Construction | Delayed | Answering all concerns expressed during the authorization process led to postponing the investment.
|  | 1068 | Bescanó | Santa Llogaia | New OHL 400kV AC double circuit Bescano-Santa Llogaia, required to connect the new HVDC interconnection to the existing network and secure the supply in the area of Gerona | 2014 | Under Construction | Investment on time | Progress as planned
214 | Interco Iceland-UK
|  | 1082 | tbd | tbd | Interco Iceland-UK | 2030 | Under Consideration | New Investment
216 | Massif Central North
|  | 999 | Marmagne | Rueyres | Erection of a new 400-kV double circuit line substituting an existing 400-kV single circuit line. | 2030 | Under Consideration | Investment on time | This long term investment is only needed for scenarios with high RES development in the area, especially wind and hydro; additional studies are needed for better investment definition.
219 | EUROASIA interconnector
|  | 949 | Korakia site (CRETE) | Athens site (GREECE) | New HVDC interconnection between Crete and Athens | 2020 | Planning | New Investment | Project application to TYNDP 2014.
|  | 971 | Vasilikos site (CYPRUS) | Korakia site (CRETE) | New HVDC interconnection between Cyprus and Crete Islands | 2022 | Planning | New Investment | Project application to TYNDP 2014.
|  | 1054 | Hadera site (ISRAEL) | Vasilikos site (CYPRUS) | New HVDC interconnection between Israel and Cyprus | 2018 | Planning | New Investment | Project application to TYNDP 2014.
220 | Southern Aegean Interconnector
|  | 936 | KANDELIOUSA | SYRNA | AC Subm. Cable to connect Kandeliousa offshore WF HV substation (18MW) to Syrna SS | 2020 | Design & Permitting | New Investment | Project application to TYNDP 2014. Commissioning date: 2018-2020
|  | 944 | KANDELIOUSA | PERGOUSA | AC Subm. Cable to connect Pergousa offshore WF HV substation (42MW) to the Kandeliousa SS | 2020 | Design & Permitting | Investment on time | Project application to TYNDP 2014.Commissioning date: 2018-2020
|  | 973 | SYRNA | LEVITHA | AC Subm. Cable to connect Syrna offshore WF HV substation (156MW) to the AC part of the Levitha Converter SS | 2020 | Design & Permitting | New Investment | Project application to TYNDP 2014. commissioning date: 2018-2020
|  | 979 | KINAROS | LEVITHA | AC Subm. Cable to connect Kinaros offshore WF HV substation (111MW) to the AC side of the Levitha Converter SS | 2020 | Design & Permitting | New Investment | Project application to TYNDP 2014. commissioning date: 2018=2020
|  | 1001 | LEVITHA island | KORAKIA (new s/s in Crete) | New DC link (2 converter SS + 250 km DC subm. cable) to Crete | 2020 | Design & Permitting | New Investment | Project application to TYNDP 2014. commissioning date: 2018-2020
|  | 1042 | LAVRION 400kV S/S | LEVITHA island | New DC link (2 converter SS + 270 km DC subm. cable) to connect 537MW of offshore WF generation to the mainland (Area of Athens) | 2020 | Design & Permitting | New Investment | Project application to TYNDP 2014. commissioning date expected: 2018-2020
225 | ALEGRO 2
|  | 1107 | BE (TBD) | DE (TBD) | This investment item envisions the possibility of a second 1 GW interconnection between Belgium and Germany. Subject to further studies. | 2030 | Under Consideration | New Investment | Preliminary studies on high RES scenario's have indicated potential for further regional welfare & RES integration increase by further increasing the interconnection capacity between Belgium & Germany towards time horizon 2025-2030.
227 | CSE8 Transbalkan Corridor
|  | 627 | Bajina Basta (RS) | Visegrad (BA) | Description of broader context - New double circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equipped. In the second phase New SS Bistrica (RS) would be connected to the existing double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 2020 | Planning | Investment on time | Ongoing Regional trilateral feasibility study (financed by WBIF and supported by EC) between three TSOs (EMS, NOS BiH and CGES), including ESIA and preliminary design. Expected finalization time mid 2014.
|  | 628 | SS Bajina Basta (RS) | SS Obrenovac (RS) | Double circuit 400 kV OHL between upgraded substation Bajina Basta and substation Obrenovac. Part of larger regional transmission corridor northeast-southwest. | 2019 | Design & Permitting | Delayed | Feasibility study, ESIA and preliminary design finalized (financed by WBIF and supported by EC). Ongoing process of adoption to local legislation needs.
|  | 630 | Bajina Basta (RS) | Pljevlja (ME) | Description of broader context - New double circuit 400kV OHL (105km RS + 16km ME) connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equipped. In the second phase New SS Bistrica (RS) would be connected to the existing double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 2020 | Planning | Investment on time | Ongoing Regional trilateral feasibility study (financed by WBIF and supported by EC) between three TSOs (EMS, NOS BiH and CGES), including ESIA and preliminary design. Expected finalization time mid 2014.
|  | 631 | Bajina Basta (RS) |  | Upgrade of existing 220/110 kV substation in Bajina Basta to 400/220/110 kV substation as part of overall western Serbia system upgrade to 400 kV voltage level. Part of larger regional transmission corridor northeast-southwest. | 2019 | Design & Permitting | Delayed | Feasibility study, ESIA and preliminary design finalized (financed by WBIF and supported by EC). Ongoing process of adoption to local legislation needs.
228 | Marex
|  | 1113 | Glinsk 400kV | Connah's Quay 400kV | 1500 MW HVDC VSC cable | 2018 | Planning | New Investment | Project application for TYNDP 2014.

## CBA analysis
Project Index | scenario | GTC direction 1 (MW) | GTC direction 2 (MW) | B1 SoS (MWh/year) | B2 SEW (MEuros/year) | B3 RES integration |  | B4 Losses (MWh/year) | B5 CO2 Emissions (kT/year) | B6 Technical Resilience | B7 Flexibility | S1 - protected areas | S2 - urban areas
1 | This project integrates new amounts of Hydro Power Plants in the Northern region of Portugal and creates better conditions to evacuate Wind Power already existent and new with authorization for connection (with the reinforcement of the local 220kV network). These new amounts of power will increase the flows in the region, and it is expected that the flows could reach 3800 MW, which must be evacuated to the littoral strip and south Portugal through three new 400kV independent routes. Part of these flows will interfere and accumulate with the already existent flows entering in Portugal through the international interconnections with Spain on the North, the 400kV Alto Lindoso-Riba de Ave-Recarei and Lagoaça-Aldeadávila axis, which induces additional needs for reinforcement of this axis in a coordinated way.
| Scenario Vision 1 - 2030 | inside=>outside: 3700-5100 | outside=>inside: 0-0 | - | [110;130] | 2432 | MW | [46000;56000] | [-410;-340] | 1 | 3 | Negligible or less than 15km | 15-25km
| Scenario Vision 2 - 2030 |  |  | - | [110;130] | 2432 | MW | [50000;61000] | [-410;-340]
| Scenario Vision 3 - 2030 |  |  | - | [120;150] | 2900 | MW | [55000;68000] | [-500;-410]
| Scenario Vision 4 - 2030 |  |  | - | [92;110] | 3000 | MW | [4100;5100] | [-390;-320]
2 | This project integrates new hydro power plants (some of them with pumping) and evacuates the existent and new wind generation in the inner central region of Portugal (the wind target in this region overcomes surmounts of more than 2000 MW). The existing network of 220 kV and 150kV is no more adequate to integrate these new amounts of power, and a new 400kV axis should be launched in this region in two major routes: one to the littoral strip (Penela/Paraimo/Batalha) and another by the interior, establishing a connection to Falagueira substation, where there is an interconnection with Spain (Falagueira-Cedillo).
| Scenario Vision 1 - 2030 | upstream=>downstream: 1200-1600 | downstream=>upstream: 0-0 | - | [29;36] | 576 | MW | [9200;11000] | [-110;-90] | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [29;36] | 576 | MW | [10000;12000] | [-110;-90]
| Scenario Vision 3 - 2030 |  |  | - | [76;93] | 1000 | MW | [17000;21000] | [-320;-260]
| Scenario Vision 4 - 2030 |  |  | - | [63;77] | 1050 | MW | [1400;1700] | [-260;-210]
4 | This project increases the interconnection capacity between Portugal and Spain. Larger and more volatile flows are expected between both countries due to the huge increase of volatile sources and the market interchanges. The project includes two 400kV interconnection routes, besides the 400kV internal reinforcements required, one in the North (Fontefría - V.Conde) and other in the South (P.Guzman – Tavira that will be commissioned in 2014), due to the important loop flows between the two countries. Only with these both new 400kV interconnections is possible to reach the interconnection capacity of 3200 MW agreed between Portugal and Spain. This project will also have a benefit in reducing the spilled energy in the Iberian Peninsula.
| Scenario Vision 1 - 2030 | PT=>ES: 400 | ES=>PT: 1000 | - | [4;30] | [7200;8800] | MWh | [-14000;-12000] | [180;220] | 3 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [3;33] | [7900;9600] | MWh | [-13000;-11000] | [160;200]
| Scenario Vision 3 - 2030 |  |  | - | [20;50] | [160000;200000] | MWh | [3600;4400] | [-110;-90]
| Scenario Vision 4 - 2030 |  |  | - | [64;130] | [630000;770000] | MWh | [8100;9900] | [-330;-270]
5 | In order to fulfill the governmental 2800 MW objective of exchange capacity between France-Spain, the Eastern interconnection was planned. After being classified as a Priority Project by the European Commission, and after the involvement of Prof. Monti as European Coordinator, it was stated that the unique feasible alternative for thedevelopment of the Spanish-French interconnection by the Eastern Pyrenees was a solution in DC totally buried for the cross-border section of the interconnection, with a terrestrial drawing up, as well as using, as far as possible, existing infrastructure corridors within a certain area. The interconnection link based on the new VSC technology will connect Baixas (France) to Santa-Llogaia (Spain), via a 65-km long HVDC +/- 320 kV underground cable system, with 2*1000 MW rated power and AC/DC converters at both ends. This project is carried out by INELFE, a REE-RTE joint venture, created for this purpose. Some internal reinforcements, both in Spain and France, are required. In France, the uprate of Baixas –Gaudiere 400kV is already commissioned. In Spain, reinforcements are included in project 213 in addition to certain individual investments of regional relevance. The project allows important Social Economic Welfare, as it allows the use of more efficient and cheaper technologies, and avoids spillage of RES, especially in the Iberian Peninsula.
| Scenario Vision 1 - 2030 | ES=>FR: 1400 | FR=>ES: 1200 | [100;250] | [20;130] | [110000;130000] | MWh | [450000;550000] | [1600;2000] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | [110;260] | [22;140] | [120000;150000] | MWh | [280000;380000] | [1800;2200]
| Scenario Vision 3 - 2030 |  |  | [120;270] | [70;150] | [590000;720000] | MWh | [180000;280000] | [-1100;-870]
| Scenario Vision 4 - 2030 |  |  | [120;280] | [210;280] | [1300000;1500000] | MWh | [360000;460000] | [-1500;-1300]
13 | A new double circuit Caparacena-Baza-La Ribina 400 kV OHL, with two new 400 kV substations in Baza and La Ribina, will allow integrating an important contingent of wind and solar generation, both at transmission and distribution level in an area of Jaen where the transmission network is very weak. Moreover, a new pumping hydropower plant with pumping storage is expected in this area. On the other hand, the project will help reducing congestion in the existing single circuit Litoral-Tabernas-Hueneja-Caparacena 400 kV, between Almeria and Granada.
| Scenario Vision 1 - 2030 | inside=>outside: 550-770 | outside=>inside: 3280-3630 | - | [33;40] | [380000;470000] | MWh | [-18000;-14000] | [-180;-140] | 2 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [35;42] | [400000;490000] | MWh | [-18000;-15000] | [-190;-150]
| Scenario Vision 3 - 2030 |  |  | - | [180;230] | [2000000;2500000] | MWh | [-20000;-16000] | [-870;-710]
| Scenario Vision 4 - 2030 |  |  | - | [230;280] | [2400000;3000000] | MWh | [-20000;-16000] | [-790;-640]
16 | In order to fulfill the governmental long term objective of exchange capacity between France-Spain, the Western interconnection is under analysis. Deep technical and environmental prefeasibility studies across the whole French-Spanish border showed that the preferential strategy was a new HVDC submarine interconnection through the Biscay/Gascogne Bay from the Basque Country in Spain to the Aquitaine area in France. Since the last TYNDP the analysis on technical feasibility and environmental aspects, especially for the subsea route have had good process. However, the project is still under analysis and final definition is in progress. The project allows important Social Economic Welfare, as it allows the use of more efficient and cheaper technologies, avoids spillage of RES, especially in the Iberian Peninsula and reduces the consideration of Spain as an electric island.
| Scenario Vision 1 - 2030 | ES=>FR: 2500 | FR=>ES: 2200 | - | [90;210] | [130000;160000] | MWh | [200000;300000] | [3300;4000] | 2 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [95;220] | [140000;170000] | MWh | [210000;310000] | [3500;4300]
| Scenario Vision 3 - 2030 |  |  | - | [90;250] | [900000;1100000] | MWh | [240000;340000] | [-1900;-1500]
| Scenario Vision 4 - 2030 |  |  | - | [310;470] | [2100000;2600000] | MWh | [390000;490000] | [-2400;-2000]
21 | The Project comprises a new HVDC interconnection between France and Italy as well as the removing of limitations on existing 380 kV internal Italian lines. The removing of limitation is necessary to take full advantage of the increase of interconnection capacity provided by the cross-border line. The project favours the market integration between Italy and France as well as the use of the most efficient generation capacity; it also increases possible mutual support of both countries. In addition, the project can contribute to RES integration in the European interconnected system by improving cross border exchanges. Such benefits are ensured within different future scenarios.
| Scenario Vision 1 - 2030 | FR=>IT: 1200 | IT=>FR: 1000 | - | [43;52] | 0 | MWh | [250000;310000] | [220;260] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [29;36] | 0 | MWh | [250000;300000] | 0
| Scenario Vision 3 - 2030 |  |  | - | [94;120] | [49000;60000] | MWh | [8100;9900] | [-440;-360]
| Scenario Vision 4 - 2030 |  |  | - | [190;230] | [290000;350000] | MWh | [36000;44000] | [-1200;-980]
22 | The project will increase the France-Switzerland cross-border capacity and secure the supply to Geneva by uprating the existing 225kV cross-border line Genissiat(FR)-Verbois(CH).
| Scenario Vision 1 - 2030 | FR=>CH: 500 | CH=>FR: 200 | - | [3;4] | 0 | MWh | [9000;11000] | 0 | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [4;5] | 0 | MWh | [9000;11000] | 0
| Scenario Vision 3 - 2030 |  |  | - | [27;33] | [16000;19000] | MWh | [9000;11000] | [-190;-160]
| Scenario Vision 4 - 2030 |  |  | - | [72;89] | [90000;110000] | MWh | [23000;28000] | [-510;-420]
23 | The project aims at ensuring reliable grid operation to cope with more volatile south-north flows, and at increasing the exchange capacities between France & Belgium to sustain an adequate level of market integration.
| Scenario Vision 1 - 2030 | FR=>BE: 600-1300 | BE=>FR: 600-1300 | - | [5;15] | [18000;22000] | MWh | 0 | [-120;-99] | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [0;10] | [19000;23000] | MWh | 0 | [27;33]
| Scenario Vision 3 - 2030 |  |  | - | [10;20] | [77000;94000] | MWh | 0 | [-130;-100]
| Scenario Vision 4 - 2030 |  |  | - | [20;60] | [200000;240000] | MWh | 0 | [-240;-200]
24 | The need to reinforce the Belgian North Border is driven by a congruation of factors - ensuring reliable grid cooperation in a context of increasing & more volatile international fluxes on Belgian north-south axis (Zandvliet to Horta; Van Eyck to Gramme) which could cause internal congestions and negatively effect market capacity - desire to further develop market capacity between Belgium & the Netherlands with +- 1000 MW - possible connection of new central production units on these north-south axis: potential projects exist on each axis of 900-1000 MW each - increasing industrial demand around Antwerp harbour area The project as such consists of the following subprojects facilitating its realization in a modular way: - Brabo & PST4 (+upgrade Doel-Zandvliet): integration of 4th PST on Belgian North Border and the realization of a new 380kV circuit via Lillo creating a parallel path to the existing Zandvliet-Mercator connection - Horta-Mercator in HTLS: the upgrade of this central link to transport fluxes between France, Stevin & the Netherlands consists in replacing the existing 380kV double circuit with high-performance conductors (HTLS). - Gramme-Van Eyck: capacity increase by going from 1 to 2 380kV circuits and creating a subsequent substation Van Eyck - Gramme-Van Eyck + Massenhoven-Meerhout-Van Eyck: the need to futher upgrade these axis has been identified but depends heavily on the evolution of production in the Limburg-Liège area in combination with the evolution of the (transit)flux, and will as such be further monitored
| S1 EU202020 - 2020 | NL=>BE: 1000-1500 | BE=>NL: 1000-1500 | [300;570] | [18;22] | [45000;55000] | MWh | 0 | [0;500] | 5 | 2 | 15-50km | 25-50km
25 | IFA2 is a new subsea HVDC VSC interconnection that will develop between the area of Caen in France and the region of Southampton in Great Britain. the objective is to increase the interconnection capacity between Great Britain and continent and to integrate RES generation, especially wind in Great Britain. It has been selected as PCI 1.7.2 in the NSCOG corridor on 14/10/13. Some mutual support is also expected but this is not reflected in the security of supply indicator assessed according to the CBA rules.
| Scenario Vision 1 - 2030 | FR=>GB: 1000 | GB=>FR: 1000 | - | [35;75] | [230000;280000] | MWh | [200000;240000] | [170;210] | 1 | 4 | 50-100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [0;60] | [36000;44000] | MWh | [200000;240000] | [220;260]
| Scenario Vision 3 - 2030 |  |  | - | [170;250] | [1700000;2000000] | MWh | [190000;240000] | [-1400;-1200]
| Scenario Vision 4 - 2030 |  |  | - | [180;210] | [1500000;1800000] | MWh | [190000;240000] | [-1100;-940]
26 | Reinforcement of the interconnection between Italy and Austria via two new single circuit cross-border lines and closure of the 380-kV-Security Ring in Austria. The project supports the interaction between the of RES in Italy and the eastern part of Austria with the pump storage power plants in the Austrian Alps.
| Scenario Vision 1 - 2030 | AT=>IT: 1450 | IT=>AT: 1350 | - | [57;70] | 0 | MWh | [-510000;-410000] | [520;640] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [89;110] | [2700;3300] | MWh | [-520000;-420000] | [-490;-400]
| Scenario Vision 3 - 2030 |  |  | - | [56;69] | [1100;1300] | MWh | [-200000;-160000] | [-130;-100]
| Scenario Vision 4 - 2030 |  |  | - | [100;130] | [11000;14000] | MWh | [-280000;-230000] | [-300;-240]
28 | The Italy-Montenegro interconnection project includes a new HVDC subsea cable between Villanova (Italy) and Lastva (Montenegro) and the DC converter stations. The project is also correlated to cluster 146 where Montenegrin internal line and Montenegro- Serbia-Bosnia interconnections are planned. The project allows the market development between Italy and the Balkans; increases the transmission capacities; helps to use most efficient generation capacity; enables possible mutual support of Italian and Balkan power systems; contributes to RES integration in the European interconnected system by improving cross border exchanges. Such benefits are ensured within different future scenarios.
| Scenario Vision 1 - 2030 | IT=>ME: 1000 | ME=>IT: 1000 | - | [140;170] | [13000;15000] | MWh | [-18000;-14000] | [1400;1700] | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [110;130] | 0 | MWh | [-18000;-14000] | [1100;1300]
| Scenario Vision 3 - 2030 |  |  | - | [290;360] | [330000;410000] | MWh | [1800;2200] | [-650;-530]
| Scenario Vision 4 - 2030 |  |  | - | [290;350] | [990000;1200000] | MWh | [3600;4400] | [-1700;-1400]
29 | The project consists in a new interconnection between Italy and North Africa to be realized through an HVDC submarine cable. The project favors the use of the most efficient capacity in the PAN European interconnected system. The project also increases the system operational flexibility. Such benefits are ensured according to different future scenarios
| Scenario Vision 1 - 2030 | IT=>South: 600 | South=>IT: 600 | - | [81;99] | 0 | MWh | [18000;22000] | 0 | 1 | 4 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [81;99] | 0 | MWh | [18000;22000] | 0
| Scenario Vision 3 - 2030 |  |  | - | [81;99] | 0 | MWh | [18000;22000] | 0
| Scenario Vision 4 - 2030 |  |  | - | [81;99] | 0 | MWh | [18000;22000] | 0
30 | The project consists in the strengthening of Sicily - mainland 400 kV interconnection through a new double circuit line which will be realized partly as a subsea cable as well as over-head line. The activity is part of the wider network reinforcement program which involves the Sicilian 400 kV grid. The project allows removing internal bottlenecks and increases market and RES integration.
| Scenario Vision 1 - 2030 | South=>IT: 1000 | IT=>South: 1000 | [18000;22000] | [320;390] | [1500000;1900000] | MWh | [-39000;-32000] | [-1400;-1200] | 1 | 2 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | [19000;23000] | [300;370] | [1500000;1800000] | MWh | [-39000;-32000] | [-1300;-1100]
| Scenario Vision 3 - 2030 |  |  | [23000;28000] | [490;590] | [2000000;2400000] | MWh | [-55000;-45000] | [-2000;-1700]
| Scenario Vision 4 - 2030 |  |  | [37000;45000] | [410;510] | [2000000;2400000] | MWh | [-61000;-50000] | [-2000;-1600]
31 | The project consists of a new 400 kV line San Giacomo-Pallanzeno, conversion from AC to DC of the 220 kV line, including the realization of the 2 AC/DC converter stations and 220 kV to 400 KV substation upgrade. Additional internal lines in Italy and in Switzerland are required to get full advantage from the interconnection capacity provided by the cross-border line. The project significantly increases interconnection capacity between Switzerland and Italy; favours the market integration; helps to use of the most efficient generation capacity and could potentially contribute to RES integration. Such benefits are assured according to different future scenarios.
| Scenario Vision 1 - 2030 | CH=>IT: 1000 | IT=>CH: 950 | - | [26;31] | 0 | MWh | [230000;290000] | [190;230] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [32;39] | 0 | MWh | [230000;290000] | [-340;-280]
| Scenario Vision 3 - 2030 |  |  | - | [26;31] | 0 | MWh | [17000;21000] | 0
| Scenario Vision 4 - 2030 |  |  | - | [54;66] | 0 | MWh | [50000;61000] | [-140;-120]
33 | The project consists in the strengthening of interconnection between the northern and the central part of Italy. It will involve the upgrading of existing 220 kV over-head line to 400 kV between Colunga and Calenzano substations as well as the removing of limitations on the existing 220 kV network in Central Italy. The projects allows removing internal bottlenecks and increases market and RES integration.
| Scenario Vision 1 - 2030 | North=>South: 600 | South=>North: 600 | - | [110;130] | [1100000;1400000] | MWh | [-340000;-280000] | [-680;-550] | 1 | 3 | 15-50km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [100;130] | [1100000;1300000] | MWh | [-340000;-280000] | [-640;-520]
| Scenario Vision 3 - 2030 |  |  | - | [170;200] | [1300000;1500000] | MWh | [-310000;-260000] | [-940;-770]
| Scenario Vision 4 - 2030 |  |  | - | [180;220] | [1500000;1800000] | MWh | [-350000;-290000] | [-1100;-900]
35 | This project represent second phase of Czech North-South corridor which enables the power flow from northwester border to southeastern border. This project is required to facilitate power flows in the direction North-South and East-West, enhance the grid transfer capability between Czech Republic and Germany and supports the future thermal generation evacuation and RES - connectiuon point of wind generation is substation Vernerov. In addition the project ensures security of supply of the North-western part of Czech Republic in general terms. Project is represented by 400kV double-circuit overheadline.
This project was assessed together with the project 200. Please refer to the project 200 values.
36 | The Kriegers Flak Combined Grid Solution (CGS) is a new DC offshore connection between Denmark and Germany. It had been designed and was simulated for this TYNDP as a combined grid connection of the offshore wind farms Kriegers Flak (Denmark), Baltic 1 and 2 (Germany) and a 400 MW interconnection between both countries connecting Ishøj/Bjæverskov (Denmark) and Bentwisch/Güstrow (Germany). The project facilitates RES connection and increased trade of electricity. The modelling results refer to the infrastructure part only, not to the benefit of the involved offshore wind farms, which would be an evaluation of the benefit of new generation, which is beyond the scope of the TYNDP. Thus also the cost reflect only the extra cost compared to the usual way of connecting the offshore wind farms to the two systems. The project is supported by the European Energy Programme for Recovery (EEPR) and labelled by the EC as project of common interest (PCI).
| Scenario Vision 1 - 2030 | DKE=>DE: 400 | DE=>DKE: 400 | - | [19;24] | [54000;66000] | MWh | [-62000;-51000] | [-130;-110] | 3 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [7;8] | [9000;11000] | MWh | [-62000;-50000] | [-4;-3]
| Scenario Vision 3 - 2030 |  |  | - | [10;13] | [18000;22000] | MWh | [4500;5500] | [-390;-320]
| Scenario Vision 4 - 2030 |  |  | - | [36;44] | [18000;22000] | MWh | [4500;5500] | [-760;-620]
37 | A 514 km long subsea interconnector between Norway and Germany is planned to be realized in 2018. The main driver for the project is to integrate the hydro-based Norwegian system with the thermal/wind/solar-based Continental system. The interconnector will improve security of supply both in Norway in dry years and in Germany in periods with negative power balance (low wind, low solar, high demand etc.). Additional the interconnector will be positive both for the European market integration, for facilitating renewable energy and also for preparing for a power system with lower CO2-emission. The interconnector is planned to be a 500 kV 1400 MW HVDC subsea interconnector between southern Norway and northern Germany.
| Scenario Vision 1 - 2030 | DE=>NO: 1400 | NO=>DE: 1400 | - | [120;140] | [510000;620000] | MWh | [910000;1100000] | [-930;-760] | 3 | 4 | 50-100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [65;110] | [950000;1200000] | MWh | [910000;1100000] | [-670;-550]
| Scenario Vision 3 - 2030 |  |  | - | [210;280] | [1500000;1800000] | MWh | [910000;1100000] | [-2200;-1800]
| Scenario Vision 4 - 2030 |  |  | - | [350;400] | [1700000;2100000] | MWh | [910000;1100000] | [-3400;-2800]
39 | This project is the third phase in the Danish-German agreement to upgrade the transfer capacity between Denmark West and Germany. The investments of the second phase were included in the TYNDP 2012 edition and have been commissioned in the meantime, thus increasing the cross border capacity since then. The third-phase project consists of a new 400 kV line from Kassoe (Denmark) to Audorf (Germany). It mainly follows the trace of an existing 220 kV line, which will be substituted by the higher voltage line. The project helps to integrate RES and to strenghten the connection between the Scandinavian and Continental market. The project is labelled by the EC as project of common interest (PCI).
| Scenario Vision 1 - 2030 | DKW=>DE: 720 | DE=>DKW: 1000 | - | [10;30] | [54000;66000] | MWh | [-46000;-38000] | [-120;-94] | 3 | 3 | 15-50km | 15-25km
| Scenario Vision 2 - 2030 |  |  | - | [0;10] | [110000;130000] | MWh | [32000;39000] | [-38;-31]
| Scenario Vision 3 - 2030 |  |  | - | [35;95] | [190000;230000] | MWh | [50000;62000] | [-680;-560]
| Scenario Vision 4 - 2030 |  |  | - | [120;150] | [370000;460000] | MWh | [51000;62000] | [-1300;-1000]
40 | The project envisions the realization of an interconnection between Luxembourg and Belgium allowing to increase the transfer capability between LU, DE, BE and FR and contributing to the security of supply of both countries. The interconnection is realized in two steps - On short-term (end 2015) a phase shift transformer is integrated and connected to existing overhead line via an additional cable, in order to control the transit flows from Germany to Belgium - On longer-term (2020) a solution with cables is under study envisioning an 1000 MVA path between Belgium and Luxembourg In parallel a 1000 MVA reinforcement of the internal Luxembourg network is being constructed in order to create a loop around Luxembourg city, including substations for in feed in lower voltage levels.
| Scenario Vision 1 - 2030 | LU=>BE: 700 | BE=>LU: 700 | [900;1100] | [0;10] | [16000;20000] | MWh | 0 | [80;97] | 2 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | [900;1100] | [0;10] | [9000;11000] | MWh | 0 | [54;66]
| Scenario Vision 3 - 2030 |  |  | [900;1100] | [20;30] | [9000;11000] | MWh | 0 | [-530;-440]
| Scenario Vision 4 - 2030 |  |  | [900;1100] | [30;50] | [130000;160000] | MWh | 0 | [-870;-710]
42 | Germany is planinng to build a big amount of offshore wind power plants in the Northsea. The OWP will help to reach the European goal of CO2 reduction and RES integration. This project is for the connection of the OWP with the German grid.
| Scenario Vision 1 - 2030 | North=>South: 5750 | South=>North: 5750 | - | [1300;1600] | 4033 | MW | 0 | [-13000;-11000] | 2 | 3 | More than 100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [620;760] | 4033 | MW | 0 | [-8500;-7000]
| Scenario Vision 3 - 2030 |  |  | - | [1900;2300] | 5748 | MW | 0 | [-10000;-8400]
| Scenario Vision 4 - 2030 |  |  | - | [1600;2000] | 5748 | MW | 0 | [-8900;-7300]
46 | Grid connections of offshore wind farms (using AC-technology), connecting offshore wind farms in the Baltic Sea to the German transmission grid in Bentwisch, Lüdershagen and Lubmin. According to German law, the grid connection has to be constructed and operated by the TSO (50Hertz Transmission).
| Scenario Vision 1 - 2030 | North=>South: 4500 | South=>North: 4500 | - | [300;360] | 1568 | MW | 0 | [-3300;-2700] | 0 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [210;250] | 1568 | MW | 0 | [-3000;-2400]
| Scenario Vision 3 - 2030 |  |  | - | [1300;1600] | 4342 | MW | 0 | [-7300;-6000]
| Scenario Vision 4 - 2030 |  |  | - | [1100;1400] | 4342 | MW | 0 | [-6400;-5200]
47 | This project reinforces the interconnection capacity between Austria and Germany. The national investments comprised are a precondition to achieve the full benefit of the cross border investments and are vital for the Austrian security of supply (e.g. part of the Austrian 380-kV-Security Ring). It supports the interaction of RES in Northern Europe (mainly in Germany) and in the eastern part of Austria with the pump storages in the Austrian Alps and therewith facilitates their utilisation.
| Scenario Vision 1 - 2030 | DE=>AT: 2900 | AT=>DE: 2900 | - | [53;64] | 0 | MWh | [-450000;-370000] | [530;650] | 1 | 4 | 15-50km | 15-25km
| Scenario Vision 2 - 2030 |  |  | - | [110;140] | 0 | MWh | [-420000;-340000] | [390;480]
| Scenario Vision 3 - 2030 |  |  | - | [310;380] | [300000;360000] | MWh | [-330000;-270000] | [-1500;-1300]
| Scenario Vision 4 - 2030 |  |  | - | [470;490] | [690000;850000] | MWh | [-300000;-330000] | [-1300;-1500]
48 | This project will increase the transfer capacity between Slovak and Hungarian transmission systems, improve security and reliability of operation both transmission systems and support North - South RES power flows in CCE region. Main investments of this project are double circuit 400 kV line from new Gabcikovo (Slovakia) substation to Gönyű (Hungary) substation and double circuit 400 kV line from Rimavska Sobota (Slovakia) substation to Sajóivánka (Hungary) substation.
| Scenario Vision 1 - 2030 | SK=>HU: 0-500 | HU=>SK: 0-425 | - | [27;34] | 0 | MW | [-160000;-150000] | [410;500] | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [23;28] | 0 | MW | [-220000;-180000] | [500;610]
| Scenario Vision 3 - 2030 |  |  | - | [31;38] | 0 | MW | [2500;8300] | [65;80]
| Scenario Vision 4 - 2030 |  |  | - | [66;81] | 0 | MW | [-12000;3600] | [-260;-220]
54 | This project will increase the transfer capacity between Slovak and Hungarian transmission systems, improve security and reliability of operation both transmission systems and support North - South RES power flows in CCE region. Realization of this projetct is tightly connected to the negotiations between Slovak and Ukrainian TSOs regarding future operation of the existing Slovak interconnection with Ukraine. Main and only investment of this project is double circuit 400 kV line from Velke Kapusany (Slovakia) substation to Kisvárda region (Hungary).
| Scenario Vision 1 - 2030 | SK=>HU: 0-500 | HU=>SK: 0-500 | - | [2;3] | 0 | MW | [-27000;-21000] | [-53;-44] | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [3;4] | 0 | MW | [-37000;-45000] | [87;110]
| Scenario Vision 3 - 2030 |  |  | - | [12;15] | 0 | MW | [-57000;-50000] | [-16;-13]
| Scenario Vision 4 - 2030 |  |  | - | [26;31] | 0 | MW | [-27000;-19000] | [-92;-75]
55 | This project is required to ease power flows West to East and enables market integration of generation with high flexibility in to the power grid. Project consists of 400kV OHL lines in existing corridors by building new double circuit with target capacities of 1700MVA per circuit. Project also brings ability to current and new connected generation free access to cross-border ancilliary market.
| Scenario Vision 1 - 2030 | West=>East: 1250-1750 | East=>West: 1400-1600 | - | [77;97] | 0 | MWh | [-88000;-110000] | [210;260] | 2 | 3 | 15-50km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [79;99] | 0 | MWh | [60000;72000] | [280;350]
| Scenario Vision 3 - 2030 |  |  | - | [67;87] | 0 | MWh | [-48000;-58000] | [-2200;-2600]
| Scenario Vision 4 - 2030 |  |  | - | [35;45] | 0 | MWh | [-19000;-36000] | [-1600;-2000]
58 | The construction of a new (third) interconnection between Polish and German power systems includes the construction of the interconnector between Eisenhuetenstadt and Plewiska as well as two internal lines (Mikułowa-Świebodzice and Krajnik -Baczyna) and substations Plewiska BIS, Gubin and Zielona Góra to connect the new line in the Polish transmission system and contributes to the following: • increase of market integration between member states - additional NTC of 1500 import and 500 MW export on PL-DE/SK/CZ synchronous profile; • integration of additional Renewable Energy Sources on the area of western and north-western Poland as well as eastern part of Germany; • improving network security - project contributes to increase of security of supply and flexibility of the transmission network (security of supply of Poznań agglomeration area).
| Scenario Vision 1 - 2030 | PL=>DE: 0-500 | DE=>PL: 0-1500 | - | [69;84] | 0 | MW | [-170000;-140000] | [760;930] | 1 | 4 | 15-50km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [67;82] | 0 | MW | [-160000;-130000] | [1000;1200]
| Scenario Vision 3 - 2030 |  |  | - | [99;120] | [300000;370000] | MWh | [-770000;-630000] | [-81;-66]
| Scenario Vision 4 - 2030 |  |  | - | [98;120] | [650000;800000] | MWh | [-910000;-740000] | [87;110]
59 | The LitPol Link Project is an interconnection between Poland and Lithuania. The first stage of the LitPol Link interconnection project is realized by the construction of new double circuit 400 kV interconnector between Elk and Alytus together with 500 MW back-to-back convertor station in substation Alytus and strengthening of the internal high voltage transmission grid in Poland and Lithuania in order to utilize the capacity of the interconnection. The capacity increase in first stage is 500 MW (on the direction from Lithuania to Poland; the capacity in opposite direction is curtailed by the limitations of the internal Polish transmission grid) and the expected commissioning date is 2015. The project removes an energy island by connecting the Baltic States to the Continental Europe and completes Baltic Sea ring.
| Scenario Vision 1 - 2030 | PL=>LT: 0-0 | LT=>PL: 0-500 | - | [40;49] | [54000;66000] | MWh | [170000;200000] | [-280;-230] | 3 | 5 | 50-100km | 25-50km
| Scenario Vision 2 - 2030 |  |  | - | [52;63] | [9000;11000] | MWh | [200000;240000] | [750;920]
| Scenario Vision 3 - 2030 |  |  | - | [23;28] | [9000;11000] | MWh | [-1100000;-890000] | [-2000;-1700]
| Scenario Vision 4 - 2030 |  |  | - | [160;200] | [9000;11000] | MWh | [-1100000;-900000] | [-2500;-2000]
60 | NordBalt project - phase one: investments before 2020. DC interconnector between Lithuania and Sweden and internal investments in Lithuania, Latvia and Sweden. The project will connect the Baltic grid to the Nordic and integrate the Baltic countries with the Nordic electricity market and also increases security of supply.
| Scenario Vision 1 - 2030 | LT=>SE: 700 | SE=>LT: 700 | - | [16;19] | [18000;22000] | MWh | [280000;340000] | [-90;-73] | 4 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [35;42] | [18000;22000] | MWh | [320000;390000] | [1100;1300]
| Scenario Vision 3 - 2030 |  |  | - | [9;12] | [110000;130000] | MWh | [140000;170000] | [-650;-530]
| Scenario Vision 4 - 2030 |  |  | - | [180;220] | [110000;130000] | MWh | [350000;430000] | [-1400;-1200]
62 | Project nr 62 is a planned third 330 kV interconnection between Estonia and Latvia. The project consists of 2 investments of which nr 386 is the main inter-area investment, AC 330 kV OHL between Kilingi-Nõmme substation in Estonia and TEC2 substation in Latvia. Estonia-Latvia third interconnection associated investment nr 735 AC 330 kV OHL Harku-Lihula-Sindi in Estonian. It increases the capacity between Estonia and Latvia by 600 MW. The project also helps to improve SoS and contributes to RES increase in the Baltics western coastal areas. The project is also a precondition for construction of off-shore wind parks in Estonia and Latvia. The Estonia-Latvia third interconnection is the significant project for all the Baltic region, because it will increase competition for electricity market in Baltic States and between Baltic States and Nordic countries. It will provide reliable transmission network corridor will improve interoperability between Baltic states. In addition after commissioning the projects forming the Baltic Energy Interconnection Plan the reinforced Baltic States transmission system and its connections to Nordic and Central Europe can also serve as an alternative route for exporting Nordic surplus to the Central European power system.
| Scenario Vision 1 - 2030 | EE=>LV: 450-600 | LV=>EE: 450-600 | - | [8;9] | [36000;44000] | MWh | [53000;65000] | [90;110] | 4 | 4 | More than 100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [10;13] | [36000;44000] | MWh | [91000;110000] | [7;8]
| Scenario Vision 3 - 2030 |  |  | - | [0;1] | [9000;11000] | MWh | [-1100;-900] | [-9;-8]
| Scenario Vision 4 - 2030 |  |  | - | [8;9] | [11000;13000] | MWh | [11000;13000] | [-31;-26]
64 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Project changed in TYNDP 2014, stage 1 includes the investments up until 2016.
| S1 EU202020 - 2020 | North=>South: 700-1400 | South=>North: 700-1400 | [30;300] | [30;100] | [500;1500] | MW | [0;-3000] | [500;1000] | 2 | 4 | NA | NA
69 | This group of investments are in response to an expected growth in offshore wind and nuclear generation in and around the Norfolk and East Anglia region.
| Scenario Vision 1 - 2030 | inside=>downstream: 3600 | downstream=>inside: 3600 | - | [170;200] | [4000;4500] | MW | [350000;450000] | [-8700;-9400] | 2 | 3 | 15-50km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [160;200] | [4000;4500] | MW | [360000;440000] | [-9900;-8100]
| Scenario Vision 3 - 2030 |  |  | - | [590;720] | [8600;11000] | MW | [450000;550000] | [-6500;-5300]
| Scenario Vision 4 - 2030 |  |  | - | [580;720] | [8600;11000] | MW | [440000;560000] | [-4900;-6900]
71 | The project is an interconnection between Endrup (Denmark) and Eemshaven (The Netherlands). The purpose is to incorporate more renewable energy into both the Dutch and the Danish power systems and to improve the security of supply. Moreover, the cable will help to intensify competition on the northwest European electricity markets. The project consists of a 320 kV 700 MW DC subsea cable and related substations on both ends, 320-350 km apart, applying VSC DC technology. The project is supported by the European Energy Programme for Recovery (EEPR) and is labelled by the EC as project of common interest (PCI).
| Scenario Vision 1 - 2030 | DKW=>NL: 700 | NL=>DKW: 700 | - | [5;25] | [45000;55000] | MWh | [44000;54000] | [-120;-94] | 3 | 3 | 50-100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [0;10] | [27000;33000] | MWh | [44000;54000] | [-44;-36]
| Scenario Vision 3 - 2030 |  |  | - | [25;85] | [180000;220000] | MWh | [110000;130000] | [-560;-460]
| Scenario Vision 4 - 2030 |  |  | - | [100;150] | [350000;420000] | MWh | [110000;130000] | [-920;-760]
74 | This group of investments includes the 1 GW NEMO interconnector between Great Britain and Belgium and a number of onshore UK reinforcements to facilitate this and other potential interconnector connections within the Thames Estuary region.
| Scenario Vision 1 - 2030 | BE=>GB: 1000 | GB=>BE: 1000 | - | [32;74] | [220000;270000] | MWh | [410000;420000] | [180;220] | 2 | 5 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [20;30] | [50000;61000] | MWh | [370000;460000] | [160;190]
| Scenario Vision 3 - 2030 |  |  | - | [200;280] | [1800000;2200000] | MWh | [190000;230000] | [-1300;-1400]
| Scenario Vision 4 - 2030 |  |  | - | [240;280] | [1100000;1400000] | MWh | [190000;230000] | [-1700;-1400]
75 | This project facilitates the integration of up to 2,3 GW of offshore wind production into the Belgian grid via the construction of an offshore hub (BOG: Belgian Offshore Grid project) and the extension of the 380kV backbone to the coastal area (STEVIN project) to which the offshore hub will be connected. The final design as well as the legal, ownership & regulatory framework for BOG is being defined in concertation with stakeholders (wind farm developers,...). Note that the STEVIN project is also required for the integration of the NEMO interconnector (BE-UK) into the BE 380kV network.
| Scenario Vision 1 - 2030 | North=>South: 3000 | South=>North: 0 | - | [390;490] | 1800 | MW | [27000;33000] | [-4100;-3300] | 2 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [420;490] | 1800 | MW | [27000;33000] | [-3400;-2700]
| Scenario Vision 3 - 2030 |  |  | - | [510;520] | 1800 | MW | [27000;33000] | [-2600;-2100]
| Scenario Vision 4 - 2030 |  |  | - | [330;460] | 1800 | MW | [27000;33000] | [-2000;-1600]
76 | All of these investments are required due to a combination of age related asset replacement, increasing power flows and changing customer demand connection requirements. A further driver for all of these projects is that power flows through London increase during interconnector export to mainland Europe. Power flows from the north through London to the interconnectors within the Thames Estuary.
| Scenario Vision 1 - 2030 | North=>South: 800 | South=>North: 800 | [130;210] | [11;19] | [1600;2000] | MW | [-290000;-410000] | [20000;40000] | 2 | 1 | NA | NA
| Scenario Vision 2 - 2030 |  |  | [160;240] | [14;22] | [1600;2000] | MW | [-350000;-490000] | [24000;48000]
| Scenario Vision 3 - 2030 |  |  | [1200;1500] | [130;170] | [1600;2000] | MW | [230000;330000] | [-9200;-10000]
| Scenario Vision 4 - 2030 |  |  | [1400;1800] | [170;220] | [1600;2000] | MW | [290000;410000] | [-10000;-12000]
77 | These projects facilitate the connection of RES and the connection of the remote Scottish Islands.
| Scenario Vision 1 - 2030 | North=>South: 4200 | South=>North: 4200 | - | [160;310] | [7500;8500] | MW | 0 | [-9000;-11000] | 2 | 1 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [240;330] | [7700;11000] | MW | 0 | [-9000;-11000]
| Scenario Vision 3 - 2030 |  |  | - | [420;490] | [9300;12000] | MW | [-600000;-900000] | [-18000;-20000]
| Scenario Vision 4 - 2030 |  |  | - | [520;600] | [11000;14000] | MW | [-600000;-900000] | [-18000;-20000]
78 | Project needed for renewables off of the South West peninsula, the replanting of Hinkley Point nuclear power station and further CCGT at Seabank.
| Scenario Vision 1 - 2030 | West=>East: 3200 | East=>West: 3200 | - | [1600;1800] | 1100 | MW | [200000;240000] | [-290000;-390000] | 1 | 1 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [2000;2300] | 1100 | MW | [200000;240000] | [-290000;-390000]
| Scenario Vision 3 - 2030 |  |  | - | [3500;3800] | [2000;4400] | MW | [-300000;-400000] | [-810000;-890000]
| Scenario Vision 4 - 2030 |  |  | - | [4300;4700] | [3600;6000] | MW | [-300000;-400000] | [-810000;-890000]
79 | Reinforcement of the internal grid to facilitate the integration of nuclear plant and RES.
| Scenario Vision 1 - 2030 | West=>East: 2000 | East=>West: 2000 | - | [15;240] | [2200;2800] | MW | [-330000;-470000] | [-850;-1400] | 2 | 1 | 50-100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [140;170] | [2500;3500] | MW | [-330000;-470000] | [-12000;-9900]
| Scenario Vision 3 - 2030 |  |  | - | [400;490] | [5200;9200] | MW | [-44000;-64000] | [-19000;-20000]
| Scenario Vision 4 - 2030 |  |  | - | [520;610] | [6800;11000] | MW | [-44000;-64000] | [-19000;-20000]
81 | A new 400 kV interconnector between Woodland in Ireland and Turleenan in Northern Ireland.
| Scenario Vision 1 - 2030 | IE=>NI: 660 | NI=>IE: 580 | - | [18;36] | [6300;7700] | MWh | [-50000;-41000] | [-45;-36] | 3 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [12;15] | 0 | MWh | [39000;47000] | [-27;-22]
| Scenario Vision 3 - 2030 |  |  | - | [27;34] | 0 | MWh | [39000;47000] | [-48;-39]
| Scenario Vision 4 - 2030 |  |  | - | [55;77] | [1800;2200] | MWh | [-45000;-37000] | [-110;-90]
82 | The infrastructure development is required to facilitate connection of renewables in the North and West of the Island; It will further integrate the Ireland and Northern Ireland transmission systems and provide capacity for substantial demand growth in the area.
| Scenario Vision 1 - 2030 | IE=>NI: 570 | NI=>IE: 570 | - | [120;140] | [120000;150000] | MWh | [-64000;-52000] | [-1100;-920] | 3 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [140;150] | [32000;39000] | MWh | [-72000;-59000] | [-120;-94]
| Scenario Vision 3 - 2030 |  |  | - | [70;100] | [810000;1000000] | MWh | [-72000;-59000] | [-400;-320]
| Scenario Vision 4 - 2030 |  |  | - | [55;75] | [970000;1200000] | MWh | [-86000;-70000] | [-190;-160]
85 | This project integrates new amounts of solar (and also some wind) generation in the south of Portugal. The existing network of 150 kV is not sufficient to integrate these amounts of power and a new 400 kV axis should be launched in this region, establishing a connection between the two Southern interconnections between Portugal and Spain, the Ferreira do Alentejo-Alqueva-Brovales and Tavira-Puebla de Gusman. This axis will also close a ring of 400 kV in the Southern part of Portugal that will guarantee the load growth in the region (Algarve is one of the regions that presents the biggest growth rate in Portugal) in a safe, secure and quality way.
| Scenario Vision 1 - 2030 | inside=>outside: 1400 | outside=>inside: 0 | - | [22;27] | 150 | MW | [-9800;-8000] | [-89;-72] | 1 | 2 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [22;27] | 150 | MW | [-11000;-8800] | [-89;-72]
| Scenario Vision 3 - 2030 |  |  | - | [37;46] | 350 | MW | [-15000;-13000] | [-150;-120]
| Scenario Vision 4 - 2030 |  |  | - | [120;150] | 1350 | MW | [41000;50000] | [-490;-400]
86 | A very high level indication of the works required for GB East Coast. In detail the projects will consist of multiple offshore HVDC and AC circuits and connecting platforms joining to multiple onshore connection points with their own reinforcement requirements.
| Scenario Vision 1 - 2030 | East=>West: 3000 | West=>East: 3000 | - | [58;110] | [5700;7700] | MW | 0 | [-26000;-30000] | 2 | 2 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [81;140] | [7500;11000] | MW | 0 | [-26000;-30000]
| Scenario Vision 3 - 2030 |  |  | - | [680;920] | [16000;21000] | MW | [-1500;-1900] | [-33000;-38000]
| Scenario Vision 4 - 2030 |  |  | - | [920;1000] | [20000;27000] | MW | [-1500;-1900] | [-32000;-38000]
90 | This project increases the capacity between CH and its neighbours DE and AT. This enables to connect large renewable generation in Northern Europe to pump storage devices in the Alps, thus noticeably increasing the mutual balancing between both regions. Project 90 is completed by Project 198.
| Scenario Vision 1 - 2030 | upstream=>upstream: 0 | upstream=>upstream: 0 | - | [90;110] | 0 | MWh | [-200000;-160000] | [820;1000] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [140;170] | 0 | MWh | [-270000;-220000] | [1900;2400]
| Scenario Vision 3 - 2030 |  |  | - | [310;380] | [450000;550000] | MWh | [-180000;-150000] | [-1200;-950]
| Scenario Vision 4 - 2030 |  |  | - | [480;580] | [900000;1100000] | MWh | [-360000;-300000] | [-2100;-1700]
91 | The project helps accommodating new pumping storage units which mainly support the increasing RES generation in the European areas with solar or wind generation. While importing or exporting, the Swiss Ellipse project uses the capacity of the 'Italy - Switzerland' (31), 'Swiss Roof' (90) and 'France - Switzerland' (22) projects.
| Scenario Vision 1 - 2030 | inside=>outside: 5000 | outside=>inside: 5000 | - | [18;23] | [170;200] | MWh | 0 | [730;890] | 1 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [21;26] | [1000;1300] | MWh | 0 | [440;530]
| Scenario Vision 3 - 2030 |  |  | - | [200;250] | [36000;44000] | MWh | 0 | [-480;-390]
| Scenario Vision 4 - 2030 |  |  | - | [310;380] | [230000;280000] | MWh | 0 | [-800;-650]
92 | The ALEGrO (Aachen Liège Electricity Grid Overlay) project involves the realization of a HVDC link with a bidirectional rated power of approximately 1.000 MW capacity, as the first interconnection between Belgium and Germany. First of all, it enhances the internal market integration by enabling direct power exchanges between these countries Secondly, the new interconnection will play a major role for the transition to a generation mix which is undergoing structural changes in the region (high penetration of RES, nuclear phase-out, commissioning and decommissioning of conventional power plants etc.). Given these major changes in the production mix, the new interconnection also contributes to the security of supply in facing the arising challenges for secure system operation. The project has been selected as PCI 2.2.
| Scenario Vision 1 - 2030 | BE=>DE: 1000 | DE=>BE: 1000 | - | [5;15] | [9000;11000] | MWh | [150000;180000] | [140;170] | 3 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [5;15] | [4500;5500] | MWh | [150000;180000] | [-22;-18]
| Scenario Vision 3 - 2030 |  |  | - | [35;45] | [100000;130000] | MWh | [120000;140000] | [-800;-650]
| Scenario Vision 4 - 2030 |  |  | - | [45;75] | [180000;210000] | MWh | [120000;140000] | [-1100;-900]
94 | Upgrade of the existing 220 kV double interconnection line between Krajnik and Vierraden to 400 kV double line in the same direction together with installation of Phase Shifting Transformers on two existing interconnection lines (Krajnik-Vierraden by 50Hertz Transmission GmbH in Vierraden and Mikułowa-Hagenverder by PSE S.A. in Mikułowa) on the PL/DE border including an upgrade of substations Vierraden, Krajnik and Mikułowa contribute to the following: • decreasing of unscheduled flow from Germany to Poland, Poland to Czech Republic and Poland to Slovakia by increasing of controllability on entire synchronous profile; • enhancement of market capacity on Polish synchronous profile - PL/DE as well as PL-CZ/SK border in case of both import and export. The project provides additional capacity (NTC – Net Transfer Capability) of 500 MW in terms of import and 1500 MW export; greater level of safety and reliability of operation of the transmission network in Poland due to enhanced control of power flow.
| Scenario Vision 1 - 2030 | PL=>DE: 0-1500 | DE=>PL: 0-500 | - | [250;300] | [110000;130000] | MWh | [-60000;-49000] | [2000;2400] | 2 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [240;300] | [41000;50000] | MWh | [-49000;-40000] | [2800;3400]
| Scenario Vision 3 - 2030 |  |  | - | [75;92] | [130000;160000] | MWh | [-140000;-110000] | [1300;1600]
| Scenario Vision 4 - 2030 |  |  | - | [270;330] | [800000;970000] | MWh | [-190000;-150000] | [50;61]
96 | The project is 400 kV overhead line in North Finland. Integration of new generation at Bothnian bay and increased transmission capacity demand. Will help utilizing the Swedish/Finnish cross border capacity.
| Scenario Vision 1 - 2030 | North=>South: 500-1000 | South=>North: 500-1000 | - | [0;14] | 1050 | MW | [-30000;-60000] | [0;240] | 2 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | 0 | [800;1200] | MW | [-30000;-60000] | [0;500]
| Scenario Vision 3 - 2030 |  |  | - | [0;6] | 1000 | MW | [-35000;-65000] | [0;-40]
| Scenario Vision 4 - 2030 |  |  | - | [0;68] | [1300;1800] | MW | [-20000;-80000] | [0;-100]
103 | The project reinforces the Dutch grid to accommodate new conventional and renewable generation, to handle new flow patterns and to fully facilitate the increase that is foreseen by cross border projects (project 113 and 201) in interconnection capacity between Germany and The Netherlands and to a higher robustness for the interconnection with Belgium (especially in relation to project 24).
| Scenario Vision 1 - 2030 | NL=>DE: 500 | DE=>NL: 500 | - | 0 | 0 | MWh | [-190000;-160000] | [13;16] | 1 | 3 | More than 100km | More than 50km
| Scenario Vision 2 - 2030 |  |  | - | 0 | 0 | MWh | [-190000;-160000] | [-27;-22]
| Scenario Vision 3 - 2030 |  |  | - | [5;15] | [45000;55000] | MWh | 0 | [-210;-180]
| Scenario Vision 4 - 2030 |  |  | - | [5;15] | [23000;28000] | MWh | 0 | [-270;-220]
106 | A second Ireland GB HVDC interconnector
| Scenario Vision 1 - 2030 | IE=>GB: 700 | GB=>IE: 700 | - | [10;24] | [140000;170000] | MWh | [69000;84000] | [-74;-61] | 2 | 4 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [10;20] | [110000;130000] | MWh | [72000;88000] | [-120;-99]
| Scenario Vision 3 - 2030 |  |  | - | [45;65] | [390000;470000] | MWh | [72000;88000] | [-290;-240]
| Scenario Vision 4 - 2030 |  |  | - | [57;93] | [540000;660000] | MWh | [77000;94000] | [-370;-300]
107 | Celtic Interconnector will be the first interconnection between Ireland and France. This HVDC (VSC)link with 700 MW capacity will connect Great Island or Knockraha (Ireland) to the Finistère in France. It will not only create a direct link between the French and Irish markets, but also increase RES integration, especially wind in Ireland. Some positive impact on the security of supply is also expected, in particular for Brittany, although this is not shown by the corresponding indicator assessed according to the CBA rules. The project has been selected as PCI 1.6 in the NSCOG corridor on 14/10/13.
| Scenario Vision 1 - 2030 | FR=>IE: 700 | IE=>FR: 700 | - | [30;70] | [270000;320000] | MWh | [200000;300000] | [63;77] | 1 | 4 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [20;30] | [170000;200000] | MWh | [200000;300000] | [-33;-27]
| Scenario Vision 3 - 2030 |  |  | - | [140;170] | [1300000;1600000] | MWh | [170000;270000] | [-970;-790]
| Scenario Vision 4 - 2030 |  |  | - | [150;200] | [1500000;1800000] | MWh | [170000;270000] | [-920;-760]
108 | The project consists of two double circuit 400-kV lines that are needed to connect to the grid the future 1000MW Hydro Pumped Storage Tarnita-Lapustesti, situated in the North-West of Romania. The project will supply reserve/balancing services for Romania and possibly for neighboring countries (Hungary, Serbia, Bulgaria,other). It will support integration of intermittent RES generation.
| Scenario Vision 1 - 2030 | inside=>outside: 1000 | outside=>inside: 1000 | - | [9;12] | [35000;43000] | MWh | [-47000;-39000] | [400;490] | 3 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [4;5] | [9900;12000] | MWh | [-21000;-17000] | [250;310]
| Scenario Vision 3 - 2030 |  |  | - | [3;4] | [19000;23000] | MWh | [-200000;-170000] | [-46;-37]
| Scenario Vision 4 - 2030 |  |  | - | [94;120] | [660000;800000] | MWh | [51000;62000] | [-550;-450]
110 | A 720 km long subsea interconnector between Norway and England is planned to be realized in 2020. If realized it will be the world's longest. The main driver for the project is to integrate the hydro-based Norwegian system with the thermal/nuclear/wind-based British system. The interconnector will improve security of supply both in Norway in dry years and in Great Britain in periods with negative power balance (low wind, low solar, high demand etc.). Additional the interconnector will be positive both for the European market integration, for facilitating renewable energy and also for preparing for a power system with lower CO2-emission. The interconnector is planned to be a 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern England.
| Scenario Vision 1 - 2030 | GB=>NO: 1400 | NO=>GB: 1400 | - | [150;220] | [1000000;1200000] | MWh | [760000;930000] | [-440;-360] | 2 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [90;170] | [900000;1100000] | MWh | [760000;930000] | [-240;-190]
| Scenario Vision 3 - 2030 |  |  | - | [280;360] | [2700000;3300000] | MWh | [760000;930000] | [-2000;-1700]
| Scenario Vision 4 - 2030 |  |  | - | [280;300] | [2100000;2600000] | MWh | [760000;930000] | [-1800;-1500]
111 | Third AC 400 kV interconnector between Finland north and Sweden SE1. Strengthening the AC connection between Finland and Sweden is necessary due to new wind power generation, larger conventional units and decommissioning of the existing 220 kV interconnector.
| Scenario Vision 1 - 2030 | FI=>SE: 500 | SE=>FI: 800 | - | [12;15] | [19000;23000] | MWh | [230000;280000] | [230;280] | 6 | 6 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [4;5] | [1800;2200] | MWh | [210000;250000] | [440;530]
| Scenario Vision 3 - 2030 |  |  | - | [4;5] | [23000;28000] | MWh | [110000;130000] | [-48;-39]
| Scenario Vision 4 - 2030 |  |  | - | [54;66] | [54000;66000] | MWh | [170000;210000] | [-120;-96]
113 | This new AC 400-kV double circuit overhead line will interconnect The Netherlands and Germany (Ruhr-Rhein area). Upon realisation of the project, the border between The Netherlands and Germany will consist of four double circuit interconnections in total. The project will increase the cross border capacity and will facilitate the further integration of the European Energy market especially in Central West Europe.
| Scenario Vision 1 - 2030 | NL=>DE: 1400 | DE=>NL: 1400 | - | [0;10] | [4500;5500] | MWh | [-39000;-32000] | [-11;-9] | 3 | 3 | 15-50km | 25-50km
| Scenario Vision 2 - 2030 |  |  | - | [4;5] | 0 | MWh | [-39000;-32000] | [-27;-22]
| Scenario Vision 3 - 2030 |  |  | - | [15;65] | [100000;130000] | MWh | [-180000;-150000] | [-770;-630]
| Scenario Vision 4 - 2030 |  |  | - | [40;60] | [63000;77000] | MWh | [-180000;-150000] | [-1000;-1200]
120 | Second Offshore-Onshore Corridor This is a conceptual project that could be considered as a long-term investment option, triggered by the vision 3 & 4 scenario where up to 4GW of offshore wind capacity is envisioned in the Belgian part of the North Sea (note that this 4 GW is not ensured in official government plans for offshore wind development). Compared to the current forecast of 2,3 GW of offshore wind as to which Elia portfolio is designed, it implies an additional reinforcement under the form of a second offshore-onshore corridor. Preliminary analysis indicates that this corridor could consist of multiple reinforcements to different inland locations. The determination of optimal location/route, technology and the integration of this corridor in relation to the BE offshore hub Alfa and nearby onshore substation Stevin at Zeebruge are subject of further studies.
| Scenario Vision 3 - 2030 | outside=>inside: 1800 | inside=>outside: 0 | - | [510;520] | 1800 | MW | [170000;210000] | [-2600;-2200] | 2 | 1 | NA | NA
| Scenario Vision 4 - 2030 |  |  | - | [430;450] | 1800 | MW | [170000;210000] | [-2000;-1600]
121 | This is a conceptual project that could be considered as a long-term investment option, triggered by the vision 3 & 4 scenario's where preliminary analysis shows potential of justifying additional regional welfare & RES integration increase via the construction of an additional +- 1000MW HVDC interconnection between the UK and Belgium. The determination of the optimal capacity, location, technology, potentially needed internal grid reinfocements and possible synergies on the integration of this interconnector in relation to the BE offshore platform Alfa are subject of further studies.
| Scenario Vision 3 - 2030 | BE=>GB: 1000 | GB=>BE: 1000 | - | [170;260] | [1700000;2000000] | MWh | [220000;260000] | [-1700;-1400] | 2 | 2 | NA | NA
| Scenario Vision 4 - 2030 |  |  | - | [210;250] | [1400000;1700000] | MWh | [220000;260000] | [-1400;-1100]
123 | The LitPol Link Stage 2 is a continuation of building of the interconnection between Poland and Lithuania in order to achieve the planned transmission capacity of 1000 MW in both directions. Building of additional internal investments in Poland and Lithuania are necessary. In Poland three additional lines will be erected (Ostrołeka-Olsztyn Mątki, Ostrołęka-Stanisławów and Kozienice-Siedlce Ujrzanów). In Lithuania a second 500 MW back-to-back converter station will be built in substation Alytus. The project improves connection the Baltic States to the Continental Europe and Baltic Sea ring.
| Scenario Vision 1 - 2030 | PL=>LT: 0-1000 | LT=>PL: 0-1000 | - | [36;45] | [18000;22000] | MWh | [190000;230000] | [-350;-290] | 1 | 5 | 15-50km | 25-50km
| Scenario Vision 2 - 2030 |  |  | - | [32;39] | [18000;22000] | MWh | [170000;210000] | [290;360]
| Scenario Vision 3 - 2030 |  |  | - | [36;44] | [27000;33000] | MWh | [-670000;-550000] | [-1900;-1600]
| Scenario Vision 4 - 2030 |  |  | - | [150;180] | [27000;33000] | MWh | [-290000;-240000] | [-2200;-1800]
124 | NordBalt - phase two: internal investments after 2020 in Lithuania and Sweden to be able to fully utilize the interconnector between Lithuania and Sweden (project 60) that will connect the Baltic grid to the Nordic and integrate the Baltic countries with the Nordic electricity market.
| Scenario Vision 1 - 2030 | LT=>SE: 700 | SE=>LT: 700 | - | 0 | 0 | MWh | [-23000;-19000] | 0 | 4 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | 0 | 0 | MWh | [61000;75000] | 0
| Scenario Vision 3 - 2030 |  |  | - | 0 | 0 | MWh | [83000;100000] | 0
| Scenario Vision 4 - 2030 |  |  | - | 0 | 0 | MWh | [11000;13000] | 0
126 | Reinforcements, both lines and stations, in and between bidding area SE1, SE2 and SE3 will accomplish RES integration in northern Sweden.
| Scenario Vision 1 - 2030 | North=>South: 700 | South=>North: 700 | - | [69;84] | [70000;86000] | MWh | [110000;130000] | [9;12] | 2 | 4 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [39;48] | [15000;19000] | MWh | [120000;150000] | [36;44]
| Scenario Vision 3 - 2030 |  |  | - | [44;53] | [28000;34000] | MWh | [110000;130000] | [18;22]
| Scenario Vision 4 - 2030 |  |  | - | [32;39] | [380000;460000] | MWh | [230000;280000] | [-52;-43]
127 | The project consists in the reinforcement of southern Italy 400 kV network through new 400 kV lines as well as upgrading of existing assets. The activities will involve the network portions between the substation of Villanova and Foggia, Foggia and Benevento,Deliceto and Bisaccia as well as Laino and Altomonte. The projects allows removing internal bottlenecks and increases market and RES integration.
| Scenario Vision 1 - 2030 | North=>South: 0 | South=>North: 1250 | - | [370;450] | [4600000;5600000] | MWh | [-170000;-140000] | [-3100;-2600] | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [350;420] | [4300000;5300000] | MWh | [-170000;-140000] | [-3000;-2400]
| Scenario Vision 3 - 2030 |  |  | - | [460;560] | [5100000;6200000] | MWh | [-130000;-110000] | [-3500;-2900]
| Scenario Vision 4 - 2030 |  |  | - | [460;560] | [5100000;6300000] | MWh | [-280000;-230000] | [-3500;-2900]
129 | Germany is planning to build a big amount of wind offshore power plants in the Northsea. The OWP will help to reach the European goal of CO2 reduction and RES integration. This project is for the connection of the OWP with the German grid. This project becomes necessary in case of further longterm strong increase in OWP generation like in Vision 3 and 4. The project is not in focus of Vision 1 and 2.
| Scenario Vision 3 - 2030 | inside=>DE: 3600 | DE=>inside: 3600 | - | [900;1100] | 3074 | MW | 0 | [-4900;-4000] | 2 | 3 | More than 100km | Negligible or less than 15km
| Scenario Vision 4 - 2030 |  |  | - | [770;940] | 3074 | MW | 0 | [-4300;-3500]
130 | This corridor is necessary, due to the strong increase in RES generation, meeting the goals of the European and especially German energy policy. It connects areas with high installed capacities of RES and areas with high consumption and storage capabilities. For this reason the development of new North-South and Northeast-Southwest electricity transmission capacity in Germany is necessary. This corridor begins in the North-East of Germany, an area with high RES generation (planned and existing), conventional generation and connections with Scandinavia (planned and existing).The corridor ends in the South of Germany, an area with high consumptions and connections to Austria and Switzerland (transit to Italy and pump storage in the Alps). Thus, the corridor is an essential element for the integration of renewable energy sources into the German power system and the provision of additional transmission capacities in order to meet the increasing demand of the European electricity market and to avoid unscheduled transit flows to neighboring countries. Moreover, due to the nuclear phase out in Germany, the amount of reliable available capacity in southern Germany decreases and the security of supply of this area require additional transmission capacity to areas with conventional generation units.
| Scenario Vision 1 - 2030 | North=>South: 11800 | South=>North: 11800 | - | [340;420] | [3100000;3700000] | MWh | [-4200000;-3400000] | [-1500;-1200] | 5 | 5 | More than 100km | More than 50km
| Scenario Vision 2 - 2030 |  |  | - | [310;380] | [3000000;3600000] | MWh | [-4300000;-3500000] | [110;130]
| Scenario Vision 3 - 2030 |  |  | - | [1300;1600] | [8700000;11000000] | MWh | [-5200000;-4200000] | [-7300;-6000]
| Scenario Vision 4 - 2030 |  |  | - | [2000;2400] | [14000000;17000000] | MWh | [-6400000;-5200000] | [-12000;-9700]
132 | This corridor is necessary, due to the strong increase in RES generation, meeting the goals of the European and especially German energy policy. It connects areas with high installed capacities of RES and areas with high consumption and storage capabilities. For this reason the development of new North-South and Northeast-Southwest electricity transmission capacity in Germany is necessary. This corridor begins in the North-East of Germany, an area with high RES generation (planned and existing), conventional generation and connections with Scandinavia (planned and existing).The corridor ends in the South of Germany, an area with high consumptions and connections to Austria and Switzerland (transit to Italy and pump storage in the Alps). Thus, the corridor is an essential element for the integration of renewable energy sources into the German power system and the provision of additional transmission capacities in order to meet the increasing demand of the European electricity market and to avoid unscheduled transit flow to neighboring countries . Moreover, due to the nuclear phase out in Germany, the amount of reliable available capacity in southern Germany decreases and the security of supply of this area requires additional transmission capacity to areas with conventional generation units.
| Scenario Vision 1 - 2030 | North=>South: 5500 | South=>North: 5500 | - | [410;500] | [6000000;7300000] | MWh | [-2500000;-2100000] | [-4600;-3800] | 5 | 4 | More than 100km | More than 50km
| Scenario Vision 2 - 2030 |  |  | - | [290;350] | [5400000;6600000] | MWh | [-1200000;-1000000] | [-3600;-2900]
| Scenario Vision 3 - 2030 |  |  | - | [1400;1700] | [14000000;17000000] | MWh | [-6200000;-5000000] | [-6700;-5500]
| Scenario Vision 4 - 2030 |  |  | - | [1300;1600] | [15000000;18000000] | MWh | [-5100000;-4100000] | [-6500;-5300]
133 | This project becomes necessary in case of further longterm strong increase in RES generation like in Vision 3 and 4. The project is not in Vision 1 and 2. It connects areas with high installed capacities of RES and areas with high consumption and storage capabilities. For this reason the development of new North-South and Northeast- Southwest electricity transmission capacity in Germany is necessary. This project begins in the North and North-East of Germany, areas with high RES generation (planned and existing) and connections with Scandinavia (planed and existing).The project ends in the South of Germany, an area with high consumptions and connections to Austria and Switzerland (transit to Italy and pump storage in the Alps).
| Scenario Vision 3 - 2030 | North=>South: 18000 | South=>North: 18000 | - | [57;140] | [860000;1000000] | MWh | [-3300000;-2700000] | [-380;-310] | 5 | 4 | NA | NA
| Scenario Vision 4 - 2030 |  |  | - | [180;260] | [1600000;2000000] | MWh | [-4000000;-3200000] | [-1200;-960]
134 | North-South transmission Western Germany - second DC/AC section towards the load center of Baden-Württemberg and Switzerland
This project was assessed together within the North South Eastern German Corridor. Please refer to the project 132 values.
135 | North-South transmission - DC/AC link towards Southern Germany incl. area of Frankfurt
This project was assessed together within the North South Eastern German Corridor. Please refer to the project 132 values.
136 | The project in Croatia include a new 400 kV OHL replacing the aging 220 kV OHL between existing substations Brinje and Konjsko, interdepending with the construction of two new 400/(220)/110 kV substations Brinje and Lika. The new 400 kV interconnection BanjaLuka(BA)-Lika(HR) will support market and RES integration in the area – South and Mid Croatia and North and Mid Bosnia and Herzegovina. The increased transfer capacity will enable higher diversity of supply&generation sources and routes, increasing resilience and flexibility of the transmission network.
| Scenario Vision 1 - 2030 | HR=>BA: 612 | BA=>HR: 594 | - | [50;61] | 830 | MW | [9900;12000] | [-320;-260] | 1 | 4 | Negligible or less than 15km | 15-25km
| Scenario Vision 2 - 2030 |  |  | - | [130;160] | 830 | MW | [-110000;-89000] | [-300;-240]
| Scenario Vision 3 - 2030 |  |  | - | [420;510] | 900 | MW | [-5300;-4300] | [-2700;-2200]
| Scenario Vision 4 - 2030 |  |  | - | [270;330] | 900 | MW | [8100;9900] | [-2300;-1900]
138 | The project reinforces the corridor along the coast of the Black Sea (Romania-Bulgaria) and between this coast and the rest of Europe and Turkey. Regional and European market integration will be enhanced, allowing for increased exchanges in the area. Development of intermittent RES will be made possible by the capacity of the grid to transport their generation to consumption and storage centres and to accommodate balancing at regional/continental level. The project improves operational regimes from the point of vue of stability and voltage collapse and facilitates maintenance of the network in the area.
| Scenario Vision 1 - 2030 | RO=>BG: 1260 | BG=>RO: 2196 | - | [110;130] | 1330 | MW | [-66000;-54000] | [-420;-340] | 3 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [61;74] | 1330 | MW | [27000;33000] | [-780;-640]
| Scenario Vision 3 - 2030 |  |  | - | [410;500] | 1330 | MW | [-170000;-140000] | [-3400;-2700]
| Scenario Vision 4 - 2030 |  |  | - | [360;440] | 1330 | MW | [-25000;-20000] | [-2100;-1800]
141 | The project consists of a new double circuit 400 kV line Cirkovce-Pince and a new 400 kV Cirkovce substation (Slovenia) by which a new connection to one circuit of the existing double circuit interconnection line between Hungary and Croatia will be made, thus creating two new cross border interconnection between Slovenia and Hungary and between Slovenia and Croatia. Existing 220 kV lines of the corridor Cirkovce-Divaca will be upgraded to 400 kV level. PCI project.
| Scenario Vision 1 - 2030 | HU=>SI: 765 | SI=>HU: 1085 | - | [42;51] | 0 | MW | [-120000;-95000] | [-200;-160] | 0 | 4 | More than 100km | 15-25km
| Scenario Vision 2 - 2030 |  |  | - | [40;49] | 0 | MW | [-460000;-370000] | [-44;-36]
| Scenario Vision 3 - 2030 |  |  | - | [480;580] | 0 | MW | [-240000;-190000] | [-3800;-3100]
| Scenario Vision 4 - 2030 |  |  | - | [300;370] | 0 | MW | [-190000;-150000] | [-1700;-1400]
142 | This project will facilitate market integration by increasing the transfer capacity in the Bulgaria-Greece borders. It will also contribute to increase the volume of exchanges between the Continental Europe synchronous area and Turkey. Furthermore it will contribute to the safe evacuation of the power from the wind farms expected to be installed in the North-East part of Greece and the North-East of Bulgaria as well as photovoltaic power plants in the South part of Bulgaria. Mentioned project will be composed of a new 400kV AC interconnection between Bulgaria and Greece as well as two new 400kV OHL aiming at the strengthening of the transmission network at the South part of Bulgaria.
| Scenario Vision 1 - 2030 | BG=>GR: 648 | GR=>BG: 82 | - | [54;67] | 250 | MW | [-110000;-88000] | [-22;-18] | 2 | 4 | 15-50km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [200;250] | 250 | MW | [-140000;-110000] | [-150;-130]
| Scenario Vision 3 - 2030 |  |  | - | [100;120] | 250 | MW | [-170000;-140000] | [-510;-410]
| Scenario Vision 4 - 2030 |  |  | - | [150;180] | 250 | MW | [-130000;-110000] | [-970;-790]
144 | The project consists of one double circuit 400 kV line between Serbia and Romania and reinforcement of the network along the western border in Romania: one new simple circuit 400 kV line from Portile de Fier to Resita and upgrade from 220 kV double circuit to 400 kV double circuit of the axis between Resita and Arad, including upgrade to 400 kV of three substations along this path. The project aims at enhancing the transmission capacity along the East-West corridor in south-eastern and central Europe. It will provide access to the market for more than 1000 MW installed new wind generation in Banat area (Serbia and Romania) as well as to the pumped storage plant of more than 1000 MW in north-western Romania.
| Scenario Vision 1 - 2030 | East=>West: 737 | West=>East: 453 | - | [170;210] | 1000 | MW | [-96000;-78000] | [1200;1500] | 3 | 4 | 15-50km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [66;81] | 1000 | MW | [-160000;-130000] | [700;860]
| Scenario Vision 3 - 2030 |  |  | - | [18;22] | 1000 | MW | [-220000;-180000] | [-380;-310]
| Scenario Vision 4 - 2030 |  |  | - | [190;230] | 1000 | MW | [-340000;-280000] | [-330;-270]
146 | Cluster CSE8 contains investments in the south-east Europe region planned with purpose for supporting increase of power transfers from north-west towards south-east part of this area and enabling further market integration. Investments which form this cluster are located on the territory of four countries: Serbia, Bosnia and Hertzegovina, Montenegro and Italy. These investments assume construction of new 400 kV overhead lines and substations, and particularly new HVDC 400 kV cable between Montenegro and Italy.
| Scenario Vision 1 - 2030 | East=>West: 1095 | West=>East: 1095 | - | [330;410] | 1000 | MW | [-440000;-360000] | [500;620] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [450;550] | 1000 | MW | [-740000;-610000] | [-3700;-3000]
| Scenario Vision 3 - 2030 |  |  | - | [280;340] | 1000 | MW | [-660000;-540000] | [-730;-590]
| Scenario Vision 4 - 2030 |  |  | - | [620;760] | 1000 | MW | [-390000;-320000] | [-4400;-3600]
147 | The project aims to increase the transfer capacity in the predominant North-South direction that is from Romania, Serbia and Bulgaria towards Greece, FYR of Macedonia and Albania. In addition, a part of this project will increase the security of supply in the South-West part of the FYR of Macedonia. The investments forming the project are 400 kV lines and corresponding substations located in Greece, FYR of Macedonia, Serbia and Albania.
| Scenario Vision 1 - 2030 | North=>South: 1157 | South=>North: 2709 | - | [380;460] | 300 | MW | [-210000;-170000] | [-55;-45] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [190;230] | 300 | MW | [-86000;-70000] | [120;140]
| Scenario Vision 3 - 2030 |  |  | - | [510;620] | 300 | MW | [-61000;-50000] | [-2200;-1800]
| Scenario Vision 4 - 2030 |  |  | - | [600;730] | 300 | MW | [-100000;-85000] | [-5300;-4400]
148 | The project consists in the new 400 kV overhead cross-border line Udine – Okroglo, including a phase-shiffter in the Okroglo substation in Slovenia and the 400 kV internal line in Italy. The internal reinforcements are necessary to allow the realization of the interconnection and to take full advantage of the increase of cross-border capacity. The project increases the transmission capacities between Slovenia and Italy and allows stronger market integration between Italy and Slovenia and broader region. Such benefits are ensured according to different future scenarios. The project improves reliability and security of supply by allowing mutual support of both countries. PCI project.
| Scenario Vision 1 - 2030 | SI=>IT: 800 | IT=>SI: 350 | - | [23;28] | 0 | MWh | [-110000;-90000] | [220;270] | 1 | 4 | More than 100km | 15-25km
| Scenario Vision 2 - 2030 |  |  | - | [49;60] | 0 | MWh | [-140000;-120000] | [-260;-210]
| Scenario Vision 3 - 2030 |  |  | - | [15;18] | 0 | MWh | [-41000;-33000] | [0;1]
| Scenario Vision 4 - 2030 |  |  | - | [18;23] | 0 | MWh | [-260000;-220000] | 0
150 | The project consists in a new HVDC link between Salgareda (Italy) and Divača\Beričevo (Slovenia) wich will strengthen the connection between Slovenia and Italy. The project increases the transmission capacity between Slovenia and Italy and allows stronger market integration between Italy and Slovenia and broader region. Such benefits are ensured according to different future scenarios. The project could also improve the reliability and security of supply by allowing mutual support of both countries. PCI project.
| Scenario Vision 1 - 2030 | SI=>IT: 800 | IT=>SI: 700 | - | [22;27] | 0 | MWh | [1800;2200] | [220;270] | 1 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [49;60] | 0 | MWh | [900;1100] | [-230;-190]
| Scenario Vision 3 - 2030 |  |  | - | [15;18] | 0 | MWh | [3600;4400] | [12;15]
| Scenario Vision 4 - 2030 |  |  | - | [19;24] | 0 | MWh | 0 | 0
151 | This project consist of closing the 400kV Asturias Ring in the northern part of Spain, and comprises a new 400 kV line between Gozón and Sama, with two new 400kV subestations in Reboria and Costa Verde (Spain) , which main purpose is support the distribution network. Therefore, this project is required to ensure the security of supply in the area of Asturias in a future with very low thermal generation in the region.
| Scenario Vision 1 - 2030 | outside=>inside: 400-500 | inside=>outside: 700-700 | [2300;2800] | [1;2] | 0 | MWh | [-17000;-14000] | 0 | 2 | 2 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | [2300;2800] | [1;2] | 0 | MWh | [-17000;-14000] | 0
| Scenario Vision 3 - 2030 |  |  | [2600;3200] | [18;23] | 0 | MWh | [-34000;-28000] | [-11;-9]
| Scenario Vision 4 - 2030 |  |  | [3000;3700] | [20;25] | 0 | MWh | [-34000;-28000] | [-12;-9]
152 | The project aims at increasing the cross-border capacity between Germany and France by reinforcing the existing axes in Lorraine-Saar and Alsace-Baden areas. Studies in progress showed positive impact, with main benefits in terms of market and RES generation integration. Detailed timeline is under discussion between RTE, Amprion and TransnetBW.
| Scenario Vision 1 - 2030 | FR=>DE: 1000-2000 | DE=>FR: 1000-2000 | - | [18;22] | 0 | MWh | 0 | 0 | 1 | 4 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [48;59] | 0 | MWh | 0 | [1200;1400]
| Scenario Vision 3 - 2030 |  |  | - | [140;170] | [130000;160000] | MWh | 0 | [-860;-700]
| Scenario Vision 4 - 2030 |  |  | - | [220;270] | [200000;250000] | MWh | 0 | [-1400;-1100]
153 | France-Alderney-Britain (FAB) is a new HVDC subsea interconnector between Exeter (UK) and Cotentin Nord (France) with 1.4 GW capacity. The project will not only increase the interconnection between Great Britain and continent but alos integrate additional RES (especially wind generation from Great Britain); 2.8 GW of afuture tidal generation could also be connected to this link when it develops off the Cotentin coasts. The investment has been selected as PCI 1.7.1 in the NSCOG Corridor.
| Scenario Vision 1 - 2030 | FR=>GB: 1400 | GB=>FR: 1400 | - | [40;100] | [300000;360000] | MWh | [270000;340000] | [260;310] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [0;90] | [59000;72000] | MWh | [270000;340000] | [270;340]
| Scenario Vision 3 - 2030 |  |  | - | [230;350] | [2400000;2900000] | MWh | [260000;320000] | [-2000;-1600]
| Scenario Vision 4 - 2030 |  |  | - | [260;300] | [2100000;2500000] | MWh | [260000;320000] | [-1700;-1400]
157 | This project is a reinforcement between Aragón and Cataluña required to solve the congestion on the existing grid, due to unbalanced production and consumption between Aragón and Cataluña, mainly between Teruel and Tarragona. The project consist of a new 400 kV double circuit OHL line between Escatrón and La Secuita ( Spain), and includes new subestations in Els Aubals (with direct connection of wind power) and in La Secuita (400/220 kV).
| Scenario Vision 1 - 2030 | East=>West: 0-30 | West=>East: 0-500 | - | [37;46] | [370000;450000] | MWh | [-32000;-26000] | [-180;-150] | 2 | 2 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [41;50] | [400000;490000] | MWh | [-35000;-29000] | [-200;-160]
| Scenario Vision 3 - 2030 |  |  | - | [84;100] | [590000;730000] | MWh | [-30000;-24000] | [-270;-220]
| Scenario Vision 4 - 2030 |  |  | - | [110;140] | [840000;1000000] | MWh | [-30000;-24000] | [-310;-250]
158 | The main driver for the project is the integration of existing and new wind &hydro generation in the Massif Central (France) including possible pump storage. The project will develop in the north-south direction, mainly consisting of a new 400kV line substituting to the existing one. For visions 3&4, it will be complemented by a northern part (project 216). In TYNDP2012, both parts were described as a single investment.
| Scenario Vision 1 - 2030 | North=>South: 3300 | South=>North: 3800 | - | [18;22] | [90000;110000] | MWh | [-41000;-33000] | [-220;-180] | 2 | 2 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [18;22] | [90000;110000] | MWh | [-41000;-33000] | [-220;-180]
| Scenario Vision 3 - 2030 |  |  | - | [85;100] | [540000;660000] | MWh | [-99000;-81000] | [-770;-630]
| Scenario Vision 4 - 2030 |  |  | - | [85;100] | [540000;660000] | MWh | [-99000;-81000] | [-770;-630]
163 | Baltic corridor project includes several investments to enable the increase of 600MW though the Baltic States starting from Norht Estonia until Lithuania - Poland border in the south of Baltics. The project is strongly related to Baltic market integration to common European market and enables great new possibilities for large scale RES integration up to 1200MW. Additionally, this project can be considered as an alternative possibility to transfer electricity from North Scandinavia to continental Europe. The investments in this project are also seen as relevant preconditions for synchronous operation of Baltic States with the Continental Europe. So it means the project serves also as a backbone for project Baltics Synchronization with CE (project nr 170). The project includes reinforcement of existing 330 kV lines internally and on the borders of Baltic States. The new standards of line construction enable significant increase of the line capacity, up to 50%.
| Scenario Vision 1 - 2030 | North=>South: 600 | South=>North: 600 | - | 0 | [36000;44000] | MWh | [-59000;-49000] | [60;73] | 2 | 1 | More than 100km | More than 50km
| Scenario Vision 2 - 2030 |  |  | - | [1;2] | [36000;44000] | MWh | [38000;46000] | [-22;-18]
| Scenario Vision 3 - 2030 |  |  | - | [2;3] | 0 | MWh | [18000;22000] | [-69;-56]
| Scenario Vision 4 - 2030 |  |  | - | [3;4] | [54000;66000] | MWh | [83000;100000] | [-17;-14]
164 | North-South transmission - DC/AC link towards the load centers of Bavaria and Baden-Württemberg
This project was assessed together within the North South Eastern German Corridor. Please refer to the project 130 values.
167 | This project, known as Viking Link and under development by National Grid Interconnector Holdings Limited and Energinet.dk, investigates a connection of up to 1400MW between Denmark West and Great Britain by two parallel up to 700 MW HVDC subsea cables and related substations on both ends. A final route is not designed yet - the investigated project is one out of several possible alternatives. The project cluster includes in Denmark additionally the establishment of a 400 kV AC underground cable system between the 400 kV substation Idomlund and the existing 400 kV substation Endrup with needed compensation arrangements. The parts of national investments already known from TYNDP12 are included in this project cluster. The project adds cross-border transmission capacity between both countries, thereby facilitating the incorporation of more RES, as the wind is not correlated between both markets.
| Scenario Vision 1 - 2030 | DKW=>GB: 1400 | GB=>DKW: 1400 | - | [75;110] | [320000;400000] | MWh | [200000;250000] | [570;690] | 2 | 4 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [25;45] | [77000;94000] | MWh | [240000;290000] | [380;460]
| Scenario Vision 3 - 2030 |  |  | - | [220;300] | [2300000;2900000] | MWh | [360000;440000] | [-2000;-1600]
| Scenario Vision 4 - 2030 |  |  | - | [240;270] | [1800000;2200000] | MWh | [350000;420000] | [-1800;-1400]
168 | This project is the next step in the project 103 ("Ring upgrade") and consists of a new AC 400 kV double circuit line connecting the ring between the Sliedrecht area in the west of The Netherlands and the Dodewaard area in the east of The Netherlands. The investment in this project is expected to be commissioned more than 5 years from the investments in project 103 but it has the same drivers and benefits as project 103. Therefore this project is not assessed separately but together with project 103.
This project was assessed together with the project 103. Please refer to the project 103 values.
170 | The PCI project Estonia/Latvia/Lithuania synchronous interconnection with the Continental European networks is aimed at infrastructure development for deeper market integration and synchronous operation of the power systems of the Baltic States with the Continental European networks. Two different landing points and two differently routed interconnections are required to achieve physical separation of the two redundant interconnections in order to establish a reliable synchronous connection between the transmission systems of Baltic States and Continental Europe networks. The first Lithuania – Poland connection (LitPol Link) is already decided and it will be the first connection. The second connection is still under investigation. The projects consists mainly of the 330-400 kV cross-border lines and internal lines in order to reinforce internal grids to handle the situation. Baltics synchronisation with EU is unique project as main driver for it is not to increase GTC but to disconnect from Russia system and connect with Continental European networks synchronously.
| Scenario Vision 1 - 2030 | North=>South: 600 | South=>North: 600 | - | [26;31] | 0 | MWh | 0 | [-340;-280] | 2 | 4 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [12;15] | 0 | MWh | 0 | [86;110]
| Scenario Vision 3 - 2030 |  |  | - | [34;41] | 0 | MWh | 0 | [-2600;-2100]
| Scenario Vision 4 - 2030 |  |  | - | [120;140] | [54000;66000] | MWh | 0 | [-2000;-1700]
172 | Eleclink is a new HVDC interconnection between France and the United Kingdom with 1000 MW capacity through the Channel tunnel. This project has been selected as PCI n°1.7.3 in the NSCOG Corridor on 14/10/13.
| Scenario Vision 1 - 2030 | FR=>GB: 1000 | GB=>FR: 1000 | - | [35;75] | [230000;280000] | MWh | [200000;240000] | [170;210] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [0;60] | [36000;44000] | MWh | [200000;240000] | [220;260]
| Scenario Vision 3 - 2030 |  |  | - | [170;250] | [1700000;2000000] | MWh | [140000;170000] | [-1400;-1200]
| Scenario Vision 4 - 2030 |  |  | - | [180;210] | [1500000;1800000] | MWh | [140000;170000] | [-1100;-940]
173 | Preliminary analyses show the need for an additional reinforcement in visions 3&4 between France & Belgium, complementary to project # 23. The determination of the amount of additional market exchange that can be secured with this project, its optimal location & technology are subject to further studies.
| Scenario Vision 3 - 2030 | FR=>BE: 1400 | BE=>FR: 1400 | - | [20;30] | [160000;200000] | MWh | 0 | [-210;-180] | 2 | 1 | NA | NA
| Scenario Vision 4 - 2030 |  |  | - | [60;100] | [360000;430000] | MWh | 0 | [-540;-450]
174 | Project promoted by Worldenergy. The projects consists of a new HVDC interconnection between Italy and Switzerland which will increase the transmission capacity between the two countries. The project, promoted by non-ENTSO-E member, could potentially contribute to market and RES integration in the future European interconnected system.
| Scenario Vision 1 - 2030 | CH=>IT: 800 | IT=>CH: 800 | - | [19;24] | 0 | MWh | [-20000;-16000] | [170;210] | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [17;20] | 0 | MWh | [-24000;-20000] | [-500;-410]
| Scenario Vision 3 - 2030 |  |  | - | [18;23] | 0 | MWh | [1800;2200] | 0
| Scenario Vision 4 - 2030 |  |  | - | [42;51] | 0 | MWh | [-17000;-14000] | [-120;-99]
175 | This project candidate includes a 1x 600 MW HVDC connector between Denmark-West (DKW) and Denmark-East (DKE). The connector is called Great Belt-2. It could among other variants be located between the 400 kV substation Malling in DKW and the reconstructed 400 kV substation Kyndby in DKE. The main purpose of this project is to incorporate more RES into the Danish system by sharing reserves between both systems and improve market integration.
| Scenario Vision 1 - 2030 | DKW=>DKE: 600 | DKE=>DKW: 600 | - | 0 | 0 | MWh | [72000;87000] | [190;230] | 3 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | 0 | 0 | MWh | [72000;88000] | [65;80]
| Scenario Vision 3 - 2030 |  |  | - | [0;1] | [18000;22000] | MWh | [62000;76000] | [-50;-41]
| Scenario Vision 4 - 2030 |  |  | - | [2;3] | [45000;55000] | MWh | [62000;76000] | [-40;-33]
176 | New interconnector between Sweden (SE4) and Germany (50 Hertz). There has been joint studies with 4 options for this project. The other options were new interconnectors Latvia-Sweden, Lithuania-Sweden and Poland-Sweden. CBA indicators are based only on the SE4-DE interconnector.
| Scenario Vision 1 - 2030 | DE=>SE: 600 | SE=>DE: 600 | - | [72;88] | [36000;44000] | MWh | [420000;520000] | [590;720] | 3 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [15;18] | [36000;44000] | MWh | [190000;230000] | [340;420]
| Scenario Vision 3 - 2030 |  |  | - | [28;35] | [90000;110000] | MWh | [62000;75000] | [-710;-580]
| Scenario Vision 4 - 2030 |  |  | - | [220;270] | [90000;110000] | MWh | [280000;350000] | [-2200;-1800]
177 | Construction of this project enables control of power flow on the border to support system security - in terms of N-1 security, effective utilization of the infrustructure and cross-border market exchanges. The target capacity of phase shifting transformers is 1700MVA per each circuit of tie-lines between CEPS and 50Hertz, that means 3400MVA of thermal capacity. Devices are located in 400kV substation Hradec.
| Scenario Vision 1 - 2030 | CZ=>DE: 0-500 | DE=>CZ: 0-500 | - | [10;14] | 0 | MWh | [110;150] | [140;160] | 2 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [79;99] | 0 | MWh | [110;160] | [170;210]
| Scenario Vision 3 - 2030 |  |  | - | [14;18] | [62000;76000] | MWh | [130;230] | [-58;-78]
| Scenario Vision 4 - 2030 |  |  | - | [20;24] | [210000;250000] | MWh | [190;320] | [-120;-140]
179 | This project includes a 600 MW HVDC subsea interconnector between Denmark-East (DKE) and Germany (DE)and is called Kontek-2. A final grid-connection solution is not prepared yet; one of the possible alternatives could establish the Danish HVDC converter station in the area of Lolland-Falster. This alternative has been investigated for the TYNDP and comprises among other things an HVDC converter station being connected to the existing 400 kV substation Bjæverskov via 400 kV underground cables and/or 400 kV OHL. Some additional investments in eastern Danmark would be necessary, which are not described in detail in this document.
| Scenario Vision 1 - 2030 | DKE=>DE: 600 | DE=>DKE: 600 | - | [31;38] | [54000;66000] | MWh | [17000;21000] | [82;100] | 3 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [22;27] | [54000;66000] | MWh | [-2200;-1800] | [73;90]
| Scenario Vision 3 - 2030 |  |  | - | [22;27] | [63000;77000] | MWh | [120000;150000] | [-890;-720]
| Scenario Vision 4 - 2030 |  |  | - | [140;170] | [63000;77000] | MWh | [120000;150000] | [-1900;-1600]
182 | Project promoted by ACS and COBRA. Interconnection project between Indian Queens (Great Britain), Cordemais (France) and Gatica (Spain) in a multiterminal HVDC configuration with 3 sections of 1000 MW each, and a submarine route from Spain to Great Britain along the french coast. It is proposed to take advantage of complementarity of resources in the three countries involved in the project.
| Scenario Vision 1 - 2030 | ES=>GB: 1000 | GB=>ES: 1000 | - | [65;130] | [93000;110000] | MWh | [200000;300000] | [900;1100] | 2 | 5 | 50-100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [75;140] | [110000;130000] | MWh | [230000;330000] | [780;960]
| Scenario Vision 3 - 2030 |  |  | - | [200;280] | [1800000;2200000] | MWh | [430000;530000] | [-1700;-1400]
| Scenario Vision 4 - 2030 |  |  | - | [280;350] | [2100000;2500000] | MWh | [510000;610000] | [-1800;-1400]
183 | The project consists of a new 400 kV line from Endrup (Denmark) to Niebüll (Germany), adding another 500 MW at the West Coast between these countries. On the Danish side, this project includes the establishment a 400 kV AC underground cable system from the existing 400 kV substation Endrup, via Ribe and Bredebro to the border, from where the interconnector continues to Niebüll. The project helps to integrate RES and to strenghten the connection between the Scandinavian and Continental market. The project is labelled by the EC as project of common interest (PCI).
| Scenario Vision 1 - 2030 | DKW=>DE: 500 | DE=>DKW: 500 | - | [0;10] | [14000;17000] | MWh | [-11000;-9000] | [-88;-72] | 2 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [4;5] | [14000;17000] | MWh | [-11000;-9000] | [-22;-18]
| Scenario Vision 3 - 2030 |  |  | - | [20;60] | [120000;140000] | MWh | [-12000;-9900] | [-440;-360]
| Scenario Vision 4 - 2030 |  |  | - | [80;100] | [260000;310000] | MWh | [-12000;-9600] | [-830;-680]
184 | This project is a new PST (phase shifting transformer) in the Spanish substation Arkale 220 kV with affection to the Arkale-Argia cross border line between France and Spain. This device is required to increase the France-Spain exchange capacity, especially from Spain to France, and not only is able to have an independent good impact in the exchange capacity without taking into account the Eastern and Western interconnections (projects 5 and 16), but also helps making the most of these projects. In addition, as this project avoids the tripping of the Arkale-Argia tieline in case of contingencies,it helps improving the Security of supply in the French Basque country. This project have been included in the 2013 PCI list.
| Scenario Vision 1 - 2030 | ES=>FR: 500-900 | FR=>ES: 100-500 | [22;27] | [5;13] | [8700;11000] | MWh | [7000;11000] | [210;250] | 3 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | [23;28] | [7;15] | [8900;11000] | MWh | [7500;12000] | [230;290]
| Scenario Vision 3 - 2030 |  |  | [27;33] | [12;26] | [54000;66000] | MWh | [10000;14000] | [-190;-150]
| Scenario Vision 4 - 2030 |  |  | [36;45] | [33;53] | [150000;190000] | MWh | [14000;18000] | [-280;-230]
185 | Greenwire Interconnetor spurs, enables additional 1500MW of interconnection between UK and Irish market
| Scenario Vision 1 - 2030 | IE=>GB: 1500 | GB=>IE: 1500 | - | [510;660] | [7000000;8600000] | MWh | [360000;440000] | [-4500;-3700] | 6 | 4 | 15-50km | 15-25km
| Scenario Vision 2 - 2030 |  |  | - | [590;670] | [7200000;8800000] | MWh | [360000;440000] | [-4600;-3800]
| Scenario Vision 3 - 2030 |  |  | - | [420;640] | [5100000;6200000] | MWh | [490000;600000] | [-2400;-1900]
| Scenario Vision 4 - 2030 |  |  | - | [360;390] | [4200000;5200000] | MWh | [490000;600000] | [-1600;-1300]
186 | To allow the grid integration of the planned renewable energy generation (mainly wind power) in the north-eastern part of Austria ("Weinviertel") the transmission grid infrastructure (currently a rather weak 220kV line) has to be enforced and new substations for the connection need to be erected.
| Scenario Vision 1 - 2030 | outside=>inside: 1500 | inside=>outside: 1500 | - | [220;260] | 1100 | MW | [-5500;-4500] | [-1000;-840] | 1 | 2 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [130;160] | 1100 | MW | [-1100;-900] | [-320;-260]
| Scenario Vision 3 - 2030 |  |  | - | [300;370] | 1500 | MW | [-2600;-2200] | [-1200;-990]
| Scenario Vision 4 - 2030 |  |  | - | [230;280] | 1500 | MW | [-7900;-6500] | [-1200;-990]
187 | Increase of the cross border transmission capacity by erecting a new 380kV line between St. Peter (Austria) and Pleinting (Germany). This leads to an improved connection of the very high amount of RES in Germany and the pump storages in the Austrian Alps.
| Scenario Vision 1 - 2030 | AT=>DE: 1500 | DE=>AT: 1500 | - | [13;16] | 0 | MWh | [-79000;-65000] | [140;170] | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [15;18] | [4400;5400] | MWh | [-83000;-68000] | [560;680]
| Scenario Vision 3 - 2030 |  |  | - | [100;130] | [140000;170000] | MWh | [-88000;-72000] | [-520;-420]
| Scenario Vision 4 - 2030 |  |  | - | [190;230] | [220000;260000] | MWh | [-110000;-90000] | [-720;-590]
189 | Project promoted by the Scottish Government. Conceived as a number of complementary multi-terminal HVDC connections that can be operated without the need for DC breakers and without breaching existing onshore loss of infeed limits but which can be reconfigured post-fault to re-establish power transfer paths. The benefits of the design are that offshore wind or tidal power can be brought to either of two shores, there is redundancy in connections and, in particular, interconnection capacity is provided between the GB market and the Single Electricity Market on the island of Ireland. Thus, while not 'dedicated to security of supply', it contributes to it.
| Scenario Vision 1 - 2030 | NI=>GB: 1500 | GB=>NI: 1500 | - | 0 | 0 | MWh | 0 | 0 | 4 | 6 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | 0 | 0 | MWh | 0 | 0
| Scenario Vision 3 - 2030 |  |  | - | [30;40] | [180000;220000] | MWh | [270000;330000] | [-190;-160]
| Scenario Vision 4 - 2030 |  |  | - | [45;55] | [400000;490000] | MWh | [270000;330000] | [-310;-250]
190 | A 650 km long subsea interconnector between Norway and Scotland is planned to be realized in 2021. The main driver for the project is to integrate the hydro-based Norwegian system with the thermal/nuclear/wind-based British system. The interconnector will improve security of supply both in Norway in dry years and in Great Britain in periods with negative power balance (low wind, low solar, high demand etc.). Additional the interconnector will be positive both for the European market integration, for facilitating renewable energy and also for preparing for a power system with lower CO2-emission. The interconnector is planned to be a 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern Scotland.
| Scenario Vision 1 - 2030 | GB=>NO: 1400 | NO=>GB: 1400 | - | [150;220] | [1000000;1200000] | MWh | [760000;930000] | [-440;-360] | 2 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [90;170] | [900000;1100000] | MWh | [760000;930000] | [-240;-190]
| Scenario Vision 3 - 2030 |  |  | - | [280;360] | [2700000;3300000] | MWh | [760000;930000] | [-2000;-1700]
| Scenario Vision 4 - 2030 |  |  | - | [280;300] | [2100000;2600000] | MWh | [760000;930000] | [-1800;-1500]
191 | Germany is planning to build a big amount of wind offshore power plants in the Northsea. The OWP will help to reach the European goal of CO2 reduction and RES integration. This project is for the connection of the OWP with the German grid.
| Scenario Vision 1 - 2030 | inside=>DE: 5400 | DE=>inside: 5400 | - | [520;640] | 3788 | MW | 0 | [-6200;-5100] | 4 | 3 | More than 100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [330;400] | 3788 | MW | 0 | [-5600;-4500]
| Scenario Vision 3 - 2030 |  |  | - | [1700;2100] | 5401 | MW | 0 | [-9400;-7700]
| Scenario Vision 4 - 2030 |  |  | - | [1500;1900] | [5300;5500] | MW | 0 | [-8700;-7100]
192 | Germany is planning to build a big amount of wind offshore power plants in the Northsea. The OWP will help to reach the European goal of CO2 reduction and RES integration. This project is for the connection of the OWP with the German grid.This project becomes necessary in case of further longterm strong increase in OWP generation like in Vision 3 and 4. The project is not in focus of Vision 1 and 2.
| Scenario Vision 3 - 2030 | inside=>DE: 4500 | DE=>inside: 4500 | - | [1400;1700] | 4499 | MW | 0 | [-7400;-6000] | 4 | 3 | More than 100km | Negligible or less than 15km
| Scenario Vision 4 - 2030 |  |  | - | [1100;1400] | [4400;4600] | MW | 0 | [-6100;-5000]
193 | This projects consist of a new OHL 400 kV AC axis Godelleta-Morella/La Plana (Spain) and represents the reinforcement of the Mediterranean axis needed to accommodate geographical unbalances between North and South, especially between Castellón and Valencia, which besides are influenced by the exchanges with France. Congestions are expected due to important south-north flows caused by renewable energy sources (onshore wind but mainly solar), which result in dumped energy without the project.
| Scenario Vision 1 - 2030 | North=>South: 670-850 | South=>North: 1400-1500 | - | [11;14] | [23000;28000] | MWh | [23000;28000] | [-14;-11] | 2 | 2 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [12;15] | [25000;30000] | MWh | [25000;30000] | [-15;-12]
| Scenario Vision 3 - 2030 |  |  | - | [120;140] | [880000;1100000] | MWh | [350000;430000] | [-210;-170]
| Scenario Vision 4 - 2030 |  |  | - | [290;350] | [3800000;4700000] | MWh | [290000;350000] | [-1400;-1200]
194 | The 400 kV double circuit Cartuja-Arcos de la Frontera and the Cartuja 400 kV substation intend to be the connection point of an important amount of wind power energy in the coastal area of Cadiz, mainly offshore but also onshore. In case of low wind production, the project will be useful as an additional injection for secure the load in the area of Cadiz.
| Scenario Vision 1 - 2030 | South=>North: 425-600 | North=>South: 1560-2700 | - | [77;94] | [95000;120000] | MWh | [-35000;-29000] | [-420;-340] | 1 | 2 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [81;99] | [100000;120000] | MWh | [-37000;-30000] | [-440;-360]
| Scenario Vision 3 - 2030 |  |  | - | [96;120] | [1100000;1400000] | MWh | [-1100;-900] | [-460;-380]
| Scenario Vision 4 - 2030 |  |  | - | [99;120] | [1200000;1500000] | MWh | [3600;4400] | [-390;-320]
197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | [12 empty] | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South. | 197 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thus enabling the integration of new renewable and conventional generation in northern Finland and to compensate the dismantling of the obsolescent exiting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term. Change in TYNDP 2014, taken the latest investment as its own project. This project is 400 kV overhead line from connecting North Finland to South.
| S1 EU202020 - 2020 | North=>South: 1000 | South=>North: 1000 | [30;300] | [30;100] | [500;1500] | MW | [0;-3000] | [500;1000] | 2 | 4 | NA | NA
198 | The transmission capacity of the 380-kV-grid in this grid area and especially the cross-border lines between Germany and Austria are extended significantly by this project. Capacity overloads with existing lines are eliminated and therefore connection between the German and the Austrian transportation grid is strengthened.
| Scenario Vision 1 - 2030 | DE=>CH: 3400 | CH=>DE: 1400 | - | [90;110] | 0 | MWh | [-99000;-81000] | [820;1000] | 1 | 4 | 50-100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [140;170] | 0 | MWh | [-140000;-110000] | [1900;2400]
| Scenario Vision 3 - 2030 |  |  | - | [310;380] | [450000;550000] | MWh | [-91000;-75000] | [-1200;-950]
| Scenario Vision 4 - 2030 |  |  | - | [480;580] | [900000;1100000] | MWh | [-180000;-150000] | [-2100;-1700]
199 | This project comes on top of the Lake Geneva West project and will further increase the France-Switzerland cross-border capacity by upgrading to 400 kV the existing 225kV line south of Lake Geneva; some grid restructuration in Genissiat area will allow taking full benefit of this new axis. Main benefits are expected in terms of market integration and better integration of Swiss hydro generation, especially storage.
| Scenario Vision 1 - 2030 | FR=>CH: 1000 | CH=>FR: 1500 | - | [8;9] | 0 | MWh | [-39000;-32000] | [-130;-100] | 0 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [7;8] | 0 | MWh | [-37000;-31000] | [700;860]
| Scenario Vision 3 - 2030 |  |  | - | [63;77] | [36000;44000] | MWh | [-33000;-27000] | [-430;-350]
| Scenario Vision 4 - 2030 |  |  | - | [150;180] | [180000;220000] | MWh | [9000;11000] | [-1000;-840]
200 | This project represent first phase of Czech North-South corridor which enables the power flow from northwester border to southeastern border. This project is required to facilitate power flows in the direction North-South and East-West, enhance the grid transfer capability between Czech Republic and Germany and supports the future thermal generation evacuation and RES - connectiuon point of wind generation is substation Vernerov. In addition the project ensures security of supply of the North-western part of Czech Republic in general terms. Project is represented by 400kV double-circiut overheadline
| Scenario Vision 1 - 2030 | CZ=>DE: 0-500 | DE=>CZ: 0-500 | - | [250;310] | [200000;250000] | MWh | [-220000;-260000] | [-2100;-2500] | 2 | 3 | 15-50km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [270;330] | [200000;240000] | MWh | [-260000;-320000] | [-1800;-2100]
| Scenario Vision 3 - 2030 |  |  | - | [1400;1700] | [210000;260000] | MWh | [-340000;-580000] | [-7900;-9500]
| Scenario Vision 4 - 2030 |  |  | - | [1200;1500] | [210000;260000] | MWh | [-280000;-300000] | [-7000;-8600]
203 | This project represents the reinforcement of the Cantabric-Mediterranean axis needed to accommodate geographical unbalances between Northern Spain and the Mediterranean area, which otherwise would produce congestions in the 400 kV corridors. Therefore, this project is required to solve constraints in the existing and future network, caused by existing and new RES and because of flows in both directions between Aragón and Castellón. The project consists of two 400kV axis Mudejar-Morella and Mezquita-Morella that converge in an axis Morella-La Plana. The project also includes a new 400kV subestation Mudejar with connection to the axis Aragón-Teruel (Spain).
| Scenario Vision 1 - 2030 | West=>East: 100-900 | East=>West: 1900-2600 | - | [52;63] | [25000;30000] | MWh | [-89000;-73000] | [-58;-47] | 2 | 2 | 50-100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [57;70] | [27000;33000] | MWh | [-98000;-80000] | [-63;-52]
| Scenario Vision 3 - 2030 |  |  | - | [87;110] | [920000;1100000] | MWh | [310000;380000] | [-210;-170]
| Scenario Vision 4 - 2030 |  |  | - | [380;470] | [4800000;5900000] | MWh | [490000;600000] | [-1800;-1500]
204 | North-South transmission - AC-measures in support of the existing grid
This project was assessed together within the North South Eastern German Corridor. Please refer to the project 130 values.
205 | North-South transmission - AC-measures in support of the existing grid
This project was assessed together within the North South Eastern German Corridor. Please refer to the project 130 values.
206 | "AC-busbar" in Southern Germany for energy dispatching within Bavaria and Baden-Württemberg and gathering solar energy
This project was assessed together within the North South Western German Corridor. Please refer to the project 130 values.
207 | "AC-busbar" in Northern Germany for wind energy towards the DC connections
This project was assessed together within the North South Eastern German Corridor. Please refer to the project 132 values.
208 | North-South transmission Western Germany - first section towards the load center of the Ruhr area Part 1
This project was assessed together within the North South Eastern German Corridor. Please refer to the project 132 values.
209 | "AC-busbar" in Northern Germany for wind energy towards the DC connections
This project was assessed together within the North South Eastern German Corridor. Please refer to the project 130 values.
210 | A 3rd party project promoted by Alpe Adria Energia SpA - planned 220kV line from Würmlach (Austria) to Somplago (Italy).
| Scenario Vision 1 - 2030 | AT=>IT: 150 | IT=>AT: 150 | - | [4;5] | 0 | MWh | [-13000;-11000] | 0 | 1 | 3 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [9;11] | 0 | MWh | [-13000;-11000] | 0
| Scenario Vision 3 - 2030 |  |  | - | [2;3] | 0 | MWh | [-2600;-2200] | 0
| Scenario Vision 4 - 2030 |  |  | - | [5;6] | 0 | MWh | [-3600;-3000] | 0
213 | This project consists of a double 400kV circuit from Santa Llogaia to Bescanó which first is needed to connect the Spain-France Eastern HVDC interconnection project (project 5) to the existing transmission network in Spain. Secondly, the projects contributes to improve the security of supply of the area of Gerona with the new injection from the new 400 kV Ramis and Santa Llogaia subestations to the distribution network. Therefore, the benefits attached to this project join the cross border benefits and the local benefits. This project have been included in the 2013 PCI list.
| Scenario Vision 1 - 2030 | ES=>FR: 1400 | FR=>ES: 1200 | [100;250] | [20;130] | [110000;130000] | MWh | [19000;23000] | [1600;2000] | 1 | 4 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | [110;260] | [22;140] | [120000;150000] | MWh | [21000;26000] | [1800;2200]
| Scenario Vision 3 - 2030 |  |  | [120;270] | [70;150] | [590000;720000] | MWh | [18000;22000] | [-1100;-870]
| Scenario Vision 4 - 2030 |  |  | [120;280] | [210;280] | [1300000;1500000] | MWh | [26000;32000] | [-1500;-1300]
214 | Interconnector (Sea cable) between Iceland and Great Britain. The Cable is DC with 800-1200 MW capacity and 1.000 km long. 99.98% of the generation in Iceland is RES. Icelands hydro generation is highly flexible and ideal for complementing intermittency of GB’s growing wind sector. It will provide flexible electricity for fast delivery of energy during peak periods and is also able to provide ancillary services to GB
| Scenario Vision 1 - 2030 | IS=>GB: 1000 | GB=>IS: 1000 | - | [410;470] | [63000;77000] | MWh | [810000;990000] | [-2900;-2300] | 2 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [420;460] | [14000;17000] | MWh | [810000;990000] | [-2800;-2300]
| Scenario Vision 3 - 2030 |  |  | - | [340;370] | [810000;990000] | MWh | 0 | [-1600;-1300]
| Scenario Vision 4 - 2030 |  |  | - | [290;310] | 0 | MWh | [810000;990000] | [-1300;-1000]
216 | The main driver of the project is the integration of exisiting and new wind&hydro generation in the Massif Central (France) including possible pump storage. The project will develop in the north to south direction, north of project 158 that it complements. It is needed only for visions 3 and 4. Studies are ongoing to define the scope of the project.
| Scenario Vision 3 - 2030 | North=>South: 3300 | South=>North: 3800 | - | [85;100] | [540000;660000] | MWh | [-230000;-190000] | [-770;-630] | 2 | 2 | NA | NA
| Scenario Vision 4 - 2030 |  |  | - | [85;100] | [540000;660000] | MWh | [-230000;-190000] | [-770;-630]
219 | Promoted by DEH Quantum Energy LTD . A 2000 MW link between Israel, Cyprus, and Greece (Creta and mainland).
| Scenario Vision 1 - 2030 | East=>West: 2000 | West=>East: 2000 | - | [530;640] | [3400000;4100000] | MWh | [1400000;1700000] | 0 | 2 | 3 | NA | NA
| Scenario Vision 2 - 2030 |  |  | - | [530;650] | [3600000;4400000] | MWh | [1400000;1700000] | 0
| Scenario Vision 3 - 2030 |  |  | - | [330;410] | [3500000;4200000] | MWh | [1200000;1400000] | 0
| Scenario Vision 4 - 2030 |  |  | - | [310;380] | [3500000;4300000] | MWh | [1100000;1400000] | 0
220 | Promoted by Kykladika Meltemia S.A. The project consists of collecting about 600 MW of RES in the Islands north-east to Crete via HVDC cables.
| Scenario Vision 1 - 2030 | North=>South: 650 | South=>North: 650 | - | [150;180] | [2000000;2400000] | MWh | [120000;150000] | 0 | 2 | 2 | Negligible or less than 15km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [140;170] | [2000000;2400000] | MWh | [130000;160000] | 0
| Scenario Vision 3 - 2030 |  |  | - | [160;200] | [2000000;2400000] | MWh | [110000;130000] | 0
| Scenario Vision 4 - 2030 |  |  | - | [150;190] | [2000000;2400000] | MWh | [100000;130000] | 0
225 | This is a conceptual project that could be considered as an investment option, triggered by high RES scenario's. Preliminary analysis shows potential of justifying additional regional welfare & RES integration increase via the construction of an additional +- 1000MW interconnection between Germany and Belgium. The determination of the optimal capacity, timing (2025-2030), location, technology, and potential needed internal grid reinforcements are subject of further studies.
| Scenario Vision 4 - 2030 | BE=>DE: 1000 | DE=>BE: 1000 | - | [45;55] | [150000;180000] | MWh | [120000;140000] | [-850;-690] | 2 | 1 | NA | NA
227 | Project 227 is the second phase of investments of the Transbalkan Corridor (phase 1 being Project 146). The two projects share the same assessment.
This project was assessed together with the project 146. Please refer to the project 146 values.
228 | Project promoted by Organic Power Limited. Combined 1900MW wind generation, with 6.1GWh storage in mayo Ireland, connected to GB via 1500mw HVDC VSC cable
| Scenario Vision 1 - 2030 | IE=>GB: 1900 | GB=>IE: 1900 | - | [290;400] | [190000;240000] | MWh | 0 | [-2800;-2300] | 0 | 0 | More than 100km | Negligible or less than 15km
| Scenario Vision 2 - 2030 |  |  | - | [370000;380000] | [58;71] | MWh | 0 | [-2800;-2300]
| Scenario Vision 3 - 2030 |  |  | - | [200;240] | [1900000;2300000] | MWh | 0 | [-930;-760]
| Scenario Vision 4 - 2030 |  |  | - | [170;180] | [1700000;2100000] | MWh | 0 | [-580;-470]