## Key
Legend
|  | ENTSO-E Drafting Proposal |  | NRAs Approval preparation
|  | Consultation |  | NRAs Approval publication
| w | Workshop |  | ACER Decision preparation
|  | ENTSO-E Proposal submission |  | ACER Decision publication
|  | CCRs Drafting Proposals | W | NRAs Workshop
NEMOs Drafting proposal

## All consultations
All Consultations | 2017 |  |  |  | 2018 | [11 empty] | 2019 | [11 empty] | Consultation? | Consultation period | Workshop
| S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
CACM | [28 empty] | Y | bar: 2018 J to 2019 D
Congestion income distribution methodology | bar: 2017 S to 2017 D
Proposal for intraday cross-zonal gate opening and gate closure times | bar: 2017 N to 2018 A
Intraday capacity pricing methodology | bar: 2018 M to 2018 A
Scheduled exchanges calculation methodologies | bar: 2017 S to 2017 D
Capacity calculation methodology | [28 empty] | Y | bar: 2017 S; 2017 N; 2018 J to 2018 F; 2018 A to 2018 M
Nordic | bar: 2018 A to 2018 M
Baltic | bar: 2017 S; 2018 A to 2018 M
Hansa | bar: 2018 A to 2018 M
Core | bar: 2018 A to 2018 M
Italy North | [29 empty] | tbc | bar: 2018 J to 2018 F
Greece Italy (GRIT) | bar: 2018 A to 2018 M
South West Europe (SWE) | bar: 2018 A to 2018 M
Ireland and United Kingdom (IU) | bar: 2018 A to 2018 M
Channel | bar: 2018 A to 2018 M
South East Europe (SEE) | bar: 2017 N; 2018 J to 2018 J
Coordinated redispatching and countertrading methodologies | [28 empty] | Y | bar: 2017 S to 2018 M
Nordic | bar: 2018 J; 2018 M
Baltic | bar: 2018 J; 2018 M
Hansa | bar: 2017 D to 2018 J; 2018 M
Core | [29 empty] | 06/02- 06/03/2018 | bar: 2018 F; 2018 A
Italy North
Greece Italy (GRIT) | [29 empty] | 08/02- 15/03/2018 | bar: 2018 F; 2018 A
South West Europe (SWE) | bar: 2018 J; 2018 M
Ireland and United Kingdom (IU) | bar: 2018 J to 2018 F; 2018 A
Channel | bar: 2017 D to 2018 J; 2018 M
South East Europe (SEE) | [29 empty] | 02/02-04/03/2018 | bar: 2018 F; 2018 A
Redispatching or countertrading cost sharing methodologies | bar: 2017 S to 2018 M
Technical report on current bidding zone configuration | bar: 2017 S to 2018 J
Algorithm proposals (including DA and ID algorithm requirements) | bar: 2017 S to 2017 O
FCA | [28 empty] | Y | bar: 2018 J to 2019 D
Harmonised allocation rules for long-term transmission rights | bar: 2017 S to 2017 O
Requirements for the single allocation platform
Methodology for sharing costs for establishment and development of the signle allocation platform
Congestion income distribution methodology | bar: 2018 J to 2018 J
Methodology for sharing costs to ensure firmness and remuneration | bar: 2018 J to 2018 J
Capacity calculation methodology (assuming CACM CCMs are approved in July 2017) | [28 empty] | Y | bar: 2018 F; 2018 J; 2018 A to 2019 J
Nordic | [29 empty] | tbc | bar: 2018 J; 2018 A to 2019 J
Baltic | bar: 2018 A to 2019 J
Hansa | bar: 2018 A to 2019 J
Core | [29 empty] | tbc | bar: 2018 J; 2018 A to 2019 J
Italy North | bar: 2018 A to 2019 J
Greece Italy (GRIT) | bar: 2018 A to 2019 J
South West Europe (SWE) | bar: 2018 A to 2019 J
Ireland and United Kingdom (IU) | bar: 2018 A to 2019 J
Channel | bar: 2018 A to 2019 J
South East Europe (SEE) | bar: 2018 A to 2019 J
Methodology for splitting cross-zonal capacity | [28 empty] | Y | bar: 2018 J; 2018 A to 2019 J
Nordic | [29 empty] | tbc | bar: 2018 J; 2018 A to 2019 J
Baltic | bar: 2018 A to 2019 J
Hansa | bar: 2018 A to 2019 J
Core | [29 empty] | tbc | bar: 2018 J; 2018 A to 2019 J
Italy North | [29 empty] | tbc | bar: 2018 J; 2018 A to 2019 J
Greece Italy (GRIT) | [29 empty] | tbc | bar: 2018 J; 2018 A to 2019 J
South West Europe (SWE) | bar: 2018 A to 2019 J
Ireland and United Kingdom (IU) | bar: 2018 A to 2019 J
Channel | bar: 2018 A to 2019 J
South East Europe (SEE) | bar: 2018 A to 2019 J
GLEB | [28 empty] | Y | bar: 2018 J to 2019 D
ENTSO-E to update manual procedures of Transparency Regulation | bar: 2017 S to 2018 A
Proposal for activation purposes | [28 empty] | Y | Expected: Sept. - Oct. | bar: 2018 F to 2018 D
Each TSO to propose T&Cs for BSPs and BRPs | [28 empty] | Y | bar: 2017 S to 2018 J
Proposal for pricing method for all products | [28 empty] | Y | Expected: Sept. - Oct. | bar: 2018 F to 2018 D
Proposal for TSO-TSO settlement of intended exchanges of energy | [29 empty] | Expected: Sept. - Oct. | bar: 2018 F to 2018 D
Proposal for TSO-TSO settlement of settlement of ramps and FCR and unintended exchanges within and between SA | bar: 2018 A to 2019 J
Proposal for harmonisation of certain features of imbalance calculation & pricing | [28 empty] | Y | Expected: Sept. - Oct. | Expected: March | bar: 2017 S to 2018 D
CZC Allocation - Proposal for list of Standard Balancing Capacity Products | [28 empty] | Y | bar: 2017 S to 2019 D
CZC Allocation - Methodology for calculating CZC for balancing
CZC Allocation - Harmonise allocation of CZC within CCR
CZC Allocation - Methodology for cooptimised CZC allocation | [28 empty] | Y | bar: 2017 S to 2019 D
CZC Allocation - Methodology for market based CZC allocation | [28 empty] | Y | bar: 2017 S to 2019 D
ENTSO-E monitoring plan | bar: 2017 S to 2018 J
Proposal for implementation framework for European platform for replacement reserves | [28 empty] | Y | 12/02/18 - 23/03/18 | 2018-03-19 | bar: 2017 S to 2018 J
Proposal for implementation framework for European platform for frequency restoration reserves with manual activation | [28 empty] | Y | Expected: May-June 2018, pot. June-July 2018 | 27/03/2018; 20/06/2018 | bar: 2017 S to 2018 D
Proposal for implementation framework for European platform for frequency restoration reserves with automatic activation | [28 empty] | Y | Expected: May-June 2018; pot. June-July 2018 | 26/03/2018; 20/06/2018 | bar: 2017 S to 2018 D
Proposal for implementation framework for European platform for imbalance netting | [28 empty] | Y | 15/01/2018 - 15/03/2018 | bar: 2017 S to 2018 J
SOGL | [28 empty] | Y | bar: 2018 J
SOGL: Pan-European activities | [28 empty] | Y | bar: 2018 J to 2019 D
Key organisational requirements, roles and responsibilities in relation to data exchange (Art. 40.6) | [28 empty] | Y | bar: 2017 S to 2018 M
Methodology for building the year-ahead, day-ahead and intraday common grid models from the individual models and for saving them (Art. 67.1) | [28 empty] | Y | bar: 2017 S to 2018 M
Methodology for coordinating operational security analysis (Art. 75.1) | [28 empty] | Y | 26/02/2018-06/04/2018 | 2018-03-21 | bar: 2017 S to 2018 S
SOGL: Regional activities on synchronous area level | [28 empty] | Y | bar: 2018 J to 2019 D
OPTIONAL Methodology for the definition of minimum inertia required to maintain operational security and prevent violation of stability limits (Art. 39b)
Methodology for assessing the relevance of assets for outage coordination (Art. 84.1) | [28 empty] | Y | 26/02/2018-06/04/2018 | 2018-03-21 | bar: 2017 S to 2018 S
Methodologies, conditions and values included in operational agreements (Art. 118.1) | [28 empty] | Y | 03/04/2018-03/05/2018 | 2018-04-13 | bar: 2017 S to 2018 S
Determination of LFC blocks (Art. 141.2) | [28 empty] | Y | bar: 2017 S to 2018 J
Assumptions and methodology for a CBA to be conducted to assess the minimum activation time of FCR - in CE and Nordic synchronous areas (Art. 156.11) | [28 empty] | Y | bar: 2017 S to 2018 M
Cost-benefit analysis suggesting the minimum FCR activation period (156.11) | [28 empty] | Y | bar: 2018 O to 2019 S
SOGL: Regional activities on CCR level | [28 empty] | Y | bar: 2018 J to 2019 D
Common provisions for regional operational security coordination (Art. 76.1) | [28 empty] | Y | bar: 2019 M to 2019 J
CNCs (RfG, DCC, HVDC) - All/relevant TSOs and ENTSO-E tasks
RfG NC - Cordinate and monitor implementation activities in each country / use of Active Library (transposition) | bar: 2018 J to 2018 M
DCC and HVDC NC - Cordinate and monitor implementation activities in each country / use of Active Library (transposition) | bar: 2018 J to 2018 S
Prepare Implementation Guidance Documents on frequency related parameters | [29 empty] | 20/11/17 - 21/12/17 | bar: 2018 J
Prepare Implementation Guidance Documents on Cost Benefit Analysis (CBA) | [29 empty] | 26/01/18 - 27/02/18 | bar: 2018 J to 2018 M
Prepare Implementation Guidance Documents on Embedded HVDC systems – frequency settings in case of system split | [29 empty] | 19/03/18 - 20/04/18 | bar: 2018 J to 2018 A
Prepare Implementation Guidance Documents on HVDC systems default parameters | [29 empty] | 19/03/18 - 20/04/19 | bar: 2018 J to 2018 A
Prepare Implementation Guidance Documents on Interaction between HVDC controllers and other connections | [29 empty] | 19/03/18 - 20/04/20 | bar: 2018 J to 2018 A
Report on inter-TSO coordination activities
Collect and treat needs for CNC amendments | bar: 2018 M to 2019 D
Engage with standardisation bodies i.e. CENELEC for consistency between the Codes and Standards | bar: 2018 J to 2019 D
Engage with stakeholders/ACER/EC though Expert Groups and European Stakeholder Committee (tentative dates) | bar: 2018 J to 2019 D
Monitoring of implementation (regulation compliance) | bar: 2018 J to 2019 D
Report/Data to ACER on implmentation on RfG and HVDC | bar: 2019 M to 2019 J
[10 empty] | ENTSO-E Drafting Proposal | [12 empty] | NRAs Approval preparation
[10 empty] | Consultation | [12 empty] | NRAs Approval publication
[8 empty] | w |  | Workshop | [12 empty] | ACER Decision preparation
[10 empty] | ENTSO-E Proposal submission | [12 empty] | ACER Decision publication
[10 empty] | CCRs Drafting Proposals | [10 empty] | W |  | NRAs Workshop
NEMOs Drafting proposal

## CACM
CACM All/relevant TSOs and ENTSO-E tasks | 2017 |  |  |  | 2018 | [11 empty] | 2019 | [11 empty] | Consultation period | Workshop
| S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Congestion income distribution methodology | bar: 2017 S to 2017 D
Proposal for intraday cross-zonal gate opening and gate closure times | bar: 2017 N to 2018 A
Intraday capacity pricing methodology | bar: 2018 M to 2018 A
Scheduled exchanges calculation methodologies | bar: 2017 S to 2017 D
Capacity calculation methodology | bar: 2017 S; 2017 N; 2018 J to 2018 F; 2018 A to 2018 M
Nordic | bar: 2018 A to 2018 M
Baltic | bar: 2017 S; 2018 A to 2018 M
Hansa | bar: 2018 A to 2018 M
Core | bar: 2018 A to 2018 M
Italy North | [28 empty] | tbc | bar: 2018 J to 2018 F
Greece Italy (GRIT) | bar: 2018 A to 2018 M
South West Europe (SWE) | bar: 2018 A to 2018 M
Ireland and United Kingdom (IU) | bar: 2018 A to 2018 M
Channel | bar: 2018 A to 2018 M
South East Europe (SEE) | bar: 2017 N; 2018 J to 2018 J
Coordinated redispatching and countertrading methodologies | bar: 2017 S to 2018 M
Nordic | bar: 2018 J; 2018 M
Baltic | bar: 2018 J; 2018 M
Hansa | bar: 2017 D to 2018 J; 2018 M
Core | [28 empty] | 06/02- 06/03/2018 | bar: 2018 F; 2018 A
Italy North
Greece Italy (GRIT) | [28 empty] | 08/02- 15/03/2018 | bar: 2018 F; 2018 A
South West Europe (SWE) | bar: 2018 J; 2018 M
Ireland and United Kingdom (IU) | bar: 2018 J to 2018 F; 2018 A
Channel | bar: 2017 D to 2018 J; 2018 M
South East Europe (SEE) | [28 empty] | 02/02-04/03/2018 | bar: 2018 F; 2018 A
Redispatching or countertrading cost sharing methodologies | bar: 2017 S to 2018 M
Technical report on current bidding zone configuration | bar: 2017 S to 2018 J
Algorithm proposals (including DA and ID algorithm requirements) | bar: 2017 S to 2017 O
[8 empty] | ENTSO-E Drafting Proposal | [12 empty] | NRAs Approval preparation
[8 empty] | Consultation | [12 empty] | NRAs Approval publication
[6 empty] | w |  | Workshop | [12 empty] | ACER Decision preparation
[8 empty] | ENTSO-E Proposal submission | [12 empty] | ACER Decision publication
CCRs Drafting Proposals
NEMOs Drafting proposal

## FCA
FCA All/relevant TSOs and ENTSO-E tasks | 2017 |  |  |  | 2018 | [11 empty] | 2019 | [11 empty] | Consultation period | Workshop
| S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Harmonised allocation rules for long-term transmission rights | bar: 2017 S to 2017 O
Requirements for the single allocation platform
Methodology for sharing costs for establishment and development of the signle allocation platform
Congestion income distribution methodology | bar: 2018 J to 2018 J
Methodology for sharing costs to ensure firmness and remuneration | bar: 2018 J to 2018 J
Capacity calculation methodology (assuming CACM CCMs are approved in July 2017) | bar: 2018 F; 2018 J; 2018 N
Nordic | [28 empty] | tbc | bar: 2018 J; 2018 N
Baltic | bar: 2018 N
Hansa | bar: 2018 N
Core | [28 empty] | tbc | bar: 2018 J; 2018 N
Italy North | bar: 2018 N
Greece Italy (GRIT) | bar: 2018 N
South West Europe (SWE) | bar: 2018 N
Ireland and United Kingdom (IU) | bar: 2018 N
Channel | bar: 2018 N
South East Europe (SEE) | bar: 2018 N
Methodology for splitting cross-zonal capacity | bar: 2018 J; 2018 N
Nordic | [28 empty] | tbc | bar: 2018 J; 2018 N
Baltic | bar: 2018 N
Hansa | bar: 2018 N
Core | [28 empty] | tbc | bar: 2018 J; 2018 N
Italy North | [28 empty] | tbc | bar: 2018 J; 2018 N
Greece Italy (GRIT) | [28 empty] | tbc | bar: 2018 J; 2018 N
South West Europe (SWE) | bar: 2018 N
Ireland and United Kingdom (IU) | bar: 2018 N
Channel | bar: 2018 N
South East Europe (SEE) | bar: 2018 N
[8 empty] | ENTSO-E Drafting Proposal | [12 empty] | NRAs Approval preparation
[8 empty] | Consultation | [12 empty] | NRAs Approval publication
[6 empty] | w |  | Workshop | [12 empty] | ACER Decision preparation
[8 empty] | ENTSO-E Proposal submission | [12 empty] | ACER Decision publication
[8 empty] | CCRs Drafting Proposals | [10 empty] | W |  | NRAs Workshop
NEMOs Drafting proposal

## GLEB
GLEB All/relevant TSOs and ENTSO-E tasks | 2017 |  |  |  | 2018 | [11 empty] | 2019 | [11 empty] | Consultation period | Workshop
| S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
ENTSO-E to update manual of procedures of Transparency Regulation | bar: 2017 S to 2018 J; 2018 M
Proposal for activation purposes | [28 empty] | Expected: Sept. - Oct. | bar: 2018 M; 2018 M to 2018 D
Each TSO to propose T&Cs for BSPs and BRPs | bar: 2017 S to 2018 J; 2018 M to 2018 J
Proposal for pricing method for all products | [28 empty] | Expected: Sept. - Oct. | bar: 2018 M; 2018 M to 2018 D
Proposal for TSO-TSO settlement of intended exchanges of energy | [28 empty] | Expected: Sept. - Oct. | bar: 2018 M; 2018 M to 2018 D
Proposal for TSO-TSO settlement of settlement of ramps and FCR and unintended exchanges within and between SA | bar: 2018 M to 2019 J
Proposal for harmonisation of certain features of imbalance calculation & pricing | [28 empty] | Expected: Sept. - Oct. | 2018-03-23 | bar: 2017 S to 2018 J; 2018 M; 2018 M to 2018 D
CZC Allocation - Proposal for list of Standard Balancing Capacity Products | bar: 2017 S to 2018 J; 2018 M; 2018 M to 2019 D
CZC Allocation - Methodology for calculating CZC for balancing
CZC Allocation - Harmonise allocation of CZC within CCR
CZC Allocation - Methodology for cooptimised CZC allocation | bar: 2017 S to 2018 J; 2018 M; 2018 M to 2019 D
CZC Allocation - Methodology for market based CZC allocation | bar: 2017 S to 2018 J; 2018 M; 2018 M to 2019 D
ENTSO-E monitoring plan | bar: 2017 S to 2018 J; 2018 M; 2018 M to 2018 J
Proposal for implementation framework for European platform for replacement reserves | [28 empty] | 21/02/18 - 04/04/18 | 19/03/2018; | bar: 2017 S to 2018 J; 2018 M; 2018 M to 2018 J
Proposal for implementation framework for European platform for frequency restoration reserves with manual activation | [28 empty] | Expected: May-June 2018, pot. June-July 2018 | 27/03/2018; 20/06/2018 | bar: 2017 S to 2018 J; 2018 M; 2018 M to 2018 D
Proposal for implementation framework for European platform for frequency restoration reserves with automatic activation | [28 empty] | Expected: May-June 2018; pot. June-July 2018 | 26/03/2018; 20/06/2018 | bar: 2017 S to 2018 J; 2018 M; 2018 M to 2018 D
Proposal for implementation framework for European platform for imbalance netting | [28 empty] | 15/01/2018 - 15/03/2018 | bar: 2017 S to 2018 M; 2018 M to 2018 J
[8 empty] | ENTSO-E Drafting Proposal | [11 empty] | NRAs Approval preparation
[8 empty] | Consultation | [11 empty] | NRAs Approval publication
[6 empty] | w |  | Workshop
ENTSO-E Proposal submission

## SOGL
SO GL All/relevant TSOs and ENTSO-E tasks | 2017 |  |  |  | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | Consultation period | Workshop
| S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Pan-European activities
Key organisational requirements, roles and responsibilities in relation to data exchange (Art. 40.6) | bar: 2017 S to 2018 M
Methodology for building the year-ahead, day-ahead and intraday common grid models from the individual models and for saving them (Art. 67.1) | bar: 2017 S to 2018 M
Methodology for coordinating operational security analysis (Art. 75.1) | [40 empty] | 26/02/2018-06/04/2018 | 2018-03-21 | bar: 2017 S to 2018 S
Regional activities on synchronous area level
OPTIONAL Methodology for the definition of minimum inertia required to maintain operational security and prevent violation of stability limits (Art. 39b) | bar: 2019 O to 2020 M
Methodology for assessing the relevance of assets for outage coordination (Art. 84.1) | [40 empty] | 26/02/2018-06/04/2018 | 2018-03-21 | bar: 2017 S to 2018 S
Methodologies, conditions and values included in operational agreements (Art. 118.1) | [40 empty] | 03/04/2018-03/05/2018 | 2018-04-19 | bar: 2017 S to 2018 S
Determination of LFC blocks (Art. 141.2) | bar: 2017 S to 2018 J
Assumptions and methodology for a CBA to be conducted to assess the minimum activation time of FCR - in CE and Nordic synchronous areas (Art. 156.11) | bar: 2017 S to 2018 M
Cost-benefit analysis suggesting the minimum FCR activation period (156.11) | bar: 2018 O to 2019 S
Regional activities on CCR level
Common provisions for regional operational security coordination (Art. 76.1) | bar: 2019 M to 2019 J
[8 empty] | ENTSO-E Drafting Proposal / Activity | [14 empty] | NRAs Approval preparation
[8 empty] | Consultation | [14 empty] | NRAs Approval publication
[6 empty] | w |  | Workshop
ENTSO-E Proposal submission / Deadline

## CNCs
CNCs (RfG, DCC, HVDC) All/relevant TSOs and ENTSO-E tasks | 2017 |  |  |  | 2018 | [11 empty] | 2019 | [11 empty] | Consultation period | Workshop
| S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
RfG NC - Cordinate and monitor implementation activities in each country / use of Active Library (transposition) | bar: 2017 S to 2018 M
DCC and HVDC NC - Cordinate and monitor implementation activities in each country / use of Active Library (transposition) | bar: 2017 S to 2018 S
Prepare Implementation Guidance Documents on frequency related parameters | [28 empty] | 20/11/17 - 21/12/17 | bar: 2017 S to 2018 J
Prepare Implementation Guidance Documents on Cost Benefit Analysis (CBA) | [28 empty] | 26/01/18 - 27/02/18 | bar: 2017 S to 2018 M
Prepare Implementation Guidance Documents on Embedded HVDC systems – frequency settings in case of system split | [28 empty] | 19/03/18 - 20/04/18 | bar: 2017 S to 2018 A
Prepare Implementation Guidance Documents on HVDC systems default parameters | [28 empty] | 19/03/18 - 20/04/19 | bar: 2017 S to 2018 A
Prepare Implementation Guidance Documents on Interaction between HVDC controllers and other connections | [28 empty] | 19/03/18 - 20/04/20 | bar: 2017 S to 2018 A
Report on inter-TSO coordination activities | bar: 2017 S to 2017 D
Collect and treat needs for CNC amendments | bar: 2018 M to 2019 D
Engage with standardisation bodies i.e. CENELEC for consistency between the Codes and Standards
Engage with stakeholders/ACER/EC though Expert Groups and European Stakeholder Committee (tentative dates) | bar: 2017 S to 2019 D
Monitoring of implementation (regulation compliance) | bar: 2018 J to 2019 D
Report/Data to ACER on implmentation on RfG and HVDC | bar: 2019 M to 2019 J
[8 empty] | ENTSO-E Drafting Proposal / Activity | [14 empty] | NRAs Approval preparation
[8 empty] | Consultation | [14 empty] | NRAs Approval publication
[6 empty] | w |  | Workshop
ENTSO-E Proposal submission / Deadline