## Implementation Plan
| Year | Article | Project Team (accountable PT) | Topic | Duration | Start | Finish | Links | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Month | [7 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Entry Into Force - assumed to be Sept 2017 | bar: 2017 Sep
Balancing Stakeholder Group Meetings (7th of every third month) | bar: 2017 Mar; 2017 Jun; 2017 Sep; 2017 Dec; 2018 Mar; 2018 Jun; 2018 Sep; 2018 Dec; 2019 Mar; 2019 Jun; 2019 Sep; 2019 Dec; 2020 Mar; 2020 Jun; 2020 Sep; 2020 Dec; 2021 Mar; 2021 Jun; 2021 Sep; 2021 Dec; 2022 Mar; 2022 Jun; 2022 Sep; 2022 Dec; 2023 Mar; 2023 Jun; 2023 Sep; 2023 Dec; 2024 Mar; 2024 Jun; 2024 Sep; 2024 Dec
General EB GL Obligations
EIF + 4m | ENTSO-E to update manual procedures of Transparency Regulation | A.12.5 | Reporting PT | bar: 2017 Mar to 2017 Jun; 2017 Sep to 2018 Mar
EIF + 2yrs | Publication of information | A.12.5 | Reporting PT | bar: 2018 Apr to 2019 Sep
EIF + 6m | Each TSO to propose T&Cs for BSPs and BRPs | A.18.1 | Each TSO | bar: 2017 May to 2017 Aug; 2017 Nov to 2018 Sep
EIF + 2yrs | Each CDS TSO to define ISP GCT | A.24.5 | Each TSO | bar: 2018 Nov to 2019 Feb; 2019 May to 2020 Mar
2yrs | Possible Derogation for definition of ISP GCT | A.62.2.b | Each TSO | bar: 2019 Oct to 2021 Sep
EIF + 1yr | Proposal for Activation Purposes | A.29.3 | Process PTs (mFRR) | bar: 2017 Nov to 2018 Feb; 2018 May to 2019 Mar
Pricing & Settlement
EIF + 1yr | Proposal for pricing method for all products | A.30.1 | Process PTs (aFRR) | bar: 2017 Nov to 2018 Feb; 2018 May to 2019 Mar
EIF + 1yr | Proposal for TSO-TSO settlement of intended exchanges of energy | A.50.1 | Process PTs (aFRR) | bar: 2017 Nov to 2018 Feb; 2018 May to 2019 Mar
EIF + 18m | Proposal for TSO-TSO settlement of ramps and FCR within SA | A.50.3 | FSUE PT | bar: 2018 May to 2018 Aug; 2018 Nov to 2019 Sep
EIF + 18m | Proposal of TSO-TSO settlement of ramps and FCR between SA | A.50.4 | FSUE PT | bar: 2018 May to 2018 Aug; 2018 Nov to 2019 Sep
EIF + 18m | Proposal for TSO-TSO settlement of unintended exchanges within SA | A.51.1 | FSUE PT | bar: 2018 May to 2018 Aug; 2018 Nov to 2019 Sep
EIF + 18m | Proposal for TSO-TSO settlement of unintended exchanges between SA | A.51.2 | FSUE PT | bar: 2018 May to 2018 Aug; 2018 Nov to 2019 Sep
1yr Transition Period | Implementation of minimum requirements for Imbalance Settlement | Various | Each TSO | bar: 2017 Oct to 2018 Sep
2yrs | Possible derogation for minimum requirements for Imbalance Settlement | A.62.2.e | Each TSO | bar: 2018 Oct to 2020 Sep
EIF + 1yr | Proposal for harmonisation of main features of imbalance calculation & pricing | A.52.2 | Imb Set PT | bar: 2017 Nov to 2018 Feb; 2018 May to 2019 Mar
NRA Approval + 18m | Harmonisation of main features of imbalance calculation & pricing | A.52.4 | Imb Set PT | bar: 2019 Apr to 2020 Sep
EIF + 3yrs | Harmonisation of Imbalance Settlement Period | A.53.1 | Each TSO | bar: 2017 Jan to 2020 Sep
4yrs | Possible Derrogation for Harmonisation of ISP | A.62.2.c | Each TSO | bar: 2020 Oct to 2024 Sep
Balancing Capacity & CZC Allocation
EIF + 2yrs | Proposal for list of Standard Balancing Capacity Products | A.25.2 | Process PTs (CZC PT) | bar: 2018 Nov to 2019 Feb; 2019 May to 2020 Mar
EIF + 5yrs | Methodology for calculating CZC for balancing | A.37.3 | CZC PT | bar: 2021 Nov to 2023 Mar
EIF + 5yrs | Harmonise allocation of CZC within CCR | A.38.2 | CZC PT | bar: 2021 Nov to 2023 Mar
EIF + 2yrs | Methodology for cooptimised CZC allocation | A.40.1 | CZC PT | bar: 2018 Nov to 2019 Feb; 2019 May to 2020 Mar
EIF + 2yrs | Methodology for market based CZC allocation | A.41.1 | CZC PT | bar: 2018 Nov to 2019 Feb; 2019 May to 2020 Mar
Reporting & Monitoring
EIF + 2yrs | European report on integration of balancing markets (Detailed) | A.59.2.a | Reporting PT | bar: 2018 Nov to 2020 Mar
EIF + 3yrs | European report on integration of balancing markets (High Level) | A.59.2.b | Reporting PT | bar: 2019 Nov to 2020 Feb; 2020 May to 2021 Mar
EIF + 6m | ENTSO-E monitoring plan | A.63.2 | Reporting PT | bar: 2017 May to 2017 Aug; 2017 Nov to 2018 Sep
EIF + 1yr | ENTSO-E & ACER to draw up list of relvant info to be communicated | A.63.3 | Reporting PT | bar: 2017 Oct to 2018 Sep
Replacement Reserves
EIF + 6m | Proposal for implementation framework for Platform | A.19.1 | RR PT | bar: 2017 May to 2017 Aug; 2017 Nov to 2018 Sep
EIF + 6m | Proposal for list of RR Standard Balancing Energy Products | A.25.1 | RR PT | bar: 2017 May to 2017 Aug; 2017 Nov to 2018 Sep
EIF + 18m | Appointment of entity | A.19.4 | RR PT | bar: 2018 May to 2019 Mar
6m | Procurement of IT Provider (TERRE) | - | RR PT | bar: 2017 Jan to 2017 Jun
6m | Detailed Design (TERRE) | - | RR PT | bar: 2017 Jul to 2017 Dec
1yr | Development & Implmentation (TERRE) | - | RR PT | bar: 2018 Jan to 2018 Dec
3m | Testing (TERRE) | - | RR PT | bar: 2019 Jan to 2019 Mar
3m | Go-Live (TERRE) | - | RR PT | bar: 2019 Apr to 2019 Jun
EIF +2yrs | Implementation of Platform | A.19.5 | RR PT | bar: 2019 Sep
2yrs | National Implementation Ready for Testing | - | Each TSO | bar: 2017 Jan to 2018 Dec
2yrs | Possible Derrogation for TSO joining | A.62.2.a | Each TSO | bar: 2019 Oct to 2021 Oct
manual Frequency Restoration Reserves
EIF + 1yr | Proposal for implementation framework for Platform | A.20.1 | mFRR PT | bar: 2017 Nov to 2018 Feb; 2018 May to 2019 Mar
EIF + 1yr | Proposal for list of mFRR Standard Balancing Energy Products | A.25.1 | mFRR PT | bar: 2017 Nov to 2018 Feb; 2018 May to 2019 Mar
EIF + 2yrs | Appointment of entity | A.20.4 | mFRR PT | bar: 2018 Nov to 2020 Mar
EIF + 3yrs | Proposal for modifications to European Platform | A.20.5 | mFRR PT / CBA PT | bar: 2019 Nov to 2020 Feb; 2020 May to 2020 Sep
6m | Procurement of IT Provider | - | mFRR PT | bar: 2019 Apr to 2019 Sep
6m | Detailed Design | - | mFRR PT | bar: 2019 Oct to 2020 Mar
1yr | Development & Implmentation | - | mFRR PT | bar: 2020 Apr to 2021 Mar
3m | Testing | - | mFRR PT | bar: 2021 Apr to 2021 Jun
3m | Go-Live | - | mFRR PT | bar: 2021 Jul to 2021 Sep
EIF +4yrs | Implementation of Platform | A.20.6 | mFRR PT | bar: 2021 Sep
2yrs | National Implementation Ready for Testing | - | Each TSO | bar: 2019 Apr to 2021 Mar
2yrs | Possible Derrogation | A.62.2.a | Each TSO | bar: 2021 Oct to 2023 Sep
Imbalance Netting
EIF + 6m | Proposal for implementation framework for Platform | A.22.1 | IN PT | bar: 2017 May to 2017 Aug; 2017 Nov to 2018 Sep
EIF + 18m | Appointment of entity | A.22.4 | IN PT | bar: 2018 May to 2019 Mar
6m | Detailed Design (iGCC) | - | IN PT | bar: 2017 Jul to 2017 Dec
1yr | Development & Adaption (iGCC) | - | IN PT | bar: 2018 Jan to 2018 Dec
3m | Testing (iGCC) | - | IN PT | bar: 2019 Jan to 2019 Mar
3m | Go-Live (iGCC) | - | IN PT | bar: 2019 Apr to 2019 Jun
EIF +2yrs | Implementation of Platform | A.22.5 | IN PT | bar: 2019 Sep
2yrs | National Implementation Ready for Testing | - | Each TSO | bar: 2017 Jan to 2018 Dec
2yrs | Possible Derrogation for TSO joining | A.62.2.a | Each TSO | bar: 2019 Oct to 2021 Oct
automatic Frequency Restoration Reserves
EIF + 1yr | Proposal for implementation framework for Platform | A.21.1 | aFRR PT | bar: 2017 Nov to 2018 Feb; 2018 May to 2019 Mar
EIF + 1yr | Proposal for list of aFRR Standard Balancing Energy Products | A.25.1 | aFRR PT | bar: 2017 Nov to 2018 Feb; 2018 May to 2019 Mar
EIF + 2yrs | Appointment of entity | A.21.4 | aFRR PT | bar: 2018 Nov to 2020 Mar
EIF + 3yrs | Proposal for modifications to European Platform | A.21.5 | aFRR PT / CBA PT | bar: 2019 Nov to 2020 Feb; 2020 May to 2020 Sep
6m | Procurement of IT Provider | - | aFRR PT | bar: 2019 Apr to 2019 Sep
6m | Detailed Design | - | aFRR PT | bar: 2019 Oct to 2020 Mar
1yr | Development & Implmentation | - | aFRR PT | bar: 2020 Apr to 2021 Mar
3m | Testing | - | aFRR PT | bar: 2021 Apr to 2021 Jun
3m | Go-Live | - | aFRR PT | bar: 2021 Jul to 2021 Sep
EIF +4yrs | Implementation of Platform | A.21.6 | aFRR PT | bar: 2021 Sep
2yrs | National Implementation Ready for Testing | - | Each TSO | bar: 2019 Apr to 2021 Mar
2yrs | Possible Derrogation | A.62.2.a | Each TSO | bar: 2021 Oct to 2023 Sep

## Key
TSO process for developing methodology
Public Consultation
TSO deadline for submitting proposal
NRA Approval process
NRA Approval
Implementation
Implementation Deadline
Derrogation

## Questions
Have we got all the obligations captured?
Does the consultation process need to take place before or after the deadline?
What tasks should be considered prior to deadline of methodology/proposal and how long?
| Design/drafting |  | 2 Months | 10 month process in total
| ENTSO-E Approval |  | 2 Months
| Consultation |  | 2 Months
| Modification/re-work |  | 2 Months
| ENTSO-E Final Approval |  | 2 Months
What else should be considered as part of the implementation of processes?
| High level design | Is part of the implementation framework?
| Consultation | Is this part of the implementation framework?
| Procurement of IT provider |  | 6 months
| Detailed design |  | 6 months
| Development & Implementation |  | 1 year
| testing |  | 3 months
| go live |  | 3 months
What about interactions between the EU and National implementation projects?
How long should we consider the NRA approval to be?
6 months