## TYNDP 2018 Projects
Project Id | Promotor | Project Name | Description | Investment ID | Name | From | To | Elements Type | Technology Type | Voltage Level | Expected Commissioning Year | Status | Tso In Charge From | Tso In Charge To | country 1 | country 2 | country 3
1 | REN | RES in north of Portugal | The main objective of this project consists in introducing the network reinforcements that are needed to allow the connection of new RES generation (hydro with pumping and also wind) that is foreseen in the north of Portugal, where the RES potential is high. The project includes a set of new 400 kV OHL that will form a new axis between V. Minho-R. Pena-Fridão-Feira. A new 400 kV OHL Pedralva-Sobrado (PCI 2.16.1) is also included in this cluster, in order to ensure the maintenance of the NTC values between PT and ES that were available prior to the connection of these new power plants. | 2 | Pedralva-Sobrado | Pedralva (PT) | Sobrado (PT) | Overhead Line | AC | 400 | 2022-2023 | Planned But Not Yet Permitting | REN | REN | Portugal
|  |  |  | 4 | V.Minho -R.Pena-Fridão-Feira | V.Minho (by Ribeira de Pena and Fridão) | Feira (by Ribeira de Pena and Fridão) | Overhead Line | AC | 400 | 2022-2024 | In Permitting | REN | REN | Portugal
|  |  |  | 474 | Substation Ribeira de Pena | Ribeira de Pena (PT) | - | Substation | AC | 400 | 2022-2024 | In Permitting | REN | - | Portugal
|  |  |  | 941 | Switching station Fridão | Fridão | - | Substation | AC | 400 | 2026-2030 | In Permitting | REN | - | Portugal
4 | REE;REN | Interconnection Portugal-Spain | In order to reach a complete operational Iberian Electricity Market (MIBEL), and strengthening the Internal Energy Market (IEM), the increase of the interconnection between Spain and Portugal is needed. A new OHL 400kV interconnection between Fontefría (Spain) and Ponte de Lima (Portugal). Internal reinforcements complement the cross border section, such as the axis in Spain between Fontefría and Beariz and in Portugal between Ponte de Lima (previously Viana do Castelo) and Vila Nova de Famalicão (previously Vila doConde).This project was included in the 2013, 2015 and 2017 PCI list (PCI 2.17). | 18 | Beariz (ES) - Fontefria (ES) | Beariz (ES) | Fontefria (ES) | Overhead Line | AC | 400 | 1/ 1/ 2021 | In Permitting | REE | REE | Portugal | Spain
|  |  |  | 496 | Fontefria (ES) - Vila Nova de FamalicÆo (PT) | Fontefria (ES) | Vila Nova de FamalicÆo (PT) (By Ponte de Lima) | Overhead Line | AC | 400 | 1/ 1/ 2021 | In Permitting | REE | REN | Portugal | Spain
|  |  |  | 498 | SE Fontefria 400/220kV | Fontefria (ES) | REE | Substation | AC | 400 | 1/ 1/ 2021 | In Permitting | REE | REE | Portugal | Spain
|  |  |  | 499 | Beariz 400kV (ES) | Beariz (ES) | Beariz (ES) | Substation | AC | 400 | 1/ 1/ 2021 | In Permitting | REE | REE | Portugal | Spain
|  |  |  | 500 | Ponte de Lima (PT) | Ponte de Lima (PT) | Ponte de Lima (PT) | Substation | AC | 400 | 2020-2021 | In Permitting | REN | REN | Portugal | Spain
13 | REE | Baza project | This Project includes a new double circuit Caparacena-Baza-La Ribina 400 kV OHL, in Spain with two new 400 kV substations in Baza and La Ribina. This project allows to solve today restrictions and integrate new RES generation in an area without transmission network. | 31 | Axis Caparacena-Baza-La Ribina | Caparacena (ES) | La Ribina (ES) | Overhead Line | AC | 400 | 2025 | Under Consideration | REE | REE | Spain
|  |  |  | 569 | New substation Baza | Baza (ES) | Baza (ES) | Substation | AC | 400 | 2025 | Under Consideration | REE | REE | Spain
|  |  |  | 570 | New substation La Ribina | La Ribina (ES) | La Ribina (ES) | Substation | AC | 400 | 2025 | Under Consideration | REE | REE | Spain
16 | REE;RTE | Biscay Gulf | The project consist of 370 km HVDC-VSC link (2 bipoles of 1000 MW each) mainly subsea in the Biscay Gulf, between Gatica (Basque Counrty, ES) and Cubnezais (Aquitaine, FR). Included in the Madrid Declaration, this project aims at improving the interconnection ES-FR. This project was included in the 2013,2015 and 2017 PCi list (PCI 2.7) | 38 | HVDC Gatica-Cubnezais | Gatica (ES) | Cubnezais (FR) | Subsea Cable | DC | 320 | 01/ 01/ 2025 | In Permitting | REE | RTE | Spain | France
21 | RTE;TERNA | Italy-France | "The Project comprises a new 320 kV HVDC interconnection between France and Italy. The new HVDC link will connect the substations of Piossasco and Grand Ile mainly along motor way infrastructures and the Fréjus tunnel." | 55 | Savoie - Pièmont | Grande Ile (FR) | Piossasco (IT) | Underground Cable | DC | 320 | 2019 | Under Construction | RTE | TERNA | France | Italy
23 | ELIA; RTE | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | The project consists in the reconductoring of the existing 80km double-circuit 400kV AC cross-border line between Lille (Avelin/Mastaing, FR) - Avelgem (BE) and onwards to Zomergem (Horta, BE) with High Temperature Low Sag conductors to double its capacity. | 60 | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | Avelin/Mastaing (FR) | Horta (BE) | Overhead Line | AC | 400 | 1/1/2022 | In Permitting | RTE | ELIA | France | Belgium
25 | NGIHL,RTE | IFA2 | IFA2 is a new HVDC VSC subsea interconnector that will develop between Tourbe in France (area of Caen) and Chilling in Great Britain (area of Southampton). | 62 | IFA2 | Tourbe (FR) | Chilling (GB) | Subsea Cable | DC | 320 | 1/ 1/ 2020 | Under Construction | RTE | NGIHL | France | Great Britain
26 | APG; TERNA | Reschenpass Interconnector Project | New 220kV interconnector between the substations Nauders (AT) and Glorenza (IT) | 614 | Reschenpass Interconnector | Nauders (AT) | Glorenza (IT) | Underground Cable | AC | 220 | 2021 | In Permitting | APG | Terna | Austria | Italy
28 | CGES;TERNA | Italy-Montenegro | " The Italy-Montenegro interconnection project includes a new HVDC subsea cable between Villanova (Italy) and Lastva (Montenegro) and the DC converter stations. The HVDC link between Italy and Balkansis correlated with the Transbalkan Corridor (projects 146 and 227) and the Mid Continental East Corridor (project 144)." | 70 | First HVDC Module IT-ME | Villanova (IT) | Lastva (ME) | Subsea Cable | DC | 500 | 2019 | Under Construction | TERNA | CGES | Italy | Montenegro
|  |  |  | 624 | SS 400/110 kV Lastva | Lastva (ME) | N/A | Substation | AC | 400 | 31/12/ 2018 | Under Construction | CGES | N/A | Italy | Montenegro
|  |  |  | 1503 | Second HVDC Module IT-ME | Villanova (IT) | Lastva (ME) | Subsea Cable | DC | 500 | 2026 | Under Construction | Terna | CGES | Italy | Montenegro
29 | TERNA; STEG | Italy-Tunisia | "The project consists in a new interconnection between Tunisia and Sicily to be realized through an HVDC submarine cable. The realization of the project is supported by the Italian and Tunisian Governments to increase the interconnection capacity of the Euro-Mediterranean system. Moreover, the project will contribute to reduce, under specific conditions, present and future limitations to the power exchanges on the northern Italian border, with France, Switzerland, Austria and Slovenia, and therefore it will allow to significantly increase the transmission capacity and its exploitation by at least 500 MW on that boundary." | 635 | Elmed Project | Sicily Area (IT) | Tunisia node | Subsea Cable | DC | 400 | 2025 | In Permitting | TERNA | STEG | Italy | Tunisia
31 | SWISSGRID;TERNA | Italy-Switzerland | " The project consists of a new 400 kV line San Giacomo-Pallanzeno, conversion from AC to DC of the 220 kV line between Pallanzeno and Milan area, including the realization of the 2 AC/DC converter stations and 220 kV to 400 KV substation upgrade. Additional internal lines in Italy and in Switzerland are required to get the full advantage from the interconnection capacity provided by the cross-border line" | 642 | San Giacomo Project | All'Acqua (CH) | Pallanzeno(IT)-Baggio(IT) | Overhead Line | AC | 380 | 2025 | In Permitting | SWISSGRID | TERNA | Switzerland | Italy
33 | TERNA | Central Northern Italy | "The project consists in the strengthening of interconnection between the northern and the central part of Italy. It will involve the upgrading of existing 220 kV over-head line to 400 kV between Colunga and Calenzano substations as well as the removing of limitations on the existing 220 kV network in Central Italy" | 90 | 90 | Calenzano (IT) | Colunga (IT) | Overhead Line | AC | 400 | 2022 | In Permitting | TERNA | TERNA | Italy
|  |  |  | 1041 | Rem. lim. in Central Italy | Villanova (IT) | S. Barbara (IT) | Overhead Line | AC | 220 | 2022 | Planned But Not Yet Permitting | TERNA | TERNA | Italy
35 | CEPS | CZ Southwest-east corridor | "A corridor of internal 400 kV overhead lines inside the Czech Republic connecting existing 420 kV substations between Prestice, Kocin, Mirovka and Cebin in the southwest-east direction. The project consists of buidling a new AC 400 kV overhead line which connects 420 kV substations Kocin and Mirovka with double circuit line of about 120.5 km lenght and a capacity of 2x1730 MVA, building of a 400 kV overhead lines that involves changing of a 400 kV existing single-ciruit line to double-circuit line with a capacity of 2x1730 MVA between Kocin-Prestice. The upgrading of the existing 420 kV substation Kocin is also a part of the project" | 311 | R Kocin | Kocin (CZ) | N/A | Substation | AC | 400 | 1/ 1/ 2024 | Under Construction | CEPS | CEPS | Czech Republic
|  |  |  | 313 | Kocin-Mirovka | Kocin (CZ) | Mirovka (CZ) | Overhead Line | AC | 400 | 1/ 1/ 2024 | In Permitting | CEPS | CEPS | Czech Republic
|  |  |  | 315 | Kocin-Prestice | Kocin (CZ) | Prestice (CZ) | Overhead Line | AC | 400 | 1/ 1/ 2028 | In Permitting | CEPS | CEPS | Czech Republic
36 | 50Hertz Transmission, Energinet.dk | Kriegers Flak CGS | The Combined Grid Solution (CGS) is new a AC offshore connection between Denmark and Germany with back to back stations placed in Germany. The project is a combined grid connection of the offshore wind farms Kriegers Flak, Baltic 1, 2 and an interconnection between both countries. | 141 | Kriegers Flak CGS, TYNDP ID: 36.141 | Ishøj / Bjæverskov (DK) | Bentwisch (DE) | Subsea Cable | AC | 150 | 31/12/2018 | Under Construction | Energinet.dk | 50Hertz Transmission GmbH | Denmark | Germany
37 | STATNETT;TENNET-DE | "Norway - Germany, NordLink" | NordLink: a new HVDC connection between Southern Norway and Northern Germany. Estimated subsea cable length: 514km. Capacity: 1400 MW. | 142 | Norway - Germany HVDC | Tonstad (NO) | Wilster (DE) | Subsea Cable | DC | 500 | 01/ 01/ 2020 | Under Construction | Statnett | TenneT-DE | Norway | Germany
|  |  |  | 406 | Western corridor | (Southern part of Norway) (NO) | (Southern part of Norway)(NO) | Overhead Line | AC | 400 | 2020 | Under Construction | Statnett | Statnett | Norway | Germany
39 | Energinet.dk; TENNET-DE | "DKW-DE, step 3" | New double circuit 380kV line from Kassoe (DK) to Audorf (DE). As third phase of the Danish-German agreement to upgrade cross border transfere capacity. The project is labelled by the EC as project of common interes (PCI 1.4.1) | 144 | Audorf - Kassoe | Audorf (DE) | Kassoe (DK) | Overhead Line | AC | 380 | 31/ 12/ 2020 | Under Construction | TenneT-DE | Energinet.dk | Denmark | Germany
40 | CREOS; ELIA; AMPRION | Belgium-Luxemburg-Germany: long-term perspective | An increase of transfer capacity across the BE-LU-DE corridor is envisioned towards the 2030-2040 time horizon. Further studies will determine the appropriate implementation option and timing, taking into account - the recent evolutions with installation of PST in Schifflange and creation of the LuxRing as reported in previous TYNDPs - the expected evolution on the LU-DE border as presented in project 328 | 650 | BE-LUX-DE Long-Term perspective | Aubange (TBC) | LUX-DE (TBC) | Underground Cable | AC | 0 | 2035 | Under Consideration | ELIA | CREOS; AMPRION | Belgium | Germany | Luxembourg
47 | AMPRION; APG | Westtirol - Vöhringen | Westtirol (AT) - Zell/Ziller (AT) Westtirol (AT) - Vöhringen (DE) | 219 | 219: Westtirol - Zell/Ziller (AT internal) | Westtirol (AT) | Zell-Ziller (AT) | Overhead Line | AC | 380 | 2024 | Planned But Not Yet Permitting | APG | APG | Germany | Austria
|  |  |  | 689 | 689: Vöhringen (DE) - Westtirol (AT) | Vöhringen (DE) | Westtirol (AT) | Overhead Line | AC | 380 | 2024 | Planned But Not Yet Permitting | Amprion | APG | Germany | Austria
48 | MAVIR,SEPS | New SK-HU intercon. - phase 1 | This project will increase the transfer capacity between Slovak and Hungarian transmission systems, improve security and reliability of operation both transmission systems and support North - South RES power flows in CCE region. Main investments of this project are double circuit AC OHL 400 kV from new Gabcikovo (Slovakia) substation to Gonyu (Hungary) substation, with one circuit connected to the Velky Dur (Slovakia) substation and double circuit AC OHL (preliminary armed only with one circuit on Hungarian side) 400 kV from Rimavska Sobota (Slovakia) substation to Sajoivanka (Hungary) substation. | 696 | Hunew 1 | Sajóivánka (HU) | N/A | Compensation | AC | 400 | 2020 | In Permitting | MAVIR | N/A | Slovakia | Hungary
|  |  |  | 697 | Hunew 2 | Sajóivánka (HU) | N/A | Substation | AC | 400 | 2020 | In Permitting | MAVIR | N/A | Slovakia | Hungary
|  |  |  | 1500 | 1. SK-HU interconnection | Gabcikovo (SK) | Gonyu (HU) | Overhead Line | AC | 400 | 2020 | In Permitting | SEPS | MAVIR | Slovakia | Hungary
|  |  |  | 1501 | 2. SK-HU interconnection | Rimavska Sobota (SK) | Sajoivanka (HU) | Overhead Line | AC | 400 | 2020 | In Permitting | SEPS | MAVIR | Slovakia | Hungary
62 | AST; ELERING | Estonia-Latvia 3rd IC | Project nr 62 is a planned third 330 kV interconnection between Estonia and Latvia. The project consists of 3 investments of which nr 386 is the main inter-area investment, AC 330 kV OHL between Kilingi-Nõmme substation in Estonia and Riga CHP2 substations | 386 | 3rd EE-LV interconnection | Kilingi-Nomme (EE) | Riga CHP2 (LV) | Overhead Line | AC | 330 | 2020 | Under Construction | Elering | AST | Estonia | Latvia
|  |  |  | 735 | Harku-Sindi 330kV OHL | Harku (EE) | Sindi (EE) | Overhead Line | AC | 330 | 31/ 12/ 2020 | Under Construction | Elering | Elering | Estonia | Latvia
|  |  |  | 1062 | Riga CHP2 - Riga HPP | Riga CHP2 | Riga HPP | Overhead Line | AC | 330 | 1/ 1/ 2020 | In Permitting | AST | AST | Estonia | Latvia
71 | Energinet,TENNET-NL | COBRA cable | The project is an interconnection between Endrup (Denmark) and Eemshaven (The Netherlands). The project consists of a 320 kV DC subsea cable and related substations on both ends, 325 km apart, applying VSC DC technology. | 427 | COBRA Cable | Endrup (DK) | Eemshaven (NL) | Subsea Cable | DC | 400 | 2019 | Under Construction | Energinet | TENNET-NL | Denmark | Netherlands
74 | ELIA, NGIHL, NGET | Thames Estuary Cluster (NEMO-Link) | This project envisions the realization of NEMO-Link – the first interconnector between Great Britain and Belgium – as a 1 GW HVDC link of ~140km with technical commissioning by 2018 and operation in 2019, including a number of onshore UK reinforcements to facilitate this and other potential interconnector connections within the Thames Estuary region.The NEMO interconnector is promoted by NGIHL and Elia. The reinforcements to the internal GB network are the responsibility of NGET. | 443 | NEMO | Richborough (GB) | Gezelle (BE) | Subsea Cable | DC | 400 | 1/ 1/ 2019 | Under Construction | NGET | ELIA | Belgium | Great Britain
|  |  |  | 449 | Richborough - Canterbury | Richborough (GB) | Canterbury (GB) | Overhead Line | AC | 400 | 2018 | In Permitting | NGET | NGET | Great Britain | Great Britain
|  |  |  | 450 | SELL - DUNG Reconductoring | Sellindge (GB) | Dungeness (GB) | Overhead Line | AC | 400 | 30/ 11/ 2016 | Commisioned | NGET | NGET | Great Britain | Great Britain
75 | ELIA | Modular Offshore Grid (MOG) | The Modular Offshore Grid aims at centralizing the offshore wind of four offshore future wind farms in Belgium in an offshore hub and transporting it via three 220 kV AC cables to the new substation Stevin at Zeebrugge. Via the substation Stevin the MOG makes the connection to the STEVIN link (new 400kV axis between Zeebrugge & Zomergem). The MOG is expected to be fully operational by 2020. | 752 | Modular Offshore Grid | Offshore platform | Stevin (Zeebrugge) | Subsea Cable | AC | 220 | 2020 | Under Construction | ELIA | ELIA | Belgium
77 | NGET; SPT | Anglo-Scottish -1 | A new 2.4GW (short term rating) submarine HVDC cable route from Hunterston to Deeside with associated AC network reinforcement works at both ends. | 452 | Western HVDC Link | Hunterston (GB) | Deeside (GB) | Subsea Cable | DC | 500 | 2017 | Under Construction | SPT | NGET | United Kingdom
78 | NGET | South West Cluster | New 400kV substation at Hinkley Point. New 400kV transmission route from Hinkley Point to Seabank. Reconstruction of Bridgewater substation for 400kV operation. Uprate Bridgewater - Melksham to 400kV. | 458 | HINP-SEAB New Double Circuit | Hinkley Point (GB) | Seabank (GB) | Overhead Line | AC | 400 | 2024 | In Permitting | NGET | NGET | United Kingdom
81 | EIRGRID, SONI | North South Interconnector | A new 400 kV interconnector between Woodland in Ireland and Turleenan in Northern Ireland. | 462 | 462 | Woodland (IE) | Turleenan (NI) | Overhead Line | AC | 400 | 2020 | In Permitting | EirGrid | SONI | Ireland | Northern Ireland
82 | EIRGRID, SONI | RIDP I | The infrastructure development is required to facilitate connection of renewable generation in the North and West of the Island. It will further integrate the Ireland and Northern Ireland transmission systems and provide capacity for substantial demand growth. | 463 | Srananagh - South Donegal | Srananagh (IE) | New substation in South Donegal (IE) | Overhead Line | AC | 220 | 2029 | Planned But Not Yet Permitting | EirGrid | EirGrid | Ireland | Northern Ireland
|  |  |  | 896 | Omagh South to South Donegal | South Donegal (IE) | Omagh South (NI) | Overhead Line | AC | 275 | 2029 | Planned But Not Yet Permitting | EirGrid | SONI | Ireland | Northern Ireland
|  |  |  | 897 | Omagh South to Turleenan | Omagh South | Turleenan | Overhead Line | AC | 275 | 2029 | Planned But Not Yet Permitting | SONI | SONI | Ireland | Northern Ireland
85 | REN | Integration of RES in Alentejo | The main objective of this project consists in introducing the network reinforcements that are needed to allow the connection of new RES generation (mostly solar but also some wind) that is foreseen for the south region of Portugal, where the solar potential is considerably high. The project includes two new 400 kV OHL that will constitute a new axis between F. Alentejo-Ourique-Tavira substations. It is also included the expansion of the Ourique substation to include the 400 kV voltage level. | 779 | F.Alentejo-Ourique-Tavira | F. Alentejo (by Ourique) | Tavira (by Ourique) | Overhead Line | AC | 400 | 2024-2026 | Planned But Not Yet Permitting | REN | REN | Portugal
85 | REN | Integration of RES in Alentejo | The main objective of this project consists in introducing the network reinforcements that are needed to allow the connection of new RES generation (mostly solar but also some wind) that is foreseen for the south region of Portugal, where the solar potential is considerably high. The project includes two new 400 kV OHL that will constitute a new axis between F. Alentejo-Ourique-Tavira substations. It is also included the expansion of the Ourique substation to include the 400 kV voltage level. | 780 | Extension of Ourique substation | Ourique (PT) | - | Substation | AC | 400 | 2024-2026 | Planned But Not Yet Permitting | REN | - | Portugal
92 | AMPRION;ELIA | ALEGrO | This project realizes the first interconnection between Belgium (Lixhe) and Germany (Oberzier) as a 100 km HVDC link with a bidirectional rated power of 1.000 MW capacity | 146 | ALEGrO | Oberzier (DE) | Lixhe (BE) | Underground Cable | DC | 320 | 2020 | In Permitting | AMPRION | ELIA | Belgium | Germany
94 | 50Hertz Transmission, PSE | GerPol Improvements | Upgrade of the existing 220 kV double interconnection line between Krajnik and Vierraden to 400 kV double line in the same direction together with installation of Phase Shifting Transformers on two existing interconnection lines (Krajnik-Vierraden by 50Hertz) | 139 | Krajnik-Vierraden | Vierraden (DE) | Krajnik (PL) | Overhead Line | AC | 400 | 31/12/2020 | Under Construction | 50Hertz | PSE S.A. | Poland | Germany
|  |  |  | 796 | Krajnik | Krajnik (PL) | Krajnik (PL) | Substation | AC | 400 | 2019 | Under Construction | PSE S.A. | PSE S.A. | Poland | Germany
|  |  |  | 1492 | PST in Mikulowa | Mikulowa (PL) | Mikulowa (PL) | PST | AC | 400 | 30/06/2016 | Commisioned | PSE | PSE | Poland
|  |  |  | 1493 | PST Vierraden | Vierraden (DE) | Vierraden (DE) | Phase Shift Transformer | AC | 400 | 31/12/2018 | Under Construction | 50Hertz | 50Hertz | Germany
96 | FINGRID | Keminmaa-Pyhänselkä | The project is 400 kV overhead line in North Finland. It is part of the 3rd AC cross border project between Finland and Sweden. Will also allow integration of new RES generation at Bothnian bay. | 801 | FI5 KI-PS | Keminmaa (FI) | Pyhanselka (FI) | Overhead Line | AC | 400 | 1/ 1/ 2024 | In Permitting | Fingrid | Fingrid | Finland
103 | TENNET-NL | Reinforcements Ring NL phase I | Upgrade of existing 380kV circuits in the Dutch main ring from 2,5 kA to 4 kA. | 1488 | Diemen-Lelystad-Ens | Diemen | Ens | Overhead Line | AC | 380 | 2020 | Under Construction | TENNET-NL | TENNET-NL | Netherlands
|  |  |  | 1490 | Ens-Zwolle | Ens | Zwolle | Overhead Line | AC | 380 | 2022 | Planned But Not Yet Permitting | TENNET-NL | TENNET-NL | Netherlands
|  |  |  | 1539 | Krimpen-Geertruidenberg | Krimpen | Geertruidenberg | Overhead Line | AC | 380 | 2020 | In Permitting | TENNET-NL | TENNET-NL | Netherlands
|  |  |  | 1540 | Eindhoven-Maasbracht | Eindhoven | Maasbracht | Overhead Line | AC | 380 | 2023 | In Permitting | TENNET-NL | TENNET-NL | Netherlands
|  |  |  | 1560 | Randstad380 noordring | Beverwijk | Bleiswijk | Overhead Line | AC | 380 | 2018 | Under Construction | TENNET-NL | TENNET-NL | Netherlands
107 | EIRGRID,RTE | Celtic Interconnector | Celtic Interconnector will be the first interconnection between Ireland and France. A survey of the route of the HVDC (VSC) link with 700 MW capacity has been done from the southern coast of Ireland to La Martyre (Finistère) in France. | 810 | France Ireland Interconnector | West Wexford or East Cork (IE) | La Martyre (FR) | Subsea Cable | DC | 320 | 2026 | Under Consideration | EIRGRID | RTE | France | Ireland
110 | NGIHL;STATNETT | Norway-Great Britain NSN | North Sea Link, 1400 MW and 720 km long interconnector between Norway and England. | 424 | Norway - Great Britain | Kvilldal (NO) | Blythe (GB) | Subsea Cable | DC | 500 | 2021 | Under Construction | Statnett | NHIGL | United Kingdom | norway
111 | FINGRID;SVK | 3rd AC Finland-Sweden north | Third AC 400 kV overhead line interconnector between Finland north and Sweden SE1. Strengthening the AC connection between Finland and Sweden is necessary due to market needs, security of supply in Finland, new wind power generation and larger conventional units. | 396 | 3rd AC Finland-Sweden north | Keminmaa (Finland) | Messaure (Sweden, bidding area SE1) | Overhead Line | AC | 400 | 2025 | In Permitting | Fingrid | Svenska kraftnät | Finland | Sweden
113 | AMPRION;TENNET-NL | Doetinchem - Niederrhein | This new AC 380-kV double circuit overhead line will interconnect The Netherlands and Germany (Rhine-Ruhr area). Upon realisation of the project there will be four double circuit interconnections between The Netherlands and Germany. The project will increase the cross border capacity and will facilitate the further integration of the European Energy market especially in Central West Europe. The new line will also increase the security of supply. | 145 | Doetinchem-Niederrhein | Niederrhein (DE) | Doetinchem (NL) | Overhead Line | AC | 380 | 2018 | Under Construction | AMPRION | TENNET-NL | Netherlands | Germany
120 | ELIA | MOG II: connection of up to 2 GW additional offshore wind Belgium | As per the concept of MOG (project 75), the MOG II aims at centralizing the offshore wind farms in an offshore hub and transporting it via 220 kV AC cables to a substation along a new corridor Stevin-Avelgem (see project 329). Current hypothesis is to apply this concept in two-fold thus two platforms and cable sets centralizing ~1000 MW each Structure, capacity, timing etc. are all subject to the identification of new offshore concession zones in the Belgian part of the North Sea and subsequent proces to translate this into an implementation plan with all involved stakeholders. | 1625 | MOG II: connection of up to 2 GW additional offshore wind Belgium | Offshore (TBD) | Onshore (TBD) | Subsea Cable | AC | 220 | 2030 | Under Consideration | Elia | Elia | Belgium
121 | ELIA;NGIHL | Nautilus: 2nd interconnector Belgium - UK | This project considers the possibility of a ~1 - 1.4 GW second HVDC connection between UK and Belgium at the earliest by 2028 (indicative timing). The timing as well as location, routing, capacity are subject to further studies. In this context, Elia and NGIHL are conducting a bilateral feasibility study. | 934 | Nautilus: 2nd interco UK - BE | Leiston (UK) | TBD (BE) | Subsea Cable | DC | 400 | 2028 | Under Consideration | NGHIL | ELIA | Belgium | Great Britain
123 | LITGRID,PSE | LitPol Link Stage 2 | The LitPol Link Stage 2 is a continuation of building of the interconnection between Poland and Lithuania in order to achieve the planned transmission capacity of 1000 MW in both directions. Building of additional internal investments in Poland and Lithuania are necessary. Project will help to further strenghten of Baltics integration into European market. | 373 | Ostroleka-Stanislawow | Ostroleka (PL) | Stanislawow (PL) | Overhead Line | AC | 400 | 31/ 12/ 2023 | Planned But Not Yet Permitting | PSE | PSE | Poland | Lithuania
124 | AST;LITGRID;SVK | NordBalt phase 2 | Second phase includes the internal network reinforcements in Sweden, Lithuania and Latvia, a key investments to accomplish full utilization of the NordBalt cable between Lithuania and Sweden | 378 | 330 kV OHL Panevezys-Musa | Panevezys | Musa | Overhead Line | AC | 330 | 2023 | Planned But Not Yet Permitting | LITGRID | LITGRID | Lithuania | Sweden
|  |  |  | 385 | Grobina (LV) - Imanta (LV) | Grobina (LV) | Imanta (LV) | Overhead Line | AC | 330 | 2019 | Under Construction | AST | AST | Lithuania | Sweden
|  |  |  | 733 | Ekhyddan-Nybro-Hemsjo | Ekhyddan (SE) | Nybro/Hemsjo (SE) | Overhead Line | AC | 400 | 2023 | In Permitting | Svk | Svk | Lithuania | Sweden
126 | SVK | SE North-south reinforcements | Reactive measures in substations and series compensations in order to increase capacity between SE2 and SE3. Replacement of ageing overhead lines that also will contribute to the increased capacity. | 403 | Reinforcements SE2-SE3 in Sweden | SE2 | SE3 | Compensation | AC | 400 | 2030 | Under Consideration | Svk | Svk | Sweden
127 | TERNA | Central Southern Italy | "The project consists in the reinforcement of southern Italy 400 kV network through new 400 kV lines. The activities will involve the network portions between the substation of Villanova and Foggia, Deliceto and Bisaccia as well as Laino and Altomonte" | 86 | 86 | Foggia (IT) | Villanova (IT) | Overhead Line | AC | 400 | 2022 | In Permitting | TERNA | TERNA | Italy
|  |  |  | 96 | 96 | Deliceto (IT) | Bisaccia (IT) | Overhead Line | AC | 400 | 31/ 12/ 2022 | In Permitting | TERNA | TERNA | Italy
|  |  |  | 645 | ITA-3 | Laino (IT) | Altomonte (IT) | Overhead Line | AC | 400 | 1/ 1/ 2022 | In Permitting | TERNA | TERNA | Italy
130 | 50Hertz Transmission, TenneT DE | HVDC Wolmirstedt to area Isar | 2 GW HVDC-connection from North-East Germany (Area of Wolmirstedt), an area with high installed capacities of RES, to the South of Bavaria (area of Isar), an area with high consumption and connections to storage capabilities. A Capacity extension to 4 GW is under investigation. | 665 | Wolmirstedt | Wolmirstedt (DE) | Isar (DE) | Underground Cable | DC | n/a | 2025 | In Permitting | 50Hertz | TenneT DE | Germany
132 | Amprion | HVDC Line A-North | Project 132 consists of a new HVDC cable from Emden-East to Osterath. This HVDC has a transfer capacity of 2 GW. | 661 | HVDC Line A-North | Emden East (DE) | Osterath (DE) | Overhead Line | DC | 400 | 1/ 1/ 2025 | Planned but not yet permitting | Amprion | Amprion | Germany
134 | AMPRION;TRANSNET-BW | N-S Western DE_section South | Project 134 provides significant North-South transmission capacity in Western Germany. The project consists of AC reinforcements and upgrades of existing corridors towards the load centers of Baden-Württemberg and Switzerland. | 176 | Daxlanden-Eichstetten | Daxlanden (DE) | Eichstetten (DE) | Overhead Line | AC | 380 | 1/ 1/ 2021 | Planned but not yet permitting | TransnetBW | TransnetBW | Germany
|  |  |  | 680 | Urberach - Daxlanden | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 400 | 1/ 1/ 2023 | Planned but not yet permitting | Amprion | TransnetBW | Germany
135 | AMPRION | N-S Western DE_parallel lines | Project 135 provides significant grid reinforcement between Cologne and the Ruhr district (North-West-Germany) and Koblenz/Frankfurt (South-West-Germany) to integrate RES. | 179 | Rommerskirchen - Weißenthurm | Rommerskirchen (DE) | Weißenthurm (DE) | Overhead Line | AC | 400 | 1/ 1/ 2019 | Under Construction | Amprion | Amprion | Germany
|  |  |  | 188 | Kruckel - Dauersberg | Kruckel (DE) | Dauersberg (DE) | Overhead Line | AC | 380 | 1/ 1/ 2021 | In Permitting | Amprion | Amprion | Germany
138 | "TRANSELECTRICA, ESO-EAD" | Black Sea Corridor | The project consists of one 400kV double circuit OHL Cernavoda-Stalpu with in/out connection of one circuit in Gura Ialomitei, one 400 kV double circuit OHL Smardan-Gutinas in Romania and also the new 400 kV OHL Dobrujda-Burgas in Bulgaria. | 273 | 400kV OHL Cernavoda-Stalpu | Cernavoda (RO) | Stalpu (RO) | Overhead Line | AC | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | Romania | Bulgaria
|  |  |  | 275 | 400 kV OHL Smardan-Gutinas | Smardan (RO) | Gutinas (RO) | Overhead Line | AC | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | Romania | Bulgaria
|  |  |  | 715 | 220kV Stalpu substation upgrade to 400 kV | Stalpu (RO) | Stalpu (RO) | Substation | AC | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | Romania | Bulgaria
|  |  |  | 800 | 400 kV OHL Varna-Burgas | Varna(BG) | Burgas(BG) | Overhead Line | AC | 400 | 31/ 03/ 2021 | In Permitting | ESO-EAD | ESO-EAD | Romania | Bulgaria
142 | ESO,IPTO-SA | CSE4 | The project concerns the construction of a new AC 400kV interconnection between Bulgaria and Greece and new AC 400kV overhead lines at the south part of Bulgaria. This project will increase cross border transfer capacity between Bulgaria and Greece | 256 | 256 | Maritsa East 1 (BG) | N.Santa (GR) | Overhead Line | AC | 400 | 30/01/ 2023 | In Permitting | ESO-EAD | IPTO-SA | Bulgaria | Greece
|  |  |  | 257 | 257 | Maritsa East 1 (BG) | Plovdiv (BG) | Overhead Line | AC | 400 | 30/ 12/ 2020 | In Permitting | ESO-EAD | ESO-EAD | Bulgaria | Greece
|  |  |  | 258 | 258 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | Overhead Line | AC | 400 | 30/ 06/ 2019 | In Permitting | ESO-EAD | ESO-EAD | Bulgaria | Greece
|  |  |  | 262 | 262 | Maritsa East 1 (BG) | Burgas (BG) | Overhead Line | AC | 400 | 01/ 06/ 2021 | In Permitting | ESO-EAD | ESO-EAD | Bulgaria | Greece
144 | TRANSELECTRICA; EMS | Mid Continental East corridor | The project consists of one double circuit 400 kV line between Serbia and Romania and reinforcement of the network along the western border in Romania: one new simple circuit 400 kV line from Portile de Fier to Resita and upgrade from 220 kV double circuit to 400 kV double circuit of the axis between Resita and Arad, including upgrade to 400 kV of three substations along this path: Resita, Timisoara, Sacalaz. | 238 | New_400 kV OHL RO-RS | Resita (RO) | Pancevo (RS) | Overhead Line | AC | 400 | 31/03/2018 | Under Construction | Transelectrica | EMS | Romania | Serbia
|  |  |  | 269 | 400 kV OHL Portile de Fier-Resita | Portile de Fier (RO) | Resita (RO) | Overhead Line | AC | 400 | 2019 | Under Construction | Transelectrica | Transelectrica | Romania | Serbia | Hungary
|  |  |  | 270 | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz - Arad to 400kV double circuit line | Resita (RO) | Timisoara-Sacalaz-Arad (RO) | Overhead Line | AC | 400 | 2023 | In Permitting | Transelectrica | Transelectrica | Romania | Serbia | Hungary
|  |  |  | 701 | 400 kV Substation Resita | Resita (RO) | Resita (RO) | Substation | AC | 400 | 2019 | Under Construction | Transelectrica | Transelectrica | Romania | Serbia
|  |  |  | 705 | 400 kV Substation Timisoara | Timisoara (RO) | Timisoara (RO) | Substation | AC | 400 | 2023 | In Permitting | Transelectrica | Transelectrica | Romania | Serbia
150 | TERNA;ELES | Italy-Slovenia | "The project consists in a new HVDC link between Salgareda (Italy) and Beričevo (Slovenia) which will strengthen the connection between Slovenia and Italy. On italian side the project is under permitting since 2012. Terna and ELES are evaluating the opportunity to implement the project according to the following two phases: • phase 1 reinforcement of existing grid (PSTs, upgrade of existing lines) o Commissioning date: 2020 o Delta GTC contribution: 400 MW • phase 2 HVDC link (two separate investments: one for the IT side and one for the SI side) o Substation 1: Beričevo o Rated power: 800/600 MW o Commissioning date: 2022/2025 o Delta GTC contribution: 600 MW | 616 | Salgareda - Border IT-SI | Salgareda (IT) | Border IT-SI | Underground Cable | DC | 500 | 2022 | In Permitting | TERNA | ELES | Slovenia | Italy
|  |  |  | 1616 | Beričevo - Border IT-SI | Beričevo (SI) | Border IT-SI | Underground Cable | DC | 500 | after 2022 | Under Consideration | ELES | TERNA | Slovenia | Italy
153 | RTE,FAB Link Ltd | France-Alderney-Britain | France-Alderney-Britain (FAB) is a new HVDC subsea interconnector between Exeter (UK) and Menuel (France) with 1,4 GW capacity. | 987 | France-Alderney-Britain | Menuel (FR) | Exeter (GB) | Subsea Cable | DC | 320 | 1/ 1/ 2022 | In Permitting | RTE (FR) | NGIHL (UK) | France | Great Britain
164 | TENNET-DE | N-S Eastern DE_central section | North-South transmission in Germany. AC links from Northern Germany towards the load centers of Bavaria and Baden-Württemberg. | 149 | Dollern - Stade | Dollern (DE) | Stade (DE) | Overhead Line | AC | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | Germany
|  |  |  | 157 | Wahle - Mecklar | Wahle (DE) | Mecklar (DE) | Overhead Line | AC | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | Germany
|  |  |  | 677 | Dollern - Landesbergen | Dollern (DE) | Landesbergen (DE) | Overhead Line | AC | 380 | 2023 | In Permitting | TenneT-DE | TenneT-DE | Germany
|  |  |  | 685 | Mecklar - Grafenrheinfeld | Mecklar (DE) | Grafenrheinfeld (DE) | Overhead Line | AC | 380 | 2027 | Planned But Not Yet Permitting | TenneT-DE | TenneT-DE | Germany
167 | Energinet.dk, NGIHL | Viking DKW-GB | 2x700 MW HVDC subsea link across the North Seas. New substations on both sides; Bicker Fen (GB); Revsing (DK) | 998 | Viking Link DKW-GB, TYNDP ID 167.998 | Revsing (DKW) | Bicker Fen (GB) | Subsea Cable | DC | 515 | 31/12/ 2022 | In Permitting | Energinet.dk | National Grid | Denmark | Great Britain
170 | AST;ELERING;LITGRID | Baltics synchro with CE | The power system of the Baltic States which includes Estonia, Latvia, Lithuania (Baltic Integrated Power System) currently is operating in parallel with the Integrated/Unified Power System (IPS/UPS) of Russia and Belarus. The aim of this project is to remove the energy isolation of the Baltic States from the rest of the EU and connect their power systems with systems using the same technical standards and developing in the same European legal framework. This strategic goal has been set by the Prime Ministers of the Baltic States in 2007. | 382 | New 330 kV OHL Vilnius-Neris | Vilnius | Neris | Overhead Line | AC | 330 | 2024 | Planned But Not Yet Permitting | LITGRID | LITGRID | Lithuania
|  | #REF! | #REF! | 1004 | 330kV OHL Paide-Sindi (L346) | Sindi | Paide | Overhead Line | AC | 330 | 01/01/2025 | Under Consideration | ELERING | ELERING | Estonia
|  | #REF! | #REF! | 1010 | 330 kV OHL Tartu-Valmiera | Tartu | Valmiera | Overhead Line | AC | 330 | 1/ 1/ 2025 | Planned But Not Yet Permitting | Elering | AST | Lithuania
|  | #REF! | #REF! | 1011 | Valmiera -Tsirguliina 330 kV | Tsirguliina | Valmiera | Overhead Line | AC | 330 | 1/ 1/ 2025 | Planned But Not Yet Permitting | Elering | AST | Lithuania
|  | #REF! | #REF! | 1012 | 330 kV OHL Tartu-Balti (L300) | Balti | Tartu | Overhead Line | AC | 330 | 1/ 1/ 2024 | Planned But Not Yet Permitting | ELERING | ELERING | Lithuania
|  | #REF! | #REF! | 1013 | Viru-Tsirguliina 330kV OHL | Viru | Tsirguliina | Overhead Line | AC | 330 | 1/ 1/ 2025 | Planned But Not Yet Permitting | ELERING | ELERING | Lithuania
|  | #REF! | #REF! | 1034 | New 400 kV interconnection line from Lithuania to state border | Marijampole | State border | Overhead Line | AC | 400 | 2024 | Planned But Not Yet Permitting | LITGRID | LITGRID | Lithuania
|  | #REF! | #REF! | 1118 | SVC and control upgrades | Eesti 330 kV | - | Compensation | AC | 330 | 1/ 1/ 2024 | Planned But Not Yet Permitting | LITGRID; AST; ELERING | - | Lithuania | Estonia | Latvia
|  | #REF! | #REF! | 1564 | New 110 kV OHL Pagegiai-Bitenai near LT-RU border | Pagegiai | Bitenai | Overhead Line | AC | 110 | 2019 | Under Construction | LITGRID | LITGRID | Lithuania
|  | #REF! | #REF! | 1565 | Reconstruction of 330 kV OHL LE-Vilnius | LE | Vilnius | Overhead Line | AC | 330 | 2018 | Under Construction | LITGRID | LITGRID | Lithuania
|  | #REF! | #REF! | 1566 | Reconstructions in North Eastern Lithuania | - | - | Substation | AC | 330 | 2021 | Under Construction | LITGRID | LITGRID | Lithuania
|  | #REF! | #REF! | 1567 | Reinforcements of 110 kV lines near LT-BY border | Griskonys | Valkininkai | Overhead Line | AC | 110 | 2023 | Planned But Not Yet Permitting | LITGRID | - | Lithuania
|  | #REF! | #REF! | 1568 | Construction of new 400/330 kV autotransformers in Alytus substation | Alytus | - | Substation | AC | 400 | 2021 | Planned But Not Yet Permitting | LITGRID | - | Lithuania
|  | #REF! | #REF! | 1569 | Rerouting of exicting HVDC converter in Alytus | Alytus | - | LCC converter station | DC | 0 | 2024 | Planned But Not Yet Permitting | LITGRID | - | Lithuania
|  | #REF! | #REF! | 1570 | Construction of new HVDC converter in Bitenai | Bitenai | - | LCC converter station | DC | 0 | 2024 | Planned But Not Yet Permitting | LITGRID | - | Lithuania
|  | #REF! | #REF! | 1571 | New voltage control units (such as SVC) in LT | - | - | Substation | AC | 0 | 2023 | Planned But Not Yet Permitting | LITGRID | - | Lithuania
|  | #REF! | #REF! | 1572 | Preparation works in Baltics: Baltic AGC system, frequency control monitoring system. | - | - | Substation | AC | 0 | 2024 | Planned But Not Yet Permitting | LITGRID; AST; ELERING | - | Lithuania | Estonia | Latvia
|  | #REF! | #REF! | 1632 | New 330 kV Musa substation | Musa | - | Substation | AC | 330 | 2023 | Planned But Not Yet Permitting | - | -
|  | #REF! | #REF! | 1633 | Reconstruction of 330 kV OHL Klaipeda - Bitenai | Klaipeda | Bitenai | Overhead Line | AC | 330 | 2024 | Planned But Not Yet Permitting | LITGRID | - | Lithuania
|  | #REF! | #REF! | 1634 | Reconstruction of 330 kV OHL Bitėnai - Jurbarkas | Bitenai | Jurbarkas | Overhead Line | AC | 330 | 2024 | Planned But Not Yet Permitting | LITGRID | - | Lithuania
|  | #REF! | #REF! | 1635 | New 330 kV OHL Jurbarkas - KHAE | Jurbarkas | KHAE | Overhead Line | AC | 330 | 2024 | Planned But Not Yet Permitting | LITGRID | - | Lithuania
172 | ElecLink | ElecLink | ElecLink is a new FR – UK interconnection cable with 1000 MW capacity through the Channel Tunnel between Sellindge (UK) and Mandarins (FR). Converter stations will be located on Eurotunnel concession at Folkestone and Coquelles. This HVDC interconnection is a PCI project (Project of Common Interest) no. 1.7.3 | 1487 | ElecLink | Sellindge (UK) | Mandarins (FR) | Underground Cable | DC | 320 | 2019 | Under Construction | NG | RTE | United Kingdom | France
173 | ELIA;RTE | FR-BE II: PSTs Aubange-Moulaine | Installation of two phase shifting transformers in Aubange, one on each of the 225kV circuits of the Aubange-Moulaine interconnector. | 1281 | Aubange-Moulaine: PSTs | Aubange (BE) | Moulaine (FR) | Phase Shift Transformer | AC | 220 | 2021 | Planned But Not Yet Permitting | ELIA | RTE | France | Belgium
174 | Worldenergy SA | Greenconnector | Greenconnector is an HVDC interconnector project between Italy and Switzerland for power transport using DC cables rather than overhead lines. The route length is about 150 km. The design power is 1000 MW (1200 MW in overload condition), while the DC voltage is +/- 400 kV DC. Two cables will be installed, working with a bipolar scheme. Great part of the cables route will exploit a section of an existing oil pipeline, no longer in service since January 1997. This pipeline crosses the Italian and Switzerland border at Splügenpass and is running close by the two end stations of the Greenconnector project (Sils in Graubunden Canton and Verderio Inferiore, Lecco). The cables will be pulled inside the pipeline itself, reducing the amount of civil works required before and after cable laying and therefore limiting even temporary environmental impact. For about 47 km the cables will run across the Como lake. | 1014 | Greenconnector | Verderio | Sils i.D. | Underground Cable | DC | 400 | 2022 | In Permitting | Terna | Swissgrid | Italy | Switzerland
175 | Energinet.dk | Great Belt II | This project candidate includes an HVDC connector between Denmark-West (DKW) and Denmark-East (DKE). The connector is called Great Belt-2. | 1000 | Great Belt II | Malling (DKW) | Kyndby (DKE) | Subsea Cable | DC | 400 | 2030 | Under Consideration | Energinet | Energinet | Denmark | Denmark
176 | 50Hertz Transmission, Svenska Kraftnät (SvK) | Hansa PowerBridge I | New HVDC interconnector between Sweden (SE4) and Germany (50 Hertz, Continental) aiming to enhance the integration of the Nordic and the continental power market. Moreover the interconnector facilitates RES integration and increases the system adequacy in both systems. | 995 | Hansa PowerBridge I | Hurva (SE4) | Guestrow (DE) | Subsea Cable | DC | 300 | 2026 | In Permitting | Svk | 50Hertz | Germany | Sweden
179 | 50Hertz Transmission, Energinet.dk | DKE - DE (Kontek2) | This project includes a HVDC subsea interconnector between Denmark-East (DKE) and Germany (DE) and is called Kontek-2. A final grid-connection solution is not prepared yet. | 1016 | DKE-DE (Kontek 2) | Bjæverskov (DK2) | Bentwisch (DE) | Subsea Cable | DC | 400 | > 2030 | Under Consideration | Energinet.dk | 50Hertz | Denmark | Germany
183 | Energinet.dk,TENNET-DE | "DKW-DE, Westcoast" | New 400 kV line from Endrup (DK) to Klixbüll (DE), increasing the transfer capacity at the West Coast between these countries. The project is labelled by the EC as project of common interest (PCI 1.3.1). | 1018 | DKW-DE, Westcoast, TYNDP ID 183.1018 | Klixbüll (DE) | Endrup (DKW) | Overhead Line | AC | 380 | 31/ 12/ 2022 | In Permitting | TenneT-DE | Energinet.dk | Denmark | Germany
186 | APG | east of Austria | To allow the grid integration of the planned renewable energy generation (mainly wind power) in the north-eastern part of Austria ("Weinviertel") the transmission grid infrastructure (currently a rather weak 220kV line) has to be enforced and new substation for the connection needs to be erected. | 886 | east of Austria | Seyring | Neusiedl/Zaya | Overhead Line | AC | 380 | 2021 | In Permitting | APG | APG | Austria
187 | APG;TENNET-DE | St. Peter (AT) - Pleinting (DE) | Increase of the cross border transmission capacity by erecting a new 380kV line between St. Peter (Austria) and Pleinting (Germany). This leads to an improved connection of the very high amount of RES in Germany and the pump storages in the Austrian Alps. | 997 | St. Peter (AT) - Pleinting (DE) | Pleinting (DE) | St. Peter (AT) | Overhead Line | AC | 380 | 2024 | In Permitting | TenneT-DE | APG | Austria | Germany
190 | NorthConnect KS | NorthConnect | "A 650 km long subsea interconnector between Norway and Scotland is planned to be realised in 2022. The interconnector is planned to be a 500 kV, 1400 MW HVDC subsea interconnector between western Norway (Simadalen) and eastern Scotland (Peterhead), UK." | 1382 | NorthConnect | Sima | Peterhead | Subsea Cable | DC | 500 | 2022 | Under Consideration | Statnett | National Grid (SSEN is TO) | Great Britain | Norway
191 | TENNET-DE | OWP TenneT Northsea Part 2 | Connection of offshore wind parks in the North Sea to Germany. Mainly subsea DC cable. The OWP will help to reach the European goal of CO2 reduction and RES integration | 656 | BorWin3 | Cluster BorWin3 | Emden/East (DE) | Subsea Cable | DC | 320 | 2019 | Under Construction | TenneT-DE | TenneT-DE | Germany
|  | #REF! | #REF! | 952 | Cluster DolWin 5 (NOR 1-1) | Cluster DolWin 5 (NOR-1-1) | Emden/East (DE) | Subsea Cable | DC | 320 | 2024 | Planned But Not Yet Permitting | TenneT-DE | TenneT-DE | Germany
|  | #REF! | #REF! | 953 | Cluster DolWin6 | Cluster DolWin 6 (NOR-3-3) | Emden/East | Subsea Cable | DC | 320 | 2023 | Under Construction | TenneT-DE | TenneT-DE | Germany
|  | #REF! | #REF! | 1513 | DolWin3 | Cluster DolWin3 (DE) | Dörpen/West (DE) | Subsea Cable | DC | 320 | 2018 | Under Construction | TenneT-DE | TenneT-DE | Germany
192 | TENNET-DE | OWP Northsea TenneT Part 3 | Connection of offshore wind parks in the North Sea to Germany. Mainly subsea DC cable. The OWP will help to reach the European goal of CO2 reduction and RES integration | 659 | SylWin2 | Cluster SylWin2 (DE) | Büttel (DE) | Subsea Cable | DC | 320 | 2025 | Planned But Not Yet Permitting | TenneT-DE | TenneT-DE | Germany
|  |  |  | 954 | Cluster BorWin 5 (NOR-7-1) | Cluster BorWin 5 (NOR-7-1) | area of Cloppenburg/East | Subsea Cable | DC | 320 | 2025 | Planned But Not Yet Permitting | TenneT-DE | TenneT-DE | Germany
381 | Amprion | OWP Northsea Part 4 | Connection of offshore wind parks in the North Sea to Germany. Mainly subsea DC cable. The OWP will help to reach the European goal of CO2 reduction and RES integration. This project has been approved in the national grid development process 2017 under the condition, that it is to be re-confirmed in 2019. | 211 | DolWin 4 (NOR-3-2) | Cluster DolWin 4 (NOR 3-2) | Hanekenfähr | Subsea Cable | DC | 320 | 2028 | Planned But Not Yet Permitting | Amprion | Amprion | Germany
|  |  |  | 1485 | BorWin 6 (NOR-7-2) | Cluster BorWin 6 (NOR-7-2) | Hanekenfähr | Subsea Cable | DC | 320 | 2030 | Planned But Not Yet Permitting | Amprion | Amprion | Germany
193 | REE | Godelleta-Morella/La Plana | This project consist of a new OHL 400 kV AC axis Godelleta-Morella/La Plana (Spain). This project allows to solve today and future congestion in the north-south axis of Levante | 927 | La Plana/Morella-Godelleta | La Plana/Morella | Godelleta | Overhead Line | AC | 400 | 2025 | Under Consideration | REE | REE | Spain
194 | REE | Cartuja | This project includes a new 400 kV double circuit Cartuja-Arcos de la Frontera and a new substation Cartuja 400 kV (Spain). This project would allow in the long term to connect future onshore and offshore wind generation. | 561 | New substation Cartuja | Cartuja (ES) | Cartuja (ES) | Substation | AC | 400 | 2029 | Under Consideration | REE | REE | Spain
|  | #REF! |  | 929 | Cartuja-Arcos 400 kV | Cartuja | Arcos | Overhead Line | AC | 400 | 2029 | Under Consideration | REE | REE | Spain
197 | FINGRID | N-S Finland P1 stage 2 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thusenabling the integration of new renewable and conventional generation in northern Finland and to compensate dismantling of obsolescent existing 220 kV lines. This project is fifth 400 kV overhead line connecting North Finland to South Finland. | 742 | Pyhanselka-Petajavesi | Pyhanselka (FI) | Petajavesi (FI) | Overhead Line | AC | 400 | 1/ 7/ 2022 | In Permitting | Fingrid | Fingrid | Finland
199 | RTE,SWISSGRID | Lake Geneva South | This project comes on top of "PST Foretaille" and "upstream grid reinforcement in France" projects. It consists in upgrading the existing 225-kV overhead line south of Lake Geneva, possibly to 400-kV. | 1051 | Cornier - La Bâtiaz | Cornier (FR) | La Bâtiaz (CH) | Overhead Line | AC | 400 | 2035 | Under Consideration | RTE | SWISSGRID | France | Switzerland
200 | CEPS | CZ Northwest-South corridor | "A corridor of internal 400 kV overhead lines inside the Czech Republic connecting new 420 kV substations between Vernerov, Vitkov and existing substation Prestice in the northwest-south direction incuding looping of existing 400 kV overheadline (V413: Reporyje-Prosenice) into the existing substation 420 kV Mirovka. The project consists of building of two new 420 kV substations Vernerov and Vitkov, building of two 400 kV overhead lines involving changing a 220 kV double-circuit lines to 400 kV double-circuit lines with a capacity of 2x1730 MVA between Vernerov-Vitkov and Vitkov-Prestice and building a new double-circuit overhead line between Mirovka and V413" | 306 | R Vitkov | Vitkov (CZ) | N/A | Substation | AC | 400 | 30/ 11/ 2022 | In Permitting | CEPS | N/A | Czech Republic
|  | #REF! | #REF! | 308 | Vernerov-Vitkov | Vernerov (CZ) | Vitkov (CZ) | Overhead Line | AC | 400 | 30/ 07/ 2025 | In Permitting | CEPS | CEPS | Czech Republic
|  | #REF! | #REF! | 309 | Vitkov-Prestice | Vitkov (CZ) | Prestice (CZ) | Overhead Line | AC | 400 | 30/ 11/ 2022 | In Permitting | CEPS | CEPS | Czech Republic
|  | #REF! | #REF! | 312 | R Mirovka | Mirovka (CZ) | N/A | Substation | AC | 400 | 30/ 09/ 2025 | In Permitting | CEPS | N/A | Czech Republic
|  | #REF! | #REF! | 314 | Mirkovka-V413 | Mirovka (CZ) | V413 (CZ) | Overhead Line | AC | 400 | 30/ 05/ 2019 | In Permitting | CEPS | CEPS | Czech Republic
203 | REE | Morella-La Plana (previosly Aragón-Castellon) | he project consists of a 400kV axis Morella-La Plana. The previous project already considered additional investments that are already in service, that is Mudejar-Morella , Mezquita-Morella and a new 400kV substation Mudejar with connection to the axis Aragón-Teruel (Spain). This project reinforces the Cantabric-Mediterranean axis solving today and future congestions. | 538 | Morella-La Plana | Morella (ES) | La Plana(ES) | Overhead Line | AC | 400 | 2020 | In Permitting | REE | REE | Spain
206 | TENNET-DE;TRANSNET-BW | Reinforcement Southern DE | AC-busbar"" in Southern Germany for energy dispatching within Bavaria and Baden-Württemberg and gathering solar energy. | 682 | Großgartach - Endersbach | Großgartach (DE) | Endersbach (DE) | Overhead Line | AC | 380 | 2025 | Planned But Not Yet Permitting | TransnetBW | TransnetBW | Germany
|  | #REF! | #REF! | 687 | Redwitz - Schwandorf | Redwitz (DE) | Schwandorf (DE) | Overhead Line | AC | 380 | 2023 | In Permitting | TenneT-DE | TenneT-DE | Germany
|  | #REF! | #REF! | 688 | Raitersaich-Altheim | Raitersaich (DE) | Altheim (DE) | Overhead Line | AC | 380 | 2026 | Planned But Not Yet Permitting | TenneT-DE | TenneT-DE | Germany
|  | #REF! | #REF! | 990 | Grafenrheinfeld - Großgartach | Grafenrheinfeld (DE) | Großgartach (DE) | Overhead Line | AC | 380 | 2022 | Planned But Not Yet Permitting | TenneT-DE | TransnetBW | Germany
207 | TENNET-DE | Reinforcement Northwestern DE | Integration of on- and offshore RES in Lower Saxony | 676 | Dollern - Elsfleth/West | Dollern (DE) | Elsfleht/West (DE) | Overhead Line | AC | 380 | 2026 | In Permitting | TenneT-DE | TenneT-DE | Germany
|  | #REF! | #REF! | 939 | Conneforde - Emden | Conneforde | Emden/Ost | Overhead Line | AC | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | Germany
|  | #REF! | #REF! | 940 | Emden - Halbemond | Emden/Ost | Halbemond | Overhead Line | AC | 380 | 2022 | Planned But Not Yet Permitting | TenneT-DE | TenneT-DE | Germany
208 | AMPRION;TENNET-DE | N-S Western DE_section North_1 | Project 208 consists of new 380 kV overhead line s(partly in existing corridor). The project is needed for integration of on- and offshore wind energy and transport to the load centres in western and southern parts of Germany. | 150 | Conneforde-Wilhelmshaven | Conneforde (DE) | Wilhelmshaven (DE) | Overhead Line | AC | 380 | 2020 | In Permitting | TenneT-DE | TenneT-DE | Germany
|  | #REF! | #REF! | 151 | Ganderkesee - Wehrendorf | Wehrendorf (DE) | Ganderkesee (DE) | Overhead Line | AC | 380 | 2021 | In Permitting | TenneT-DE | Amprion | Germany
|  | #REF! | #REF! | 156 | Niederrhein-Dörpen | Niederrhein (DE) | Dörpen/West (DE) | Overhead Line | AC | 380 | 2021 | In Permitting | Amprion | TenneT-DE | Germany
209 | TENNET-DE | Reinforcement Northeastern DE | New 380-kV-lines in the area of Schleswig-Holstein mainly for integration of Onshore-Wind. | 935 | Kreis Segeberg - Siems | Kreis Segeberg | Göhl/Siems | Overhead Line | AC | 380 | 2022 | Planned But Not Yet Permitting | TenneT-DE | TenneT-DE | Germany
210 | Alpe Adria Energia Srl | Wurmlach (AT) - Somplago (IT) interconnection | Somplago - Wurmlach interconnection is a cross-border electrical line promoted by Alpe Adria Energia Srl. The project concerns a 220kV a.c. merchant line, about 300 MW from Somplago substation to new Wurmlach substation, including Phase Shifter Transformer located in Austria". | 1380 | Wurmlach (AT) - Somplago (IT) interconnection | SOMPLAGO | WURMLACH | Underground Cable | AC | 220 | 2021 | In Permitting | TERNA SPA | Austrian Power Grid AG | Austria | Italy
214 | LANDSNET;NGIHL | Interco Iceland-UK | Interconnector (Sea cable) between Iceland and Great Britain. The Cable is DC with 800-1200 MW capacity and over 1.000 km long. 99.98% of the generation in Iceland is RES. Icelands hydro generation is highly flexible and ideal for complementing intermittency of GB´s growing wind sector. | 1082 | Interco Iceland-UK | tbd | tbd | Subsea Cable | DC | 500 | 2030 | Under Consideration | tbd | tbd | Iceland | Great Britain
219 | EuroAsia Interconnector | EuroAsia Interconnector | "The Euro Asia Interconnector consists of a 500 kV DC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot, Israeli and the Greek transmission networks (offshore). The Interconnector will have a capacity of 2000 MW and a total length of around 820 nautical miles/around 1518 km (approx. 329 km between CY and IL, 879 km between CY and Crete and 310 km between Crete and Athens) and allow for reverse transmission of electricity." | 1407 | EuroAsia Interconnector | Hadera Site | Kofinou Site | Subsea Cable | DC | 500 | 2020 | In Permitting | IEC | TSO Cyprus | Cyprus | Greece | Isreal
|  | #REF! |  | 1409 | EuroAsia Interconnector | Kofinou Site | Korakia (Crete)Site | Subsea Cable | DC | 500 | 2021 | In Permitting | TSO Cyprus | ADMHE | Cyprus | Greece | Isreal
|  | #REF! |  | 1410 | EuroAsia Interconnector | Korakia (Crete)Site | Athens Site | Subsea Cable | DC | 500 | 2020 | In Permitting | ADMHE | ADMHE | Cyprus | Greece | Isreal
225 | AMPRION;ELIA | 2nd interconnector Belgium - Germany | This project considers the possibility of a second ~1GW HVDC interconnection between Belgium and Germany at the earliest by 2028 (indicative timing). The timing as well as location, routing, capacity are subject to further studies. In this context, Elia and Amprion are conducting a bilateral feasibility study. | 1107 | 2nd interconnecter between Belgium and Germany | to be defined (BE) | to be defined (DE) | Underground Cable | DC | 0 | 2028 | Under Consideration | ELIA | AMPRION | Belgium | Germany
227 | EMS, CGES, NOSBiH | Transbalkan Corridor | The project aim is to increase transmission capacity within Serbia and facilitate exchange of energy between north-east part of Europe and south-west of Europe. | 627 | 400kV interconnection RS-BA | Bajina Basta (RS) | Visegrad (BA) | Overhead Line | AC | 400 | 2024 | In Permitting | EMS | NOSBIH | Serbia | Bosnia & Herzegovina | Montenegro
|  | #REF! | #REF! | 628 | 400kV OHL B.Basta-Obrenovac | SS Bajina Basta (RS) | SS Obrenovac (RS) | Overhead Line | AC | 400 | 2024 | In Permitting | EMS | EMS | Serbia | Bosnia & Herzegovina | Montenegro
|  | #REF! | #REF! | 630 | 400kV interconnection RS-ME | Bajina Basta (RS) | Pljevlja (ME) | Overhead Line | AC | 400 | 2024 | In Permitting | EMS | CGES | Serbia | Bosnia & Herzegovina | Montenegro
|  | #REF! | #REF! | 631 | 400kV SS B.Basta upgrade | Bajina Basta (RS) | Bajina Basta (RS) | Substation | AC | 400 | 2024 | In Permitting | EMS | EMS | Serbia | Bosnia & Herzegovina | Montenegro
|  | #REF! | #REF! | 1526 | 400 kV OHL Lastva - Pljevlja | SS Lastva | SS Pljevlja | Overhead Line | AC | 400 | 2019 | Under Construction | CGES | CGES | Montenegro
|  | #REF! | #REF! | 1527 | 400 kV OHL Kragujevac-Kraljevo | SS Kragujevac | SS Kraljevo | Overhead Line | AC | 400 | 2020 | Under Construction | EMS | EMS | Serbia | Montenegro
|  | #REF! | #REF! | 1528 | Upgrade of SS Kraljevo | SS Kraljevo | SS Kraljevo | Substation | AC | 400 | 2020 | Under Construction | EMS | EMS | Serbia
228 | RTE; TransnetBW; Amprion | Muhlbach - Eichstetten | Reinforcement of the existing 400kV OHL: Deployment of a second 400kV circuit at existing double circuit OHL Muhlbach - Eichstetten, instead of the currently operated circuit Eichstetten - Vogelgruen (currently operated with 225kV). Some topological adjustments of the existing grid in the area might prove to be necessary. | 1231 | Muhlbach Eichstetten | Muhlbach | Eichstetten | Overhead Line | AC | 400 | 2025 | Planned But Not Yet Permitting | RTE | TransnetBW GmbH | France | Germany
229 | 50Hertz Transmission, PSE | GerPol Power Bridge II | Project consist from following investments: indentation to the 2x400 kV line Baczyna-Plewiska (new routes: Baczyna-Zielona Góra, Zielona Góra-Plewiska), 2x400 kV line Zielona Góra - Gubin, crossborder line 2x400 kV line Gubin (PL)-Eisenhuettenstadt (DE) | 1270 | Baczyna-Zielona Góra | Baczyna-Plewiska indentation | Zielona Góra | Overhead Line | AC | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | Poland | Germany
|  | #REF! | #REF! | 1271 | Zielona Góra - Plewiska | Zielona Góra | Baczyna-Plewiska indentation | Overhead Line | AC | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | Poland | Germany
|  | #REF! | #REF! | 1272 | Zielona Góra | Zielona Góra | n.a. | Substation | AC | 400 | >2030 | Under Consideration | PSE S.A. | n.a. | Poland | Germany
|  | #REF! | #REF! | 1273 | Zielona Góra-Gubin | Zielona Góra | Gubin | Overhead Line | AC | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | Poland | Germany
|  | #REF! | #REF! | 1274 | Gubin | Gubin | n.a. | Substation | AC | 400 | >2030 | Under Consideration | PSE S.A. | n.a. | Poland | Germany
|  | #REF! | #REF! | 1275 | Eisenhuettenstadt | Gubin (PL) | Eisenhuettenstadt (DE) | Overhead Line | AC | 400 | >2030 | Under Consideration | PSE S.A. | 50Hertz | Poland | Germany
230 | PSE | GerPol Power Bridge I | The reinforcements in the Polish transmission network in western part of the country near Polish/German border. Construction new AC 2x400 kV lines Mikułowa - Świebodzice, Krajnik - Baczyna and Baczyna - Plewiska. | 353 | Krajnik-Baczyna | Krajnik (PL) | Baczyna (PL) | Overhead Line | AC | 400 | 2021 | In Permitting | PSE S.A. | PSE S.A. | Poland | Poland
|  | #REF! | #REF! | 355 | Mikułowa - Świebodzice | Mikułowa (PL) | Świebodzice (PL) | Overhead Line | AC | 400 | 2023 | Planned But Not Yet Permitting | PSE S.A. | PSE S.A. | Poland | Poland
|  | #REF! | #REF! | 1035 | Baczyna | Baczyna | n.a. | Substation | AC | 400 | 2020 | In Permitting | PSE S.A. | n.a. | Poland | Poland
|  | #REF! | #REF! | 1232 | Plewiska | Baczyna | Plewiska | Overhead Line | AC | 400 | 2024 | Planned But Not Yet Permitting | PSE S.A. | PSE S.A. | Poland | Poland
231 | swissgrid; TransnetBW; Amprion | Concept project Germany-Switzerland | "This concept project focuses on increasing the transmission capacity between Germany and Switzerland. One already identified investment is the upgrade of a 220 kV crossborder line to 380 kV between the substations of Tiengen (DE) and Beznau (CH)." | 1282 | 380 kV Grid Reinforcement Beznau - Tiengen | Beznau (CH) | Tiengen (DE) | Overhead Line | AC | 380 | 2030 | Under Consideration | Swissgrid | Amprion | Switzerland | Germany
|  | #REF! | #REF! | 1457 | Additional measures | Germany | Switzerland | Overhead Line | DC | 380 | 2035 | Under Consideration | TransnetBW | Swissgrid | Germany | Switzerland
233 | REE | Connection of Aragon Pumping hydro | Potential necessary transmission development for the connection of 3rd party storage project (pumping hydro) that has received a PCI label in the 3rd list 2017. No details about the required network are known yet. | 1235 | Conceptual project | - | - | Overhead Line | AC | 400 | 2027 | Under Consideration | REE | REE | Spain
234 | Energinet; PSE | DKE - PL-1 | HVDC connection DKE-PL; | 1236 | DKE-PL-1 | Avedøre (DKE) | Dunowo (PL) | Subsea Cable | DC | 400 | >2030 | Under Consideration | Energinet | PSE | Denmark | Poland
235 | TenneT-DE; TransnetBW | HVDC Brunsbüttel/Wilster to Großgartach/Grafenrheinfeld | 4 GW HVDC connection from Northern Germany (areas of Brunsbüttel/Wilster) to Bavaria / Baden-Württemberg (areas of Großgartach/Grafenrheinfeld).North Germany is characterised by a high amount of RES, the feed-in exceeds the local load and therefore there is a high demand for transfer to the load centres in southern parts of Germany. With the further installation of additional renewable energy, the relevance of this projects increases | 664 | HVDC Line C | "Brunsbüttel, Wilster" | "Großgartach, Grafenrheinfeld" | Underground Cable | DC | 520 | 2025 | In Permitting | TenneT-DE | TransnetBW | Germany
236 | ELIA | Internal Belgian Backbone West: HTLS upgrade Horta-Mercator | Project consists of replacing the conductors of the ~50km double circuit 380 kV overhead line between the substations of Horta and Mercator with high performance conductors, hereby doubling the transport capacity of the Horta-Mercator corridor. | 608 | HTLS upgrade Horta-Mercator | Horta (BE) | Mercator (BE) | Overhead Line | AC | 380 | 31/12/2019 | Under Construction | ELIA | ELIA | Belgium
239 | Fingrid;Svenska Kraftnät | Fenno-Skan 1 renewal | Replacement of the existing 400 kV HVDC cable interconnection between Finland and Sweden. Fennoskan 1 will be decomissioned at the same time with this project being commisioned, which reduces capacity between FI and SE3 by 400 MW while increasing SE2-FI by 800 MW. | 1241 | Fenno-Skan 1 renewal | Hjalta (SE2) | Tuovila (FI) | Subsea Cable | DC | 300 | 2029 | Under Consideration | SVK | FINGRID | Finland | Sweden
240 | 50Hertz Transmission | 380-kV-grid enhancement between Area Güstrow and Wolmirstedt | 380-kV-grid enhancement between Area Güstrow and Wolmirstedt | 1460 | AC Enhancement Güstrow-Wolmirstedt | Güstrow (DE) | Wolmirstedt (DE) | Overhead Line | AC | 380 | 2021 | In Permitting | 50Hertz | 50Hertz | Germany
241 | HOPS;NOS BiH | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV lines between SS Dakovo (HR) and SS Tuzla/Gradacac (BA) to 400 kV lines. The project 241, has been proposed assessed in the TYNDP 2016, based on the results of common planning studies performed in the CSE Region during preparation of Regional investment plan 2015. The project assumes upgrade of existing 220 kV lines between SS Đakovo (HR) and SS Tuzla (BH) and SS Gradačac (BH) to 400 kV, with additional internal new double 400 kV line connecting SS Đakovo to existing 400 kV line Žerjavinec - Ernestinovo. This project is under consideration and there is a need for pre-feasibility study. | 1276 | Upgrading of existing 220 kV line between SS Dakovo (HR) and TPP Tuzla (BA) to 400 kV line | Dakovo | Tuzla | Overhead Line | AC | 400 | 31/12/2032 | Under Consideration | HOPS | NOS BIH | Croatia | Bosnia & Herzegovina
|  | #REF! | #REF! | 1277 | Upgrading of existing 220 kV line between SS Dakovo (HR) and Gradacac (BA) to 400 kV line | Dakovo | Gradacac | Overhead Line | AC | 400 | 31/12/2032 | Under Consideration | HOPS | NOS BIH | Croatia | Bosnia & Herzegovina
|  | #REF! | #REF! | 1278 | Upgrading existing 220 kV SS Dakovo to 400 kV | Dakovo | Dakovo | Substation | AC | 400 | 31/12/2032 | Under Consideration | HOPS | HOPS | Croatia | Bosnia & Herzegovina
|  | #REF! | #REF! | 1279 | New double 400 kV line between SS Dakovo and location Razbojiste | Dakovo | Razbojiste | Overhead Line | AC | 400 | 31/12/2032 | Under Consideration | HOPS | HOPS | Croatia | Bosnia & Herzegovina
|  | #REF! | #REF! | 1530 | Upgrading of existing 220 kV line between SS Gradacac (BA) and TPP Tuzla (BA) to 400 kV line | SS Gradacac (BA) | TPP Tuzla (BA) | Overhead Line | AC | 400 | 2032 | Under Consideration | NOS BIH | NOS BIH | Bosnia & Herzegovina
|  | #REF! | #REF! | 1531 | Upgrading existing 220 kV SS Gradacac (BA) to 400 kV | SS Gradacac (BA) | SS Gradacac (BA) | Substation | AC | 400 | 2032 | Under Consideration | NOS BIH | NOS BIH | Bosnia & Herzegovina
242 | 50Hertz Transmission | Offshore Wind Baltic Sea (I) | AC grid connections connecting Offshore Wind Farms in Cluster 1 of the Baltic Sea (see German Offshore Grid Development Plan). Cluster 1 is located north east of Ruegen in the German Exclusive Economic Zone. | 194 | Offshore Connection Cluster 1 | OWF Cluster Baltic Sea East (DE) | Lubmin (DE) | Subsea Cable | AC | 220 | 2019 | Under Construction | 50Hertz | 50Hertz | Germany
243 | EMS, HOPS | New 400 kV interconnection line between Serbia and Croatia | Construction of new 400 kV interconnection line Sombor (RS) - Ernestinovo (HR) | 1269 | New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | Ernestinovo | Sombor | Overhead Line | AC | 400 | 01/01/2035 | Under Consideration | HOPS | EMS | Croatia | Serbia
244 | Amprion;Rte | Vigy - Uchtelfangen area | An upgrade of the existing over headline between the substations Ensdorf, Uchtelfangen and Vigy is planned to increase the thermal cross-border capacity. For this reinforcement the options are either the implementation of High Temperature Low Sag (HTLS) conductors or a reconstruction of the tie-line in the existing route. To allow an optimal use of the capacity increase the installation of phase shifter transformers (PSTs) is necessary. For these measures the substations have to be adjusted accordingly. | 1245 | Vigy - Uchtelfangen (or beyond) | Vigy (FR) | Uchtelfangen (DE) | Overhead Line | AC | 400 | 2027 | Planned But Not Yet Permitting | Rte | Amprion | France | Germany
|  | #REF! | #REF! | 1514 | Power flow control between Vigy - Uchtelfangen | Vigy (FR) | Uchtelfangen (DE) | Phase Shift Transformer | AC | 400 | 2027 | Planned But Not Yet Permitting | Rte | Amprion | France | Germany
245 | TENNET-NL;TENNET-DE | Upgrade Meeden - Diele | Increase of the interconnection capacity between The Netherlands and Germany by adding one new phase shifting transformer and apply dynamic line rating on the existing 380 kV double circuit tie line between Meeden and Diele. | 1246 | Upgrade Meeden - Diele | Meeden [NL] | Diele [DE] | Overhead Line | AC | 380 | 2019 | Under Construction | TENNET-NL | TENNET-DE | Netherlands | Germany
247 | Aquind Limited | AQUIND Interconnector | AQUIND Interconnector is a proposed High Voltage Direct Current (HVDC) subsea and underground electric power transmission link between the South of England and Normandy in France with a net nominal power capacity of 2 GW. The Proposed Development shall consist of two independent 1000 MW interconnector links. • The 320 kV DC subsea cable route will be between 170 km to 190 km in length, spanning between the two landfall sites at Eastney (UK) and near Dieppe (France). • The British 320 kV DC terrestrial cables will be approximately 20 km long. • The French 320 kV DC terrestrial cables will be approximately 40 km long. • The 400 kV AC cable routes are not anticipated to exceed 2 km in UK. • The 400 kV AC cable routes are not anticipated to exceed 2 km in France. The main investment items are listed above, additional items will include the procurement of spare parts for the cables and converter stations. | 1381 | AQUIND Interconnector | Lovedean (GB) | Barnabos (FR) | Subsea Cable | DC | 320 | 2022 | In Permitting | National Grid plc | Réseau de transport d'électricité | France | Great Britain
248 | 50Hertz Transmission | Offshore Wind Baltic Sea (II) | AC and DC grid connections connecting Offshore Wind Farms in Cluster 1, 2, 4 and 6 of the Baltic Sea (see German Offshore Grid Development Plan) | 1248 | AC Offshore Connection Cluster 1, 2,4 | OWF Cluster Baltic Sea (DE) | Lubmin (DE) | Subsea Cable | AC | 220 | 2022 | In Permitting | 50Hertz | 50Hertz | Germany | Germany
|  | #REF! | #REF! | 1613 | DC Offshore Connection Cluster 1, 2, 4 | OWF Cluster Baltic Sea (DE) | Siedenbrünzow/Alt Telin/Bartow (DE) | Subsea Cable | DC | 320 | 2027 | Planned But Not Yet Permitting | 50Hertz | 50Hertz | Germany | Germany
|  | #REF! | #REF! | 1627 | Offshore Connection Cluster 6 | OWF Cluster Baltic Sea (DE) | Sanitz/Dettmannsdorf | Subsea Cable | AC | 220 | 2029 | Planned But Not Yet Permitting | 50Hertz | 50Hertz | Germany | Germany
250 | Mera srl (a 100% subsidiary of Repower AG) | "Merchant line ""Castasegna (CH) - Mese (IT)""" | The planned Transmission project is a merchant line on the swiss-italian border between Castasegna (CH) and Mese (IT). The planned Cable connection in 220 kV AC has a length of around 14 km, 13.5 of witch in Italy. In connection with the realisation of the project a Ra-tionalisation of the 380 and 132 kV Grid in the region Mese (Provincia di Sondrio) is planned. The expected NTC increase is around 200-250 MW. | 1384 | "Merchant line ""Castasegna (CH) - Mese (IT)""" | Castasegna | Mese | Underground Cable | AC | 220 | 2021 | In Permitting | swissgrid | Terna | Italy | Switzerland
251 | TenneT-DE | Audorf-Dollern | New 380-kV-line Audorf – Hamburg/Nord – Dollern” in existing 220-kV-corridor. Main focus of the project is the integration of onshore-RES – mainly wind – in Schleswig-Holstein. The project is labeled as PCI 1.4.2. and 1.4.3. It is the southbound connection of PCI 1.4.1. and is necessary to increase the GTC between Dänemark/West and Germany by 720/1000 MW. | 147 | Dollern - Hamburg/Nord | Dollern (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 380 | 2018 | Under Construction | TenneT-DE | TenneT-DE | Germany
|  | #REF! | #REF! | 148 | Audorf - Hamburg/Nord | Audorf (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 380 | 2017 | Under Construction | TenneT-DE | TenneT-DE | Germany
252 | ELIA | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | This project structurally strenghtens the central & eastern part of the internal Belgian backbone. The current conductors on the 380kV ring Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator will be replaced by HTLS conductors, doubling the capacity. The implementation starts with the upgrade of the Massenhoven-VanEyck section by 2024 as this is the weakest link only having 1 conductor at the moment. It then follows a phased approach running up to 2035. Phasing is subject to optimalisation in function of outage constraints (operational secutiry) and the evolution of the production park. | 1050 | HTLS upgrade VanEyck-Gramme | Van Eyck | Gramme | Overhead Line | AC | 380 | 31/12/2029 | Under Consideration | ELIA | ELIA | Belgium
|  | #REF! | #REF! | 1456 | Massenhoven - Van Eyck: HTLS upgrade | Massenhoven (BE) | Van Eyck (BE) | Overhead Line | AC | 380 | 31/12/2024 | Under Consideration | ELIA | ELIA | Belgium
|  | #REF! | #REF! | 1515 | Gramme - Courcelles: HTLS upgrade | Gramme | Courcelles | Overhead Line | AC | 380 | 2033 | Under Consideration | ELIA | ELIA | Belgium
|  | #REF! | #REF! | 1516 | Bruegel - Courcelles: HTLS upgrade | Bruegel | Courcelles | Overhead Line | AC | 380 | 2035 | Under Consideration | ELIA | ELIA | Belgium
|  | #REF! | #REF! | 1517 | Mercator - Bruegel: HTLS upgrade | Mercator | Bruegel | Overhead Line | AC | 380 | 2025 | Under Consideration | ELIA | ELIA | Belgium
253 | RTE | Upstream reinforcement in France to increase FR-CH capacity | The project consists in attracting the flows to the interconnection south of Lake Geneva in order to alleviate the congestion on the link west to Lake Geneva. It is necessary before implementing Project 199 ""Lake Geneva South"" project. This project is coupled with the "PST Foretaille" project and will be implemented right after the implementation of PST in Foretaille. | 1224 | Uprate of Creys-St Vulbas | Creys(FR) | Saint Vulbas (FR) | Overhead Line | AC | 400 | 2031 | Under Consideration | RTE | RTE | France | Switzerland
|  | #REF! | #REF! | 1225 | PST in Cornier | Cornier (FR) | Cornier (FR) | Phase Shift Transformer | AC | 400 | 2031 | Under Consideration | RTE | RTE | France | Switzerland
254 | Amprion;TransnetBW | Ultranet | The Ultranet project consists of a 2 GW HVDC-connection from the Region of Osterath (Rhineland) to the Region of Philippsburg (Baden-Württemberg). It's a pilot project with DC circuits on the same pylons as AC lines and will therefore deliver profund knowledge. | 660 | HVDC Line A South - Ultranet | Osterath (DE) | Philippsburg (DE) | Overhead Line | DC | 400 | 01/01/2021 | In Permitting | Amprion | TransnetBW | Germany
255 | REE | Connection Navarra-Basque Country | New AC OHL 400kV double circuit Ichaso-Castejón/Muruarte 400kV (one circuit Castejon-Ichaso, second circuit Muruarte-Ichaso). This projects allows to solve today and future congestions associated to RES integration. In addition it allows the future connection of the cross border project 276. | 1251 | New line 400 kV Muruarte-Ichaso | Muruarte | Ichaso | Overhead Line | AC | 400 | 2023 | In Permitting | REE | REE | Spain
|  | #REF! |  | 1455 | New line 400 kV Castejon-Ichaso | Castejon | Ichaso | Overhead Line | AC | 400 | 2023 | In Permitting | REE | REE | Spain
256 | Amprion;TENNET-NL | Study to upgrade interconnection DE-NL | Market analysis revealed the need for additional cross-border capacity between Germany and The Netherlands. Therefore, a bilateral study is started to investigate options for a further increase in addition to existing and planned interconnections. | 1252 | Long term upgrade interconnection DE-NL | to be defined (DE) | to be defined (NL) | Overhead Line | AC | 380 | 2040 | Under Consideration | Amprion | TENNET-NL | Germany
|  | #REF! | #REF! | 1529 | Upgrade interconnection DE-NL | tbd | tbd | Phase Shift Transformer | AC | 380 | 2035 | Under Consideration | Amprion | TENNET-NL | Germany
258 | TenneT-DE | Westcoast line | New 380-kV-line Brunsbüttel – Niebül inside Schleswig – Holstein. Main focus of the project is the integration of onshoreRES – mainly wind – in Western Schleswig-Holstein. The project is labeled as PCI 1.3.2. It is the southbound connection of PCI 1.3.1. and is necessary to increase the GTC between Dänemark/West and Germany by 500 MW. | 667 | Brunsbttel - Klixbüll | Brunsbüttel (DE) | Klixbüll (DE) | Overhead Line | AC | 380 | 2019 | In Permitting | TenneT-DE | TenneT-DE | Germany
259 | MAVIR,Transelectrica | HU-RO | 400 kV OHL between Hungary and Romania. In Romania, the following internal investments are necessary associated to this project: -new 400/220 kV transformer in substation Rosiori -reconductoring 220 kV OH line Urechesti-Tg. Jiu-Paroseni- Baru Mare-Hasdat -new 400/220 kV transformer in substation Resita | 1205 | HU-RO | Józsa | Oradea | Overhead Line | AC | 400 | >2030 | Under Consideration | MAVIR | Transelectrica | Hungary | romania
260 | NGIHL;TENNET-NL | New Great Britain - Netherlands interconnection | This project considers the possibility of a second 1- 2GW interconnector between GB and the Netherlands. The project will also consider UK / NL offshore wind connection optionality. | 1255 | Interconnector GB-NL | TBD | TBD | Subsea Cable | DC | 0 | 2030 | Under Consideration | National Grid | TENNET-NL | Great Britain | Netherlands
262 | ELIA; TENNET-NL | Belgium-Netherlands: Zandvliet-Rilland | Bilateral study has assessed multiple reinforcement options. The study concluded that an upgrade of the existing corridor Zandvliet-Rilland via the installation of two additional PSTs in Zandvliet and the upgrade of Zandvliet-Rilland line to high capacity conductors is the most appropriate solution. The constuction of the substation Rilland is part of TenneT's project "Zuid-West 380", id XXX. | 1257 | Belgium-Netherlands: Zandvliet-Rilland | Zandvliet (BE) | Rilland (NL) | Overhead Line | AC | 380 | 2022 | Planned But Not Yet Permitting | ELIA | TENNET-NL | Belgium | Netherlands
263 | Swissgrid, VUEN | Lake Constance East | This project increases the capacity between CH and its neighbours DE and AT. This enables to connect large renewable generation in Northern Europe to consumers and pump storage devices in the Alps, thus noticeably increasing the mutual balancing between both regions. | 1258 | Rüthi - Bonaduz/Mettlen | Rüthi | Mettlen & Bonaduz | Overhead Line | AC | 380 | 2035 | Under Consideration | Swissgrid | Swissgrid | Switzerland | austria | germany
|  | #REF! | #REF! | 1583 | Vorarlberg | Rüthi | Border area (DE-AT) | Overhead Line | AC | 380 | 2035 | Under Consideration | Swissgrid | VUEN | Switzerland | austria | germany
264 | Swissgrid | Swiss Roof I | This project increases the capacity between CH and its neighbours DE and AT. This enables to connect large renewable generation in Northern Europe to pump storage devices in the Alps, thus noticeably increasing the mutual balancing between both regions. | 1259 | Beznau - Mettlen | Beznau | Mettlen | Overhead Line | AC | 380 | 2025 | In Permitting | Swissgrid | Swissgrid | Switzerland | Germany | Austria
|  | #REF! | #REF! | 1284 | Pradella - La Punt | Pradella | La Punt | Overhead Line | AC | 380 | 2021 | Under Construction | Swissgrid | Swissgrid | Switzerland | Germany | Austria
|  | #REF! | #REF! | 1287 | Bassecourt - Mühleberg | Bassecourt | Mühleberg | Overhead Line | AC | 380 | 2025 | In Permitting | Swissgrid | Swissgrid | Switzerland | Germany | Austria
|  | #REF! | #REF! | 1288 | Mettlen - Ulrichen | Mettlen | Ulrichen | Overhead Line | AC | 380 | 2030 | In Permitting | Swissgrid | Swissgrid | Switzerland | Germany | Austria
265 | Swissgrid | Tessin | reinforcement of the infrastructure in canton Tessin | 1290 | Magadino - Ulrichen | Magadino | Ulrichen | Overhead Line | AC | 220 | 2035 | Planned But Not Yet Permitting | Swissgrid | Swissgrid | Switzerland | Switzerland
266 | Swissgrid | Swiss Ellipse I | The project helps accommodate new pump storage units which mainly support the increasing RES generation in the European areas with solar and wind generation. | 1261 | Bickigen - Chippis - Chamoson | Bickigen | Chamoson | Overhead Line | AC | 380 | 2021 | In Permitting | Swissgrid | Swissgrid | Switzerland | Switzerland
|  | #REF! | #REF! | 1285 | Magadino | Magadino | Magadino | Overhead Line | AC | 380 | 2024 | Planned But Not Yet Permitting | Swissgrid | Swissgrid | Switzerland | Switzerland
|  | #REF! | #REF! | 1286 | Chippis - Lavorgo | Chippis | Lavorgo | Overhead Line | AC | 380 | 2024 | In Permitting | Swissgrid | Swissgrid | Switzerland | Switzerland
267 | 50Hertz Transmission, Svenska Kraftnät (SvK) | Hansa PowerBridge II | Possible second HVDC cable interconnector between southern Sweden (Bidding area SE4) and Germany (50Hertz). This project candidate is driven by market based target capacities found in the Common Planning Studies by Regional Group Baltic Sea. | 1262 | Hansa PowerBridge II | Hurva (SE4) | Guestrow (DE) | Subsea Cable | DC | 300 | 2030 | Under Consideration | Svenska Kraftnat | 50Hertz | Sweden | Germany
269 | REE | Uprate the western 220kV Sevilla Ring |  | 1228 | Uprate D.Rodrigo-Aljarafe | D.Rodrigo | Aljarafe | Overhead Line | AC | 220 | 2019 | Under Construction | REE | REE | Spain
|  | #REF! |  | 1229 | Uprate Aljarafe-Santiponce | Aljarafe | Santiponce | Overhead Line | AC | 220 | 2019 | In Permitting | REE | REE | Spain
270 | REE;RTE | FR-ES project -Aragón-Atlantic Pyrenees | This project consist of a new HVDC interconnection between France and Spain located in the Central part of the Pyrenees between Aragón region (Spain) and Marsillón (France). Internal AC reinforcements in Spain complement the cross border section, in order to connect the new converter station to the existing network. This project was included in the 2015 and 2017 PCI list (PCI 2.27.1) | 1211 | HVDC Aragon region -Marsillon | Aragon region | Marsillon | Underground Cable | DC | 320 | 01/01/2026 | Planned But Not Yet Permitting | REE | RTE | Spain | France
|  | #REF! |  | 1212 | New axis Ejea-Aragon region 400 kV | Ejea de los Caballeros | Aragon region | Overhead Line | AC | 400 | 01/01/2026 | Planned But Not Yet Permitting | REE | REE | Spain | France
|  | #REF! |  | 1214 | Ejea de los Caballeros subestation | Ejea de los Caballeros | Ejea de los Caballeros | Substation | AC | 400 | 01/01/2025 | Planned But Not Yet Permitting | REE | REE | Spain | France
|  | #REF! |  | 1215 | Aragon region subestation | Aragon region | Aragon region | Substation | AC | 400 | 01/01/2025 | Planned But Not Yet Permitting | REE | REE | Spain | France
271 | EirGrid, Elia System Operator, Energinet.dk, Creos Luxembourg, National Grid, RTE,TenneT TSO GmbH, SONI, Statnett, TenneT TSO B.V. | "Northern Seas Offshore Grid infrastructure" - a Long Term Conceptual Project | A list of individual projects of the TYNDP projects will develop into a global scheme for Offshore Grid Infrastructure in the Northern Seas. The individual projects will be described one by one on individual project sheets. | 1264 | Investments to be created | 0 | 0 | Overhead Line | DC | 0 | 0 | Under Consideration | 0 | 0
276 | REE;RTE | FR-ES project -Navarra-Landes | This Project consist of a new HVDC interconnection between France and Spain in the Western part of the Pyrenees between Pamplona area (Spain) and Cantegrit (France). The project is considered as a HVDC project of 2x1000 MW. Internal reinforcements complement the cross border section. This project was included in the 2015 and 2017 PCI list (PCI 2.27.2) | 1206 | HVDC Pamplona area -Cantegrit | Pamplona area | Cantegrit | Underground Cable | DC | 320 | 01/12/2026 | Planned But Not Yet Permitting | REE | RTE | Spain | France
|  | #REF! |  | 1207 | Upgrade Cantegrit-Saucats | Cantegrit | Saucats | Overhead Line | AC | 400 | 2026 | Planned But Not Yet Permitting | RTE | RTE | Spain | France
|  | #REF! |  | 1208 | Upgrade Cantegrit-Marsillon | Cantegrit | Marsillon | Overhead Line | AC | 400 | 2026 | Planned But Not Yet Permitting | RTE | RTE | Spain | France
|  | #REF! |  | 1210 | New substation Pamplona area | Pamplona area | Pamplona area | Substation | AC | 400 | 01/01/2026 | Planned But Not Yet Permitting | REE | REE | Spain | France
280 | ELIA; RTE | FR-BE III: study Lonny-Achene-Gramme | The project aims at sustaining further market integration within the long-term perspective of the energy transition and subsequent need to develop interconnection capacity on the French-Belgium border whilst alleviating Lonny-Achene-Gramme as bottleneck. The reinforcement strategy consists of maximizing the potential of the 400kV interconnector Lonny-Achene-Gramme (1 circuit) through the use of cost-efficient technologies such as PSTs and HTLS as well as the possibility to rebuild Lonny-Achene-Gramme as a 2-circuit solution. The bilateral study will determine the appropriate implementation option and phasing of this implementation (for example: first install a PST, then upgrade the line capacity), taking into account 1) the interaction between the 400kV interconnectors Avelin-Avelgem-Horta & Lonny-Achene-Gramme in optimizing interconnection capacity 2) the required time to implement the solution 3) that by 2025 Lonny-Achene-Gramme is a structural bottleneck due to the planned nuclear phase out in Belgium | 1008 | Study Lonny-Achene-Gramme | Lonny (FR) | Gramme (BE) | Phase Shift Transformer | AC | 400 | 2025-2030 | Under Consideration | RTE | ELIA | France | Belgium
283 | TuNur Limited | TuNur | TuNur is aimed to connect to the European network a Concentrated Solar Power plant with storage to be located in Rejim Maatoug, Kebili, Tunisia, with an overall capacity exceeding 2000 MW. The connection point to the ENTSO-E network is located in Montalto di Castro, North of Rome, Italy. The transmission project will comprise: +/- 500 kV DC DC overhead line in Tunisia from the power plant to the shoring point, submarine cables from the Tunisian Northern coast to Montalto di Castro, VSC HVDC converter stations at both terminal points, short 400 kV AC cables from the HVDC converter in Montalto to Terna 400 kV station. No sea electrode is forecast. | 1378 | TuNur DC | Rejim Maatoug (TN) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Subsea Cable | DC | 500 | 2025 | In Permitting | TuNur Limited | TuNur Limited | Tunisia | Italy
|  | #REF! | #REF! | 1430 | TuNur AC | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) Terna station 400 kV AC | Underground Cable | AC | 400 | 2025 | In Permitting | TuNur Limited | Terna | Tunisia | Italy
284 | GreenPower 2020 | LEG1 | LEG1 is a Subsea HVDC Interconnection cable project of minimum 2 000 MW allowing for an electricity exchange between Europe and the South-Eastern Mediterranean Countries. The bidirectional interconnector will link Libya (Tobruk) to Greece (Linoperamata, Crete). LEG1 also comprises the development and operation of a solar power generation plant in Tobrouk. The pilot plant, currently sized at 150 MW, will identify the optimal technological combination to be implemented in the two (2) full-scale power generation plant, 1 000 MW each. Both landing points have been discussed and agreed with GECOL (General Electricity Company of Libya) and ADMIE (Hellenic TSO). LEG1 is currently being evaluated by both Hellenic and Bulgarian authorities to envisage a clustering with an existing Greece-Bulgaria interconnection project. GreenPower2020 and ADMIE are coordinating their efforts to allow for simultaneous commissioning of LEG1 and of the HVDC Crete to Greece mainland interconnector. | 1619 | LEG1 | Tobrouk (Libya) | Linoperamata (Greece, Crete) | Subsea Cable | DC | 400 | 2021 | Planned But Not Yet Permitting | GECOL | ADMIE | Libya | Greece
285 | iCON Infrastructure LLP | GridLink | UK (KIngsnorth sub-station) - France (Warande sub-station) 1.4 GW HVDC (VSC) electricity interconnector Connection points (substations name): Kingsnorth (UK) to Warande (France) Type of conductor: copper/aluminium (stranded or keystone, Mass Impregnated or Cross-Linked Polyethylene) Type of converters (VSC/LCC): Voltage Source Converter (VSC) Nominal voltage: ±525 kV Capacity: 1,400 MW km to each border if the infrastructure is a tie-line: Not applicable (cable length is 160 km from sub-station to sub-station, comprising 112 km in UK territory and 48 km in French territory) Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.5% (33 MW) full load; 0% (0 MW) at zero load Expected yearly unavailability, differentiating between planned and forced outages, and the maximum single failure according to the design: 2% planned outages (98% availability); 0% forced outages; maximum single failure according to the design: 1400MW In case of projects other than in the “under consideration” phase the list and features of the internal reinforcements required to connect the project in the transmission network based on the affected TSO analysis: None Main environmental impact: operational reduction of 1.6m tCO2 emissions per year from transmission of renewable and nuclear power; construction environmental effects during subsea cable installation | 1383 | GridLink | Kingsnorth (UK) | "Warande (Gravelines, France)" | Subsea Cable | DC | 0 | 2022 | Planned But Not Yet Permitting | National Grid | RTE | United Kingdom | France
286 | Element Power | Greenlink | "An interconnector link between Ireland and Wales. Using subsea and onshore underground cables. Connecting EirGrid and National Grid networks / systems. Utilising high voltage direct current subsea and onshore cable. " | 1385 | Greenlink | Great Island | Pembroke | Subsea Cable | DC | 320 | 2023 | Planned But Not Yet Permitting | National Grid | EirGrid | Ireland | United Kingdom
|  | #REF! | #REF! | 1637 | New investment | [7 empty] | Eirgrid | National Grid | Ireland | GB
293 | Kykladika Meltemia SA | Southern Aegean Interconnector | The project refers to the construction of a submarine DC transmission link to connect the licensed RES plants at the South Aegean Sea to mainland Greece and the islands of Crete, Kos and the Dodecanese. The main link will be an HVDC link connecting the island of Levitha to both the metropolitan area of Athens and the island of Crete; the 400kV substation at Lavrion area will be the connection point in the Athens area and Korakia will be the connection point in Crete (located in the north coast). Both links will consist of two parallel cables in order to increase the reliability of each link; two converter stations are foreseen in Levitha and relevant converter stations in Lavrion and Korakia. Illustrative routing of the links is shown in the attached Entso-e map. The capacity of each link will be 600 to 800MW both directions using HVDC (High Voltage Direct Current) technology. VSA conversion technology in conjunction with plastic (XLPE) cables will be used. The licensed RES projects consist of wind and solar power plants located on 23 small uninhabited islands. The link will be used for transmitting electricity from the RES plants mentioned above to the mainland and the island of Crete. More specifically, the power produced in each island will be transferred to the island of Levitha where the main conversion station will be built acting as a hub. These connections (with the other islands) will be AC submarine cables (150 kV or 220 kV). The connection to Crete gives further possibilities for power transmission to Cyprus and further to Israel through the "EuroAsia Interconnector" (already accepted as a PCI by the E.C.). It is also possible to further extend this link to the main islands of the Dodecanese complex (namely Kos, Leros, Kalymnos, Nisyros, Tilos) in order to allow the supply of these islands and at the same time the supply of a complex of other smaller islands already connected to the main ones. This is a short link (10km to 15km long) and more likely it will be an AC one. All the installations on the islands (converter stations, substations etc) will be of closed type using GIS technology. The project increases the transfer capacity between Mainland Greece and Crete-Kos Islands and further on to Cyprus (through EuroAsia Interconnector). The project will provide the system with 1.9 TWh/year wind energy. o List of studies carried out so far for the project;  1. Wind measurements (completed)  2. Wind potential evaluation on the islands (completed)  3. Digital representation of each island terrain/relief (completed)  4. Orthophoto/Photomapping (completed)  5. Topographic drawings (completed)  6. Road Works preliminary design (completed)  7. Ports preliminary design (completed)  8. Desktop study of the cable route between Lavrio and Levitha (completed)  9. Desktop study of the cable route between Levitha and Crete (ongoing)  10. Single Line electrical drawings (competed)  11. Preliminary layout of underground cables. (completed)  12. Enviromental impact assessment (completed) | 1431 | Southern Aegean Interconnector | LAVRIO | LEVITHA | Subsea Cable | DC | 320 | 2024 | In Permitting | yes | no | Greece | Cyprus
293 | Kykladika Meltemia SA | Southern Aegean Interconnector | The project refers to the construction of a submarine DC transmission link to connect the licensed RES plants at the South Aegean Sea to mainland Greece and the islands of Crete, Kos and the Dodecanese. The main link will be an HVDC link connecting the island of Levitha to both the metropolitan area of Athens and the island of Crete; the 400kV substation at Lavrion area will be the connection point in the Athens area and Korakia will be the connection point in Crete (located in the north coast). Both links will consist of two parallel cables in order to increase the reliability of each link; two converter stations are foreseen in Levitha and relevant converter stations in Lavrion and Korakia. Illustrative routing of the links is shown in the attached Entso-e map. The capacity of each link will be 600 to 800MW both directions using HVDC (High Voltage Direct Current) technology. VSA conversion technology in conjunction with plastic (XLPE) cables will be used. The licensed RES projects consist of wind and solar power plants located on 23 small uninhabited islands. The link will be used for transmitting electricity from the RES plants mentioned above to the mainland and the island of Crete. More specifically, the power produced in each island will be transferred to the island of Levitha where the main conversion station will be built acting as a hub. These connections (with the other islands) will be AC submarine cables (150 kV or 220 kV). The connection to Crete gives further possibilities for power transmission to Cyprus and further to Israel through the "EuroAsia Interconnector" (already accepted as a PCI by the E.C.). It is also possible to further extend this link to the main islands of the Dodecanese complex (namely Kos, Leros, Kalymnos, Nisyros, Tilos) in order to allow the supply of these islands and at the same time the supply of a complex of other smaller islands already connected to the main ones. This is a short link (10km to 15km long) and more likely it will be an AC one. All the installations on the islands (converter stations, substations etc) will be of closed type using GIS technology. The project increases the transfer capacity between Mainland Greece and Crete-Kos Islands and further on to Cyprus (through EuroAsia Interconnector). The project will provide the system with 1.9 TWh/year wind energy. o List of studies carried out so far for the project;  1. Wind measurements (completed)  2. Wind potential evaluation on the islands (completed)  3. Digital representation of each island terrain/relief (completed)  4. Orthophoto/Photomapping (completed)  5. Topographic drawings (completed)  6. Road Works preliminary design (completed)  7. Ports preliminary design (completed)  8. Desktop study of the cable route between Lavrio and Levitha (completed)  9. Desktop study of the cable route between Levitha and Crete (ongoing)  10. Single Line electrical drawings (competed)  11. Preliminary layout of underground cables. (completed)  12. Enviromental impact assessment (completed) | 1432 | Southern Aegean Interconnector | LEVITHA | KORAKIA CRETE | Subsea Cable | DC | 320 | 2026 | In Permitting | no | yes | Greece | Cyprus
|  | #REF! | #REF! | 1433 | Southern Aegean Interconnector | Levitha | Syrna | Subsea Cable | AC | 220 | 2025 | In Permitting | no | no | Greece | Cyprus
|  | #REF! | #REF! | 1434 | Southern Aegean Interconnector | KINAROS | LEVITHA | Subsea Cable | AC | 220 | 2024 | In Permitting | no | no | Greece | Cyprus
|  | #REF! | #REF! | 1435 | Southern Aegean Interconnector | Kandeliousa | Syrna | Subsea Cable | AC | 220 | 2025 | In Permitting | no | no | Greece | Cyprus
|  | #REF! | #REF! | 1436 | Southern Aegean Interconnector | Kandeliousa | Pergousa | Subsea Cable | AC | 220 | 2025 | In Permitting | no | no | Greece | Cyprus
294 | Element Power | Maali | An interconnector link between Shetland Scotland UK and Norway. Using subsea and onshore underground cables. Connecting Statnett and National Grid networks / systems. Utilising high voltage direct current subsea and onshore cable. | 1356 | Maali | Kergord Shetland | tba e.g. Mongstad, Kollsnes, Fana | Subsea Cable | DC | 320 | 2025 | Under Consideration | NGT/Scottish Hydro | Statnett | United Kingdom | Norway
297 | ELIA | BRABO II + III | Realization of a new 380 kV corridor between Zandvliet and Mercator consisting of a double-circuit AC overhead line, including a new substation 380kV in Lillo. | 445 | BRABO II: Zandvliet - Lillo - Liefkenshoek | Zandvliet | Lillo - Liefkenshoek | Overhead Line | AC | 380 | 31/12/2020 | Under Construction | ELIA | ELIA | Belgium
|  | #REF! | #REF! | 604 | BRABO III: Liefkenshoek - Mercator | Liefkenshoek (BE) | Mercator (BE) | Overhead Line | AC | 380 | 01/01/2023 | In Permitting | ELIA | ELIA | Belgium
|  | #REF! | #REF! | 605 | BRABO II: Lillo 380 | Lillo (BE) | Lillo (BE) | Substation | AC | 380 | 31/03/2019 | Under Construction | ELIA | ELIA | Belgium
299 | Terna; EDF | SACOI3 | New HVDC line between Italy mainland, Corsica and Sardinia replacing existing link SACOI2 | 1458 | SACOI3 | Codrongianos - Lucciana | Suvereto | Subsea Cable | DC | 200 | 2023 | In Permitting | TERNA - EDF | TERNA | Italy | France
309 | Meridiam, Greenage Power, Frontier Power. | NeuConnect | NeuConnect will be the first subsea HVDC electricity interconnector to connect the GB and German electricity markets. It will be approximately 680km long with a capacity of 1.4GW. | 1628 | NeuConnect Interconnector | Grain 400kV s/s Kent, England | Fedderwarden 380kV s/s Germany | Subsea Cable | DC | 500 | 2022 | Planned But Not Yet Permitting | National Grid | Tennet Germany | United Kingdom | Germany
312 | APG | St. Peter - Tauern (AT internal) | St. Peter - Tauern | 1472 | St. Peter - Tauern (AT internal) | St. Peter | Tauern | Overhead Line | AC | 380 | 2022 | In Permitting | APG | APG | Austria
313 | TenneT-DE; APG | Isar/Altheim/Ottenhofen (DE) - St.Peter (AT) | New 380kV Line between TenneT-DE and APG (Isar/Altheim/Ottenhofen - St. Peter). This project reinforces the interconnection capacity between Austria and Germany. It supports the interaction of RES in Northern Europe (mainly in Germany) and in the eastern part of Austria with the pump storages in the Austrian Alps and therewith facilitates their utilisation. | 1473 | Isar/Altheim/Ottenhofen - St. Peter | Isar/Altheim/Ottenhofen (DE) | St. Peter (AT) | Overhead Line | AC | 380 | 2021 | In Permitting | TenneT-DE | APG | Germany | Austria
316 | ELES | Upgrade of 220 kV line Bericevo-Divaca to 400 kV | Upgrade of existing 220 kV OHL Bericevo-Divaca to 400 kV voltage level (approximate length 80 km). | 1617 | Upgrade of 220 kV line Divaca-Bericevo to 400 kV | Divaca | Bericevo | Overhead Line | AC | 400 | 2030 | Under Consideration | ELES | ELES | Slovenia
317 | ELES | Upgrade of 220 kV line Podlog-Bericevo to 400 kV | Upgrade of existing internal 220 kV OHL Podlog-Beričevo to 400 kV voltage level (approximate length 63 km). | 1615 | Upgrade of internal 220 kV line Podlog-Bericevo to 400 kV | Podlog | Bericevo | Overhead Line | AC | 400 | 2035 | Under Consideration | ELES | ELES | Slovenia
318 | ELES | Upgrade of 220 kV line Podlog-Cirkovce to 400 kV | Upgrade of existing internal 220 kV OHL Podlog-Cirkovce to 400 kV voltage level (approximate length 50km). | 1614 | Upgrade of 220 kV line Podlog-Cirkovce to 400 kV | Podlog | Cirkovce | Overhead Line | AC | 400 | 2035 | Under Consideration | ELES | ELES | Slovenia
320 | ELES; MAVIR; HOPS | Slovenia-Hungary/Croatia interconnection | The project consists of a new 80 km double circuit AC 400 kV overhead line Cirkovce-Pince and a new 400 kV Cirkovce substation (Slovenia) by which a new connection to one circuit of the existing double circuit interconnection line between Hungary and Croatia will be established. | 1558 | Double 400 kV OHL Cirkovce(SI)-Heviz(HU)/Zerjavinec(HR) | Cirkovce (SI) | Heviz (HU) \ Zerjavinec (HR) | Overhead Line | AC | 400 | 2018 | In Permitting | ELES | MAVIR; HOPS | Slovenia | Hungary | Croatia
321 | Amprion | Herbertingen - Tiengen | reinforcements of 380 kV lines between Herbertingen and Tiengen | 1475 | Herbertingen - Tiengen | Herbertingen | Tiengen | Overhead Line | AC | 380 | 2025 | Planned But Not Yet Permitting | Amprion | Amprion | Germany
322 | Amprion, VUEN | Wullenstetten - Border Area (DE-AT) | - | 1476 | Wullenstetten - Border Area (DE-AT) | Wullenstetten (DE) | Austrian National border (AT) | Overhead Line | AC | 380 | 2020 | In Permitting | Amprion | Amprion / VUEN | Germany | Austria
|  | #REF! | #REF! | 1477 | Herbertingen - Neuravensburg | Herbertingen | Neuravensburg | Overhead Line | AC | 380 | 2030 | Planned But Not Yet Permitting | Amprion | Amprion | Germany | Austria
323 | Adria Link Srl, E3 d.o.o., HSE d.o.o.. | Dekani (SI) - Zaule (IT) interconnection | The Zaule (IT) - Dekani (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Zaule (IT) substation to Dekani (SI) substation, including a 110/135 kV Phase Shifter Transformer. | 1478 | Dekani (SI) - Zaule (IT) interconnection | DEKANI | ZAULE | Underground Cable | AC | 110 | 2020 | In Permitting | ELES D.O.O. | TERNA SPA | Slovenia | Italy
324 | Adria Link Srl, E3 d.o.o., HSE d.o.o.. | Redipuglia (IT) - Vrtojba (SI) interconnection | The Redipuglia (IT) - Vrtojba (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Redipuglia (IT) substation to Vrtojba (SI) substation, including a 110/135 kV Phase Shifter Trasformer. | 1482 | Redipuglia (IT) - Vrtojba (SI) Interconnection | REDIPUGLIA | VRTOJBA | Underground Cable | AC | 110 | 2020 | In Permitting | TERNA SPA | ELES D.O.O. | Italy | Slovenia
325 | APG; TERNA; ELES | AT, SI, IT - South-East Alps Project | - Obersielach - Podlog (AT-SI) | 1483 | Upgrade Obersielach (AT) - Podlog (SI) | Obersielach (AT) | Podlog (SI) | Overhead Line | AC | 380 | 2035-2040 | Under Consideration | APG | ELES | Austria | Slovenia
|  | #REF! | - Lienz - Italy (AT - IT) | 1631 | Lienz - Italy (AT - IT) | Lienz | Veneto Region | Overhead Line | AC | 380 | 2035-2040 | Under Consideration | Terna | APG | ITALY | Austria
|  | #REF! | - Lienz - Obersielach | 1636 | Lienz - Obersielach | Lienz (AT) | Obersielach (AT) | Overhead Line | AC | 380 | 2026/27 | Planned But Not Yet Permitting | APG | APG | Austria
328 | Amprion, Creos Luxembourg | Interconnector DE-LUX | The project comprises the construction of two new 380-kV-substations in Germany (Aach) and Luxemburg (Bofferdange). The new substations will be connected via a new AC-link to allow a higher cross border capacity between Germany and Luxembourg. | 1620 | Substation Aach | N/A | N/A | Substation | AC | 400 | 2025 | Planned But Not Yet Permitting | Amprion | N/A | Germany
|  | #REF! | #REF! | 1629 | Substation Bofferdange | N/A | N/A | Substation | AC | 400 | 2025 | Planned But Not Yet Permitting | Creos Luxembourg | N/A | Luxembourg
|  | #REF! | #REF! | 1630 | AC Overhead Line Aach-Bofferdange | Aach (DE) | Bofferdange (LU) | Overhead Line | AC | 400 | 2026 | Planned But Not Yet Permitting | Amprion | Creos Luxembourg | Germany | Luxembourg
329 | ELIA | Stevin-Izegem/Avelgem (Kustlus): new corridor | The development of ~6 GW transport capacity through the elaboration of a new corridor in the western part of Belgium, between the Stevin axis and the Izegem/Avelgem substation. Should the corridor end in Izegem, it is to be complemented with an HTLS upgrade of the existing Izegem-Avelgem connection. Along this corridor a substation functioning as 'gateway' for the evacution of offshore potential (see for example project 120) is envisioned. This corridor is envisioned to be implemented in AC technology as per the example of the Stevin project. Timing, routing, scope, etc. subject to feasibility studies and subsequent spatial planning procedures. | 1518 | Stevin-Izegem/Avelgem: new corridor | Stevin | Avelgem | Overhead Line | AC | 380 | 2028 | Under Consideration | ELIA | ELIA | Belgium
330 | CEPS,SEPS | 4th 400kV CZ-SK interconnector | This new 400 kV cross-border overhead line between the substations Otrokovice (CZ) - Ladce (SK) will strenghten the transmission capacity between Slovak and Czech transmission systems, aiming to maintain secure operation of both transmission systems. | 1498 | New CZ-SK 400 kV interconnector | Otrokovice (CZ) | Ladce (SK) | Overhead Line | AC | 400 | 2035 | Under Consideration | CEPS | SEPS | Czech Republic | slovakia
|  | #REF! | #REF! | 1499 | New 400 kV substation Ladce | Ladce (SK) | Ladce (SK) | Substation | AC | 400 | 2027 | Planned But Not Yet Permitting | SEPS | SEPS | Slovakia
333 | Swissgrid | PST Foretaille | Installation of two PSTs in Foretaille that control the flow on the Foretaille - Verbois 220 kV double line | 1496 | PST Foretaille | Foretaille | Foretaille | Phase Shift Transformer | AC | 220 | 2031 | Under Consideration | Swissgrid | Swissgrid | France | Switzerland
335 | TenneT-NL, Energinet, TenneT-DE | North Sea Wind Power Hub | This project is a building block in this modular hub-and-spoke concept connecting up to 12 GW future offshore wind Projects to the systems of Denmark, the Netherlands and Germany after 2035. On the offshore hub, interconnection capacity between these countries is created by connecting the transport capacity between the hub and countries in a "copper plate" type installation. TenneT Netherlands, TenneT Germany, Energinet and Gasunie joined forces to develop a large scale European electricity system for offshore wind in the North Sea. The North Sea Wind Power Hub (NSWPH) consortium partners consider the project to be an important possible alternative path of internationally coordinated roll-out towards accomplishing the green energy transition and achieving the Paris Agreement. By developing the North Sea Wind Power Hub project, the NSWPH consortium endeavours to make the energy transition both feasible and affordable. Central to the vision is the construction of one or more hubs at a suitable location in the North Sea with interconnectors to bordering North Sea countries. The whole system may function as a hub for transport of wind energy, an interconnection hub to the connected countries, a working hub for offshore wind developers and a location for possible Power to Gas solutions. As such the NSWPH infrastructure offers benefits by optimizing integration costs of offshore wind, increasing socio-economic welfare by further integrating energy markets, supporting security of supply at wider regional level, and providing potential for innovative power-to-gas concepts to optimize system energy costs. | 1504 | Power Link Island | 0 | 0 | Substation | AC | 0 | 2035-2040 | Under Consideration | TenneT-NL, Energinet, TenneT-DE | TenneT-NL, Energinet, TenneT-DE | Netherlands | denmark | Germany
|  | #REF! | #REF! | 1505 | Interconnection DKw to Power Link Island | Endrup, DKw | Power Link Island DKw | Subsea Cable | DC | 0 | 2035-2040 | Under Consideration | Energinet | Energinet | Netherlands | denmark | Germany
|  | #REF! | #REF! | 1506 | Interconnection NL Maasvlakte to Power Link Island | Maasvlakte 380 kV | Power Link Island NL1 | Subsea Cable | DC | 0 | 2035-2040 | Under Consideration | TenneT TSO NL | TenneT TSO NL | Netherlands | denmark | Germany
|  | #REF! | #REF! | 1507 | Interconnection NL Eemshaven to Power Link Island | Eemshaven 380 kV | Power Link Island NL2 | Subsea Cable | DC | 0 | 2035-2040 | Under Consideration | TenneT TSO NL | TenneT TSO NL | Netherlands | denmark | Germany
|  | #REF! | #REF! | 1508 | Interconnection DE (area of Brunsbüttel) to Power Link Island | German substation located in the area of Brunsbüttel (north of the Elbe) | Power Link Island DE1 | Subsea Cable | DC | 0 | 2035-2040 | Under Consideration | TenneT-DE | TenneT-DE | Netherlands | denmark | Germany
|  | #REF! | #REF! | 1509 | Interconnection DE (area of Oldenburg) to Power Link Island | German substation located in the area of Oldenburg | Power Link Island DE2 | Subsea Cable | DC | 0 | 2035-2040 | Under Consideration | TenneT-DE | TenneT-DE | Netherlands | denmark | Germany
|  | #REF! | #REF! | 1511 | Interconnection DE (area of Krümmel) to Power Link Island | German substation located in the area of Krümmel | Power Link Island DE3 | Subsea Cable | DC | 0 | 2035-2040 | Under Consideration | TenneT-DE | TenneT-DE | Netherlands | denmark | Germany
336 | Terna; Tinetz | Prati (IT) – Steinach (AT) | New Italy-Austria tie-line between the existing 110kV Steinach substation in Austria and 132 kV Brennero substation, including PST; and connection to 132 kV Prati di Vizze substation. | 1556 | Prati (IT) – Steinach (AT) | Prati di Vizze (IT) | Steinach (AT) | Overhead Line | AC | 132 | 2019 | Under Construction | TERNA | TINETZ | ITALY | Austria
337 | Amprion; TenneT-DE | Conneforde-Merzen | The project consists of a new 380-kV overhead line between Merzen and Cloppenburg. North Germany is characterised by a high amount of RES, the feed-in exceeds the local load and therefore there is a high demand for transfer to the load centres in western and southern parts of Germany. With the further installation of additional offshore wind energy, the relevance of this projects increases. | 1510 | Cloppenburg East - Merzen | Cloppenburg East (DE) | Merzen (DE) | Overhead Line | AC | 380 | 2023 | Planned But Not Yet Permitting | TenneT-DE | Amprion | Germany
|  | #REF! | #REF! | 1512 | Conneforde - Cloppenburg | Conneforde (DE) | Cloppenburg (DE) | Overhead Line | AC | 380 | 2023 | Planned But Not Yet Permitting | TenneT-DE | TenneT-DE | Germany
338 | TERNA | Adriatic HVDC link | new HVDC line between Villanova and Fano existing 400 kV substations | 1521 | New HVDC line between Villanova and Fano existing 400 kV substations | Villanova | Fano | Subsea Cable | DC | 500 | 2027 | Under Consideration | Terna | Terna | Italy
339 |  | Italian HVDC tri-terminal link | Italian HVDC tri-terminal link | 1557 | Italian HVDC tri-terminal link | SARDINIA REGION | SICILY REGION - CENTRAL SOUTH OF ITALY | Subsea Cable | DC | 0 | 2027 | Under Consideration | TERNA | TERNA | Italy
340 | ELIA | Avelgem-Center: new corridor | The development of ~6 GW transport capacity through the elaboration of a new corridor between the Avelgem substation and the center of the Belgium (substation to be determined along the axis Bruegel-Courcelles). This corridor is envisioned to be implemented in AC technology as per the example of the Stevin project. Timing, routing, scope, etc. subject to feasibility studies and subsequent spatial planning procedures. | 1519 | Avelgem-Center: new corridor | Avelgem | Center (TBD) | Overhead Line | AC | 380 | 2028 | Under Consideration | ELIA | ELIA | Belgium
341 | EMS, Transelectrica | North CSE Corridor | This project will consists of three investments. The investments of this project are SS 400/110 Belgrade West, OHL 400 kV SS Belgrade West - WPP Cibuk and doubling existing OHL 400 kV Portile de Fier (RO) - Resica (RS). All investment from this project has significance cross-border impact on border between Romania and Serbia. | 1536 | Portile de Fier (RO) - Djerdap (RS) 2nd | Portile de Fier | Djerdap | Overhead Line | AC | 400 | 2030 | Under Consideration | Transelectrica | EMS | Serbia
|  | #REF! | #REF! | 1537 | New SS 400/110 kV Belgrade West | Belgrade West | Belgrade West | Substation | AC | 400 | 2030 | Under Consideration | EMS | EMS | Serbia
|  | #REF! | #REF! | 1538 | New OHL 400 kV WPP Cibuk - SS Belgrade West | WPP Cibuk | Belgrade West | Overhead Line | AC | 400 | 2030 | Under Consideration | EMS | EMS | Romania | serbia
342 | EMS, ESO | Central Balkan Corridor | This corridor will enable transmission energy from east to west on the border between Bulgaria and Serbia. It consists of several investments from SS Sofia West on the east to SS Bajina Basta. On that way this corridor will be directly connected with project Transbalkan corridor. | 1520 | Sofia West (BG) - Nis 2 (RS) 2nd | SS Sofia West | SS Nis 2 | Overhead Line | AC | 400 | 2034 | Under Consideration | ESO | EMS | Bulgaria | serbia
|  | #REF! | #REF! | 1522 | Upgrade of exsisting OHL 220 kV to 400 kV SS Nis 2 - SS Kruševac 1 | SS Nis 2 | SS Krusevac 1 | Overhead Line | AC | 400 | 2034 | Under Consideration | EMS | EMS | Bulgaria
|  | #REF! | #REF! | 1523 | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | SS Krusevac 1 | SS Krusevac 1 | Substation | AC | 400 | 2034 | Under Consideration | EMS | EMS | Serbia
|  | #REF! | #REF! | 1524 | Upgrading of exsisting OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | SS Krusevac 1 | SS Kraljevo 3 | Overhead Line | AC | 400 | 2034 | Under Consideration | EMS | EMS | Serbia
|  | #REF! | #REF! | 1525 | Uprading exsisting OHL 220 kV to 400 kV SS Kraljevo 3 - Vardiste | EMS | EMS | Overhead Line | AC | 400 | 2033 | Under Consideration | EMS | EMS | Serbia
343 | HOPS, NOS BIH | CSE1 New | The project will contribute in strengthen Croatian transmission grid along its main north-south axis (in parallel with eastern Adriatic coast) allowing for additional long-distance power transfers (including cross border) from existing and new planned power plants (RES/wind/ and conventional/hydro and thermal/) in Croatia (coastal parts) and BiH to major consumption areas in Italy (through Slovenia) and north Croatia. The increased transfer capacity will support market integration (particularly between Croatia and Bosnia-Herzegovina) by improving security of supply (also for emergency situations), achieving higher diversity of supply&generation sources and routes, increasing resilience and flexibility of the transmission network | 1532 | New OHL 400 kV Banja Luka - Lika | Banja Luka (BA) | Lika (HR) | Overhead Line | AC | 400 | 2030 | Planned But Not Yet Permitting | NOS BIH | HOPS | Croatia | Bosnia & Herzegovina
|  | #REF! | #REF! | 1533 | New OHL 400 kV Lika – Melina | Lika (HR) | Melina (HR) | Overhead Line | AC | 400 | 2030 | Planned But Not Yet Permitting | HOPS | HOPS | Croatia | Bosnia & Herzegovina
|  | #REF! | #REF! | 1534 | New OHL 400 kV Lika – Konjsko | Lika (HR) | Konjsko (HR) | Overhead Line | AC | 400 | 2030 | Planned But Not Yet Permitting | HOPS | HOPS | Croatia | Bosnia & Herzegovina
|  | #REF! | #REF! | 1535 | New Substation 400/110 kV Lika | Lika (HR) | Lika (HR) | Substation | AC | 400 | 2029 | Planned But Not Yet Permitting | HOPS | HOPS | Croatia
344 | TENNET-NL | Reinforcements Ring NL phase II | Upgrade of existing 380kV circuits from 2,5 kA to 4 kA | 1541 | Zwolle-Hengelo-Doetinchem-Dodewaard | Zwolle | Dodewaard | Overhead Line | AC | 380 | 2035 | Under Consideration | TENNET-NL | TENNET-NL | Netherlands
345 | TENNET-NL | Northern East-West connection NL | New double circuit 380 kV connection between the North East and Western part of the Netherlands. | 1542 | Northern East-West connection NL | tbd | tbd | Overhead Line | AC | 0 | 2040 | Under Consideration | TENNET-NL | TENNET-NL | Netherlands
346 | TENNET-NL | ZuidWest380 NL | New 380 kV connection between Borssele and Tilburg, including new 380 kV substations Rilland and Tilburg. | 1543 | ZuidWest380 West | Borssele | Rilland | Overhead Line | AC | 380 | 2021 | Under Construction | TENNET-NL | TENNET-NL | Netherlands
|  | #REF! | #REF! | 1544 | ZuidWest3808 Oost | Rilland | Tilburg | Overhead Line | AC | 380 | 2025 | In Permitting | TENNET-NL | TENNET-NL | Netherlands
347 | TENNET-NL | Maasvlakte – Noord Brabant connection NL | New double circuit 380 kV connection between the Maasvlakte and Noord-Brabant area within the Netherlands | 1545 | Maasvlakte – Noord Brabant connection | Krimpen | Geertruidenberg | Overhead Line | AC | 0 | 2040 | Under Consideration | TENNET-NL | TENNET-NL | Netherlands
348 | TENNET-NL | NoordWest380 NL | Upgrade of existing 220kV circuits between Eemshaven and Vierverlaten to 2* 380kV – 2645MVA circuits | 1546 | NoordWest380 | Eemshaven Oude Schip | Vierverlaten | Overhead Line | AC | 380 | 2021 | Under Construction | TENNET-NL | TENNET-NL | Netherlands
350 | MEPSO | South Balkan Corridor | Тhis project consists of three investments: one 400 kV OHL Bitola(MK)- Elbasan(AL), and two 400 kV SS Ohrid and Kumanovo, in Macedonia. The interconnection contributes to increasing the transmission capacity in the East-West direction. Мentioned two SS-s will increase the security of supply in the SouthWest part of the FYR of Macedonia. Construction of 400 kV OHTL interconnection from SS Bitola 2 to Macedonian/Albanian border and SS 400/110 kV Ohrid 400 kV interconnection transmission line Bitola (Macedonia) - Elbasan (Albania) is the last part of the implementation of the Corridor 8 in the context of creating a corridor East-West power transmission corridor between Bulgaria, Macedonia, Albania and Italy. | 1622 | 400kV OHL SS Bitola - SS Elbasan | Bitola | Elbasan | Overhead Line | AC | 400 | 2020 | In Permitting | MEPSO | OST | FYR of Macedonia | Albania
|  | #REF! | #REF! | 1623 | 400 kV SS Ohrid |  |  | Substation | AC | 400 | 2020 | In Permitting | MEPSO |  | FYR of Macedonia
|  | #REF! | #REF! | 1624 | 400 kV SS Kumanovo |  |  | Substation | AC | 400 | 2030 | Under Consideration |  |  | FYR of Macedonia
351 | NGET; SHETL | Eastern HVDC Link | A new ~2GW submarine HVDC cable route from Peterhead to Hawthorn Pit with associated AC network reinforcement works at both ends | 1547 | Eastern HVDC Link | Peterhead (GB) | Hawthorn Pit (GB) | Subsea Cable | DC | 500 | 2024 | Under Consideration | SHETL | NGET | United Kingdom
375 | TERNA; APG | Lienz (AT) - Veneto region (IT) 220 kV | Reconstruction of the existing 220kV-interconnection line between Lienz and Veneto Region (IT) | 1555 | Lienz (AT) - Veneto region (IT) | Lienz (AT) | Veneto region (IT) | Overhead Line | AC | 220 | 2024 | In Permitting | APG | TERNA | Italy | Austria
376 | MEPSO(MK), IPTO(GR) | Refurbishment of the 400kV Meliti(GR)-Bitola(MK) interconnector | The project aims at the reconductoring of the already existing 400kV interconnector between Meliti(GR) and Bitola(MK), in order to increase transfer capacity of the interconnector. | 1559 | New investment | Bitola (MK) | Meliti (GR) | Overhead Line | AC | 400 | 2030 | Under Consideration | MEPSO | IPTO | Greece | macedonia
377 | Elia, TENNET-NL | Upgrade BE-NL interconnector VanEyck-Maasbracht | This study envisions an upgrade of the existing interconnector VanEyck-Maasbracht between Belgium and the Netherlands making use of PSTs and/or HTLS technology. The study will determine the appropriate implementation option and timing, taking into account - The already planned upgrade of the Zandvliet-Rilland interconnector on the BE-NL border (see project 262) - The synchronisation with project study to upgrade interconnection DE-NL, also currently under consideration (see project 256) | 1561 | BE-NL interconnector: upgrade VanEyck-Maasbracht | VanEyck | Maasbracht | Overhead Line | AC | 380 | 2030 | Under Consideration | Elia | TENNET-NL | Belgium | netherlands
378 | REE | Transformer Gatica | New tranformer 400/220 kV in existing Gatica subestation, with potential impact in cross border values | 1584 | Transformer Gatica | Gatica 400 | Gatica 220 | Substation | AC | 220 | 2025 | Planned But Not Yet Permitting | REE | REE | Spain
379 | REE | Uprate Gatica lines | Uprate of the following 400kV lines that reach Gatica subestation : Gatica-Gueñes, Gatica-Amorebieta-Ichaso and Gatica-Azpeitia, with potential impact in cross border values | 1593 | Uprate Gatica-Guenes | Gatica | Guenes | Overhead Line | AC | 400 | 2025 | Under Consideration | REE | REE | Spain
|  | #REF! |  | 1595 | Uprate Gatica-Amorebieta-Ichaso | Gatica | Ichaso | Overhead Line | AC | 400 | REE | Under Consideration | REE | REE | Spain
|  | #REF! |  | 1597 | Uprate Gatica-Azpeitia | Gatica | Azpeitia | Overhead Line | AC | 400 | 2025 | Under Consideration | REE | REE | Spain
S T O R A G E P R O J E C T S
Project ID | Promtor | Project Name | Description | Type Of Storage |  | Connection Point | Country | Connection Point Voltage | Status | Commissioning Date | Storage Unit LifeTime
1000 | Bernegger GmbH+C2:C4 | Hydro Pump Storage Power Plant Pfaffenboden in Molln | The Hydro Pump Storage Power Plant Pfaffenboden in Molln will have an installed capacity of +300/-329 MW that is provided by 2 reversible Francis-Pump-Turbines. The average annual net generation capacity is about 600 GWhours/year. The power plant offers a full flexible controllrange as a Full-Size-Converter (FSC) and a hydraulic short are installed (state of the art). The upstream storage consists of 4 in-ground tunnles with a total volume of 1.24 Mio.m³ (1,5 km length and 16m diameter each). The power unit is as well located in an in-ground shaft. The Volume of the Downstream-Storage is 1.4 Million m³ and is located in a former gravel-pit. The total storage capacity is 2,4 GWh Operation hours at full load: 6h (turbine-mode) 8h (pump-mode) There is no natural inflow – the plant runs a closed-water loop. The power-to-power efficiency is at least 75%. The nominal head is up to 650 m. The plant is designed to operate with day ahead, intraday and balancing electricity The implantation of additional storage capacities – as it is provided with this promoted project - is an essential part to reach the EU’s energy and climate targets to ensure the current level of security of supply as well as the system stability& flexibility. | Hydro Pump Storage | Total Storage Capacity | Transmission Substation Molln (to be built) | Austria | 220 | Under Construction | 2021 | more than 90 years
1001 | tiwag.at | Kaunertal Extension Project | "Extension of the existing Kaunertal hydro storage power station by: the new pumped hydro storage power station Versetz and the new reservoir Platzertal including new water intakes, the additional power stations Prutz 2, Imst 2 and Haiming. " Storage capacity: 64 GWh related to Versetz and 152 GWh related to Prutz 2. The round trip efficiency of 75,4% is related to the storing function at KW Versetz. The total efficiency of all power stations of the "Kaunertal Extention project" referring to an additional generation by additional natural inflow of 787 GWh/a will be 89,5%. Project description and in particular technical design data have been unchanged related to TYNDP 2016 and are used also for the TYNDP 2018 process. However, compared to our last application RES-E generation from natural inflow has been reduced by legal reasons. The "Kaunertal Extension project" is considered within the national network development plan of Austrian Power Grid AG (APG) as documented in pages 25 and 41 of the document "Netzentwicklungsplan 2016". (Draft Netzentwicklungsplan2017: pages 30, 44). The values reported as "Installed Generating Capcity" are referring to the whole project, the values refere to the pumping station KW Versetz, whereas the value for "Installed Electrical Storage Minimum Acrtive Power" (93 MW) represents the value referring to one unit of in total four units. | Pumped Hydro Storage | 1.8 | UW Prutz (220 kV, 380 kV) 09PRUT21, D7PRUT21 | Austria | 220 | In Permitting | 17.02.2034 | 90
1002 | THV iLand | iLand | "iLand consists in building a innovative hydro-pumped storage facility on an artificial island off the coast of Belgium (approximately 5 km offshore with an imprint of 4 x 2,5 km). iLand should provide a total hydraulic storage capacity of ca. 2,2 GWh, i.e., a total net storage capacity of 2,0 GWh, assuming a 90% efficiency in turbine-mode, and a net annual electricity generation of approximately 750 GWh. Flexible access is being considered due to the specific nature of iLand and its complementarity with offshore wind. iLand would be able to store energy during peak wind periods and inject energy into the grid when there is little wind. iLand is thus not dependent on specific grid enhancements, which could suffer delays. Flexible access also enables TSOs to better maintain security of supply and allows for more efficient grid management. iLand will enable a significant increase in the regional balancing capabilities of the Belgian grid and the grids of the Netherlands and France. Even the UK will benefit from iLand’s balancing properties if it is connected to the pending “NEMO” interconnector between Belgium and the UK. " | Pumped Hydro - Offshore | 152 | Stevin | Belgium | 380 | Planned But not yet Permitting | 2022 | iLand’s expected lifetime is approximately 46 years as a storage unit, which lifetime may be extended by an additional 25 years.
1011 | INGENIERIA PONTIFICIA S.L. | REVERSIBLE PUMPED-STORAGE HYDROELECTRIC EXPLOITATION "MONT- NEGRE" POWER 3,300 MW ZARAGOZA, SPAIN | The Project is located in the Segre River where it flows into the Ebro River (Mequinenza, Zaragoza). The exploitation works with compensation reservoirs. The upper water pond (Mont-Negre), to be constructed, will have a capacity of 118 Hm3. The pond depth is of 36 m, and its water surface maximum height will be 398 m. above sea level. The upper water pond will have a perimeter dike of 8,050 m and its water surface will be of 330 Has. The lower intake, which is located in the Segre River which has a maximum depth of 64 m above sea level and its height is of 70 m. There is an underground power plant with a length of 502 m and a height of 122 m. It is also fully equipped with medium voltage transformers, alternators and turbines. There are five vertical pipes of 338 m, with a diameter of 13.4 m, between the upper water pond and the power plant, as well as twelve pipes (one per turbine) with a diameter of 5.73 m each. Pipes connecting the power plant to the Segre river are 1,760 m long. The electromechanical equipment includes 12 reversible Francis turbines of 275 MW each. There are 12 synchronous alternators of 300 MVA (generated voltage 20 kV), 48 medium voltage transformers (output voltage 45 kV and unitary power 80 MVA) and a high voltage transformer unit (voltage steps 45/220/400 kV). | Pure Pumping | 2 | Mequinenza – Nueva Mequinenza | SPAIN | 400 | Planned But not yet Permitting | October 2020 | The lifetime is set at 75 years due to the concession of water granted by the Ministry of Agriculture and Fisheries, Food and Environment.
1012 | CDR TREMOR, S.L. | Purifying -Pumped Hydroelectric Energy Storage (P-PHES Navaleo) | "P-PHES NAVALEO in Leon, Spain, is pure pumped plant (CLOSED LOOP) with an installed capàcity of 552 Mw. (3 x 184 Mw.) in generating mode and 548 Mw in pumping mode and generate an annual capacity of 1332 Gwh/year. The projects consists in two reservoirs with a volume of 2,23 Mio m3. The total rated flow are 90 m3/s in generating mode and 70 m3/s in pumping mode. Normal static head is 710 m. The cycle efficiency is up to 77,8%. " Moreover the energy storage, the P-PHES NAVALEO has another 3 IMPORTANT DIMENSIONS: ENVIRONMENTAL: The power plant is integrated in a puryfing cycle of water flowing trough abandoned mines that are currently being directly discharged to the rivers. SOCIAL: Located in the economically depresed region of Castilla y León with unemployment rates of 20% - 30%. P-PHES NAVALEO will contribute to the reintegrationof unemployed professionals ahnd shift to a low carbon regional economy. INNOVATIVE: The Hybrid purification – generation – storage process was awarded a patet by the WIPO for the hihgest ratings to all claims for its novelty, inventiveness and industrial applicability | Hydro Pure Pumped Storage (closed loop) | 75.11 | Electrical Power Substation of Montearenas, property of Red Eléctrica de España, S.A. | Spain | 400 | Planned But not yet Permitting | 30/12/2023 | Over 50 years
1015 | ScottishPower | Cruachan II | Up to 600MW pumped storage hydro facility at Cruachan, Argyll, Scotland | Pumped Storage Hydro | 3.5 | Dalmally, Argyll, Scotland | UK - Scotland | 275 | Under Consideration | 2025 | Cruachan II will have a longer lifetime than the 25 years currently used to compare PCI projects. The existing 440MW Cruachan pumped storage project has been operating effectively for the last 50 years and will continue to operate for many decades to come.
1019 | gruporomeropolo.com | TWO REVERSIBLE HIDROELECTRIC PLANTS: GIRONES & RAIMATS IN SPAIN | GIRONES & RAÏMATS is a reversible hydroelectric plant that has its outlet on the right bank of the Riba-roja reservoir, on the EBRO river, 1.5 km upstream of the dam of the same name. The main characteristic is that it has two upper rafts at different levels: GIRONES with a gross jump of 379 m and RAÏMATS with another of 493 m. This fact allows managing the variability of renewables with RAÏMATS - by managing more energy with less flow and therefore affecting as little as possible the fluctuation of the water surface of the Riba-roja reservoir - leaving GIRONÉS as backup for important needs of secondary and tertiary coverage of the electrical system. The requested flow of 762 m3 / s produces a water level variation of 1.5 m in continuous operation for 8 hours, estimating that this is the maximum stroke compatible with other uses of the reservoir. The design of GIRONÉS & RAÏMATS is based on the one hand on compliance with national and European environmental regulations (both in regard to civil works sites and the 135 km of high voltage lines of 400 Kv to the New SSEE Mequinenza, Peñalba and Osera) and on the other in adjusting to the Planning of REE 2015-2020. For this second reason, two phases in this PCI project have been considered: - GIRONES & RAÏMATS (1st phase) implements an installed power of 1,920 Mw in pumping and 1556 Mw in turbined to fulfill the planning in the horizon 2020. Because the start-up is foreseen for 2025, the total of civil works and facilities is projected by only reducing the number of binary groups destined for the GIRONÉS raft (located in the single cave next to the 4 groups of RAÏMATS) from 6 to 2 units. The energy stored in this first phase is the total expected for the start of operation in 2025 with 34,904 Mwh operating with a maximum flow of 400 m3 / s. The estimated budget is 1,822 M € + VAT. - In GIRONES & RAÏMATS (2nd phase) will be installed only the 4 groups that are missing for GIRONÉS, adding a power of 1,480 Mw in pumping and 1,200 Mw in turbined to complete the total average design power of 3,078 Mw. The operational flow is increased by 360 m3 / s covering the total requested. The budget of this second phase is 185 M € + VAT , being the total € 2,007 M + VAT. At the technical level, two peculiarities stand out that make our geographical position unbeatable for a pumping station (always without affecting the Natura 2000 Network): - The storage capacity can be expanded, modularly, by more than 53,000 Mwh. - The design allows the construction of a lower raft on foot of the Flix reservoir (downstream of the Riba-roja reservoir), to operate in a closed circuit independently of the Ebro river. The energy involved would be 26,600 Mwh in pumping and 21,500 Mwh in turbined. | Hydro | 7.2 | SE "NUEVA MEQUINENZA"; SE "PEÑALBA"; SE "OSERA" | Spain | 400 | Under Consideration | 2025 | 100 years
1025 | Siga Hydro Limited / Roadbridge Ltd. | Silvermines Hydroelectric Power Station | Silvermines Hydroelectric Power Station provides 1.8GWh of storage with 360MW export capacity and 360MW of pumping load. The scheme is located close to the transmission system on an abandoned open-cast mining site and consists of upper and lower reservoirs with capacities of approximately 2.6Mm3 and a head height of 300m. The upper reservoir will be constructed using a gravity dam. The lower reservoir is the existing mining pit which currently contains approximately 1.7Mm3 of water. The preferred design uses 1.1km of surface penstock to convey water from the upper reservoir to a powerhouse built into the side wall of the lower reservoir. Subject to optimisation, the project will have 3 x 120 MW synchronous motor/generators and associated turbines. Synchronous units have been selected to provide system inertia at times of low demand and high wind generation. At least one unit will have the capability to be switched to full frequency converter mode to provide fast frequency containment services. The optimisation and final design of the project will be focussed on the provision of system services for renewables integration. | Pumped Hydro | 24.5 | Shallee Co. Tipperary | Ireland | 220000 | Under Consideration | 2026 | 50 years+
1026 | Donaukraftwerk Jochenstein AG | Hydro pumped storage Riedl | A pumped storage power plant is planned upstream from Jochenstein hydro power plant at the Danube. Drawdown and return of water will be ensured via Danube and a storage lake to be created southwest of Gottsdorf village, approx. 350 m above the live storage of Jochenstein. The upstream water conduit is designed as an inclined shaft. The power shaft will be located in the best possible situation given the encountered geological conditions. The downstream water conduit joins the intake/outlet structure on the Danube underground. Currently, extensive preliminary work is in progress in order to obtain the approval of both the Bavarian and Austrian government agencies. The design of the project will be optimized to include the relocation of the intake/outlet structure to the headwaters of Jochenstein HPP. Among all optimisation options technically and economically assessed, the shaft power plant variant will be pursued. | hydro-pumped storage |  | 220 kV Switchyard Jochenstein | Germany | 220 | In Permitting | 01.01.2025 | ~ 100 years
1027 | CENTRAL DEPURADORA REVERSIBLE DEL RIO CUA, S.L. | P-PHES CUA | P-PHES CUA is an innovative project that combines the power storage by pumping with purifying mine water contaminated with toxic metals. The scheme is as follows: mine waters discharged to the river currently untreated and after homogenization and purification, are introduced into the hydraulic circuit of a pumping plant consisting of 2 tanks dug outside the river with a slope of 322 m. Through the transfer of water between reservoirs by pumping and turbine hereinafter the oxygen needed to precipitate contaminants which are removed periodically and managed in accordance with the rules of residues. Subsequently, the water is returned to the river purified allowing to meet the "good ecological status" under Directive 2000/60/EC Water Framework. Moreover the energy storage, the P-PHES CUA has another 3 IMPORTANT DIMENSIONS: ENVIRONMENTAL: The power plant is integrated in a puryfing cycle of water flowing trough abandoned mines that are currently being directly discharged to the rivers. SOCIAL: Located in the economically depresed region of Castilla y León with unemployment rates of 20% - 30%. P-PHES CUA will contribute to the reintegrationof unemployed professionals ahnd shift to a low carbon regional economy. INNOVATIVE: The Hybrid purification – generation – storage process was awarded a patet by the WIPO for the hihgest ratings to all claims for its novelty, inventiveness and industrial applicability | PURE PUMPING PLANT (Closed loop) |  | SET MONTEARENAS of Red Electrica de España. | SPAIN | 400 | Planned But not yet Permitting | 01/01/2028 | over 50 years
1029 | Dravske elektrarne Maribor d.o.o., Obrezna 170, 2000 Maribor | PSPP Kozjak | Brief technical description of the storage project: type of storage: hydro, pure pumping and turbining The project is designed as continuation of the energy exploitation of the Drava River within the framework of the received concession for energy exploitation of the gross potential of the Drava River. The objective of the project is to generate high quality level peak energy during the time of daily consumption peaks, it will also be important for the needs of fast reserve in the grid and for the systems of primary and secondary regulation and voltage regulation. Optimisation analysis of the plant capacity shows good reasons for construction of a PSP plant with the unit capacity of 2 x 220 MW and output of 780 GWh. For a power plant of such capacity it is technical prudent to be connected and supply energy by means of a 400 kV OHL to the substation Maribor (direction Croatia, Hungary) or via 400 kV OHL to substation Kainachtal (direction Austria). Basic technical data of Kozjak PSPP:  Reservoir • Upper reservoir water level 995 - 975 masl • Lower reservoir water level 281,8 - 280,8 masl • Max. gross head: h = 714,2 m • Effective storage capacity: V = 3.000.000 m3 • Penstock length 2386 m • Penstock diameter 4,0 – 3,6 – 2 x 2,0 m • Penstock inclination 32,3%  Turbine and Generators • Turbine el. 210,8 masl • Powerhouse ground floor 284,3 masl • Generators: 2x200 MW | hydro, pure pumping and turbining |  | RTP Maribor (SI) and RTP Keinachtal (A) | Slovenia | 400 | In Permitting | June 2027 | > 70 years
1030 | Organic Power International SL (Spain) | Organic Power Energy Storage | 6GWh/cycle 750MW seawater PHES | PHES |  | Bellacorick | Ireland (Project) | 220 | Planned But not yet Permitting | 2024 | 100

## Sheet7 (hidden)
Id | ProjectId | Name | From | To | ElementsType | TechnologyType | ConverterType | TerminalCapabilityRange | ConductorType | ConductorSize | ConductorsNumberPerPhase | TotalRouteLength | Resistance | Reactance | Conductance | ExpectedYearlyUnavibility | VoltageLevel | ThermalLimit | ExpectedCommissioningYear | Status | Capex | Opex | TsoInChargeFrom | TsoInChargeTo | ExpectedYearlyUnavibilityPassed | ExpectedYearlyUnavibilityForced | Capacity | KmToEachBorder
2 | 1 | Pedralva-Sobrado | Pedralva (PT) | Sobrado (PT) | Overhead Line | 10 | 0 | 0 | ACSR 595 | 595 | 2 | 67 | 0.029 | 0.308 | 3.672 |  | 400 | 2680 | 2022-2023 | Under Consideration | 28.5 | 0.065 | REN | REN |  |  | 0 | 0
4 | 1 | V.Minho -R.Pena-Fridão-Feira | V.Minho (by Ribeira de Pena and Fridão) | Feira (by Ribeira de Pena and Fridão) | Overhead Line | 10 | 0 | 0 | ACSR 485 | 0 | 3 | 131 | 0.026 | 0.231 | 5.071 |  | 400 | 3423 | 2022-2024 | Planned but not yet permitting | 67.6 | 0.163 | REN | REN |  |  | 0 | 0
474 | 1 | Substation Ribeira de Pena | Ribeira de Pena (PT) | - | Substation | 10 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2022-2024 | Planned but not yet permitting | 7.4 | 0.056 | REN | - |  |  | 0 | 0
941 | 1 | Switching station Fridão | Fridão | - | Substation | 10 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2026-2030 | Planned but not yet permitting | 7.3 | 0.037 | REN | - |  |  | 0 | 0
8 | 2 | Seia-Penela | Seia | Penela | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 108 | 0 | 0 | 0 |  | 400 | 0 | 31/ 12/ 2020 | Permitting | 0 | 0 |  |  |  |  | 0 | 0
9 | 2 | FundÆo-Falagueira | FundÆo (PT) | Falagueira (PT) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 99 | 0 | 0 | 0 |  | 400 | 0 | 31/ 12/ 2017 | Design | 0 | 0 |  |  |  |  | 0 | 0
478 | 2 | Penela-Paraimo/Batalha | Penela (PT) | Paraimo / Batalha (PT) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 15 | 0 | 0 | 0 |  | 400 | 0 | 31/ 12/ 2019 | Permitting | 0 | 0 |  |  |  |  | 0 | 0
481 | 2 | Penela 400kV | Penela (PT) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 31/ 12/ 2019 | Permitting | 0 | 0 |  |  |  |  | 0 | 0
484 | 2 | FundÆo | FundÆo (PT) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 31/ 12/ 2017 | Design | 0 | 0 |  |  |  |  | 0 | 0
18 | 4 | Beariz (ES) - Fontefria (ES) | Beariz (ES) | Fontefria (ES) | Overhead Line | 10 | 0 | 0 | TX LARL CONDOR | 454.5 | 3 | 30 | 0.0256 | 0.2768 | 4.1588 |  | 400 | 2843 | 1/ 1/ 2021 | Planned but not yet permitting | 18.69 | 0.49 | REE | REE |  |  | 0 | 0
496 | 4 | Fontefria (ES) - Vila Nova de FamalicÆo (PT) | Fontefria (ES) | Vila Nova de FamalicÆo (PT) (By Ponte de Lima) | Overhead Line | 10 | 0 | 0 | Condor x3;ACSR/AW 517; ACSR 595 | 517 | 2 | 140.21 | 0.0256 | 0.2703 | 0.4 |  | 400 | 2462 | 1/ 1/ 2021 | Planned but not yet permitting | 62.42 | 0.208 | REE | REN |  |  | 0 | 17.71
498 | 4 | SE Fontefria 400/220kV | Fontefria (ES) | REE | Substation | 10 | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2021 | Planned but not yet permitting | 13.16 | 0.17 | REE | REE |  |  | 0 | 0
499 | 4 | Beariz 400kV (ES) | Beariz (ES) | Beariz (ES) | Substation | 10 | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2021 | Planned but not yet permitting | 7.17 | 0.17 | REE | REE |  |  | 0 | 0
500 | 4 | Ponte de Lima (PT) | Ponte de Lima (PT) | Ponte de Lima (PT) | Substation | 10 | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2020-2021 | Planned but not yet permitting | 10.5 | 0.055 | REN | REN |  |  | 0 | 0
31 | 13 | Axis Caparacena-Baza-La Ribina | Caparacena (ES) | La Ribina (ES) | Overhead Line | 10 | 0 | 0 | Condor | 454.5 | 3 | 177 | 0.0257 | 0.2767 | 4.1587 |  | 400 | 2786 | 2025 | 0 | 104 | 1.56 | REE | REE |  |  | 0 | 0
569 | 13 | New substation Baza | Baza (ES) | Baza (ES) | Substation | 10 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2025 | 0 | 6.26 | 0.0939 | REE | REE |  |  | 0 | 0
570 | 13 | New substation La Ribina | La Ribina (ES) | La Ribina (ES) | Substation | 10 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2025 | 0 | 8.9 | 0.1335 | REE | REE |  |  | 0 | 0 | TBD
38 | 16 | HVDC Gatica-Cubnezais | Gatica (ES) | Cubnezais (FR) | Subsea Cable | 20 | 10 | 600 | XLPE or MI | 0 | 0 | 370 | 0 | 0 | 0 | 1000 MW | 320 | 1600 | 01/ 01/ 2025 | Planned but not yet permitting | 1750 | 10.2 | REE | RTE | TBD | TBD | 2000 | 40 | 3%
55 | 21 | Savoie - Pièmont | Grande Ile (FR) | Piossasco (IT) | Underground Cable | 20 | 10 | 300 | XLPE | 0 | 0 | 190 | 0 | 0 | 0 | 600 MVA | 320 | 3750 | 2019 | In permitting | 1200 | 5 | RTE | TERNA | 4% | 3% | 1200 | 0
57 | 22 | Geneva's lake (West) | Genissiat (FR) | Verbois (CH) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 20 | 0 | 0 | 0 |  | 220 | 0 | 1/ 1/ 2018 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1291 | 22 | Foretaille - Verbois | Foretaille (CH) | Verbois (CH) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 220 | 0 | 01/01/2023 | Design & Permitting | 0 | 0 |  |  |  |  | 0 | 0
60 | 23 | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | Avelin/Mastaing (FR) | Horta (BE) | Overhead Line | 10 | 0 | 0 | HTLS | 0 | 0 | 80 | 0.0205 | 0.3135 | 3.6195 |  | 400 | 0 | 1/1/2022 | Planned but not yet permitting | 140 | 0.4 | RTE | ELIA |  |  | 0 | 0
609 | 24 | BRABO I: PST 4 + Doel-Zandvliet | Zandvliet (BE) |  | Phase Shift Transformer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 380 | 0 | 31/10/ 2016 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0 | 3%
62 | 25 | IFA2 | Tourbe (FR) | Chilling (GB) | Subsea Cable | 20 | 10 | 300 | TBD | 0 | 0 | 250 | 0 | 0 | 0 | 500 | 320 | 0 | 1/ 1/ 2020 | In permitting | 685 | 8.4 | RTE | NGIHL | 4% | 3% | 1000 | 0
614 | 26 | Reschenpass Interconnector | Nauders (AT) | Glorenza (IT) | Underground Cable | 10 | 0 | 0 | Tbd | 0 | 0 | 26 | 0.01 | 0.19 | 69.115 |  | 220 | 1133 | 2021 | Planned but not yet permitting | 180 | 3 | APG | Terna |  |  | 0 | 0 | 6%
70 | 28 | First HVDC Module IT-ME | Villanova (IT) | Lastva (ME) | Subsea Cable | 20 | 20 | 0 | N/A | 0 | 0 | 445 | 0 | 0 | 0 | 600 MVA | 500 | 0 | 2019 | In permitting | 840 | 4.2 | TERNA | CGES | 3% | 6% | 600 | 0
624 | 28 | SS 400/110 kV Lastva | Lastva (ME) | N/A | Substation | 10 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 31/12/ 2018 | In permitting | 100 | 0.5 | CGES | N/A |  |  | 0 | 0 | 6%
1503 | 28 | Second HVDC Module IT-ME | Villanova (IT) | Lastva (ME) | Subsea Cable | 20 | 20 | 0 | N/A |  |  | 445 |  |  |  | 600 MVA | 500 | 0 | 2026 | In permitting | 310 | 1.55 | Terna | CGES | 3% | 6% | 600 | 0 | 6%
635 | 29 | Elmed Project | Sicily Area (IT) | Tunisia node | Subsea Cable | 20 | 20 | 0 | TBD | 0 | 0 | 200 | 0 | 0 | 0 | 300 MVA | 400 | 0 | 2025 | Planned but not yet permitting | 600 | 3 | TERNA | STEG | 3% | 6% | 600 | 0
642 | 31 | San Giacomo Project | All'Acqua (CH) | Pallanzeno(IT)-Baggio(IT) | Overhead Line | 10 | 0 | 0 | ACSR | 0 | 0 | 100 | 0.02 | 0.27 | 0.005 |  | 380 | 2850 | 2025 | Planned but not yet permitting | 1100 | 5 | SWISSGRID | TERNA |  |  | 0 | 0
90 | 33 | 90 | Calenzano (IT) | Colunga (IT) | Overhead Line | 10 | 0 | 0 | N/A | 0 | 0 | 80 | 0.02 | 0.27 | 0.005 |  | 400 | 0 | 2022 | Planned but not yet permitting | 220 | 3.3 | TERNA | TERNA |  |  | 0 | 0
1041 | 33 | Rem. lim. in Central Italy | Villanova (IT) | S. Barbara (IT) | Overhead Line | 10 | 0 | 0 | Tbd | 0 | 0 | 350 | 0.02 | 0.27 | 0.005 |  | 220 | 0 | 2022 | Under Consideration | 140 | 2.1 | TERNA | TERNA |  |  | 0 | 0
311 | 35 | R Kocin | Kocin (CZ) | N/A | Substation | 10 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2024 | In permitting | 123.56 | 1.56 | CEPS | CEPS |  |  | 0 | 0
313 | 35 | Kocin-Mirovka | Kocin (CZ) | Mirovka (CZ) | Overhead Line | 10 | 0 | 0 | 490-AL1/64-ST1A | 490 | 3 | 121 | 0.02 | 0.28 | 3.95 |  | 400 | 2445 | 1/ 1/ 2024 | Planned but not yet permitting | 136.99 | 0.16 | CEPS | CEPS |  |  | 0 | 0
315 | 35 | Kocin-Prestice | Kocin (CZ) | Prestice (CZ) | Overhead Line | 10 | 0 | 0 | 490-AL1/64-ST1A | 490 | 3 | 116 | 0.02 | 0.28 | 3.95 |  | 400 | 2445 | 1/ 1/ 2028 | Planned but not yet permitting | 161.76 | 0.26 | CEPS | CEPS |  |  | 0 | 0
141 | 36 | Kriegers Flak CGS, TYNDP ID: 36.141 | Ishøj / Bjæverskov (DK) | Bentwisch (DE) | Subsea Cable | 10 | 0 | 0 | double circuit | 0 | 0 | 24 | 0.05375 | 0.1163 | 76.184 |  | 150 | 1500 | 31/12/2018 | In permitting | 349 | 16 | Energinet.dk | 50Hertz Transmission GmbH |  |  | 0 | 0 | 0
142 | 37 | Norway - Germany HVDC | Tonstad (NO) | Wilster (DE) | Subsea Cable | 20 | 10 | 0 | subsea cable | 0 | 0 | 514 | 0 | 0 | 0 | 0 | 500 | 0 | 01/ 01/ 2020 | In permitting | 0 | 0 | Statnett | TenneT-DE | 0 | 0 | 0 | 0
406 | 37 | Western corridor | (Southern part of Norway) (NO) | (Southern part of Norway)(NO) | Overhead Line | 10 | 0 | 0 | Overhead line | 0 | 0 | 400 | 0 | 0 | 0 |  | 400 | 0 | 2020 | Under Construction | 0 | 0 | Statnett | Statnett |  |  | 0 | 0
144 | 39 | Audorf - Kassoe | Audorf (DE) | Kassoe (DK) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 3 | 110 | 0.01236 | 0.13564 | 1.7972 |  | 380 | 4988 | 31/ 12/ 2020 | In permitting | 536 | 4 | TenneT-DE | Energinet.dk |  |  | 0 | 0
650 | 40 | BE-LUX-DE Long-Term perspective | Aubange (TBC) | LUX-DE (TBC) | Underground Cable | 10 | 0 | 0 | TBD | 0 | 0 | 16 | 0.0155 | 0.188 | 80 |  | 0 | 0 | 2035 | 0 | 210 | 0.6 | ELIA | CREOS; AMPRION |  |  | 0 | 0
160 | 42 | Nordergrnde | Offshore- Wind park Nordergrnde (DE) | Inhausen (DE) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 32 | 0 | 0 | 0 |  | 154 | 0 | 1/ 1/ 2016 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0
163 | 42 | HelWin1 | Cluster HelWin1 (DE) | Bttel (DE) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 133 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2014 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
164 | 42 | SylWin1 | Cluster SylWin1 (DE) | Bttel (DE) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 206 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2015 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
165 | 42 | DolWin1 | Cluster DolWin1 (DE) | D”rpen/West (DE) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 167 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2015 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
166 | 42 | Riffgat | Offshore Wind park Riffgat (DE) | Emden /Boráum(DE) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 77 | 0 | 0 | 0 |  | 154 | 0 | 1/ 1/ 2014 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
167 | 42 | BorWin2 | Cluster BorWin2 (DE) | Diele (DE) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 205 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2015 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
654 | 42 | DolWin2 | Cluster DolWin2 (DE) | D”rpen/West (DE) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 138 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2016 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0
657 | 42 | HelWin2 | Cluster HelWin2 | Bttel (DE) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 133 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2015 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
219 | 47 | 219: Westtirol - Zell/Ziller (AT internal) | Westtirol (AT) | Zell-Ziller (AT) | Overhead Line | 10 | 0 | 0 | Tbd | 0 | 0 | 105 | 0.0151 | 0.2536 | 4.3982 |  | 380 | 2300 | 2024 | Under Consideration | 125 | 1 | APG | APG |  |  | 0 | 0
689 | 47 | 689: Vöhringen (DE) - Westtirol (AT) | Vöhringen (DE) | Westtirol (AT) | Overhead Line | 10 | 0 | 0 | AL/ST | 550 | 4 | 157 | 0.0132 | 0.256 | 4.43 |  | 380 | 3600 | 2024 | Under Consideration | 173.8 | 1.3904 | Amprion | APG |  |  | 0 | 110
696 | 48 | Hunew 1 | Sajóivánka (HU) | N/A | Compensation | 10 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2020 | Planned but not yet permitting | 0.5 | 0.0097 | MAVIR | N/A |  |  | 0 | 0
697 | 48 | Hunew 2 | Sajóivánka (HU) | N/A | Substation | 10 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2020 | Planned but not yet permitting | 2.1 | 0.0387 | MAVIR | N/A |  |  | 0 | 0
1500 | 48 | 1. SK-HU interconnection | Gabcikovo (SK) | Gonyu (HU) | Overhead Line | 10 | 0 | 0 | SEPS side: AlFe 450/52 MAVIR side: AL/87-ST1A 381/3 | 450 | 3 | 110 | 0.0223 | 0.28 | 4.05 |  | 400 | 2400 | 2020 | Planned but not yet permitting | 27.65 | 0.7308 | SEPS | MAVIR |  |  | 0 | 1
1501 | 48 | 2. SK-HU interconnection | Rimavska Sobota (SK) | Sajoivanka (HU) | Overhead Line | 10 | 0 | 0 | SEPS side: 434-AL1/56 - ST1A; MAVIR side: ACSR 500/2 | 434 | 3 | 48 | 0.0251 | 0.294 | 3.85 |  | 400 | 2240 | 2020 | Planned but not yet permitting | 51.38 | 0.6904 | SEPS | MAVIR |  |  | 0 | 24
720 | 54 | 3. SK-HU interconnection | Ve?k‚ Kapu?any (SK) | Kisv rda area (HU) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 40 | 0 | 0 | 0 |  | 400 | 0 | 1/1/2029 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
302 | 55 | Vyskov-Cechy Stred | Vyskov (CZ) | Cechy Stred (CZ) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 98 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2016 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0
303 | 55 | Babylon-Bezdecin | Babylon (CZ) | Bezdecin (CZ) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 54 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2018 | Design & Permitting | 0 | 0 |  |  |  |  | 0 | 0
304 | 55 | Babylon-Vyskov | Babylon (CZ) | Vyskov (CZ) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 73 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2019 | Design & Permitting | 0 | 0 |  |  |  |  | 0 | 0
386 | 62 | 3rd EE-LV interconnection | Kilingi-Nomme (EE) | Riga CHP2 (LV) | Overhead Line | 10 | 0 | 0 | Aluminum Steel Core | 400 | 2 | 205 | 0.036 | 0.321 | 3.49 |  | 330 | 2000 | 2020 | In permitting | 120 | 0.6 | Elering | AST |  |  | 0 | 180
735 | 62 | Harku-Sindi 330kV OHL | Harku (EE) | Sindi (EE) | Overhead Line | 10 | 0 | 0 | Aluminum Steel Core | 400 | 3 | 175 | 0.02407 | 0.28663 | 4e-05 |  | 330 | 0 | 31/ 12/ 2020 | In permitting | 60 | 0.1145 | Elering | Elering |  |  | 0 | 0
1062 | 62 | Riga CHP2 - Riga HPP | Riga CHP2 | Riga HPP | Overhead Line | 10 | 0 | 0 | Aluminum Steel Core | 400 | 2 | 15 | 0.036 | 0.321 | 3.49 |  | 330 | 1650 | 1/ 1/ 2020 | Planned but not yet permitting | 20 | 0.1 | AST | AST |  |  | 0 | 0
747 | 69 | Bramford - Twinstead | Bramford (GB) | Twinstead (GB) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 35 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2023 | Design & Permitting | 0 | 0 |  |  |  |  | 0 | 0
427 | 71 | COBRA Cable | Endrup (DK) | Eemshaven (NL) | Subsea Cable | 20 | 10 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 700 | 400 | 1500 | 2019 | In permitting | 685 | 14 | Energinet | TENNET-NL | 4% | 4% | 700 | 0
443 | 74 | NEMO | Richborough (GB) | Gezelle (BE) | Subsea Cable | 20 | 10 | 0 | XLPE | 0 | 0 | 140 | 0 | 0 | 0 | 1 | 400 | 0 | 1/ 1/ 2019 | In permitting | 660 | 25 | NGET | ELIA | 87h | 175h | 1000 | 0 | 4%
449 | 74 | Richborough - Canterbury | Richborough (GB) | Canterbury (GB) | Overhead Line | 10 | 0 | 0 | 2 x 570mm2 AAAC | 570 | 2 | 20 | 0.024 | 0.304 | 3.7531 |  | 400 | 2180 | 2018 | Planned but not yet permitting | 0 | 0 | NGET | NGET |  |  | 0 | 0 | 175h
450 | 74 | SELL - DUNG Reconductoring | Sellindge (GB) | Dungeness (GB) | Overhead Line | 10 | 0 | 0 | 3x700mm2 AAAC 3.05R, 2x620mm2 GZTACSR | 700 | 3 | 26 | 0.0246 | 0.3015 | 3.6635 |  | 400 | 3070 | 30/ 11/ 2016 | Under Construction | 0 | 0 | NGET | NGET |  |  | 0 | 0
752 | 75 | Modular Offshore Grid | Offshore platform | Stevin (Zeebrugge) | Subsea Cable | 10 | 0 | 0 | TBC | 0 | 0 | 50 | 0.026 | 0.116 | 75.36 |  | 220 | 0 | 01/01/2020 | Planned but not yet permitting | 400 | 8.5 | ELIA | ELIA |  |  | 0 | 0
452 | 77 | Western HVDC Link | Hunterston (GB) | Deeside (GB) | Subsea Cable | 20 | 20 | 0 | TBC | 0 | 0 | 360 | 0 | 0 | 0 | TBC | 500 | 0 | 2017 | In permitting | 1220 | 0 | SPT | NGET | TBC | TBC | 2400 | 0
458 | 78 | HINP-SEAB New Double Circuit | Hinkley Point (GB) | Seabank (GB) | Overhead Line | 10 | 0 | 0 | AACSR Twin 400 kV Matthew 620mm2 | 620 | 2 | 60 | 0.0186 | 0.295 | 0 |  | 400 | 3100 | 2024 | Planned but not yet permitting | 814 | 0 | NGET | NGET |  |  | 0 | 0 | TBC
769 | 79 | WYLF-PEMB HVDC Link | Wylfa (GB) | Pembroke (GB) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 260 | 0 | 0 | 0 |  | 500 | 0 | 1/ 1/ 2024 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
462 | 81 | 462 | Woodland (IE) | Turleenan (NI) | Overhead Line | 10 | 0 | 0 | Curlew | 600 | 2 | 138 | 0.028436 | 0.32343 | 3.5446 |  | 400 | 2603 | 2020 | Planned but not yet permitting | 349 | 0.6 | EirGrid | SONI |  |  | 0 | 0
463 | 82 | Srananagh - South Donegal | Srananagh (IE) | New substation in South Donegal (IE) | Overhead Line | 10 | 0 | 0 | TBD | 0 | 0 | 83 | 0.056144 | 0.41914 | 2.7004 |  | 220 | 0 | 2029 | Under Consideration | 171.7 | 0.34 | EirGrid | EirGrid |  |  | 0 | 0
896 | 82 | Omagh South to South Donegal | South Donegal (IE) | Omagh South (NI) | Overhead Line | 10 | 0 | 0 | TBD | 0 | 0 | 58 | 0.039037 | 0.31568 | 6.6014 |  | 275 | 0 | 2029 | Under Consideration | 88.6 | 0.18 | EirGrid | SONI |  |  | 0 | 0
897 | 82 | Omagh South to Turleenan | Omagh South | Turleenan | Overhead Line | 10 | 0 | 0 | TBD | 0 | 0 | 61 | 0.039037 | 0.31568 | 6.6014 |  | 275 | 0 | 2029 | Under Consideration | 135.9 | 0.27 | SONI | SONI |  |  | 0 | 0
779 | 85 | F.Alentejo-Ourique-Tavira | F. Alentejo (by Ourique) | Tavira (by Ourique) | Overhead Line | 10 | 0 | 0 | ACSR 595 | 595 | 2 | 122 | 0.029 | 0.295 | 3.774 |  | 400 | 2680 | 2024-2026 | Under Consideration | 63 | 0.099 | REN | REN |  |  | 0 | 0
780 | 85 | Extension of Ourique substation | Ourique (PT) | - | Substation | 10 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2024-2026 | Under Consideration | 4.1 | 0.029 | REN | - |  |  | 0 | 0
781 | 86 | East Coast Offshore | Under Consideration (GB) | Under Consideration (GB) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 500 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2026 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
782 | 86 | East Coast Offshore | Under Consideration (GB) | Under Consideration (GB) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 500 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2026 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
146 | 92 | ALEGrO | Oberzier (DE) | Lixhe (BE) | Underground Cable | 20 | 10 | 300 | XLPE | 0 | 0 | 90 | 0 | 0 | 0 | 1 | 320 | 1650 | 2020 | Planned but not yet permitting | 560 | 4.2 | AMPRION | ELIA | 48 h | 284 h | 1000 | 40
139 | 94 | Krajnik-Vierraden | Vierraden (DE) | Krajnik (PL) | Overhead Line | 10 | 0 | 0 | 2xAFL-8 525 | 525 | 2 | 25.68 | 0.0265 | 0.293 | 3.86 |  | 400 | 1800 | 31/12/2020 | In permitting | 12.5 | 0.0375 | 50Hertz | PSE S.A. |  |  | 0 | 0 | 284 h
796 | 94 | Krajnik | Krajnik (PL) | Krajnik (PL) | Substation | 10 | 0 | 0 | n.a. | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2019 | In permitting | 36.5 | 1.095 | PSE S.A. | PSE S.A. |  |  | 0 | 0
1492 | 94 | PST in Mikulowa | Mikulowa (PL) | Mikulowa (PL) | PST | 10 | 0 | 0 | Cu | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 30/06/2016 | in operation | 65.7 | 1.971 | PSE | PSE |  |  | 0 | 0
1493 | 94 | PST Vierraden | Vierraden | Vierraden | Phase Shift Transformer | 10 | 0 | 0 | Cu | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 31/12/2018 | In permitting | 110.8 | 2 | 50Hertz | 50Hertz |  |  | 0 | 0
801 | 96 | FI5 KI-PS | Keminmaa (FI) | Pyhanselka (FI) | Overhead Line | 10 | 0 | 0 | 3-Finch | 850 | 3 | 156 | 0.0512 | 0.284 | 0.013 |  | 400 | 3150 | 1/ 1/ 2024 | Planned but not yet permitting | 60 | 0.1 | Fingrid | Fingrid |  |  | 0 | 0
1488 | 103 | Diemen-Lelystad-Ens | Diemen | Ens | Overhead Line | 10 |  |  | HTLS | 0 | 0 | 75 | 0 | 0 | 0 |  | 380 | 0 | 2020 | In permitting |  |  | TENNET-NL | TENNET-NL |  |  |  | 0
1490 | 103 | Ens-Zwolle | Ens | Zwolle | Overhead Line | 10 |  |  | HTLS | 0 | 0 | 32 | 0 | 0 | 0 |  | 380 | 0 | 2022 | Under Consideration | 30 |  | TENNET-NL | TENNET-NL |  |  |  | 0
1539 | 103 | Krimpen-Geertruidenberg | Krimpen | Geertruidenberg | Overhead Line | 10 |  |  | HTLS | 0 | 0 | 35 | 0 | 0 | 0 |  | 380 | 0 | 2020 | Planned but not yet permitting | 45 |  | TENNET-NL | TENNET-NL |  |  |  | 0
1540 | 103 | Eindhoven-Maasbracht | Eindhoven | Maasbracht | Overhead Line | 10 |  |  | HTLS | 0 | 0 | 50 | 0 | 0 | 0 |  | 380 | 0 | 2023 | Planned but not yet permitting | 50 |  | TENNET-NL | TENNET-NL |  |  |  | 0
1560 | 103 | Randstad380 noordring | Beverwijk | Bleiswijk | Overhead Line | 10 |  |  | 0 | 0 | 0 | 60 | 0 | 0 | 0 |  | 380 | 0 | 2018 | In permitting |  |  | TENNET-NL | TENNET-NL |  |  |  | 0
810 | 107 | France Ireland Interconnector | West Wexford or East Cork (IE) | La Martyre (FR) | Subsea Cable | 20 | 10 | 210 | TBD | 0 | 0 | 500 | 0 | 0 | 0 | 700 | 320 | 0 | 2026 | 0 | 920 | 8.5 | EIRGRID | RTE | 4% | 3% | 700 | 0
424 | 110 | Norway - Great Britain | Kvilldal (NO) | Blythe (GB) | Subsea Cable | 20 | 10 | 0 | Double circuit | 0 | 0 | 720 | 0 | 0 | 0 | TBD | 500 | 0 | 2021 | In permitting | 1800 | 15.4 | Statnett | NHIGL | TBD | TBD | 1400 | 0 | 3%
396 | 111 | 3rd AC Finland-Sweden north | Keminmaa (Finland) | Messaure (Sweden, bidding area SE1) | Overhead Line | 10 | 0 | 0 | Al-59 910 | 910 | 3 | 200 | 0.0326 | 0.284 | 0.013 |  | 400 | 3150 | 2025 | Planned but not yet permitting | 160 | 0.24 | Fingrid | Svenska kraftnät |  |  | 0 | 150 | TBD
145 | 113 | Doetinchem-Niederrhein | Niederrhein (DE) | Doetinchem (NL) | Overhead Line | 10 | 0 | 0 | 4 x 560/50 | 0 | 4 | 57 | 0.0129 | 0.26 | 4.4 |  | 380 | 3600 | 2018 | In permitting | 220 | 1.8 | AMPRION | TENNET-NL |  |  | 0 | 0
1625 | 120 | MOG II: connection of up to 2 GW additional offshore wind Belgium | Offshore (TBD) | Onshore (TBD) | Subsea Cable | 10 |  |  | TBC | 0 | 0 | 50 | 0.026 | 0.116 | 75.36 |  | 220 | 0 | 2030 | 0 | 800 | 17 | Elia | Elia |  |  |  | 0
934 | 121 | Nautilus: 2nd interco UK - BE | Leiston (UK) | TBD (BE) | Subsea Cable | 20 | 10 | 0 | TBD | 0 | 0 | 250 | 0 | 0 | 0 | 1 | 400 | 0 | 2028 | 0 | 1000 | 8 | NGHIL | ELIA | 87h | 175h | 1400 | 0
373 | 123 | Ostroleka-Stanislawow | Ostroleka (PL) | Stanislawow (PL) | Overhead Line | 10 | 0 | 0 | 3x3x408-AL1F/34-UHST | 408 | 3 | 106 | 0.0281 | 0.1982 | 3.9474 |  | 400 | 2970 | 31/ 12/ 2023 | Under Consideration | 0 | 0 | PSE | PSE |  |  | 0 | 0 | 175h
378 | 124 | 330 kV OHL Panevezys-Musa | Panevezys | Musa | Overhead Line | 10 | 0 | 0 | Al | 400 | 2 | 72 | 0.0391 | 0.322 | 3.51 |  | 330 | 1650 | 2023 | Under Consideration | 14.4 | 0.047 | LITGRID | LITGRID |  |  | 0 | 0
385 | 124 | Grobina (LV) - Imanta (LV) | Grobina (LV) | Imanta (LV) | Overhead Line | 10 | 0 | 0 | Single circuit/ Double circuit | 400 | 3 | 380 | 0.024 | 0.281 | 3.73 |  | 330 | 0 | 2019 | In permitting | 190.8 | 0.55 | AST | AST |  |  | 0 | 0
733 | 124 | Ekhyddan-Nybro-Hemsjo | Ekhyddan (SE) | Nybro/Hemsjo (SE) | Overhead Line | 10 | 0 | 0 | Al59 | 910 | 3 | 160 | 0.015 | 0.194 | 0.013 |  | 400 | 3150 | 2023 | Planned but not yet permitting | 159 | 0.1 | Svk | Svk |  |  | 0 | 160
403 | 126 | Reinforcements SE2-SE3 in Sweden | SE2 | SE3 | Compensation | 10 | 0 | 0 | - | 0 | 0 | 900 | 0 | 0 | 0 |  | 400 | 3150 | 2030 | 0 | 550 | 0 | Svk | Svk |  |  | 0 | 0
86 | 127 | 86 | Foggia (IT) | Villanova (IT) | Overhead Line | 10 | 0 | 0 | ACSR | 585 | 3 | 178 | 0.02 | 0.27 | 0.005 |  | 400 | 3000 | 2022 | Planned but not yet permitting | 400 | 6 | TERNA | TERNA |  |  | 0 | 0
96 | 127 | 96 | Deliceto (IT) | Bisaccia (IT) | Overhead Line | 10 | 0 | 0 | ACSR | 585 | 3 | 30 | 0.02 | 0.31 | 0.004 |  | 400 | 3000 | 31/ 12/ 2022 | Planned but not yet permitting | 190 | 2.85 | TERNA | TERNA |  |  | 0 | 0
645 | 127 | ITA-3 | Laino (IT) | Altomonte (IT) | Overhead Line | 10 | 0 | 0 | ACSR | 585 | 3 | 50 | 0.01 | 0.1 | 0.01 |  | 400 | 3000 | 1/ 1/ 2022 | Planned but not yet permitting | 160 | 2.4 | TERNA | TERNA |  |  | 0 | 0
943 | 129 | NOR-9-1 | NOR-9-1 | area of Unterweser | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 255 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2035 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
946 | 129 | NOR-11-1 | NOR-11-1 | area of Wilhelmshaven | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 230 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2032 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
948 | 129 | NOR-12-1 | NOR-12-1 | area of Wilhelmshafen | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 240 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2034 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
950 | 129 | NOR-13-1 | NOR-13-1 | Kreis Segeberg | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 330 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2031 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
665 | 130 | Wolmirstedt-Isar | Wolmirstedt (DE) | Isar (DE) | Underground Cable | 20 | 10 | 0 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 | Planned but not yet permitting | 2800 | 22.4 | 50Hertz | TenneT DE | 0% | 0% | 2000 | 0
661 | 132 | HVDC Line A-North | Emden East (DE) | Osterath (DE) | Overhead Line | 20 | 10 | 0 | cable | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 400 | 0 | 1/ 1/ 2025 | Planning | 1400 | 11.2 | Amprion | Amprion | 0 | 0 | 0 | 0 | 0%
662 | 133 | HVDC Line B | Wehrendorf (DE) | Urberach (DE) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 380 | 0 | 0 | 0 |  | 400 | 0 | >2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0 | 0
956 | 133 | further HCDC connections C | Schleswig-Hostein | Baden-Wrtemberg / Bavaria | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 770 | 0 | 0 | 0 |  | 500 | 0 | >2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
958 | 133 | DC Gstrow - Area Isar | Gstrow (DE) | Area of Isar (DE) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 770 | 0 | 0 | 0 |  | 500 | 0 | >2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
969 | 133 | further HVDC connections A | Lower Saxony | North Rhine-Westphalia | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 360 | 0 | 0 | 0 |  | 500 | 0 | >2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
970 | 133 | further HVDC connections B | Lower Saxony | Hesse/Baden-Wrtemberg | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 500 | 0 | 0 | 0 |  | 500 | 0 | >2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
176 | 134 | Daxlanden-Eichstetten | Daxlanden (DE) | Eichstetten (DE) | Overhead Line | 10 | 0 | 0 | - | 0 | 0 | 120 | 0.0129 | 0.26 | 0.014 |  | 380 | 0 | 1/ 1/ 2021 | Planned but not yet permitting | 290 | 2.3 | TransnetBW | TransnetBW |  |  | 0 | 0
680 | 134 | Urberach - Daxlanden | Urberach (DE) | Daxlanden (DE) | Overhead Line | 10 | 0 | 0 | - | 0 | 0 | 219 | 0.0132 | 0.256 | 0.05 |  | 400 | 3600 | 1/ 1/ 2023 | Planned but not yet permitting | 490 | 3.9 | Amprion | TransnetBW |  |  | 0 | 0
179 | 135 | Rommerskirchen - Weißenthurm | Rommerskirchen (DE) | Weißenthurm (DE) | Overhead Line | 10 | 0 | 0 | - | 0 | 0 | 94 | 0.0132 | 0.256 | 0.05 |  | 400 | 2600 | 1/ 1/ 2019 | Under Construction | 190 | 1.5 | Amprion | Amprion |  |  | 0 | 0
188 | 135 | Kruckel - Dauersberg | Kruckel (DE) | Dauersberg (DE) | Overhead Line | 10 | 0 | 0 | - | 0 | 0 | 110 | 0.0132 | 0.256 | 0.05 |  | 380 | 3600 | 1/ 1/ 2021 | Permitting | 710 | 5.7 | Amprion | Amprion |  |  | 0 | 0
227 | 136 | OHL 400 kV Banja Luka - Lika | Banja Luka (BA) | Lika (HR) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 155 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
617 | 136 | OHL 400 kV Lika - Brinje | Lika(HR) | Brinje(HR) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 55 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2025 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
618 | 136 | OHL 400 kV Lika - Velebit | Lika(HR) | Velebit(HR) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 60 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2025 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
619 | 136 | Substation 400/110 kV Lika | Lika (HR) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2027 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
620 | 136 | Substation 400/220 kV Brinje | Brinje (HR) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2025 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
633 | 136 | OHL 400 kV Konjsko - Velebit | Konjsko(HR) | Velebit(HR) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 100 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2025 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
273 | 138 | 400kV OHL Cernavoda-Stalpu | Cernavoda (RO) | Stalpu (RO) | Overhead Line | 10 | 0 | 0 | ALOL | 300 | 3 | 159 | 0.032 | 0.303 | 3.79 |  | 400 | 1741 | 2020 | Planned but not yet permitting | 60 | 0.3 | Transelectrica | Transelectrica |  |  | 0 | 0
275 | 138 | 400 kV OHL Smardan-Gutinas | Smardan (RO) | Gutinas (RO) | Overhead Line | 10 | 0 | 0 | ALOL | 300 | 3 | 140 | 0.032 | 0.303 | 3.79 |  | 400 | 1741 | 2020 | Planned but not yet permitting | 60 | 0.3 | Transelectrica | Transelectrica |  |  | 0 | 0
715 | 138 | 220kV Stalpu substation upgrade to 400 kV | Stalpu (RO) | Stalpu (RO) | Substation | 10 | 0 | 0 | GIS | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 250 | 2020 | Planned but not yet permitting | 10 | 0.1 | Transelectrica | Transelectrica |  |  | 0 | 0
800 | 138 | 400 kV OHL Varna-Burgas | Varna(BG) | Burgas(BG) | Overhead Line | 10 | 0 | 0 | Aluminum-steel | 400 | 3 | 110 | 0.0271 | 0.339 | 3.71 |  | 400 | 2475 | 31/ 03/ 2021 | Planned but not yet permitting | 63 | 0.8 | ESO-EAD | ESO-EAD |  |  | 0 | 0
223 | 141 | 223 | Cirkovce (SI) | Heviz (HU) Zerjavenec (HR) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2019 | Design & Permitting | 0 | 0 |  |  |  |  | 0 | 0
225 | 141 | 225 | Divaca (SI) | Cirkovce (SI) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 193 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2025 | Design & Permitting | 0 | 0 |  |  |  |  | 0 | 0
256 | 142 | 256 | Maritsa East 1 (BG) | N.Santa (GR) | Overhead Line | 10 | 0 | 0 | Aluminum-Steel | 400 | 3 | 151 | 0.0271 | 0.31 | 3.71 |  | 400 | 2475 | 30/01/ 2023 | Planned but not yet permitting | 80 | 1.1 | ESO-EAD | IPTO-SA |  |  | 0 | 0
257 | 142 | 257 | Maritsa East 1 (BG) | Plovdiv (BG) | Overhead Line | 10 | 0 | 0 | Aluminum-Steel | 400 | 3 | 100 | 0.0271 | 0.31 | 3.71 |  | 400 | 2475 | 30/ 12/ 2020 | Planned but not yet permitting | 57 | 0.7 | ESO-EAD | ESO-EAD |  |  | 0 | 0
258 | 142 | 258 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | Overhead Line | 10 | 0 | 0 | Aluminum-Steel | 400 | 3 | 13 | 0.0271 | 0.31 | 3.71 |  | 400 | 2475 | 30/ 06/ 2019 | Planned but not yet permitting | 7.4 | 0.1 | ESO-EAD | ESO-EAD |  |  | 0 | 0
262 | 142 | 262 | Maritsa East 1 (BG) | Burgas (BG) | Overhead Line | 10 | 0 | 0 | Aluminum-Steel | 400 | 3 | 150 | 0.0271 | 0.31 | 3.71 |  | 400 | 2475 | 01/ 06/ 2021 | Planned but not yet permitting | 80 | 1.1 | ESO-EAD | ESO-EAD |  |  | 0 | 0
238 | 144 | New_400 kV OHL RO-RS | Resita (RO) | Pancevo (RS) | Overhead Line | 10 | 0 | 0 | ALOL | 300 | 3 | 131 | 0.032 | 0.303 | 3.79 |  | 400 | 1741 | 31/03/2018 | In permitting | 46 | 0.23 | Transelectrica | EMS |  |  | 0 | 63
269 | 144 | 400 kV OHL Portile de Fier-Resita | Portile de Fier (RO) | Resita (RO) | Overhead Line | 10 | 0 | 0 | ALOL | 300 | 3 | 116 | 0.032 | 0.303 | 3.79 |  | 400 | 1741 | 2019 | In permitting | 30 | 0.15 | Transelectrica | Transelectrica |  |  | 0 | 0
270 | 144 | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz - Arad to 400kV double circuit line | Resita (RO) | Timisoara-Sacalaz-Arad (RO) | Overhead Line | 10 | 0 | 0 | ALOL | 300 | 3 | 274 | 0.032 | 0.303 | 3.79 |  | 400 | 1741 | 2023 | Planned but not yet permitting | 56 | 0.35 | Transelectrica | Transelectrica |  |  | 0 | 0
701 | 144 | 400 kV Substation Resita | Resita (RO) | Resita (RO) | Substation | 10 | 0 | 0 | AIS | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 650 | 2019 | In permitting | 18 | 0.18 | Transelectrica | Transelectrica |  |  | 0 | 0
705 | 144 | 400 kV Substation Timisoara | Timisoara (RO) | Timisoara (RO) | Substation | 10 | 0 | 0 | AIS | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 900 | 2023 | Planned but not yet permitting | 29 | 0.29 | Transelectrica | Transelectrica |  |  | 0 | 0
625 | 146 | 400 kV OHL Lastva - Pljevlja | Lastva (ME) | Pljevlja (ME) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 160 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2016 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0
1075 | 146 | 400 kV OHL Kragujevac-Kraljevo | Kragujevac | Kraljevo | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 55 | 0 | 0 | 0 |  | 400 | 0 | 2019 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0
1076 | 146 | Upgrade of SS Kraljevo | Kraljevo |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2019 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0
235 | 147 | New_400kVinterconnection_RS_AL | Tirana(AL) | Pristina (RS) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 242 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2016 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
236 | 147 | 236 | Leskovac(RS) | Shtip (MK) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 170 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2015 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
239 | 147 | 239 | Bitola (MK) | Elbasan (AL) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 151 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2020 | Design & Permitting | 0 | 0 |  |  |  |  | 0 | 0
244 | 147 | 244 | Filippi(GR) | Lagadas (GR) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 110 | 0 | 0 | 0 |  | 400 | 0 | 1/ 6/ 2017 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0
707 | 147 | 239 | Ohrid area (MK) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2020 | Design & Permitting | 0 | 0 |  |  |  |  | 0 | 0
708 | 147 | 708 | Lagadas (GR) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2016 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
912 | 147 | SS Kumanovo | Kumanovo |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2020 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1002 | 147 | Tirana 3 (AL) - Prizren (RS) | SS Skavica | SS Prizren | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 45 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2028 | Planning | 0 | 0 |  |  |  |  | 0 | 0
616 | 150 | Salgareda - Border IT-SI | Salgareda (IT) | Border IT-SI | Underground Cable | 20 | 10 | 0 | Tbd | 0 | 0 | 0 | 0 | 0 | 0 | 600 MVA | 500 | 0 | 2022 | Planned but not yet permitting | 400 | 2 | TERNA | N/A | 4% | 3% | 1000 | 0
1616 | 150 | Beričevo - Border IT-SI | Beričevo (SI) | Border IT-SI | Underground Cable | 20 | 10 | 300 | N/A |  |  | 140 |  |  |  | 600 | 500 | 2000 | after 2022 | 0 | 500 | 1.9 | ELES | N/A | 4% | 3% | 1000 | 140 | 3%
522 | 151 | New substation Sama | Sama (ES) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2020 | Planning | 0 | 0 |  |  |  |  | 0 | 0 | 0.02
523 | 151 | New substation Reboria | Reboria (ES) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2020 | Planning | 0 | 0 |  |  |  |  | 0 | 0
928 | 151 | Double circuit Gozon-Sama | GOZON (ES) | SAMA (ES) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 184 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2020 | Planning | 0 | 0 |  |  |  |  | 0 | 0
987 | 153 | France-Alderney-Britain | Menuel (FR) | Exeter (GB) | Subsea Cable | 20 | 10 | 0 | TBD | 0 | 0 | 210 | 0 | 0 | 0 | 700 | 320 | 0 | 1/ 1/ 2022 | Planned but not yet permitting | 850 | 7.6 | RTE (FR) | NGIHL (UK) | 4% | 3% | 0 | 0
545 | 157 | Escatr¢n-La Secuita | Escatron (ES) | La Secuita (ES) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 125 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2027 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0 | 3%
546 | 157 | New substation Els Aubals | Els Aubals (ES) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2027 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
547 | 157 | New substation La Secuita | La Secuita (ES) |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2027 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
597 | 158 | Southern Massif Central | La GaudiŠre (FR) | Rueyres (FR) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 175 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2025 | Planning | 0 | 0 |  |  |  |  | 0 | 0
149 | 164 | Dollern - Stade | Dollern (DE) | Stade (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 14 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2021 | Planned but not yet permitting | 20 | 0.2 | TenneT-DE | TenneT-DE |  |  | 0 | 0
157 | 164 | Wahle - Mecklar | Wahle (DE) | Mecklar (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 210 | 0.0127 | 0.253 | 10.6 |  | 380 | 0 | 2021 | Planned but not yet permitting | 610 | 4.9 | TenneT-DE | TenneT-DE |  |  | 0 | 0
677 | 164 | Dollern - Landesbergen | Dollern (DE) | Landesbergen (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 130 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2023 | Planned but not yet permitting | 340 | 2.7 | TenneT-DE | TenneT-DE |  |  | 0 | 0
685 | 164 | Mecklar - Grafenrheinfeld | Mecklar (DE) | Grafenrheinfeld (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 130 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2027 | Under Consideration | 230 | 1.8 | TenneT-DE | TenneT-DE |  |  | 0 | 0
998 | 167 | Viking Link DKW-GB, TYNDP ID 167.998 | Revsing (DKW) | Bicker Fen (GB) | Subsea Cable | 20 | 10 | 0 | Double Circuit | 0 | 0 | 770 | 0 | 0 | 0 | 1400 MW | 515 | 1410 | 31/12/ 2022 | Planned but not yet permitting | 1970 | 16 | Energinet.dk | National Grid | 4% | 4% | 1400 | 0
382 | 170 | New 330 kV OHL Vilnius-Neris | Vilnius | Neris | Overhead Line | 10 | 0 | 0 | AL | 0 | 0 | 65.2 | 0.0391 | 0.322 | 3.51 |  | 330 | 1650 | 2024 | Under Consideration | 19 | 0.042 | LITGRID | LITGRID |  |  | 0 | 0 | 4%
1004 | 170 | 330kV OHL Paide-Sindi (L346) | Sindi | Paide | Overhead Line | 10 | 0 | 0 | AL | 400 | 3 | 76 | 0.024 | 0.268 | 4e-05 |  | 330 | 1394 | 01/01/2025 | Under Consideration | 15 | 0.04 | ELERING | ELERING |  |  | 0 | 0
1010 | 170 | 330 kV OHL Tartu-Valmiera | Tartu | Valmiera | Overhead Line | 10 | 0 | 0 | Single circuit | 300 | 3 | 133 | 0.029 | 0.326 | 3.44 |  | 330 | 1394 | 1/ 1/ 2025 | Under Consideration | 21 | 0.13 | Elering | AST |  |  | 0 | 84
1011 | 170 | Valmiera -Tsirguliina 330 kV | Tsirguliina | Valmiera | Overhead Line | 10 | 0 | 0 | Single circuit | 300 | 3 | 60 | 0.029 | 0.326 | 3.44 |  | 330 | 1650 | 1/ 1/ 2025 | Under Consideration | 27.2 | 0.13 | Elering | AST |  |  | 0 | 11.5
1012 | 170 | 330 kV OHL Tartu-Balti (L300) | Balti | Tartu | Overhead Line | 10 | 0 | 0 | AL | 400 | 3 | 168 | 0.02407 | 0.26863 | 4e-05 |  | 330 | 1394 | 1/ 1/ 2024 | Planning | 42 | 0.11 | ELERING | ELERING |  |  | 0 | 0
1013 | 170 | Viru-Tsirguliina 330kV OHL | Viru | Tsirguliina | Overhead Line | 10 | 0 | 0 | AL | 400 | 3 | 243 | 0.02407 | 0.28663 | 4e-05 |  | 330 | 1394 | 1/ 1/ 2025 | Planning | 47 | 0.15 | ELERING | ELERING |  |  | 0 | 0
1034 | 170 | New 400 kV interconnection line from Lithuania to state border | Marijampole | State border | Overhead Line | 10 | 0 | 0 | Al | 350 | 3 | 33 | 0.0263 | 10.837 | 13.818 |  | 400 | 2550 | 2024 | Under Consideration | 63.5 | 0.021 | LITGRID | LITGRID |  |  | 0 | 0
1118 | 170 | SVC and control upgrades | Eesti 330 kV | - | Compensation | 10 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 330 | 0 | 1/ 1/ 2024 | Under Consideration | 0 | 0 | LITGRID; AST; ELERING | - |  |  | 0 | 0
1564 | 170 | New 110 kV OHL Pagegiai-Bitenai near LT-RU border | Pagegiai | Bitenai | Overhead Line | 10 |  |  | Al | 150 | 1 | 17 | 0.21 | 0.41 | 2.86 |  | 110 | 450 | 2019 | In permitting | 4 | 0.011 | LITGRID | LITGRID |  |  |  | 0 | 0
1565 | 170 | Reconstruction of 330 kV OHL LE-Vilnius | LE | Vilnius | Overhead Line | 10 |  |  | Al | 300 | 2 | 41 | 0.0526 | 0.3252 | 3.4524 |  | 330 | 1380 | 2018 | In permitting | 21 | 0.027 | LITGRID | LITGRID |  |  |  | 0
1566 | 170 | Reconstructions in North Eastern Lithuania | - | - | Substation | 10 |  |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 330 | 0 | 2021 | In permitting | 21 | 0.021 | LITGRID | LITGRID |  |  |  | 0
1567 | 170 | Reinforcements of 110 kV lines near LT-BY border | Griskonys | Valkininkai | Overhead Line | 10 |  |  | Al | 185 | 1 | 42.4 | 0.17 | 0.395 | 2.89 |  | 110 | 450 | 2023 | Under Consideration | 7 | 0.028 | LITGRID | - |  |  |  | 0
1568 | 170 | Construction of new 400/330 kV autotransformers in Alytus substation | Alytus | - | Substation | 10 |  |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 1050 | 2021 | Under Consideration | 18 | 0.018 | LITGRID | - |  |  |  | 0
1569 | 170 | Rerouting of exicting HVDC converter in Alytus | Alytus | - | LCC converter station | 20 | 20 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 2024 | Under Consideration | 1 | 0.001 | LITGRID | - | 0 | 0 | 500 | 0
1570 | 170 | Construction of new HVDC converter in Bitenai | Bitenai | - | LCC converter station | 20 | 10 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 2024 | Under Consideration | 200 | 0.5 | LITGRID | - | 2% | 0 | 700 | 0
1571 | 170 | New voltage control units (such as SVC) in LT | - | - | Substation | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Under Consideration | 30 | 0.03 | LITGRID | - |  |  |  | 0 | 0
1572 | 170 | Preparation works in Baltics: Baltic AGC system, frequency control monitoring system. | - | - | Substation | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2024 | Under Consideration | 6 | 0.006 | LITGRID; AST; ELERING | - |  |  |  | 0 | 0
1632 | 170 | New 330 kV Musa substation | Musa | - | Substation | 10 |  |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 330 | 0 | 2023 | Under Consideration | 4 | 0.004 | - | - |  |  |  | 0
1633 | 170 | Reconstruction of 330 kV OHL Klaipeda - Bitenai | Klaipeda | Bitenai | Overhead Line | 10 |  |  | Al | 400 | 2 | 92 | 0.0391 | 0.322 | 3.51 |  | 330 | 1650 | 2024 | Under Consideration | 19 | 0.06 | LITGRID | - |  |  |  | 0
1634 | 170 | Reconstruction of 330 kV OHL Bitėnai - Jurbarkas | Bitenai | Jurbarkas | Overhead Line | 10 |  |  | Al | 400 | 2 | 43.6 | 0.0391 | 0.322 | 3.51 |  | 330 | 1650 | 2024 | Under Consideration | 9 | 0.028 | LITGRID | - |  |  |  | 0
1635 | 170 | New 330 kV OHL Jurbarkas - KHAE | Jurbarkas | KHAE | Overhead Line | 10 |  |  | Al | 400 | 2 | 75 | 0.0391 | 0.322 | 3.51 |  | 330 | 1650 | 2024 | Under Consideration | 16 | 0.049 | LITGRID | - |  |  |  | 0
1487 | 172 | ElecLink | Sellindge (UK) | Mandarins (FR) | Underground Cable | 20 | 10 | 345 | Aluminium |  |  | 69 |  |  |  | 2% or 7 days | 320 | 1600 | 2019 | In permitting | 580 | 4.5 | National Grid Electricty Transmission, the GB TSO | Reseau de Transport d'Electricite, the French TSO | 1.5% or 5.5 days | 0.5% or 1.5 days | 1000 | 28
1281 | 173 | Aubange-Moulaine: PSTs | Aubange (BE) | Moulaine (FR) | Phase Shift Transformer | 10 | 0 | 0 | N/A | 0 | 0 | 0 | 0.059 | 0.418 | 1.9 |  | 220 | 0 | 31/12/2020 | Under Consideration | 20 | 0.1 | ELIA | RTE |  |  | 0 | 0
1014 | 174 | Greenconnector | Verderio | Sils i.D. | Underground Cable | 20 | 20 | 0 | Copper/Aluminum | 0 | 0 | 150 | 0 | 0 | 0 | 72 hours | 400 | 1350 | 2022 | Planned but not yet permitting | 609 | 1.9 | Terna | Swissgrid | 1 week/year/monopole | 0.2 faults/year/bipole | 1000 | 120 | 0.5% or 1.5 days
1000 | 175 | Great Belt II | Malling (DKW) | Kyndby (DKE) | Subsea Cable | 20 | 10 | 200 | not decided | 0 | 0 | 120 | 0 | 0 | 0 | 600 MW | 400 | 1.5 | 2030 | 0 | 300 | 6 | Energinet | Energinet | 4 % | 4 % | 600 | 0
995 | 176 | Hansa PowerBridge | Hurva (SE4) | Guestrow (DE) | Subsea Cable | 20 | 10 | 300 | not decided | 0 | 0 | 300 | 0 | 0 | 0 | n/a | 300 | 2400 | 2026 | Planned but not yet permitting | 660 | 0 | Svk | 50Hertz | 3.5 % (13 days) | 4 % (15 days) | 700 | 180 | 0.2 faults/year/bipole
889 | 177 | PST Hradec | Hradec |  | Phase Shift Transformer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2016 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0 | 4 %
1016 | 179 | DKE-DE (Kontek 2) | Bjæverskov (DK2) | Bentwisch (DE) | Subsea Cable | 20 | 20 | 0 | Not decided | 0 | 0 | 170 | 0 | 0 | 0 | 600 MW | 400 | 1.5 | 2030 | 0 | 360 | 7.2 | Energinet | 50Hertz | 4 % | 4 % | 600 | 0 | 4 % (15 days)
1018 | 183 | DKW-DE, Westcoast, TYNDP ID 183.1018 | Klixbüll (DE) | Endrup (DKW) | Overhead Line | 10 | 0 | 0 | Double Circuit | 36.2 | 3 | 92 | 0.019782 | 0.16826 | 4.9375 |  | 380 | 4988 | 31/ 12/ 2022 | Planned but not yet permitting | 313 | 2 | TenneT-DE | Energinet.dk |  |  | 0 | 0
594 | 184 | PST Arkale | Arkale (ES) |  | Phase Shift Transformer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 220 | 0 | 1/ 1/ 2017 | Permitting | 0 | 0 |  |  |  |  | 0 | 0 | 4 %
886 | 186 | 886 | Seyring | Neusiedl/Zaya | Overhead Line | 10 | 0 | 0 | Double Circuit | 764.54 | 3 | 60 | 0.0242 | 0.3071 | 4.1798 |  | 380 | 3618 | 2021 | Planned but not yet permitting | 180 | 1.44 | APG | APG |  |  | 0 | 0
997 | 187 | 997 Pleinting - St. Peter | Pleinting (DE) | St. Peter (AT) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 3 | 60 | 0.0132 | 0.256 | 4.43 |  | 380 | 3600 | 2024 | Planned but not yet permitting | 197 | 1.576 | TenneT-DE | APG |  |  | 0 | 0
1389 | 189 | Irish Scottish Links on Energy Study (ISLES) | Argyll Hub | N/A |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under consideration | 0 | 0 |  |  |  |  | 0 | 0
1390 | 189 | Irish Scottish Links on Energy Study (ISLES) | Coleraine Hub | N/A |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1391 | 189 | Irish Scottish Links on Energy Study (ISLES) | coolkeeragh hub | N/A |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1392 | 189 | Irish Scottish Links on Energy Study (ISLES) | Argyll hub | Coleraine |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1393 | 189 | Irish Scottish Links on Energy Study (ISLES) | Coolkeeragh | Coolkeeragh hub |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1394 | 189 | Irish Scottish Links on Energy Study (ISLES) | Coleraine substation | Coolkeeragh hub |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1395 | 189 | Irish Scottish Links on Energy Study (ISLES) | Southern Hub | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1396 | 189 | Irish Scottish Links on Energy Study (ISLES) | Coleraine hub | Coolkeeragh hub |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1397 | 189 | Irish Scottish Links on Energy Study (ISLES) | Southern Hub UK | Trawsfynydd |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1398 | 189 | Irish Scottish Links on Energy Study (ISLES) | Hunterston | Coleraine |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1399 | 189 | Irish Scottish Links on Energy Study (ISLES) | Southern Hub | Trawsfynydd |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1400 | 189 | Irish Scottish Links on Energy Study (ISLES) | Trawsfynydd | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1401 | 189 | Irish Scottish Links on Energy Study (ISLES) | Southern Hub | Pembroke |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1402 | 189 | Irish Scottish Links on Energy Study (ISLES) | Southern Hub | Pembroke |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1403 | 189 | Irish Scottish Links on Energy Study (ISLES) | Southern Hub | Lodgewood |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1404 | 189 | Irish Scottish Links on Energy Study (ISLES) | Southern Hub | Lodgewood |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1406 | 189 | Irish Scottish Links on Energy Study (ISLES) | Pembroke | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1408 | 189 | Irish Scottish Links on Energy Study (ISLES) | Lodgewood | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1411 | 189 | Irish Scottish Links on Energy Study (ISLES) | Central Hub | Southern Hub |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1412 | 189 | Irish Scottish Links on Energy Study (ISLES) | Central Hub | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1413 | 189 | Irish Scottish Links on Energy Study (ISLES) | Central Hub | Dunstown |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1414 | 189 | Irish Scottish Links on Energy Study (ISLES) | Central Hub | Dunstown |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9999 |  | 0 | 0 |  |  |  |  | 0 | 0
1415 | 189 | Irish Scottish Links on Energy Study (ISLES) | Central hub | Trawsfynydd |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9999 |  | 0 | 0 |  |  |  |  | 0 | 0
1416 | 189 | Irish Scottish Links on Energy Study (ISLES) | Central Hub | Trawsfynydd |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9999 |  | 0 | 0 |  |  |  |  | 0 | 0
1417 | 189 | Irish Scottish Links on Energy Study (ISLES) | Trawsfynydd | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9999 |  | 0 | 0 |  |  |  |  | 0 | 0
1418 | 189 | Irish Scottish Links on Energy Study (ISLES) | Dunstown | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9999 |  | 0 | 0 |  |  |  |  | 0 | 0
1419 | 189 | Irish Scottish Links on Energy Study (ISLES) | Central Hub | Woodland |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9999 |  | 0 | 0 |  |  |  |  | 0 | 0
1420 | 189 | Irish Scottish Links on Energy Study (ISLES) | Central Hub | Woodland |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9999 |  | 0 | 0 |  |  |  |  | 0 | 0
1421 | 189 | Irish Scottish Links on Energy Study (ISLES) | Northern Hub | Central Hub |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9999 |  | 0 | 0 |  |  |  |  | 0 | 0
1422 | 189 | Irish Scottish Links on Energy Study (ISLES) | Northern Hub | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9999 |  | 0 | 0 |  |  |  |  | 0 | 0
1423 | 189 | Irish Scottish Links on Energy Study (ISLES) | Northern Hub | Louth |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1424 | 189 | Irish Scottish Links on Energy Study (ISLES) | Northern Hub | Louth |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1425 | 189 | Irish Scottish Links on Energy Study (ISLES) | Northern Hub | Louth |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1426 | 189 | Irish Scottish Links on Energy Study (ISLES) | Louth | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1427 | 189 | Irish Scottish Links on Energy Study (ISLES) | Woodland | n/a |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1428 | 189 | Irish Scottish Links on Energy Study (ISLES) | Northern Hub | Louth |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1429 | 189 | Irish Scottish Links on Energy Study (ISLES) | Northern Hub | Louth |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 300 | 0 | 1/1/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1382 | 190 | NorthConnect | Sima | Peterhead | Subsea Cable | 20 | 10 | 0 | Undecided | 0 | 0 | 655 | 0 | 0 | 0 | 1400MW | 500 | 0 | 2022 | Design | 1813 | 30 | Statnett | National Grid (SSEN is TO) | TBC | TBC | 1400 | 0
656 | 191 | BorWin3 | Cluster BorWin3 | Emden/East (DE) | Subsea Cable | 20 | 10 | 900 | single circuit | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 320 | 0 | 2019 | In permitting | 1318 | 11 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0
952 | 191 | Cluster DolWin 5 (NOR 1-1) | Cluster DolWin 5 (NOR-1-1) | Emden/East (DE) | Subsea Cable | 20 | 10 | 900 | single circuit | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 320 | 0 | 2024 | Under Consideration | 1228 | 10 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 | TBC
953 | 191 | Cluster DolWin6 | Cluster DolWin 6 (NOR-3-3) | Emden/East | Subsea Cable | 20 | 10 | 900 | single circuit | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 320 | 0 | 2023 | In permitting | 1178 | 10 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 | 0
1513 | 191 | DolWin3 | Cluster DolWin3 (DE) | Dörpen/West (DE) | Subsea Cable | 20 | 10 | 900 | single circuit |  |  | 162 |  |  |  | 0 | 320 | 0 | 2018 | In permitting | 1290 | 10 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 | 0
211 | 192 | DolWin 4 (NOR-3-2) | Cluster DolWin 4 (NOR 3-2) | area of Cloppenburg | Subsea Cable | 20 | 10 | 900 | single circuit | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 320 | 0 | 2028 | Under Consideration | 1378 | 11 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 | 0
659 | 192 | SylWin2 | Cluster SylWin2 (DE) | Büttel (DE) | Subsea Cable | 20 | 10 | 536 | single circuit | 0 | 0 | 205 | 0 | 0 | 0 | 0 | 320 | 0 | 2025 | Under Consideration | 1408 | 11 | TenneT-DE | TenneT-DE | 0 | 0 | 536 | 0 | 0
954 | 192 | Cluster BorWin 5 (NOR-7-1) | Cluster BorWin 5 (NOR-7-1) | area of Cloppenburg/East | Subsea Cable | 20 | 10 | 900 | single circuit | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 320 | 0 | 2025 | Under Consideration | 1518 | 12 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 | 0
1485 | 192 | BorWin4 | Cluster BorWin4 (DE) | area of Cloppenburg/East | Subsea Cable | 20 | 10 | 900 | single circuit |  |  | 272 |  |  |  | 0 | 320 | 0 | 2030 | Under Consideration | 1542 | 12 | TenneT DE | TenneT DE | 0 | 0 | 900 | 0 | 0
927 | 193 | La Plana/Morella-Godelleta | La Plana/Morella | Godelleta | Overhead Line | 10 | 0 | 0 | Condor | 454.5 | 3 | 207.5 | 0.0256 | 0.2729 | 4.0993 |  | 400 | 2815 | 2025 | 0 | 67.62 | 1.0143 | REE | REE |  |  | 0 | 0 | 0
561 | 194 | New substation Cartuja | Cartuja (ES) | Cartuja (ES) | Substation | 10 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2029 | 0 | 3.1 | 0.0465 | REE | REE |  |  | 0 | 0 | 0
929 | 194 | Cartuja-Arcos 400 kV | Cartuja | Arcos | Overhead Line | 10 | 0 | 0 | TX LARL CONDOR | 454.5 | 3 | 30 | 0.0256 | 0.2768 | 4.1588 |  | 400 | 2786 | 2029 | 0 | 20.2 | 0.303 | REE | REE |  |  | 0 | 0
742 | 197 | Pyhanselka-Petajavesi | Pyhanselka (FI) | Petajavesi (FI) | Overhead Line | 10 | 0 | 0 | 3-Finch | 636.6 | 3 | 300 | 0.0171 | 0.284 | 0.013 |  | 400 | 3150 | 1/ 7/ 2022 | Planned but not yet permitting | 90 | 0.242 | Fingrid | Fingrid |  |  | 0 | 0
136 | 198 | old Investment Border Area DE-AT - Meiningen - Rüthi -> now integrated in Swiss Roof II. Investment to be deleted. | Border area (DE-AT) | Rüthi (CH) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 45 | 0 | 0 | 0 |  | 380 | 0 | ? | 0 | 0 | 0 | Amprion;vuen | Swissgrid |  |  | 0 | 0
984 | 198 | old Investment "Herbertingen - Tiengen" -> now Project 321. Investment to be deleted | Herbertingen (DE) | Tiengen (DE) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 115 | 0 | 0 | 0 |  | 380 | 0 | 1/ 1/ 2020 | Planning | 0 | 0 |  |  |  |  | 0 | 0
986 | 198 | old Investment "Wullenstetten - border area (DE-AT)" -> now Project 322. Investment to be deleted | Wullenstetten (DE) | Austrian National border (AT) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 94 | 0 | 0 | 0 |  | 380 | 0 | 1/ 1/ 2020 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1051 | 199 | Cornier - Chavalon 400 kV | CORNIER (FR) | CHAVALON (CH) | Overhead Line | 10 | 0 | 0 | To be defined | 0 | 0 | 63 | 0.02 | 0.296 | 3.66 |  | 400 | 0 | 2035 | 0 | 130 | 1 | RTE | SWISSGRID |  |  | 0
306 | 200 | R Vitkov | Vitkov (CZ) | N/A | Substation | 10 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 30/ 11/ 2022 | Planned but not yet permitting | 34.46 | 1.65 | CEPS | N/A |  |  | 0 | 0
308 | 200 | Vernerov-Vitkov | Vernerov (CZ) | Vitkov (CZ) | Overhead Line | 10 | 0 | 0 | 490-AL1/64-ST1A | 490 | 3 | 79 | 0.02 | 0.28 | 3.95 |  | 400 | 2445 | 30/ 07/ 2025 | Planned but not yet permitting | 87.8 | 1.47 | CEPS | CEPS |  |  | 0 | 0
309 | 200 | Vitkov-Prestice | Vitkov (CZ) | Prestice (CZ) | Overhead Line | 10 | 0 | 0 | 490-AL1/64-ST1A | 490 | 3 | 86 | 0.02 | 0.28 | 3.95 |  | 400 | 2445 | 30/ 11/ 2022 | Planned but not yet permitting | 92.94 | 0.13 | CEPS | CEPS |  |  | 0 | 0
312 | 200 | R Mirovka | Mirovka (CZ) | N/A | Substation | 10 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 30/ 09/ 2025 | Planned but not yet permitting | 13.84 | 1.76 | CEPS | N/A |  |  | 0 | 0
314 | 200 | Mirkovka-V413 | Mirovka (CZ) | V413 (CZ) | Overhead Line | 10 | 0 | 0 | 490-AL1/64-ST1A | 490 | 3 | 27 | 0.02 | 0.28 | 3.95 |  | 400 | 2445 | 30/ 05/ 2019 | Planned but not yet permitting | 32.16 | 0.03 | CEPS | CEPS |  |  | 0 | 0
538 | 203 | Morella-La Plana | Morella (ES) | La Plana(ES) | Overhead Line | 10 | 0 | 0 | CONDOR | 454.5 | 3 | 78 | 0.033 | 0.3227 | 3.528 |  | 400 | 2815 | 2020 | Planned but not yet permitting | 50.76 | 0.7614 | REE | REE |  |  | 0 | 0
686 | 204 | Altenfeld-Grafenrheinfeld | Schalkau / area of Altenfeld (DE) | area of Grafenrheinfeld (DE) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 130 | 0 | 0 | 0 |  | 380 | 0 | 1/ 1/ 2024 | Planning | 0 | 0 |  |  |  |  | 0 | 0
153 | 205 | Redwitz - Grafenrheinfeld | Redwitz (DE) | Grafenrheinfeld (DE) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 97 | 0 | 0 | 0 |  | 380 | 0 | 1/ 1/ 2015 | Commissioned | 0 | 0 |  |  |  |  | 0 | 0
193 | 205 | Sdwestkuppelleitung | Vieselbach (DE) | Redwitz (DE) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 92 | 0 | 0 | 0 |  | 380 | 0 | 1/ 1/ 2016 | Under Construction | 0 | 0 |  |  |  |  | 0 | 0
682 | 206 | Großgartach - Endersbach | Großgartach (DE) | Endersbach (DE) | Overhead Line | 10 | 0 | 0 | - | 0 | 0 | 32 | 0.0129 | 0.26 | 0.014 |  | 380 | 0 | 2025 | Under Consideration | 10 | 0.1 | TransnetBW | TransnetBW |  |  | 0 | 0
687 | 206 | Redwitz - Schwandorf | Redwitz (DE) | Schwandorf (DE) | Overhead Line | 10 | 0 | 0 | - | 0 | 0 | 185 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2023 | Planned but not yet permitting | 340 | 2.7 | TenneT-DE | TenneT-DE |  |  | 0 | 0
688 | 206 | Raitersaich-Altheim | Raitersaich (DE) | Altheim (DE) | Overhead Line | 10 | 0 | 0 | - | 0 | 0 | 160 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2026 | Under Consideration | 330 | 2.6 | TenneT-DE | TenneT-DE |  |  | 0 | 0
990 | 206 | Grafenrheinfeld - Großgartach | Grafenrheinfeld (DE) | Großgartach (DE) | Overhead Line | 10 | 0 | 0 | - | 0 | 0 | 158 | 0.0215 | 0.249 | 0.0143 |  | 380 | 0 | 2022 | Planned but not yet permitting | 150 | 1.2 | TenneT-DE | TransnetBW |  |  | 0 | 0
676 | 207 | Dollern - Elsfleth/West | Dollern (DE) | Elsfleht/West (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 100 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2026 | Planned but not yet permitting | 180 | 1.4 | TenneT-DE | TenneT-DE |  |  | 0 | 0
939 | 207 | Conneforde - Emden | Conneforde | Emden/Ost | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 60 | 0.0133 | 0.264 | 10.8 |  | 380 | 0 | 2021 | Planned but not yet permitting | 220 | 1.8 | TenneT-DE | TenneT-DE |  |  | 0 | 0
940 | 207 | Emden - Halbemond | Emden/Ost | Halbemond | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 30 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2022 | Under Consideration | 80 | 0.6 | TenneT-DE | TenneT-DE |  |  | 0 | 0
150 | 208 | Conneforde-Wilhelmshaven | Conneforde (DE) | Wilhelmshaven (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 30 | 0.0133 | 0.272 | 18.3 |  | 380 | 0 | 2020 | Planned but not yet permitting | 140 | 1.1 | TenneT-DE | TenneT-DE |  |  | 0 | 0
151 | 208 | Ganderkesee - Wehrendorf | Wehrendorf (DE) | Ganderkesee (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 95 | 0.0132 | 0.256 | 0.05 |  | 380 | 3600 | 2021 | Planned but not yet permitting | 330 | 2.6 | TenneT-DE | TenneT-DE |  |  | 0 | 0
156 | 208 | Niederrhein-Dörpen | Niederrhein (DE) | Dörpen/West (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 182 | 0.0132 | 0.256 | 0.05 |  | 380 | 3600 | 2021 | Planned but not yet permitting | 540 | 4.3 | Amprion | TenneT-DE |  |  | 0 | 0
935 | 209 | Kreis Segeberg - Siems | Kreis Segeberg | Göhl/Siems | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 110 | 0.0123 | 0.25 | 14.9 |  | 380 | 0 | 2022 | Under Consideration | 320 | 2.6 | TenneT-DE | TenneT-DE |  |  | 0 | 0
1380 | 210 | Wurmlach (AT) - Somplago (IT) interconnection | SOMPLAGO | WURMLACH | Underground Cable | 10 | 0 | 0 | Aluminum cable | 2000 | 1 | 51 | 0.0149 | 0.107 | 75.36 |  | 220 | 800 | 2021 | Planned but not yet permitting | 92 | 1.6 | TERNA SPA | Austrian Power Grid AG |  |  | 0 | 51
1082 | 214 | Interco Iceland-UK | tbd | tbd | Subsea Cable | 20 | 10 | 0 | TBD | 0 | 0 | 1000 | 0 | 0 | 0 | TBD | 500 | 0 | 2030 | 0 | 1800 | 21 | tbd | tbd | TBD | TBD | 1000 | 0
999 | 216 | North Massif Central | Marmagne or Eguzon | Rueyres | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 275 | 0 | 0 | 0 |  | 400 | 0 | 1/ 1/ 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1407 | 219 | EuroAsia Interconnector | Hadera Site | Kofinou Site | Subsea Cable | 20 | 10 | 0 | XLPE | 0 | 0 | 330 | 0 | 0 | 0 | 1000 MW | 500 | 0 | 2020 | Planned but not yet permitting | 5765 | 53.5 | IEC | TSO Cyprus | 2% | 5.93% | 2000 | 0 | TBD
1409 | 219 | EuroAsia Interconnector | Kofinou Site | Korakia (Crete)Site | Subsea Cable | 20 | 10 | 0 | XLPE | 0 | 0 | 880 | 0 | 0 | 0 | 1000MW | 500 | 0 | 2021 | Planned but not yet permitting | 5765 | 53.5 | TSO Cyprus | ADMHE | 2% | 5.93% | 2000 | 0
1410 | 219 | EuroAsia Interconnector | Korakia (Crete)Site | Athens Site | Subsea Cable | 20 | 10 | 0 | XLPE | 0 | 0 | 310 | 0 | 0 | 0 | 1000 MW | 500 | 0 | 2020 | Planned but not yet permitting | 5765 | 53.5 | ADMHE | ADMHE | 2% | 5.93% | 2000 | 0 | 5.93%
1107 | 225 | 2nd interconnecter between Belgium and Germany | to be defined (BE) | to be defined (DE) | Underground Cable | 20 | 10 | 0 | XLPE | 0 | 0 | 150 | 0 | 0 | 0 | 1 | 0 | 0 | 2028 | 0 | 600 | 4.8 | ELIA | AMPRION | 48 | 284 | 1000 | 75 | 5.93%
627 | 227 | 400kV interconnection RS-BA | Bajina Basta (RS) | Visegrad (BA) | Overhead Line | 10 | 0 | 0 | ACSR | 490 | 2 | 45.2 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2024 | Planned but not yet permitting | 19.6 | 0.24 | EMS | NOSBIH |  |  | 0 | 26.2 | 5.93%
628 | 227 | 400kV OHL B.Basta-Obrenovac | SS Bajina Basta (RS) | SS Obrenovac (RS) | Overhead Line | 10 | 0 | 0 | ACSR | 490 | 2 | 109 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2024 | Planned but not yet permitting | 55 | 0.66 | EMS | EMS |  |  | 0 | 0 | 284
630 | 227 | 400kV interconnection RS-ME | Bajina Basta (RS) | Pljevlja (ME) | Overhead Line | 10 | 0 | 0 | ACSR | 490 | 2 | 100 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2024 | Planned but not yet permitting | 44.4 | 0.53 | EMS | CGES |  |  | 0 | 0
631 | 227 | 400kV SS B.Basta upgrade | Bajina Basta (RS) | Bajina Basta (RS) | Substation | 10 | 0 | 0 | ALFE | 490 | 2 | 0 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2024 | Planned but not yet permitting | 0 | 0 | EMS | EMS |  |  | 0 | 0
1526 | 227 | 400 kV OHL Lastva - Pljevlja | SS Lastva | SS Pljevlja | Overhead Line | 10 |  |  | ACSR | 490 | 2 | 151 | 0.0294 | 0.341 | 3.371 |  | 400 | 2000 | 2019 | In permitting | 67.5 | 1.35 | CGES | CGES |  |  |  | 0
1527 | 227 | 400 kV OHL Kragujevac-Kraljevo | SS Kragujevac | SS Kraljevo | Overhead Line | 10 |  |  | ACSR | 490 | 2 | 60 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2020 | In permitting | 17 | 0.2 | EMS | EMS |  |  |  | 0
1528 | 227 | Upgrade of SS Kraljevo | SS Kraljevo | SS Kraljevo | Substation | 10 |  |  | ACSR | 490 | 2 | 0 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2020 | In permitting | 10.5 | 0.13 | EMS | EMS |  |  |  | 0
1231 | 228 | Muhlbach Eichstetten | Muhlbach | Eichstetten | Overhead Line | 10 | 0 | 0 | 0 | 0 | 0 | 32 | 0.024 | 0.282 | 4.45 |  | 400 | 0 | 2025 | Under Consideration | 42 | 0.7 | RTE | TransnetBW GmbH |  |  | 0 | 0
1270 | 229 | Baczyna-Zielona Góra | Baczyna-Plewiska indentation | Zielona Góra | Overhead Line | 10 | 0 | 0 | 468/24-A1F/UHST-261 | 468 | 3 | 40 | 0.0216 | 0.2919 | 3.927 |  | 400 | 3200 | >2030 | In permitting | 19 | 0.057 | PSE S.A. | PSE S.A. |  |  | 0 | 0
1271 | 229 | Zielona Góra - Plewiska | Zielona Góra | Baczyna-Plewiska indentation | Overhead Line | 10 | 0 | 0 | 468/24-A1F/UHST-261 | 468 | 3 | 40 | 0.0216 | 0.2919 | 3.927 |  | 400 | 3200 | >2030 | 0 | 19 | 0.057 | PSE S.A. | PSE S.A. |  |  | 0 | 0
1272 | 229 | Zielona Góra | Zielona Góra | n.a. | Substation | 10 | 0 | 0 | n.a. | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | >2030 | 0 | 23.7 | 0.711 | PSE S.A. | n.a. |  |  | 0 | 0
1273 | 229 | Zielona Góra-Gubin | Zielona Góra | Gubin | Overhead Line | 10 | 0 | 0 | 468/24-A1F/UHST-261 | 468 | 3 | 60 | 0.0216 | 0.2919 | 3.927 |  | 400 | 3200 | >2030 | 0 | 28.4 | 0.085 | PSE S.A. | PSE S.A. |  |  | 0 | 0
1274 | 229 | Gubin | Gubin | n.a. | Substation | 10 | 0 | 0 | n.a. | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | >2030 | 0 | 66.7 | 2.001 | PSE S.A. | n.a. |  |  | 0 | 0
1275 | 229 | Gubin - Eisenhuettenstadt | Gubin (PL) | Eisenhuettenstadt (DE) | Overhead Line | 10 | 0 | 0 | 468/24-A1F/UHST-261 | 468 | 3 | 20 | 0.0216 | 0.2919 | 3.927 |  | 400 | 3200 | >2030 | 0 | 15 | 0.045 | PSE S.A. | 50Hertz |  |  | 0 | 10
353 | 230 | Krajnik-Baczyna | Krajnik (PL) | Baczyna (PL) | Overhead Line | 10 | 0 | 0 | 408-AL1F/34-UHST | 408 | 3 | 70 | 0.0245 | 0.2917 | 3.927 |  | 400 | 3200 | 2021 | Planned but not yet permitting | 38.7 | 0.116 | PSE S.A. | PSE S.A. |  |  | 0 | 0
355 | 230 | Mikułowa - Świebodzice | Mikułowa (PL) | Świebodzice (PL) | Overhead Line | 10 | 0 | 0 | 468/24-A1F/UHST-261 | 468 | 3 | 100 | 0.0216 | 0.2919 | 3.927 |  | 400 | 3200 | 2023 | Under Consideration | 102.27 | 0.307 | PSE S.A. | PSE S.A. |  |  | 0 | 0
1035 | 230 | Baczyna | Baczyna | n.a. | Substation | 10 | 0 | 0 | n.a. | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2020 | Planned but not yet permitting | 22.5 | 0.675 | PSE S.A. | n.a. |  |  | 0 | 0
1232 | 230 | Baczyna-Plewiska | Baczyna | Plewiska | Overhead Line | 10 | 0 | 0 | 468/24-A1F/UHST-261 | 468 | 3 | 147 | 0.0216 | 0.2919 | 3.927 |  | 400 | 3200 | 2024 | Under Consideration | 107.22 | 0.7 | PSE S.A. | PSE S.A. |  |  | 0 | 0
1282 | 231 | 380 kV Grid Reinforcement Beznau - Tiengen | Beznau (CH) | Tiengen (DE) | Overhead Line | 10 | 0 | 0 | AL/ST | 550 | 4 | 11 | 0.0132 | 0.256 | 4.43 |  | 380 | 3600 | 2030 | 0 | 58 | 0.304 | Swissgrid | Amprion |  |  | 0 | 7
1457 | 231 | Additional measures | Germany | Switzerland | Overhead Line | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 | 2035 | 0 | 0 | 0 | TransnetBW | Swissgrid | 0 | 0 | 0 | 0
1234 | 232 | Investments to be created |  |  | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | > 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1235 | 233 | Conceptual project | - | - | Overhead Line | 10 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2027 | 0 | 75 | 1.125 | REE | REE |  |  | 0 | 0 | 0
1236 | 234 | DKE-PL-1 | Avedøre (DKE) | Dunowo (PL) | Subsea Cable | 20 | 10 | 200 | Not decided | 0 | 0 | 330 | 0 | 0 | 0 | 600 | 400 | 1.5 | >2030 | 0 | 700 | 14 | Energinet | PSE | 4 % | 4 % | 600 | 0
664 | 235 | HVDC Line C | "Brunsbüttel, Wilster" | "Großgartach, Grafenrheinfeld" | Underground Cable | 20 | 10 | 0 | - | 0 | 0 | 700 | 0 | 0 | 0 | tbd | 520 | 0 | 2025 | Planned but not yet permitting | 6500 | 52 | TenneT-DE | TransnetBW | tbd | tbd | 0 | 0
608 | 236 | HTLS upgrade Horta-Mercator | Horta (BE) | Mercator (BE) | Overhead Line | 10 | 0 | 0 | HTLS | 0 | 0 | 50 | 0.0205 | 0.3135 | 3.6195 |  | 380 | 0 | 31/12/2019 | In permitting | 100 | 0.2 | ELIA | ELIA |  |  | 0 | 0 | 4 %
1239 | 237 | Investments to be created |  |  | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | > 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0 | 0
1240 | 238 | Kontiskan 2 - Renewal | Lindome (SE3) | Vester Hassing (DkV) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 90 | 0 | 0 | 0 |  | 300 | 0 | >2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1241 | 239 | Fenno-Skan 1 renewal | Hjalta (SE2) | Tuovila (FI) | Subsea Cable | 20 | 10 | 300 | not decided | 0 | 0 | 200 | 0 | 0 | 0 | not known | 300 | 2700 | 2029 | 0 | 380 | 0.75 | SVK | FINGRID | 3.5 % (13 days) | 4 % (15 days) | 800 | 100
1460 | 240 | AC Enhancement Güstrow-Wolmirstedt | Güstrow (DE) | Wolmirstedt (DE) | Overhead Line | 10 |  |  | not defined yet | 0 | 0 | 192 | 0.01877 | 0.2447 | 66.3 |  | 380 | 3600 | 2021 | Planned but not yet permitting | 350 | 2.8 | 50Hertz Transmission | 50Hertz Transmission |  |  |  | 0
1276 | 241 | Upgrading of existing 220 kV line between SS Dakovo (HR) and TPP Tuzla (BA) to 400 kV line | Dakovo | Tuzla | Overhead Line | 10 | 0 | 0 | ACSR | 1107.8 | 2 | 91 | 0.02971 | 0.341 | 3.371 |  | 400 | 1905 | 31/12/2032 | 0 | 26 | 0.033 | HOPS | NOS BIH |  |  | 0 | 26 | 4 % (15 days)
1277 | 241 | Upgrading of existing 220 kV line between SS Dakovo (HR) and Gradacac (BA) to 400 kV line | Dakovo | Gradacac | Overhead Line | 10 | 0 | 0 | ACSR | 1107.8 | 2 | 46.2 | 0.031875 | 0.3243 | 3.4865 |  | 400 | 1905 | 31/12/2032 | 0 | 14.07 | 0.018 | HOPS | NOS BIH |  |  | 0 | 29.3
1278 | 241 | Upgrading existing 220 kV SS Dakovo to 400 kV | Dakovo | Dakovo | Substation | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 31/12/2032 | 0 | 11 | 0.0141 | HOPS | HOPS |  |  | 0 | 0
1279 | 241 | New double 400 kV line between SS Dakovo and location Razbojiste | Dakovo | Razbojiste | Overhead Line | 10 | 0 | 0 | ACSR | 1107.8 | 2 | 25 | 0.031875 | 0.3243 | 3.4865 |  | 400 | 1905 | 31/12/2032 | 0 | 10.375 | 0.0133 | HOPS | HOPS |  |  | 0 | 0
1530 | 241 | Upgrading of existing 220 kV line between SS Gradacac (BA) and TPP Tuzla (BA) to 400 kV line | SS Gradacac (BA) | TPP Tuzla (BA) | Overhead Line | 10 |  |  | ACSR | 1107.8 | 2 | 47.8 | 0.031875 | 0.3243 | 3.4865 |  | 400 | 1905 | 2032 | 0 | 13.7 | 0.0176 | NOS BIH | NOS BIH |  |  |  | 0
1531 | 241 | Upgrading existing 220 kV SS Gradacac (BA) to 400 kV | SS Gradacac (BA) | SS Gradacac (BA) | Substation | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2032 | 0 | 7.9 | 0.01 | NOS BIH | NOS BIH |  |  |  | 0
194 | 242 | Offshore Connection Cluster 1 | OWF Cluster Baltic Sea East (DE) | Lubmin (DE) | Subsea Cable | 10 | 0 | 0 | Cu | 0 | 0 | 100 | 0.0243 | 0.119 | 61.26 |  | 220 | 0 | 2018 | In permitting | 1605 | 54.57 | 50Hertz | 50Hertz |  |  | 0 | 0
1269 | 243 | New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | Ernestinovo | Sombor | Overhead Line | 10 | 0 | 0 | ACSR | 1107.8 | 2 | 70 | 0.031875 | 0.3243 | 3.4865 |  | 400 | 1905 | 01/01/2035 | 0 | 19.04 | 0.0245 | HOPS | EMS |  |  | 0 | 38
1245 | 244 | Vigy - Uchtelfangen (or beyond) | Vigy (FR) | Uchtelfangen (DE) | Overhead Line | 10 | 0 | 0 | HTLS | 300 | 4 | 65 | 0.0132 | 0.256 | 4.43 |  | 400 | 3600 | 2027 | Under Consideration | 60 | 0.48 | Rte | Amprion |  |  | 0 | 31
1514 | 244 | Power flow control between Vigy - Uchtelfangen | Vigy (FR) | Uchtelfangen (DE) | Phase Shift Transformer | 10 |  |  | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 3600 | 2027 | Under Consideration | 60 | 0.48 | Rte | Amprion |  |  |  | 0
1246 | 245 | Upgrade Meeden - Diele | Meeden [NL] | Diele [DE] | Overhead Line | 10 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 |  | 380 | 0 | 2019 | In permitting | 35 | 0 | TENNET-NL | TENNET-DE |  |  | 0 | 0
1381 | 247 | AQUIND Interconnector | Lovedean (GB) | Barnabos (FR) | Subsea Cable | 20 | 10 | 708 | XLPE | 0 | 0 | 250 | 0 | 0 | 0 | 1000MW (The maximum single failure of AQUIND Interconnector is expected to be induced by a cable fault or the failure of a key item of equipment in one converter pole, this would equate to the loss of 1000MW of power transfer capability. Very little mitigation of the impact on the AC network can be anticipated due to the limited thermal capability of the semi-conductor (transistor) devices.) | 320 | 1621.09 | 2022 | Planned but not yet permitting | 1400 | 29 | National Grid plc | Réseau de transport d'électricité | 0.66% | 1.00% | 2000 | 125
1248 | 248 | AC Offshore Connection Cluster 1, 2,4 | OWF Cluster Baltic Sea (DE) | Lubmin (DE) | Subsea Cable | 10 | 0 | 0 | Cu | 0 | 0 | 100 | 0.0243 | 0.119 | 61.26 |  | 220 | 0 | 2022 | Under Consideration | 1605 | 54.57 | 50Hertz | 50Hertz |  |  | 0 | 0
1613 | 248 | DC Offshore Connection Cluster 1, 2, 4 | OWF Cluster Baltic Sea (DE) | Siedenbrünzow/Alt Telin/Bartow (DE) | Subsea Cable | 20 | 10 | 0 | Cu |  |  | 210 |  |  |  | 0 | 320 | 0 | 2027 | Planned but not yet permitting | 1461 | 49.67 | 50Hertz | 50Hertz | 0 | 0 | 900 | 0 | 24 hours/year
1627 | 248 | Offshore Connection Cluster 6 | OWF Cluster Baltic Sea (DE) | Sanitz/Dettmannsdorf | Subsea Cable | 10 |  |  | Not decided yet | 0 | 0 | 250 | 0.243 | 0.119 | 61.26 |  | 220 | 0 | 2029 | Under Consideration | 1236 | 49.94 | 50Hertz Transmission | 50Hertz Transmission |  |  |  | 0
1219 | 249 | Cubnezais - Marmagne | "Cubnezais " | Marmagne | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 300 | 0 | 0 | 0 |  | 400 | 0 | 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0 | 0
1221 | 249 | Marmagne - Tabarderie | "Marmagne " | Tabarderie | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 | 0 |  | 400 | 0 | 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1384 | 250 | "Merchant line ""Castasegna (CH) - Mese (IT)""" | Castasegna | Mese | Underground Cable | 10 | 0 | 0 | 3 x XLPE Cu | 500 | 1 | 0 | 0.0366 | 0.25 | 27.3 |  | 220 | 766 | 2021 | Planned but not yet permitting | 90 | 0.1 | swissgrid | Terna |  |  | 0 | 0.4
147 | 251 | Dollern - Hamburg/Nord | Dollern (DE) | Hamburg/Nord (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 45 | 0.0132 | 0.242 | 4.7 |  | 380 | 0 | 2018 | In permitting | 160 | 1.3 | TenneT-DE | TenneT-DE |  |  | 0 | 0
148 | 251 | Audorf - Hamburg/Nord | Audorf (DE) | Hamburg/Nord (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 65 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2017 | In permitting | 230 | 1.8 | TenneT-DE | TenneT-DE |  |  | 0 | 0
1050 | 252 | Van Eyck - Gramme: HTLS upgrade | Van Eyck | Gramme | Overhead Line | 10 | 0 | 0 | HTLS | 0 | 0 | 90 | 0.0205 | 0.3135 | 3.6195 |  | 380 | 0 | 31/12/2029 | 0 | 140 | 0.4 | ELIA | ELIA |  |  | 0 | 0
1456 | 252 | Massenhoven - Van Eyck: HTLS upgrade | Massenhoven (BE) | Van Eyck (BE) | Overhead Line | 10 | 0 | 0 | HTLS | 0 | 0 | 90 | 0.0332 | 0.3139 | 3.6456 |  | 380 | 0 | 31/12/2024 | 0 | 120 | 0.4 | ELIA | ELIA |  |  | 0 | 0
1515 | 252 | Gramme - Courcelles: HTLS upgrade | Gramme | Courcelles | Overhead Line | 10 |  |  | HTLS | 0 | 0 | 60 | 0.0205 | 0.3135 | 3.6195 |  | 380 | 0 | 2033 | 0 | 150 | 0.3 | ELIA | ELIA |  |  |  | 0
1516 | 252 | Bruegel - Courcelles: HTLS upgrade | Bruegel | Courcelles | Overhead Line | 10 |  |  | HTLS | 0 | 0 | 47 | 0.0205 | 0.3135 | 3.6195 |  | 380 | 0 | 2035 | 0 | 110 | 0.2 | ELIA | ELIA |  |  |  | 0
1517 | 252 | Mercator - Bruegel: HTLS upgrade | Mercator | Bruegel | Overhead Line | 10 |  |  | HTLS | 0 | 0 | 16 | 0.0205 | 0.3135 | 3.6195 |  | 380 | 0 | 2025 | 0 | 80 | 0.1 | ELIA | ELIA |  |  |  | 0
1224 | 253 | Uprate of Creys-St Vulbas | Creys(FR) | Saint Vulbas (FR) | Overhead Line | 10 | 0 | 0 | HTLS | 0 | 0 | 21 | 0.021 | 0.305 | 3.8 |  | 400 | 0 | 2031 | 0 | 45 | 0.5 | RTE | RTE |  |  | 0 | 0
1225 | 253 | PST in Cornier | Cornier (FR) | Cornier (FR) | Phase Shift Transformer | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 10.8 | 0 |  | 400 | 0 | 2031 | 0 | 15 | 0.1 | RTE | RTE |  |  | 0 | 0
660 | 254 | HVDC Line A South - Ultranet | Osterath (DE) | Philippsburg (DE) | Overhead Line | 20 | 10 | 0 | line | 0 | 0 | 340 | 0 | 0 | 0 | tbd | 400 | 0 | 01/01/2021 | Planned but not yet permitting | 1070 | 8.6 | Amprion | TransnetBW | tbd | tbd | 0 | 0
1251 | 255 | New line 400 kV Muruarte-Ichaso | Muruarte | Ichaso | Overhead Line | 10 | 0 | 0 | TX LARL CONDOR | 454.5 | 3 | 145 | 0.0263 | 0.2824 | 4.2448 |  | 400 | 2843 | 2023 | Planned but not yet permitting | 37.75 | 0.566 | REE | REE |  |  | 0 | 0
1455 | 255 | New line 400 kV Castejon-Ichaso | Castejon | Ichaso | Overhead Line | 10 | 0 | 0 | TX LARL CONDOR | 454.5 | 3 | 169 | 0.0262 | 0.2816 | 4.2326 |  | 400 | 2843 | 2023 | Planned but not yet permitting | 37.75 | 0.566 | REE | REE |  |  | 0 | 0 | tbd
1252 | 256 | Long term upgrade interconnection DE-NL | to be defined (DE) | to be defined (NL) | Overhead Line | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 380 | 0 | 2040 | 0 | 0 | 0 | Amprion | TENNET-NL |  |  | 0 | 0
1529 | 256 | Upgrade interconnection DE-NL | tbd | tbd | Phase Shift Transformer | 10 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 380 | 3600 | 2035 | 0 |  |  | Amprion | TENNET-NL |  |  |  | 1
1253 | 257 | Reinforcement in the Douro river area |  |  | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | > 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
667 | 258 | Brunsbttel - Klixbüll | Brunsbüttel (DE) | Klixbüll (DE) | Overhead Line | 10 | 0 | 0 | double circuit | 0 | 0 | 125 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2019 | Planned but not yet permitting | 360 | 2.9 | TenneT-DE | TenneT-DE |  |  | 0 | 0
1205 | 259 | HU-RO | Józsa | Oradea | Overhead Line | 10 | 0 | 0 | ALOL | 300 | 3 | 120 | 0.032 | 0.303 | 3.79 |  | 400 | 1382 | >2030 | 0 | 200 | 0.818 | MAVIR | Transelectrica |  |  | 0 | 30
1255 | 260 | Interconnector GB-NL | TBD | TBD | Subsea Cable | 20 | 10 | 0 | o | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 0 | 850 | 6 | National Grid | TENNET-NL | 0 | 0 | 0 | 0
1256 | 261 | Investments to be created |  |  | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0
1257 | 262 | Belgium-Netherlands: Zandvliet-Rilland | Zandvliet (BE) | Rilland (NL) | Overhead Line | 10 | 0 | 0 | HTLS | 0 | 0 | 10 | 0.023 | 0.307 | 3.677 |  | 380 | 0 | 2022 | Under Consideration | 50 | 0.1 | ELIA | TENNET-NL |  |  | 0 | 0 | 0
1258 | 263 | Rüthi - Bonaduz/Grynau | Rüthi | Grynau & Bonaduz | Overhead Line | 10 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 380 | 1 | 2035 | 0 | 53 | 0 | Swissgrid | Swissgrid |  |  | 0 | 0
1583 | 263 | Vorarlberg | Rüthi | Border area (DE-AT) | Overhead Line | 10 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 380 | 1 | 2035 | 0 | 300 | 1.5 | Swissgrid | VUEN |  |  |  | 0
1259 | 264 | Beznau - Mettlen | Beznau | Mettlen | Overhead Line | 10 | 0 | 0 | 1 | 1 | 1 | 64 | 1 | 1 | 1 |  | 380 | 1 | 2025 | Planned but not yet permitting | 66 | 0 | Swissgrid | Swissgrid |  |  | 0 | 0
1284 | 264 | Pradella - La Punt | Pradella | La Punt | Overhead Line | 10 | 0 | 0 | 1 | 1 | 1 | 49 | 1 | 1 | 1 |  | 380 | 1 | 2021 | In permitting | 94 | 0 | Swissgrid | Swissgrid |  |  | 0 | 0
1287 | 264 | Bassecourt - Mühleberg | Bassecourt | Mühleberg | Overhead Line | 10 | 0 | 0 | 1 | 1 | 1 | 45.4 | 1 | 1 | 1 |  | 380 | 1 | 2025 | Planned but not yet permitting | 126 | 0 | Swissgrid | Swissgrid |  |  | 0 | 0
1288 | 264 | Mettlen - Ulrichen | Mettlen | Ulrichen | Overhead Line | 10 | 0 | 0 | 1 | 1 | 1 | 87.1 | 1 | 1 | 1 |  | 380 | 0 | 2030 | Under Consideration | 210 | 0 | Swissgrid | Swissgrid |  |  | 0 | 0
1290 | 265 | Magadino - Ulrichen | Magadino | Ulrichen | Overhead Line | 10 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 220 | 0 | 2035 | Under Consideration | 160 | 0 | Swissgrid | Swissgrid |  |  | 0 | 0
1261 | 266 | Bickigen - Chippis - Chamoson | Bickigen | Chamoson | Overhead Line | 10 | 0 | 0 | 1 | 1 | 1 | 136 | 1 | 1 | 1 |  | 380 | 0 | 2021 | Planned but not yet permitting | 172 | 0 | Swissgrid | Swissgrid |  |  | 0 | 0
1285 | 266 | Magadino | Magadino | Magadino | Overhead Line | 10 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 |  | 380 | 1 | 2024 | Under Consideration | 30 | 0 | Swissgrid | Swissgrid |  |  | 0 | 0
1286 | 266 | Chippis - Lavorgo | Chippis | Lavorgo | Overhead Line | 10 | 0 | 0 | 1 | 1 | 1 | 124 | 1 | 1 | 1 |  | 380 | 0 | 2024 | Planned but not yet permitting | 310 | 0 | Swissgrid | Swissgrid |  |  | 0 | 0
1262 | 267 | Hansa PowerBridge II | Hurva (SE4) | Guestrow (DE) | Subsea Cable | 20 | 10 | 300 | not decided | 0 | 0 | 300 | 0 | 0 | 0 | n/a | 300 | 0 | 2030 | 0 | 660 | 0 | Svenska Kraftnat | 50Hertz | 3.5 % (13 days) | 4 % (15 days) | 700 | 180
1263 | 268 | Portile de Fier (RO) - Djerdap (RS) 2nd | Portile de Fier | Djerdap | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2035 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1228 | 269 | Uprate D.Rodrigo-Aljarafe | "D.Rodrigo " | Aljarafe | Overhead Line | 10 | 0 | 0 | Gull | 381 | 2 | 33.7 | 0.0639 | 0.3692 | 3.1994 |  | 220 | 1102 | 2019 | In permitting | 0.7 | 0.0105 | REE | REE |  |  | 0 | 0 | 4 % (15 days)
1229 | 269 | Uprate Aljarafe-Santiponce | Aljarafe | Santiponce | Overhead Line | 10 | 0 | 0 | Gull | 381 | 2 | 13 | 0.0849 | 0.4151 | 2.7495 |  | 220 | 1102 | 2019 | Planned but not yet permitting | 0.3 | 0.0045 | REE | REE |  |  | 0 | 0
1211 | 270 | HVDC Aragon region -Marsillon | "Aragon region" | Marsillon | Underground Cable | 20 | 10 | 600 | TBD | 0 | 0 | 230 | 0 | 0 | 0 | 1000 MW | 320 | 1600 | 01/01/2026 | Under Consideration | 1089.41 | 3.26 | REE | RTE | TBD | TBD | 2000 | 60
1212 | 270 | New axis Ejea-Aragon region 400 kV | Ejea de los Caballeros | Aragon region | Overhead Line | 10 | 0 | 0 | TBD | 454.5 | 3 | 110 | 0.0258 | 0.2766 | 4.1596 |  | 400 | 2843 | 01/01/2026 | Under Consideration | 62.59 | 2.72 | REE | REE |  |  | 0 | 0
1214 | 270 | Ejea de los Caballeros subestation | "Ejea de los Caballeros " | "Ejea de los Caballeros" | Substation | 10 | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2025 | Under Consideration | 8 | 0.02 | REE | REE |  |  | 0 | 0 | TBD
1215 | 270 | Aragon region subestation | Aragon region | Aragon region | Substation | 10 | 10 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2025 | Under Consideration | 10 | 0.03 | REE | REE |  |  | 0 | 0
1264 | 271 | Investments to be created | 0 | 0 | Overhead Line | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1218 | 272 | Upgrade of exsisting OHL 220 kV to 400 kV between SS Nis 2 and SS Kru?evac 1 | "SS 400/110 kV Nis 2 " | SS 400/220/110 kV Krusevac 1 | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 72 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2034 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1220 | 272 | Upgrading SS 220/110 kV Krusevac 1 to 400 kV voltage level | SS 220/110 kV Krusevac 1 |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2034 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0 | 0
1222 | 272 | Upgrading of exsisting OHL 220 kV to 400 kV between SS Krusevac 1 and SS Kraljevo 3 | "SS 400/220/110 kV Krusevac 1 " | SS 400/220/110 kV Kraljevo 3 | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2034 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1223 | 272 | Uprading exsisting OHL 220 kV to 400 kV between SS Kraljevo 3 and SS Bajina Basta | "SS 400/220/110 kV Kraljevo 3 " | SS 400/220 kV Bajina Basta | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1209 | 273 | New SS 400/110 kV Belgrade West | "SS 400/110 kV Belgrade " |  | Substation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2035 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1217 | 273 | New OHL 400 kV SS Pancevo 2 - SS Belgrade West | "SS 400/220/110 kV Pancevo 2 " | SS 400/110 kV Belgrade West | Substation | 0 | 0 | 0 |  | 0 | 0 | 60 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2035 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1226 | 274 | new 400-kV France-Switzerland interconnection |  |  | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 25 | 0 | 0 | 0 |  | 400 | 0 | 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1227 | 275 | New HVDC cross-border link between France and Switzerland |  |  | Underground Cable | 0 | 0 | 0 |  | 0 | 0 | 200 | 0 | 0 | 0 |  | 320 | 0 | 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1206 | 276 | HVDC Pamplona area -Cantegrit | Pamplona area | Cantegrit | Underground Cable | 20 | 10 | 600 | TBD | 0 | 0 | 225 | 0 | 0 | 0 | 1000 MW | 320 | 1600 | 01/12/2026 | Under Consideration | 1192 | 5.33 | REE | RTE | TBD | TBD | 2000 | 90
1207 | 276 | Upgrade Cantegrit-Saucats | Cantegrit | Saucats | Overhead Line | 10 | 0 | 0 | TBD | 454.5 | 3 | 70 | 0.027 | 0.35 | 3.33 |  | 400 | 0 | 2026 | Under Consideration | 130 | 2 | RTE | RTE |  |  | 0 | 0
1208 | 276 | Upgrade Cantegrit-Marsillon | Cantegrit | Marsillon | Overhead Line | 10 | 0 | 0 | TBD | 454.5 | 3 | 80 | 0.02 | 0.273 | 4.11 |  | 400 | 0 | 2026 | Under Consideration | 140 | 2 | RTE | RTE |  |  | 0 | 0 | TBD
1210 | 276 | New substation Pamplona area | "Pamplona area " | "Pamplona area" | Substation | 10 | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2026 | Under Consideration | 8 | 0.17 | REE | REE |  |  | 0 | 0
1266 | 277 | Sofia West (BG) - Nis 2 (RS) 2nd | Sofia West (BG) | Nis 2 (RS) | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 01/01/2034 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1267 | 278 | Investments to be created |  |  | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2030 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1008 | 280 | Study Lonny-Achene-Gramme | Lonny (FR) | Gramme (BE) | Phase Shift Transformer | 10 | 0 | 0 | N/A | 0 | 0 | 0 | 0.031 | 0.328 | 3.83 |  | 400 | 0 | 2025-2030 | 0 | 100 | 0.1 | RTE | ELIA |  |  | 0 | 0
1379 | 281 | ANAI: Abengoa Northern Atlantic Interconnection | Soto de Ribera | Exeter | Subsea Cable | 20 | 10 | 0 | XLPE | 0 | 0 | 1550 | 0 | 0 | 0 | 50% | 525 | 70 | 2025 | 0 | 2700 | 10 | REE | National Grid | 1% | 0,5% | 2000 | 0
1297 | 282 | ASEI: Abengoa Southern Europe Interconnection | Vandellos | La Spezia | Subsea Cable | 20 | 10 | 0 | XLPE | 0 | 0 | 1000 | 0 | 0 | 0 | 50% | 525 | 70 | 2024 | 0 | 2400 | 10 | REE | Terna | 1% | 0,5% | 2000 | 0
1378 | 283 | TuNur DC | Rejim Maatoug (TN) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Subsea Cable | 20 | 10 | 1300 | Aluminium for deep water cable, copper for shallow water and land cable, aluminium for multiple conductor overhead lines, average specific resistance 0,010114 OHM/km | 0 | 0 | 1270 | 0 | 0 | 0 | 60 days including mobilisation for submarine cable repair | 500 | 1100 | 2025 | Planned but not yet permitting | 2680 | 41 | TuNur Limited | TuNur Limited | 8 hours/year | 8 hours/year for overhead lines, 0.1 faults/year for cables, 2 hours/year for VSC HVDC converters | 2000 | 950 | 0,5%
1430 | 283 | TuNur AC | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) Terna station 400 kV AC | Underground Cable | 10 | 0 | 0 | Copper | 2500 | 2 | 2 | 0.0036 | 0.205 | 0 |  | 400 | 2990 | 2025 | Planned but not yet permitting | 16 | 0.04 | TuNur Limited | Terna |  |  | 0 | 0 | 0,5%
1619 | 284 | LEG1 | Tobrouk (Libya) | Linoperamata (Greece, Crete) | Subsea Cable | 20 | 10 | 500 | Copper and aluminum for the deep water portion. |  |  | 370 |  |  |  | 1440 | 400 | 55 | 2021 | Under Consideration | 1600 | 2.6 | GECOL | ADMIE | 2.7 | 2.8 | 2000 | 340 | 8 hours/year for overhead lines, 0.1 faults/year for cables, 2 hours/year for VSC HVDC converters
1383 | 285 | GridLink | Kingsnorth (UK) | "Warande (Gravelines, France)" | Subsea Cable | 20 | 10 | 0 | XLPE or MI | 0 | 0 | 156 | 0 | 0 | 0 | 700MW | 0 | 0 | 2022 | Planning | 906 | 23.9 | National Grid | RTE | 98% | 2% | 0 | 0
1385 | 286 | Greenlink | Great Island | Pembroke | Subsea Cable | 20 | 10 | 500 | Cable | 0 | 0 | 195 | 0 | 0 | 0 | 100% | 320 | 803 | 2023 | Under Consideration | 396 | 8 | National Grid | EirGrid | 2% | 1% | 500 | 94 | 2.8
1637 | 286 | New investment | [26 empty] | 2%
1439 | 287 | Greenwire South | Grenwire South Hub | Pembroke (to be confirmed) |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0 | 1%
1441 | 287 | Greenwire South | Grenwire South Hub | "Dunstown, Laois or other tbc" |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1442 | 287 | Greenwire South | Grenwire South Hub | Greenwire South substation AC1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1443 | 287 | Greenwire South | Grenwire South Hub | Greenwire South substation AC2 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1444 | 287 | Greenwire South | Grenwire South Hub | Greenwire South substation AC3 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1445 | 287 | Greenwire South | Grenwire South Hub | Greenwire South substation AC4 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1446 | 287 | Greenwire South | Grenwire South Hub | Greenwire South substation AC5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1386 | 289 | MAREX UK-Ireland Intrconnector | Connah's Quay | Finglas Dublin |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2020 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1387 | 289 | MAREX UK-Ireland Intrconnector | Finglas Dublin | Bellacorick Mayo |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2020 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1369 | 290 | Greenwire North | Greenwire North Hub | Woodlands or new Midlands 400/220V substations tba |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1440 | 290 | Greenwire North | Greenwire North Hub | Pentir (to be confirmed) |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1447 | 290 | Greenwire North | Greenwire North Hub | Woodlands or new Midlands 400/220V substation tba |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1448 | 290 | Greenwire North | Greenwire North Hub | Greenwire North substation AC2 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1449 | 290 | Greenwire North | Greenwire North Hub | Greenwire North substation AC3 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1450 | 290 | Greenwire North | Greenwire North Hub | Greenwire North substation AC4 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Planning | 0 | 0 |  |  |  |  | 0 | 0
1454 | 291 | Greenwire Loop Cable | Greenwire North Hub | Grenwire South Hub | Overhead Line | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2022 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1453 | 292 | interconnection | Dublin Area ( to be agreed) | Pentir (to be agreed) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1431 | 293 | Southern Aegean Interconnector | LAVRIO | LEVITHA | Subsea Cable | 20 | 10 | 600 | Cu | 0 | 0 | 245 | 0 | 0 | 0 | one pole | 320 | 2500 | 2024 | Planned but not yet permitting | 600 | 40 | yes | no | 2% | 3% | 800 | 0
1432 | 293 | Southern Aegean Interconnector | LEVITHA | KORAKIA CRETE | Subsea Cable | 20 | 10 | 600 | Cu | 0 | 0 | 250 | 0 | 0 | 0 | one pole outage | 320 | 2500 | 2026 | Planned but not yet permitting | 600 | 40 | no | yes | 2% | 3% | 800 | 0 | 3%
1433 | 293 | Southern Aegean Interconnector | Levitha | Syrna | Subsea Cable | 10 | 0 | 0 | Cu | 800 | 1 | 81 | 0.054 | 0.12 | 66 |  | 220 | 775 | 2025 | Planned but not yet permitting | 150 | 7 | no | no |  |  | 0 | 0 | 3%
1434 | 293 | Southern Aegean Interconnector | KINAROS | LEVITHA | Subsea Cable | 10 | 0 | 0 | Cu | 800 | 1 | 14 | 0.054 | 0.12 | 66 |  | 220 | 775 | 2024 | Planned but not yet permitting | 30 | 1 | no | no |  |  | 0 | 0
1435 | 293 | Southern Aegean Interconnector | Kandeliousa | Syrna | Subsea Cable | 10 | 0 | 0 | Cu | 300 | 1 | 34 | 0.079 | 0.14 | 44 |  | 220 | 530 | 2025 | Planned but not yet permitting | 80 | 6 | no | no |  |  | 0 | 0
1436 | 293 | Southern Aegean Interconnector | Kandeliousa | Pergousa | Subsea Cable | 10 | 0 | 0 | Cu | 300 | 1 | 14 | 0.079 | 0.14 | 44 |  | 220 | 530 | 2025 | Planned but not yet permitting | 40 | 2 | no | no |  |  | 0 | 0
1356 | 294 | Maali | Kergord Shetland | tba e.g. Mongstad, Kollsnes, Fana | Subsea Cable | 20 | 10 | 700 | cable | 0 | 0 | 400 | 0 | 0 | 0 | 100% | 320 | 1094 | 2025 | 0 | 612 | 10 | National Grid / Scottish Hydro Electric Transmission | Statnett | 2% | 2% | 700 | 200
1438 | 295 | Gallant | Glenluce | Kilroot |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2023 | Under consideration | 0 | 0 |  |  |  |  | 0 | 0 | 2%
1437 | 296 | Britib | Gatica/Hernani, Cordemais and Langage/Indian Queens | Gatica/Hernani, Cordemais and Langage/Indian Queens | Subsea Cable | 20 | 10 | 950 | 3000Al XLPE/ MI-PPL | 0 | 0 | 1330 | 0 | 0 | 0 | 950MW (Bipole configuration) | 500 | 3800 | 2023-2024 | Under Consideration | 2200 | 22 | REE, RTE, NG | REE, RTE, NG | <0.5% per year | Forced bipolar outages are normaly neglictable. Forced unavailability per converter (single pole) is <1.0% per year. | 1900 | 1330
445 | 297 | BRABO II: Zandvliet - Lillo - Liefkenshoek | Zandvliet | Lillo - Liefkenshoek | Overhead Line | 10 | 0 | 0 | Two conductors: type 2*928 AMS | 0 | 0 | 18 | 0.0425 | 0.3945 | 2.9354 |  | 380 | 0 | 31/12/2020 | In permitting | 60 | 0.1 | ELIA | ELIA |  |  | 0 | 0 | Forced bipolar outages are normaly neglictable. Forced unavailability per converter (single pole) is <1.0% per year.
604 | 297 | BRABO III: Liefkenshoek - Mercator | Liefkenshoek (BE) | Mercator (BE) | Overhead Line | 10 | 0 | 0 | One conductors: type 2*928 AMS | 0 | 0 | 19 | 0.0297 | 0.3139 | 3.6456 |  | 380 | 0 | 01/01/2023 | Planned but not yet permitting | 50 | 0.1 | ELIA | ELIA |  |  | 0 | 0
605 | 297 | BRABO II: Lillo 380 | Lillo (BE) | Lillo (BE) | Substation | 10 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 |  | 380 | 0 | 31/03/2019 | In permitting | 10 | 0.1 | ELIA | ELIA |  |  | 0 | 0
453 | 298 | Eastern HVDC Link | Peterhead (GB) | Hawthorn Pit (GB) | Subsea Cable | 0 | 0 | 0 |  | 0 | 0 | 365 | 0 | 0 | 0 |  | 500 | 0 | 1/ 1/ 2023 | Under Consideration | 0 | 0 |  |  |  |  | 0 | 0
1458 | 299 | SACOI3 | Codrongianos - Lucciana | Suvereto | Subsea Cable | 20 | 10 | 0 | TBD | 0 | 0 | 300 | 0 | 0 | 0 | 400 MVA | 200 | 2000 | 2023 | Planned but not yet permitting | 700 | 7 | TERNA - EDF | TERNA | 3% | 6% | 400 | 0
1459 | 300 | Channel Cable | Ninfield (United Kingdom) | Paluel (France) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 137 |  |  |  | TBC | 400 | 0 | 2019 | Planned but not yet permitting | 546 | 10 | National Grid | RTE | 48 hours | 28.5 average | 1000 | 137 | 6%
1548 | 301 | Spain-France Route | Hernani (Spain) | La Martyre (France) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 805 |  |  |  | TBC | 400 | 0 | 2021 | Planned but not yet permitting | 1582 | 10 | Red Eléctrica de España | RTE | 48 hours | 28.5 average | 1200 | 805 | 28.5 average
1549 | 301 | France-United Kingdom Route | La Martyre (France) | Indian Queens (United Kingdom) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 245 |  |  |  | TBC | 400 | 0 | 2021 | Planned but not yet permitting | 582 | 10 | RTE | National Grid | 48 hours | 28.5 average | 1200 | 245 | 28.5 average
1550 | 301 | United Kingdom-Ireland Route | Indian Queens (United Kingdom) | Great Island (Ireland) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 276 |  |  |  | TBC | 400 | 0 | 2021 | Planned but not yet permitting | 622 | 10 | National Grid | EirGrid | 48 hours | 28.5 average | 500 | 276 | 28.5 average
1551 | 302 | Tunisia-Italy Sicily Interconnector | El Haouaria (Tunisia) | Partanna (Sicily) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 226 |  |  |  | TBC | 400 | 0 | 2021 | Planned but not yet permitting | 692 | 10 | STEG | Terna | 48 hours | 28.5 average | 1000 | 226 | 28.5 average
1553 | 303 | Spain-Morocco Interconnector | Palos (Spain) | Tahaddart (Morocco) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 250 |  |  |  | TBC | 400 | 0 | 2021 | Under Consideration | 732 | 10 | Red Eléctrica de España | Office National de l'Electricité et de l'Eau | 48 hours | 28.5 average | 1000 | 250 | 28.5 average
1554 | 304 | Algeria-Italy Interconnector | El Hadjar (Algeria) | Rumianca (Sardinia) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 388 |  |  |  | TBC | 400 | 0 | 2022 | Under Consideration | 960 | 10 | Sonelgaz | Terna | 48 hours | 28.5 average | 1000 | 388 | 28.5 average
1577 | 305 | Romania-Turkey Interconnector | Constanta Nord (Romania) | Alibeyköy (Turkey) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 446 |  |  |  | TBC | 400 | 0 | 2023 | Under Consideration | 1055 | 10 | Transelectrica | TEIAS | 48 hours | 28.5 average | 1000 | 446 | 28.5 average
1578 | 306 | Algeria-Spain Interconnector | Hassi Ameur (Algeria) | Litoral De Almeria (Spain) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 203 |  |  |  | TBC | 400 | 0 | 2023 | Under Consideration | 655 | 10 | Sonelgaz | Red Eléctrica de España | 48 hours | 28.5 average | 1000 | 203 | 28.5 average
1579 | 307 | East West 1 | Arklow (Ireland) | Pentir (United Kingdom) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 151 |  |  |  | TBC | 400 | 0 | 2024 | Under Consideration | 419 | 10 | EirGrid | National Grid | 48 hours | 28.5 average | 400 | 151 | 28.5 average
1580 | 308 | East West 2 | Great Island (Ireland) | Pembroke (United Kingdom) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 165 |  |  |  | TBC | 400 | 0 | 2024 | Under Consideration | 443 | 10 | EirGrid | National Grid | 48 hours | 28.5 average | 400 | 165 | 28.5 average
1628 | 309 | NeuConnect Interconnector | Grain 400kV s/s Kent, England | Fedderwarden 380kV s/s Germany | Subsea Cable | 20 | 10 | 600 | Copper or Aluminium |  |  | 700 |  |  |  | 1400MW | 500 | 1600 | 2022 | Under Consideration | 1500 | 22 | National Grid | Tennet Germany | 2% | 1% | 1400 | 700 | 28.5 average
1472 | 312 | St. Peter - Tauern (AT internal) | St. Peter | Tauern | Overhead Line | 10 |  |  | double circuit | 0 | 3 | 128 | 0.015 | 0.257 | 4.4545 |  | 380 | 3477 | 2022 | Planned but not yet permitting | 650 | 5.2 | APG | APG |  |  |  | 0 | 1%
1473 | 313 | Isar/Altheim/Ottenhofen - St. Peter | Isar/Altheim/Ottenhofen (DE) | St. Peter (AT) | Overhead Line | 10 |  |  | double circuit | 0 | 3 | 90 | 0.0132 | 0.256 | 4.43 |  | 380 | 3600 | 2021 | Planned but not yet permitting | 375 | 3 | TenneT-DE | APG |  |  |  | 0
1474 | 315 | DKE-PL-1 | Avedøre (DK) | Dunowo (PL) | Subsea Cable | 20 | 10 | 0 | HVDC |  |  | 330 |  |  |  | 0 | 400 | 1500 | > 2030 | 0 | 700 | 0 | Energinet | PSE | 0 | 0 | 600 | 0
1617 | 316 | Upgrade of 220 kV line Divaca-Bericevo to 400 kV | Divaca | Bericevo | Overhead Line | 10 |  |  | ACSR | 490 | 0 | 80 | 0.03 | 0.32 | 3.5 |  | 400 | 1920 | 2030 | 0 | 56 | 0.4 | ELES | ELES |  |  |  | 0 | 0
1615 | 317 | Upgrade of internal 220 kV line Podlog-Bericevo to 400 kV | Podlog | Bericevo | Overhead Line | 10 |  |  | ACSR | 490 | 3 | 63 | 0.03 | 0.32 | 3.5 |  | 400 | 1920 | 2035 | 0 | 44 | 0.3 | ELES | ELES |  |  |  | 0
1614 | 318 | Upgrade of 220 kV line Podlog-Cirkovce to 400 kV | Podlog | Cirkovce | Overhead Line | 10 |  |  | ACSR | 490 | 3 | 50 | 0.03 | 0.32 | 3.5 |  | 400 | 1920 | 2035 | 0 | 35 | 0.25 | ELES | ELES |  |  |  | 0
1558 | 320 | Double 400 kV OHL Cirkovce(SI)-Heviz(HU)/Zerjavinec(HR) | Cirkovce (SI) | Heviz (HU) \ Zerjavinec (HR) | Overhead Line | 10 |  |  | ACSR | 495 | 3 | 80 | 0.03 | 0.32 | 3.5 |  | 400 | 3800 | 2018 | Planned but not yet permitting | 132.5 | 0.9 | ELES | MAVIR; HOPS |  |  |  | 80
1475 | 321 | Herbertingen - Tiengen | Herbertingen | Tiengen | Overhead Line | 10 |  |  | - | 0 | 0 | 138 | 0.0132 | 0.256 | 0.05 |  | 380 | 3600 | 2025 | Under Consideration | 221 | 1.77 | Amprion | Amprion |  |  |  | 0
1476 | 322 | Wullenstetten - Border Area (DE-AT) | Wullenstetten (DE) | Austrian National border (AT) | Overhead Line | 10 |  |  | AL/ST | 550 | 4 | 95 | 0.0132 | 0.256 | 4.43 |  | 380 | 3600 | 2020 | Planned but not yet permitting | 58 | 0.464 | Amprion | Amprion / vuen/ APG |  |  |  | 95
1477 | 322 | Herbertingen - Neuravensburg | Herbertingen | Neuravensburg | Overhead Line | 10 |  |  | AL/ST | 550 | 4 | 56 | 0.0132 | 0.256 | 4.43 |  | 380 | 3600 | 2030 | Under Consideration | 106 | 0.84 | Amprion | Amprion |  |  |  | 0
1478 | 323 | Dekani (SI) - Zaule (IT) interconnection | DEKANI | ZAULE | Underground Cable | 10 |  |  | XLPE ALUMINUM | 1000 | 1 | 11 | 0.0291 | 0.109 | 72.26 |  | 110 | 763 | 2020 | Planned but not yet permitting | 16 | 0.3 | ELES D.O.O. | TERNA SPA |  |  |  | 11
1482 | 324 | Redipuglia (IT) - Vrtojba (SI) Interconnection | REDIPUGLIA | VRTOJBA | Underground Cable | 10 |  |  | XLPE ALUMINUM | 1000 | 1 | 22.5 | 0.0291 | 0.109 | 72.26 |  | 110 | 763 | 2020 | Planned but not yet permitting | 24 | 0.4 | TERNA SPA | ELES D.O.O. |  |  |  | 22.5
1483 | 325 | Upgrade Obersielach (AT) - Podlog (SI) | Obersielach (AT) | Podlog (SI) | Overhead Line | 10 |  |  | Tbd | 0 | 0 | 70 | 0.03 | 0.32 | 3.5 |  | 380 | 1920 | 2035 | 0 | 210 | 0.5 | APG | ELES |  |  |  | 0
1631 | 325 | Lienz - Italy (AT - IT) | Lienz | Veneto Region | Overhead Line | 10 |  |  | tbd | 764.54 | 3 | 140 | 0.0242 | 0.3071 | 4.1789 |  | 380 | 3618 | 2035 | 0 | 270 | 2.16 | TSO | APG |  |  |  | 0
1636 | 325 | Lienz - Obersielach (AT Internal, mandatory requirement for NTC increases on AT-IT and AT-SI border) | Lienz (AT) | Obersielach (AT) | Overhead Line | 10 |  |  | Double Circuit | 603.78 | 2 | 170 | 0.015 | 0.257 | 4.4506 |  | 380 | 2300 | 2026/27 | Under Consideration | 175 | 1.4 | APG | APG
1484 | 326 | Obersielach - Podlog | Obersielach | Podlog | Overhead Line | 10 | [10 empty] | 380 |  | 2040 | 0 |  |  | APG | ELES
1620 | 328 | Substation Aach | N/A | N/A | Substation | 10 |  |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2025 | Under Consideration | 50 | 0.4 | Amprion | N/A |  |  |  | 0
1629 | 328 | Substation Bofferdange | N/A | N/A | Substation | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2025 | Under Consideration | 45.8 | 0.36 | Creos Luxembourg | N/A |  |  |  | 0
1630 | 328 | AC Overhead Line Aach-Bofferdange | Aach (DE) | Bofferdange (LU) | Overhead Line | 10 |  |  | AL/ST | 265 | 4 | 38 | 0.02735 | 0.26 | 4.4 |  | 400 | 2720 | 2026 | Under Consideration | 62.2 | 0.5 | Amprion | Creos Luxembourg |  |  |  | 10
1518 | 329 | Stevin-Izegem/Avelgem: new corridor | Stevin | Avelgem | Overhead Line | 10 |  |  | 0 | 0 | 0 | 60 | 0.0205 | 0.3135 | 3.6195 |  | 380 | 0 | 2028 | 0 | 400 | 0.3 | ELIA | ELIA |  |  |  | 0
1498 | 330 | New CZ-SK 400 kV interconnector | Otrokovice (CZ) | Ladce (SK) | Overhead Line | 10 |  |  | SEPS side: 3x3xAlFe 450/52 CEPS side: 3x3x490-AL1/64-ST1A | 450 | 3 | 78 | 0.0225 | 0.284 | 3.945 |  | 400 | 2500 | 2035 | 0 | 83.2 | 0.37 | CEPS | SEPS |  |  |  | 39
1499 | 330 | New 400 kV substation Ladce | Ladce (SK) | Ladce (SK) | Substation | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2027 | Under Consideration | 3.1 | 0.25 | SEPS | SEPS |  |  |  | 0
1494 | 331 | dpp1 | 54 | 54 | LCC converter station | 20 | 10 | 76 | 45 |  |  | 45 |  |  |  | 22 | 45 | 4 | 54 | 0 | 54 | 54 | 54 | 54 | 76 | 76 | 6 | 45 | 76
1495 | 332 | ruskin | 65 | 65 | Overhead Line | 10 |  |  | 56 | 56 | 56 | 565 | 56 | 56 | 56 |  | 65 | 6 | 565 | Under Consideration | 56 | 5 | 656 | 56 |  |  |  | 65
1496 | 333 | PST Foretaille | Foretaille | Foretaille | Phase Shift Transformer | 10 |  |  | 1 | 1 | 1 | 0 | 0 | 1 | 1 |  | 220 | 1 | 2031 | 0 | 35 | 0 | Swissgrid | Swissgrid |  |  |  | 0
1497 | 334 | New investment
1504 | 335 | Power Link Island | 0 | 0 | Substation | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2035-2040 | 0 | 0 | 0 | TenneT-NL, Energinet, TenneT-DE | TenneT-NL, Energinet, TenneT-DE |  |  |  | 0
1505 | 335 | Interconnection DKw to Power Link Island | Endrup, DKw | Power Link Island DKw | Subsea Cable | 20 | 10 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 2035-2040 | 0 | 0 | 0 | Energinet | Energinet | 0 | 0 | 2000 | 0 | 0
1506 | 335 | Interconnection NL Maasvlakte to Power Link Island | Maasvlakte 380 kV | Power Link Island NL1 | Subsea Cable | 20 | 10 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 2035-2040 | 0 | 0 | 0 | TenneT TSO NL | TenneT TSO NL | 0 | 0 | 2000 | 0 | 0
1507 | 335 | Interconnection NL Eemshaven to Power Link Island | Eemshaven 380 kV | Power Link Island NL2 | Subsea Cable | 20 | 10 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 2035-2040 | 0 | 0 | 0 | TenneT TSO NL | TenneT TSO NL | 0 | 0 | 2000 | 0 | 0
1508 | 335 | Interconnection DE (area of Brunsbüttel) to Power Link Island | German substation located in the area of Brunsbüttel (north of the Elbe) | Power Link Island DE1 | Subsea Cable | 20 | 10 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 2035-2040 | 0 | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 2000 | 0 | 0
1509 | 335 | Interconnection DE (area of Oldenburg) to Power Link Island | German substation located in the area of Oldenburg | Power Link Island DE2 | Subsea Cable | 20 | 10 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 2035-2040 | 0 | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 2000 | 0 | 0
1511 | 335 | Interconnection DE (area of Krümmel) to Power Link Island | German substation located in the area of Krümmel | Power Link Island DE3 | Subsea Cable | 20 | 10 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 2035-2040 | 0 | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 2000 | 0 | 0
1556 | 336 | Prati (IT) – Steinach (AT) | Prati di Vizze (IT) | Steinach (AT) | Overhead Line | 10 |  |  | N/A | 0 | 0 | 139 | 0.06 | 0.39 | 0.023 |  | 132 | 0 | 2019 | In permitting | 40 | 0.6 | TERNA | TINETZ |  |  |  | 0
1510 | 337 | Cloppenburg East - Merzen | Cloppenburg East (DE) | Merzen (DE) | Overhead Line | 10 |  |  | double circuit | 0 | 0 | 55 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2023 | Under Consideration | 130 | 1 | TenneT-DE | Amprion |  |  |  | 0
1512 | 337 | Conneforde - Cloppenburg | Conneforde (DE) | Cloppenburg (DE) | Overhead Line | 10 |  |  | double circuit | 0 | 0 | 60 | 0.0132 | 0.256 | 4.43 |  | 380 | 0 | 2023 | Under Consideration | 130 | 1 | TenneT-DE | TenneT-DE |  |  |  | 0
1521 | 338 | New HVDC line between Villanova and Fano existing 400 kV substations | Villanova | Fano | Subsea Cable | 20 | 10 | 0 | TBD |  |  | 0 |  |  |  | N/A | 500 | 2400 | 2027 | 0 | 1150 | 17.25 | Terna | Terna | 3% | 6% | 1000 | 0 | 6%
1557 | 339 | Italian HVDC tri-terminal link | SARDINIA REGION | SICILY REGION - SOUTH OF ITALY | Subsea Cable | 20 | 10 | 0 | N/A |  |  | 0 |  |  |  | N/A | 0 | 0 | 2027 | 0 | 2600 | 39 | TERNA | TERNA | 3% | 6% | 1000 | 0 | 6%
1519 | 340 | Avelgem-Center: new corridor | Avelgem | Center (TBD) | Overhead Line | 10 |  |  | 0 | 0 | 0 | 100 | 0.0205 | 0.3135 | 3.6195 |  | 380 | 0 | 2028 | 0 | 500 | 0.5 | ELIA | ELIA |  |  |  | 0
1536 | 341 | Portile de Fier (RO) - Djerdap (RS) 2nd | Portile de Fier | Djerdap | Overhead Line | 10 |  |  | ACSR | 490 | 2 | 2 | 0.03 | 0.337 | 3.4189 |  | 400 | 1920 | 2030 | 0 | 3.5 | 0.03 | Transelektrica | EMS |  |  |  | 1.5
1537 | 341 | New SS 400/110 kV Belgrade West | Belgrade West | Belgrade West | Substation | 10 |  |  | ACSR | 490 | 2 | 0 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2030 | 0 | 27.5 | 0.33 | EMS | EMS |  |  |  | 0
1538 | 341 | New OHL 400 kV WPP Cibuk - SS Belgrade West | WPP Cibuk | Belgrade West | Overhead Line | 10 |  |  | ACSR | 490 | 2 | 60 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2030 | 0 | 12.5 | 0.15 | EMS | EMS |  |  |  | 0
1520 | 342 | Sofia West (BG) - Nis 2 (RS) 2nd | SS Sofia West | SS Nis 2 | Overhead Line | 10 |  |  | ACSR | 490 | 2 | 123 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2034 | 0 | 56 | 0.78 | ESO | EMS |  |  |  | 85
1522 | 342 | Upgrade of exsisting OHL 220 kV to 400 kV SS Nis 2 - SS Kruševac 1 | SS Nis 2 | SS Krusevac 1 | Overhead Line | 10 |  |  | ACSR | 490 | 2 | 72 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2034 | 0 | 17 | 0.2 | EMS | EMS |  |  |  | 0
1523 | 342 | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | SS Krusevac 1 | SS Krusevac 1 | Substation | 10 |  |  | ACSR | 490 | 2 | 0 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2034 | 0 | 6.5 | 0.08 | EMS | EMS |  |  |  | 0
1524 | 342 | Upgrading of exsisting OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | SS Krusevac 1 | SS Kraljevo 3 | Overhead Line | 10 |  |  | ACSR | 490 | 2 | 48 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2034 | 0 | 11.5 | 0.14 | EMS | EMS |  |  |  | 0
1525 | 342 | Uprading exsisting OHL 220 kV to 400 kV SS Kraljevo 3 - Vardiste | EMS | EMS | Overhead Line | 10 |  |  | ACSR | 490 | 2 | 120 | 0.0294 | 0.341 | 3.371 |  | 400 | 1920 | 2033 | 0 | 65 | 0.8 | EMS | EMS |  |  |  | 0
1532 | 343 | New OHL 400 kV Banja Luka - Lika | Banja Luka (BA) | Lika (HR) | Overhead Line | 10 |  |  | ACSR | 1107.8 | 2 | 155 | 0.031875 | 0.3243 | 3.4865 |  | 400 | 1905 | 2030 | Under Consideration | 43 | 0.055 | NOS BIH | HOPS |  |  |  | 115
1533 | 343 | New OHL 400 kV Lika – Melina | Lika (HR) | Melina (HR) | Overhead Line | 10 |  |  | ACSR | 1107.8 | 2 | 68 | 0.031875 | 0.3243 | 3.4865 |  | 400 | 1905 | 2030 | Under Consideration | 17.2 | 0.022 | HOPS | HOPS |  |  |  | 0
1534 | 343 | New OHL 400 kV Lika – Konjsko | Lika (HR) | Konjsko (HR) | Overhead Line | 10 |  |  | ACSR | 1107.8 | 2 | 200 | 0.031875 | 0.3243 | 3.4865 |  | 400 | 1905 | 2030 | Under Consideration | 65.5 | 0.084 | HOPS | HOPS |  |  |  | 0
1535 | 343 | New Substation 400/110 kV Lika | Lika (HR) | Lika (HR) | Substation | 10 |  |  | ACSR | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 2029 | Under Consideration | 30 | 0.038 | HOPS | HOPS |  |  |  | 0
1541 | 344 | Zwolle-Hengelo-Doetinchem-Dodewaard | Zwolle | Dodewaard | Overhead Line | 10 |  |  | HTLS | 0 | 0 | 165 | 0 | 0 | 0 |  | 380 | 0 | 2035 | 0 | 215 |  | TENNET-NL | TENNET-NL |  |  |  | 0
1542 | 345 | Northern East-West connection NL | tbd | tbd | Overhead Line | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2040 | 0 |  |  | TENNET-NL | TENNET-NL |  |  |  | 0
1543 | 346 | ZuidWest380 West | Borssele | Rilland | Overhead Line | 10 |  |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 |  | 380 | 0 | 2021 | In permitting | 400 |  | TENNET-NL | TENNET-NL |  |  |  | 0
1544 | 346 | ZuidWest3808 Oost | Rilland | Tilburg | Overhead Line | 10 |  |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 |  | 380 | 0 | 2025 | Planned but not yet permitting | 620 |  | TENNET-NL | TENNET-NL |  |  |  | 0
1545 | 347 | Maasvlakte – Noord Brabant connection | Krimpen | Geertruidenberg | Overhead Line | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2040 | 0 |  |  | TENNET-NL | TENNET-NL |  |  |  | 0
1546 | 348 | NoordWest380 | Eemshaven Oude Schip | Vierverlaten | Overhead Line | 10 |  |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 |  | 380 | 0 | 2021 | In permitting | 420 |  | TENNET-NL | TENNET-NL |  |  |  | 0
1622 | 350 | 400kV OHL SS Bitola - SS Elbasan | Bitola | Elbasan | Overhead Line | 10 |  |  | ACSR | 490 | 2 | 161 | 4.848 | 51.952 | 3.488 |  | 400 | 1920 | 2020 | Planned but not yet permitting | 63.733 | 2.867 | MEPSO | OST |  |  |  | 56.106
1623 | 350 | 400 kV SS Ohrid |  |  | Substation | 10 | [10 empty] | 400 | 433 | 2020 | Planned but not yet permitting | 17.68 | 1.414 | MEPSO
1624 | 350 | 400 kV SS Kumanovo |  |  | Substation | 10 | [10 empty] | 400 | 433 | 2030 | 0 | 15 | 1.2
1547 | 351 | Eastern HVDC Link | Peterhead (GB) | Hawthorn Pit (GB) | Subsea Cable | 20 | 10 | 0 | TBC |  |  | 365 |  |  |  | TBC | 500 | 2000 | 2024 | 0 | 1460 |  | SHETL | NGET | TBC | TBC | 2000 | 0 | TBC
1581 | 352 | United Kingdom-Denmark Interconnector | Hawthorne Pit (United Kingdom) | Lykkegård (Denmark) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 651 |  |  |  | TBA | 400 | 0 | 2024 | Under Consideration |  |  | National Grid | Energinet | TBA | TBA | 1000 | 651 | TBA
1582 | 353 | United Kingdom-Germany Interconnector | Hawthorne Pit (United Kingdom) | Brokdorf (Germany) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 730 |  |  |  | TBC | 500 | 0 | 2024 | Under Consideration | 1952 | 10 | National Grid | Tennet | 48 hours | 28.5 average | 2000 | 730 | 28.5 average
1585 | 354 | Irish Sea Offshore Export Cable | Poolbeg | Great Island | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 243 |  |  |  | TBC | 500 | 0 | 2024 | Under Consideration | 906 | 10 | EirGrid | EirGrid | 48 hours | 28.5 average | 1500 | 243 | 28.5 average
1586 | 355 | United Kingdom-Belgium Interconnector | Cleve Hill (United Kingdom) | Koksijde (Belgium) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 137 |  |  |  | TBA | 400 | 0 | 2024 | Under Consideration |  |  | National Grid | Elia System Operator | TBA | TBA | 400 | 137 | TBA
1587 | 356 | United Kingdom-France 2 Interconnector | Lovedean (United Kingdom) | Menuel (France) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 217 |  |  |  | TBA | 400 | 0 | 2024 | Under Consideration |  |  | National Grid | RTE | TBA | TBA | 1000 | 217 | TBA
1588 | 357 | United Kingdom-France 3 Interconnector | Indian Queen (United Kingdom) | La Martyre (France) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 245 |  |  |  | TBA | 400 | 0 | 2025 | Under Consideration |  |  | National Grid | RTE | TBA | TBA | 1000 | 245 | TBA
1589 | 358 | Germany-Poland Interconnector | Lubmin (Germany) | Dunowo (Poland) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 175 |  |  |  | TBC | 400 | 0 | 2025 | Under Consideration | 608 | 10 | 50Hertz Transmission GmbH | Polskie Sieci Elektroenergetyczne | 48 hours | 28.5 average | 1000 | 175 | 28.5 average
1590 | 359 | Poland-Lithuania Interconnector | Gdańsk Błonia (Poland) | Klaipėda (Lithuania) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 258 |  |  |  | TBC | 400 | 0 | 2025 | Under Consideration | 596 | 10 | Polskie Sieci Elektroenergetyczne | Litgrid | 48 hours | 28.5 average | 400 | 258 | 28.5 average
1591 | 360 | Russia-Finland Interconnector | Leningradskaya (Russia) | Loviisa (Finland) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 182 |  |  |  | TBA | 400 | 0 | 2025 | Under Consideration |  |  | RAO UES | Fingrid | TBA | TBA | 1000 | 182 | TBA
1592 | 361 | France-Spain West Interconnector | Cantegrit (France) | Hernani (Spain) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 173 |  |  |  | TBA | 400 | 0 | 2024 | Under Consideration |  |  | RTE | Red Eléctrica de España | TBA | TBA | 400 | 173 | TBA
1594 | 362 | France-Spain East Interconnector | Baixas (France) | Santa Llogaia (Spain) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 113 |  |  |  | TBC | 400 | 0 | 2024 | Under Consideration | 373 | 10 | RTE | Red Eléctrica de España | 48 hours | 28.5 average | 400 | 113 | 28.5 average
1596 | 363 | Spain-Portugal North Interconnector | Pazos de Borben (Spain) | Vermoim (Portugal) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 159 |  |  |  | TBC | 400 | 0 | 2024 | Under Consideration | 432 | 10 | Red Eléctrica de España | Redes Energéticas Nacionais | 48 hours | 28.5 average | 400 | 159 | 28.5 average
1598 | 364 | Spain-Portugal South Interconnector | Palos (Spain) | Sines (Portugal) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 330 |  |  |  | TBA | 400 | 0 | 2024 | Under Consideration |  |  | Red Eléctrica de España | Redes Energéticas Nacionais | TBA | TBA | 400 | 330 | TBA
1599 | 365 | Italy-Croatia Interconnector | Candia (Italy) | Zakučac (Croatia) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 280 |  |  |  | TBC | 400 | 0 | 2023 | Under Consideration | 782 | 10 | Terna | HOPS | 48 hours | 28.5 average | 1000 | 280 | 28.5 average
1600 | 366 | Italy-Albania Interconnector | Brindisi North (Italy) | Vlore (Albania) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 127 |  |  |  | TBC | 400 | 0 | 2023 | Under Consideration | 381 | 10 | Terna | OST | 48 hours | 28.5 average | 400 | 127 | 28.5 average
1601 | 367 | Greece-Turkey Interconnector | Pallinis (Greece) | Yeniköy (Turkey) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 393 |  |  |  | TBC | 400 | 0 | 2024 | Under Consideration | 890 | 10 | ADMIE | TEİAŞ | 48 hours | 28.5 average | 1000 | 393 | 28.5 average
1602 | 368 | New investment
1603 | 369 | Ukraine-Poland Interconnector | Dobrotvirska (Ukraine) | Rzeszów (Poland) | Underground Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 205 |  |  |  | TBC | 400 | 0 | 2021 | Under Consideration | 648 | 10 | Ukrenergo | Polskie Sieci Elektroenergetyczne | 48 hours | 28.5 average | 1000 | 205 | 28.5 average
1604 | 370 | Ukraine-Hungary Interconnector | Zakhidnoukrainska (Ukraine) | Albertirsa (Hungary) | Underground Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 520 |  |  |  | TBC | 400 | 0 | 2021 | Under Consideration | 1052 | 10 | Ukrenergo | MAVIR | 48 hours | 28.5 average | 1000 | 520 | 28.5 average
1605 | 371 | Cyprus-Turkey Interconnector | Orounda (Cyprus) | Akkuyu (Turkey) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 108 |  |  |  | TBC | 500 | 0 | 2024 | Under Consideration | 772 | 10 | Cyprus TSO | TEİAŞ | 48 hours | 28.5 average | 2000 | 108 | 28.5 average
1606 | 372 | Cyprus-Kingdom of Saudi Arabia Interconnector | Vasilikos (Cyprus) | Hail (Kingdom of Saudi Arabia) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 1321 |  |  |  | TBC | 500 | 0 | 2025 | 0 | 2749 | 10 | Cyprus TSO | Saudi Electricity Company | 48 hours | 28.5 average | 2000 | 1321 | 28.5 average
1607 | 373 | New York—Canada Route | To be decided | To be decided (substation under construction) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 2000 |  |  |  | TBA | 400 | 0 | 2025 | 0 |  |  | New York Transmission Owners NYTO | Newfoundland Power | TBA | TBA | 2000 | 2000 | TBA
1608 | 373 | Canada-Greenland Route | Soldiers Pond (substation under construction) | To be decided (substation not yet under construction) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 1500 |  |  |  | TBA | 400 | 0 | 2024 | 0 |  |  | TBA | Energinet | TBA | TBA | 2000 | 1500 | TBA
1609 | 373 | Greenland-Iceland Route | To be decided (substation not yet under construction) | To be decided | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 800 |  |  |  | TBA | 400 | 0 | 2024 | 0 |  |  | Energinet | Landsnet | TBA | TBA | 2000 | 800 | TBA
1610 | 373 | Iceland-United Kingdom Route | To be decided | To be decided | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 1800 |  |  |  | TBA | 400 | 0 | 2024 | 0 |  |  | Landsnet | National Grid | TBA | TBA | 2000 | 1800 | TBA
1611 | 374 | Germany-Russia Interconnector | Lubmin (Germany) | Ochakovo (Russia) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 2000 |  |  |  | TBC | 500 | 0 | 2026 | 0 | 4060 | 10 | Tennet | RAO UES | 48 hours | 28.5 average | 2000 | 2000 | 28.5 average
1555 | 375 | Lienz (AT) - Veneto region (IT) | Lienz (AT) | Veneto region (IT) | Overhead Line | 10 |  |  | N/A | 0 | 0 | 140 | 0.08 | 0.42 | 2.7 |  | 220 | 1500 | 2024 | Planned but not yet permitting | 90 | 1.35 | APG | TERNA |  |  |  | 0
1559 | 376 | New investment | Bitola (MK) | Meliti (GR) | Overhead Line | 10 |  |  | ACCC | 727 | 2 | 35.512 | 0.0242 | 0.3155 | 3.628 |  | 400 | 1990 | 2030 | 0 | 4.5 | 0.215 | MEPSO | IPTO |  |  |  | 18.12
1561 | 377 | BE-NL interconnector: upgrade VanEyck-Maasbracht | VanEyck | Maasbracht | Overhead Line | 10 |  |  | HTLS | 0 | 0 | 12 | 0.028 | 0.307 | 3.677 |  | 380 | 0 | 2030 | 0 | 50 | 0.1 | Elia | TENNET-NL |  |  |  | 0
1584 | 378 | Transformer Gatica | GATICA 400 | GATICA 220 | Substation | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 220 | 1575 | 2025 | Under Consideration | 8.16 | 0.1224 | REE | REE |  |  |  | 0
1593 | 379 | Uprate Gatica-Guenes | Gatica | Guenes | Overhead Line | 10 |  |  | Cardinal | 547.3 | 2 | 38.8 | 0.0297 | 0.3237 | 3.5878 |  | 400 | 2454 | 2025 | 0 | 0.22 | 0.0033 | REE | REE |  |  |  | 0
1595 | 379 | Uprate Gatica-Amorebieta-Ichaso | Gatica | Ichaso | Overhead Line | 10 |  |  | Cardinal | 547.3 | 2 | 69.12 | 0.029 | 0.32 | 3.6 |  | 400 | 2526 | REE | 0 | 1.65 | 0.02475 | REE | REE |  |  |  | 0
1597 | 379 | Uprate Gatica-Azpeitia | Gatica | Azpeitia | Overhead Line | 10 |  |  | Cardinal | 547.3 | 2 | 57 | 0.0303 | 0.3192 | 3.5089 |  | 400 | 2454 | 2025 | 0 | 0.31 | 0.00465 | REE | REE |  |  |  | 0
1576 | 380 | Tunisia-Italy Sardinia Interconnector | Mnihla (Tunisia) | Rumianca (Sardinia) | Subsea Cable | 20 | 10 | 0 | Aluminium or Copper |  |  | 255 |  |  |  | TBC | 400 | 0 | 2021 | Planned but not yet permitting | 740 | 10 | STEG | Terna | 48 hours | 28.5 average | 1000 | 255 | 28.5 average

## Sheet3 (hidden)
Id | Status
2 | 10
4 | 20
474 | 20
941 | 20
8 | Permitting
9 | Design
478 | Permitting
481 | Permitting
484 | Design
18 | 20
496 | 20
498 | 20
499 | 20
500 | 20
31 | 0
569 | 0
570 | 0
38 | 20
55 | 30
57 | Planning
1291 | Design & Permitting
60 | 20
609 | Under Construction
62 | 30
614 | 20
70 | 30
624 | 30
1503 | 30
635 | 20
642 | 20
90 | 20
1041 | 10
311 | 30
313 | 20
315 | 20
141 | 30
142 | 30
406 | Under Construction
144 | 30
650 | 0
160 | Under Construction
163 | Commissioned
164 | Commissioned
165 | Commissioned
166 | Commissioned
167 | Commissioned
654 | Under Construction
657 | Commissioned
212 | 20
216 | 20
219 | 10
689 | 10
696 | 20
697 | 20
1500 | 20
1501 | 20
720 | Under Consideration
302 | Under Construction
303 | Design & Permitting
304 | Design & Permitting
386 | 30
735 | 30
1062 | 20
747 | Design & Permitting
427 | 30
443 | 30
449 | 20
450 | Under Construction
752 | 20
452 | 30
458 | 20
769 | Under Consideration
462 | 20
463 | 10
896 | 10
897 | 10
779 | 10
780 | 10
781 | Under Consideration
782 | Under Consideration
146 | 20
139 | 30
796 | 30
1492 | in operation
1493 | 30
801 | 20
1488 | 30
1490 | 10
1539 | 20
1540 | 20
1560 | 30
810 | 0
424 | 30
396 | 20
145 | 30
1625 | 0
934 | 0
373 | 10
378 | 10
385 | 30
733 | 20
403 | 0
86 | 20
96 | 20
645 | 20
943 | Under Consideration
946 | Under Consideration
948 | Under Consideration
950 | Under Consideration
665 | 20
661 | Planning
662 | Under Consideration
956 | Under Consideration
958 | Under Consideration
969 | Under Consideration
970 | Under Consideration
176 | Planning
680 | Planning
179 | Under Construction
188 | Permitting
227 | Under Consideration
617 | Under Consideration
618 | Under Consideration
619 | Under Consideration
620 | Under Consideration
633 | Under Consideration
273 | 20
275 | 20
715 | 20
800 | 20
223 | Design & Permitting
225 | Design & Permitting
256 | 20
257 | 20
258 | 20
262 | 20
238 | 30
269 | 30
270 | 20
701 | 30
705 | 20
625 | Under Construction
1075 | Under Construction
1076 | Under Construction
235 | Commissioned
236 | Commissioned
239 | Design & Permitting
244 | Under Construction
707 | Design & Permitting
708 | Commissioned
912 | Under Consideration
1002 | Planning
616 | 20
1616 | 0
522 | Planning
523 | Planning
928 | Planning
987 | 20
545 | Under Consideration
546 | Under Consideration
547 | Under Consideration
597 | Planning
149 | 20
157 | 20
677 | 20
685 | 10
998 | 20
382 | 10
1004 | Cancelled
1010 | 10
1011 | 10
1012 | Planning
1013 | Planning
1034 | 10
1117 | Planning
1118 | Planning
1564 | 30
1565 | 30
1566 | 30
1567 | 10
1568 | 10
1569 | 10
1570 | 10
1571 | 10
1572 | 10
1632 | 10
1633 | 10
1634 | 10
1635 | 10
1487 | 30
1281 | 10
1014 | 20
1000 | 0
995 | 20
889 | Under Construction
1016 | 0
1018 | 20
594 | Permitting
886 | 20
997 | 20
1389 | Under consideration
1390 | Under Consideration
1391 | Under Consideration
1392 | Under Consideration
1393 | Under Consideration
1394 | Under Consideration
1395 | Under Consideration
1396 | Under Consideration
1397 | Under Consideration
1398 | Under Consideration
1399 | Under Consideration
1400 | Under Consideration
1401 | Under Consideration
1402 | Under Consideration
1403 | Under Consideration
1404 | Under Consideration
1406 | Under Consideration
1408 | Under Consideration
1411 | Under Consideration
1412 | Under Consideration
1413 | Under Consideration
1414
1415
1416
1417
1418
1419
1420
1421
1422
1423 | Under Consideration
1424 | Under Consideration
1425 | Under Consideration
1426 | Under Consideration
1427 | Under Consideration
1428 | Under Consideration
1429 | Under Consideration
1382 | Design
656 | 30
952 | 10
953 | 30
1513 | 30
211 | 10
659 | 10
954 | 10
1485 | 10
927 | 0
561 | 0
929 | 0
742 | 20
136 | 0
984 | Planning
986 | Planning
1051 | 0
306 | 20
308 | 20
309 | 20
312 | 20
314 | 20
538 | 20
686 | Planning
153 | Commissioned
193 | Under Construction
682 | 10
687 | 20
688 | 10
990 | 10
676 | 20
939 | 20
940 | 10
150 | 20
151 | 20
156 | 20
935 | 10
1380 | 20
1082 | 0
999 | Under Consideration
1407 | 20
1409 | 20
1410 | 20
1107 | 0
627 | 20
628 | 20
630 | 20
631 | 20
1526 | 30
1527 | 30
1528 | 30
1231 | 10
1270 | 30
1271 | 0
1272 | 0
1273 | 0
1274 | 0
1275 | 0
353 | 20
355 | 10
1035 | 20
1232 | 10
1282 | 0
1457 | 0
1234 | Under Consideration
1235 | 0
1236 | 0
664 | 20
608 | 30
1239 | Under Consideration
1240 | Under Consideration
1241 | 0
1460 | 20
1276 | 0
1277 | 0
1278 | 0
1279 | 0
1530 | 0
1531 | 0
194 | 30
1269 | 0
1245 | 10
1514 | 10
1246 | 30
1381 | 20
1248 | 10
1613 | 20
1627 | 10
1219 | Under Consideration
1221 | Under Consideration
1384 | 20
147 | 30
148 | 30
1050 | 0
1456 | 0
1515 | 0
1516 | 0
1517 | 0
1224 | 0
1225 | 0
660 | Permitting
1251 | 20
1455 | 20
1252 | 0
1529 | 0
1253 | Under Consideration
667 | 20
1205 | 0
1255 | 0
1256
1257 | 10
1258 | 0
1583 | 0
1259 | 20
1284 | 30
1287 | 20
1288 | 10
1290 | 10
1261 | 20
1285 | 10
1286 | 20
1262 | 0
1263 | Under Consideration
1228 | 30
1229 | 20
1211 | 10
1212 | 10
1214 | 10
1215 | 10
1264 | 0
1218 | Under Consideration
1220 | Under Consideration
1222 | Under Consideration
1223 | Under Consideration
1209 | Under Consideration
1217 | Under Consideration
1226 | Under Consideration
1227 | Under Consideration
1206 | 10
1207 | 10
1208 | 10
1210 | 10
1266 | Under Consideration
1267 | Under Consideration
1008 | 0
1379 | 0
1297 | 0
1378 | 20
1430 | 20
1619 | 10
1383 | Planning
1385 | 10
1439 | Planning
1441 | Planning
1442 | Planning
1443 | Planning
1444 | Planning
1445 | Planning
1446 | Planning
1386 | Under Consideration
1387 | Under Consideration
1369 | Planning
1440 | Planning
1447 | Planning
1448 | Planning
1449 | Planning
1450 | Planning
1454 | Under Consideration
1453 | Under Consideration
1431 | 20
1432 | 20
1433 | 20
1434 | 20
1435 | 20
1436 | 20
1356 | 0
1438 | Under consideration
1437 | 10
445 | 20
604 | 20
605 | 30
453 | Under Consideration
1458 | 20
1459 | 20
1548 | 20
1549 | 20
1550 | 20
1551 | 20
1553 | 10
1554 | 10
1577 | 10
1578 | 10
1579 | 10
1580 | 10
1628 | 10
1472 | 20
1473 | 20
1474 | 0
1617 | 0
1615 | 0
1614 | 0
1558 | 20
1475 | 10
1476 | 20
1477 | 10
1478 | 20
1482 | 20
1483 | 0
1631
1484 | 0
1620 | 10
1629 | 10
1630 | 10
1518 | 0
1498 | 0
1499 | 10
1494 | 0
1495 | 10
1496 | 0
1497
1504 | 0
1505 | 0
1506 | 0
1507 | 0
1508 | 0
1509 | 0
1511 | 0
1556 | 30
1510 | 10
1512 | 10
1521 | 0
1557 | 0
1519 | 0
1536 | 0
1537 | 0
1538 | 0
1520 | 0
1522 | 0
1523 | 0
1524 | 0
1525 | 0
1532 | 10
1533 | 10
1534 | 10
1535 | 10
1541 | 0
1542 | 0
1543 | 30
1544 | 20
1545 | 0
1546 | 30
1622 | 20
1623 | 20
1624 | 0
1547 | 0
1581 | 10
1582 | 10
1585 | 10
1586 | 10
1587 | 10
1588 | 10
1589 | 10
1590 | 10
1591 | 10
1592 | 10
1594 | 10
1596 | 10
1598 | 10
1599 | 10
1600 | 10
1601 | 10
1602
1603 | 10
1604 | 10
1605 | 10
1606 | 0
1607 | 0
1608 | 0
1609 | 0
1610 | 0
1611 | 0
1555 | 20
1559 | 0
1561 | 0
1584 | 10
1593 | 0
1595 | 0
1597 | 0
1576 | 20

## Sheet1 (hidden)
ProjectId | Investment ID | Name | From | To | ElementsType | TechnologyType | ConverterType | TerminalCapabilityRange | ConductorType | ConductorSize | ConductorsNumberPerPhase | TotalRouteLength (km) | Resistance (OHM/km) | Reactance (OHM/km) | Conductance (microS/km) | ExpectedYearlyUnavibility | VoltageLevel (kV) | ThermalLimitWinter (A) | ThermalLimitSummer (A) | ExpectedCommissioningYear | Status | Capex | Opex | TsoInChargeFrom | TsoInChargeTo | ExpectedYearlyUnavibilityPlanned | ExpectedYearlyUnavibilityForced | Capacity | KmToEachBorder | NST Remarks | E-mail | First Name | Second Name | E-mail1 | First Name | Second Name | E-mail2 | First Name | Second Name | E-mail sent | 348
1 | 2 | Pedralva-Sobrado | Pedralva (PT) | Sobrado (PT) | Overhead Line | AC | 0 | 0 | ACSR 595 | 0 | 2 | 67 | 0 | 0 | 0 | 0 | 400 | 2680 |  | 2022-2023 | Planned but not yet permitting | 0 | 0 | REN | REN | 0 | 0 | 0 | 0 |  | fbatista@entsoe.local | Fernando | Batista | [6 empty] | 1
1 | 4 | V.Minho -R.Pena-Fridão-Feira | V.Minho (by Ribeira de Pena and Fridão) | Feira (by Ribeira de Pena and Fridão) | Overhead Line | AC | 0 | 0 | ACSR 485 | 0 | 3 | 131 | 0 | 0 | 0 | 0 | 400 | 3423 |  | 2022-2024 | Permitting | 0 | 0 | REN | REN | 0 | 0 | 0 | 0 |  | fbatista@entsoe.local | Fernando | Batista | [6 empty] | 1
1 | 474 | Substation Ribeira de Pena | Ribeira de Pena (PT) | - | Substation | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2022-2024 | Permitting | 0 | 0 | REN | - | 0 | 0 | 0 | 0 |  | fbatista@entsoe.local | Fernando | Batista | [6 empty] | 1
1 | 941 | Switching station Fridão | Fridão | - | Substation | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 |  | 2026-2030 | Permitting | 0 | 0 | REN | - | 0 | 0 | 0 | 0 |  | fbatista@entsoe.local | Fernando | Batista | [6 empty] | 1
4 | 18 | Beariz (ES) - Fontefria (ES) | Beariz (ES) | Fontefria (ES) | Overhead Line | AC | 0 | 0 | Condor x3 | 0 | 0 | 32 | 0.0256 | 0.2768 | 4.1588 | 0 | 400 | 2843 |  | 1/ 1/ 2021 | Permitting | 0 | 0 | REE | REE | 0 | 0 | 0 | 17 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
4 | 496 | Fontefria (ES) - Vila Nova de FamalicÆo (PT) | Fontefria (ES) | Vila Nova de FamalicÆo (PT) (By Ponte de Lima) | Overhead Line | AC | 0 | 0 | Condor x3;ACSR/AW 517 | 517 | 2 | 135 | 0 | 0 | 0 | 0 | 400 | 2462 |  | 1/ 1/ 2021 | Permitting | 0 | 0 | REE | REN | 0 | 0 | 0 | 213 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
4 | 498 | SE Fontefria 400/220kV | Fontefria (ES) | REE | Substation | AC | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 1/ 1/ 2021 | Permitting | 0 | 0 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
4 | 499 | Beariz 400kV (ES) | Beariz (ES) | Beariz (ES) | Substation | AC | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 1/ 1/ 2021 | Permitting | 0 | 0 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
4 | 500 | Ponte de Lima (PT) | Ponte de Lima (PT) | Ponte de Lima (PT) | Substation | AC | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 1/ 1/ 2021 | Permitting | 0 | 0 | REN | REN | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
13 | 31 | Axis Caparacena-Baza-La Ribina | Caparacena (ES) | La Ribina (ES) | Overhead Line | AC | 0 | 0 | Condor | 0 | 3 | 177 | 0.0257 | 0.2767 | 4.1587 | 0 | 400 | 2786 |  | 2025 | Under consideration | 104 | 1.56 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
13 | 569 | New substation Baza | Baza (ES) | Baza (ES) | Substation | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2025 | Under consideration | 6.26 | 0.0939 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
13 | 570 | New substation La Ribina | La Ribina (ES) | La Ribina (ES) | Substation | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2025 | Under consideration | 8.9 | 0.1335 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
16 | 38 | HVDC Gatica-Cubnezais | Gatica (ES) | Cubnezais (FR) | Subsea Cable | DC | VSC | 600 | XLPE or MI | 0 | 0 | 370 | 0 | 0 | 0 | 1000 MW | 320 | 0 |  | 01/ 01/ 2025 | Permitting | 1750 | 10.2 | REE | RTE | TBD | TBD | 2000 | 0 |  | plabra@entsoe.local | Patricia | Labra |  |  |  | jean-gabriel.valentin@rte-france.com | Jean-Gabriel | Valentin | 1
21 | 55 | Savoie - Pièmont | Grande Ile (FR) | Piossasco (IT) | Underground Cable | DC | VSC | 300 | XLPE | 0 | 0 | 190 | 0 | 0 | 0 | 600 MVA | 320 | 3750 |  | 2019 | Under construction | 0 | 0 | RTE | TERNA | 4% | 3% | 1200 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
23 | 60 | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | Avelin/Mastaing (FR) | Horta (BE) | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 400 | 0 |  | 1/1/2022 | Permitting | 140 | 0 | RTE | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | philippe.bodin@rte-france.com | Philippe | Bodin |  |  |  | 1
25 | 62 | IFA2 | Tourbe (FR) | Chilling (GB) | Subsea Cable | DC | VSC | 0 | TBD | 0 | 0 | 250 | 0 | 0 | 0 | TBD | 320 | 0 |  | 1/ 1/ 2020 | Under construction | 685 | 0 | RTE | NGIHL | TBD | TBD | 1000 | 0 |  | pbodin@ENTSOE.local | Philippe | Bodin | [6 empty] | 1
26 | 614 | Reschenpass Interconnector | Nauders (AT) | Glorenza (IT) | Underground Cable | AC | 0 | 0 | Tbd | 0 | 0 | 26 | 0.01 | 0.19 | 0.003 | 0 | 220 | 1133 |  | 2021 | Permitting | 0 | 0 | APG | Terna | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | stefan.fuehrer@apg.at | Stefan | Führer |  |  |  | 1
28 | 70 | First HVDC Module IT-ME | Villanova (IT) | Lastva (ME) | Subsea Cable | DC | LCC | 0 | N/A | 0 | 0 | 445 | 0 | 0 | 0 | N/A | 500 | 0 |  | 2019 | Under construction | 0 | 0 | TERNA | CGES | N/A | N/A | 600 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
28 | 624 | SS 400/110 kV Lastva | Lastva (ME) | N/A | Substation | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 31/12/ 2018 | Under construction | 0 | 0 | CGES | N/A | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
28 | 1503 | Second HVDC Module IT-ME | Villanova (IT) | Lastva (ME) | Subsea Cable | DC | LCC | 0 | N/A | 0 | 0 | 445 | 0 | 0 | 0 | N/A | 500 | 0 |  | 2026 | Under construction | 0 | 0 | Terna | CGES | N/A | N/A | 600 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
29 | 635 | Elmed Project | Sicily Area (IT) | Tunisia node | Subsea Cable | DC | LCC | 0 | TBD | 0 | 0 | 200 | 0 | 0 | 0 | TBD | 400 | 0 |  | 2022 | Permitting | 0 | 0 | TERNA | STEG | N/A | N/A | 600 | 0 | Tunisia not modelled | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
31 | 642 | San Giacomo Project | All'Acqua (CH) | Pallanzeno(IT)-Baggio(IT) | Overhead Line | AC | 0 | 0 | ACSR | 0 | 0 | 100 | 0.02 | 0.27 | 0.005 | 0 | 380 | 2850 |  | 2025 | Permitting | 0 | 0 | SWISSGRID | TERNA | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
33 | 90 | 90 | Calenzano (IT) | Colunga (IT) | Overhead Line | AC | 0 | 0 | N/A | 0 | 0 | 80 | 0.02 | 0.27 | 0.005 | 0 | 400 | 0 |  | 2022 | Permitting | 0 | 0 | TERNA | TERNA | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
33 | 1041 | Rem. lim. in Central Italy | Villanova (IT) | S. Barbara (IT) | Overhead Line | AC | 0 | 0 | Tbd | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 220 | 0 |  | 1/ 1/ 2022 | Planned but not yet permitting | 0 | 0 | TERNA | TERNA | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
35 | 311 | R Kocin | Kocin (CZ) | N/A | Substation | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 1/ 1/ 2024 | Under construction | 0 | 0 | CEPS | CEPS | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | akasembe@entsoe.local | Andrew | Kasembe | [6 empty] | 1
35 | 313 | Kocin-Mirovka | Kocin (CZ) | Mirovka (CZ) | Overhead Line | AC | 0 | 0 | 3x3x490-AL1/64-ST1A | 0 | 0 | 121 | 0.02 | 0.28 | 3.95 | 0 | 400 | 2445 |  | 1/ 1/ 2024 | Permitting | 0 | 0 | CEPS | CEPS | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | akasembe@entsoe.local | Andrew | Kasembe | [6 empty] | 1
35 | 315 | Kocin-Prestice | Kocin (CZ) | Prestice (CZ) | Overhead Line | AC | 0 | 0 | 3x3x490-AL1/64-ST1A | 0 | 0 | 116 | 0.02 | 0.28 | 3.95 | 0 | 400 | 2445 |  | 1/ 1/ 2028 | Permitting | 0 | 0 | CEPS | CEPS | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | akasembe@entsoe.local | Andrew | Kasembe | [6 empty] | 1
36 | 141 | Kriegers Flak CGS, TYNDP ID: 36.141 | Ishøj / Bjæverskov (DK) | Bentwisch (DE) | Subsea Cable | AC | 0 | 0 | double circuit | 0 | 0 | 24 | 0.053 | 0.115 | 75.4 | 0 | 150 | 400 |  | 31/12/2018 | Under construction | 350 | 22.4 | Energinet.dk | 50Hertz Transmission GmbH | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | ano@energinet.dk | Antje | Orths | thomas.koebinger@50hertz.com | Thomas | Köbinger | 1
37 | 142 | Norway - Germany HVDC | Tonstad (NO) | Wilster (DE) | Subsea Cable | DC | VSC | 0 | subsea cable | 0 | 0 | 514 | 0.0101 | Not relevant for DC cable | Very small and not normally used for DC cables (order of 10-6 µS/km at 20 deg. C) | 0 | 500 | 0 |  | 01/ 01/ 2020 | Under construction | 1850 | 8.2 | Statnett | TenneT-DE | 0 | 0 | 0 | 0 |  | apettersen@entsoe.local | Arne | Egil Pettersen | kedar.kolharkar@tennet.eu | Kedar | Kolharkar |  |  |  | 1
37 | 406 | Western corridor | (Southern part of Norway) (NO) | (Southern part of Norway)(NO) | Overhead Line | AC | 0 | 0 | Overhead line | 0 | 0 | 400 |  |  |  | 0 | 400 | 0 |  | 2020 | Under Construction | 0 | 0 | Statnett | Statnett | 0 | 0 | 0 | 0 |  | apettersen@entsoe.local | Arne | Egil Pettersen | kedar.kolharkar@tennet.eu | Kedar | Kolharkar |  |  |  | 1
39 | 144 | Audorf - Kassoe | Audorf (DE) | Kassoe (DK) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 3 | 110 | 1.39 | 14.92 | 197.69 | 0 | 380 | 4988 |  | 31/ 12/ 2020 | Under construction | 0 | 0 | TenneT-DE | Energienet.dk | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | kedar.kolharkar@tennet.eu | Kedar | Kolharkar | ano@energinet.dk | Antje | Orths | 1
40 | 650 | BE-LUX-DE Long-Term perspective | Aubange (TBC) | LUX-DE (TBC) | Overhead Line | AC | 0 | 0 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2035 | Under consideration | 0 | 0 | ELIA | CREOS; AMPRION | 0 | 0 | 0 | 0 |  | lphilippe@entsoe.local | Louis | Philippe | [6 empty] | 1
47 | 212 | (is a single investment project, please consider only content of project 313) 212 Isar/Altheim/Ottenhofen - St. Peter | Isar (DE) | St. Peter (AT) | Overhead Line | AC | 0 | 0 | Tbd | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2021 | Permitting | 0 | 0 | TenneT-DE | APG | 0 | 0 | 0 | 0 |  | dboehm@ENTSOE.local | David | Boehm | stefan.fuehrer@apg.at | Stefan | Führer | Christian.Neus@amprion.net | Christian | Neus | 1
47 | 216 | (is a single investment project, please consider only content of project 312) 216 | St. Peter (AT) | Tauern (AT) | Overhead Line | AC | 0 | 0 | Tbd | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2022 | Permitting | 0 | 0 | APG | APG | 0 | 0 | 0 | 0 |  | dboehm@ENTSOE.local | David | Boehm | stefan.fuehrer@apg.at | Stefan | Führer | Christian.Neus@amprion.net | Christian | Neus | 1
47 | 219 | 219: Westtirol - Zell/Ziller (AT internal) | Westtirol (AT) | Zell-Ziller (AT) | Overhead Line | AC | 0 | 0 | Tbd | 0 | 0 | 105 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | APG | APG | 0 | 0 | 0 | 0 |  | dboehm@ENTSOE.local | David | Boehm | stefan.fuehrer@apg.at | Stefan | Führer | Christian.Neus@amprion.net | Christian | Neus | 1
47 | 689 | 689: Vöhringen (DE) - Westtirol (AT) | Vöhringen (DE) | Westtirol (AT) | Overhead Line | AC | 0 | 0 | Tbd | 0 | 0 | 114 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | Amprion | APG | 0 | 0 | 0 | 0 |  | dboehm@ENTSOE.local | david | boehm | stefan.fuehrer@apg.at | Stefan | Führer | Christian.Neus@amprion.net | Christian | Neus | 1
48 | 696 | Hunew 1 | Sajóivánka (HU) | N/A | Compensation | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2020 | Permitting | 0 | 0 | MAVIR | N/A | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
48 | 697 | Hunew 2 | Sajóivánka (HU) | N/A | Substation | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2020 | Permitting | 0 | 0 | MAVIR | N/A | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
48 | 1500 | 1. SK-HU interconnection | Gabcikovo (SK) | Gonyu (HU) | Overhead Line | AC | 0 | 0 | SEPS side: AlFe 450/52 MAVIR side: AL/87-ST1A 381/3 | 450 | 3 | 110 | 0.0223 | 0.28 | 4.05 | 0 | 400 | 2400 |  | 2020 | Permitting | 0 | 0 | SEPS | MAVIR | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
48 | 1501 | 2. SK-HU interconnection | Rimavska Sobota (SK) | Sajoivanka (HU) | Overhead Line | AC | 0 | 0 | SEPS side: 434-AL1/56 - ST1A; MAVIR side: ACSR 500/2 | 434 | 3 | 48 | 0.0251 | 0.294 | 3.85 | 0 | 400 | 2240 |  | 2020 | Permitting | 0 | 0 | SEPS | MAVIR | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
62 | 386 | 3rd EE-LV interconnection | Kilingi-Nomme (EE) | Riga CHP2 (LV) | Overhead Line | AC | 0 | 0 | Aluminum Steel Core | 400 | 2 | 205 | 0.036 | 0.321 | 3.49 | 0 | 330 | 2000 |  | 2020 | Under construction | 120 | 0 | Elering | AST | 0 | 0 | 0 | 180 |  | azbanovs@entsoe.local | Ansis | Zbanovs | [6 empty] | 1
62 | 735 | Harku-Sindi 330kV OHL | Harku (EE) | Sindi (EE) | Overhead Line | AC | 0 | 0 | Aluminum Steel Core | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 330 | 0 |  | 31/ 12/ 2020 | Under construction | 60 | 0 | Elering | Elering | 0 | 0 | 0 | 0 |  | azbanovs@entsoe.local | Ansis | Zbanovs | [6 empty] | 1
62 | 1062 | Riga CHP2 - Riga HPP | Riga CHP2 | Riga HPP | Overhead Line | AC | 0 | 0 | Aluminum Steel Core | 400 | 2 | 15 | 0.036 | 0.321 | 3.49 | 0 | 330 | 1650 |  | 1/ 1/ 2020 | Permitting | 20 | 0 | AST | AST | 0 | 0 | 0 | 0 |  | azbanovs@entsoe.local | Ansis | Zbanovs | [6 empty] | 1
71 | 427 | COBRA Cable | Endrup (DK) | Eemshaven (NL) | Subsea Cable | DC | VSC | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2019 | Under construction | 620 | 0 | Energinet | TENNET-NL | 0 | 0 | 700 | 0 |  | jbos@entsoe.local | Jorrit | Bos | kedar.kolharkar@tennet.eu | Kedar | Kolharkar | ano@energinet.dk | Antje | Orths | 1
74 | 443 | NEMO | Richborough (GB) | Gezelle (BE) | Subsea Cable | DC | VSC | 0 | XLPE | 0 | 0 | 140 | 0 | 0 | 0 | TBD | 400 | 0 |  | 1/ 1/ 2019 | Under construction | 660 | 0 | NGET | ELIA | TBD | TBD | 1000 | 0 |  | aalikhanzadeh@ENTSOE.local | Amir | Alikhanzadeh | [6 empty] | 1
74 | 449 | Richborough - Canterbury | Richborough (GB) | Canterbury (GB) | Overhead Line | AC | 0 | 0 | 2 x 570mm2 AAAC | 570 | 0 | 20 | 0.13 | 0.83 | 0 | 0 | 400 | 0 |  | 2018 | Permitting | 0 | 0 | NGET | NGET | 0 | 0 | 0 | 0 |  | aalikhanzadeh@ENTSOE.local | Amir | Alikhanzadeh | [6 empty] | 1
74 | 450 | SELL - DUNG Reconductoring | Sellindge (GB) | Dungeness (GB) | Overhead Line | AC | 0 | 0 | 3x700mm2 AAAC 3.05R, 2x620mm2 GZTACSR | 700 | 0 | 26 | 0.12 | 0.81 | 0 | 0 | 400 | 0 |  | 30/ 11/ 2016 | Under Construction | 0 | 0 | NGET | NGET | 0 | 0 | 0 | 0 |  | aalikhanzadeh@ENTSOE.local | Amir | Alikhanzadeh | [6 empty] | 1
75 | 752 | Modular Offshore Grid | Offshore platform | Stevin (Zeebrugge) | Subsea Cable | AC | 0 | 0 | TBC | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 220 | 0 |  | 01/01/2020 | Permitting | 400 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | [6 empty] | 1
77 | 452 | Western HVDC Link | Hunterston (GB) | Deeside (GB) | Subsea Cable | DC | LCC | 0 | TBC | 0 | 0 | 360 | 0 | 0 | 0 | TBC | 500 | 0 |  | 2017 | Under construction | 1220 | 0 | SPT | NGET | TBC | TBC | 2400 | 0 |  | aalikhanzadeh@ENTSOE.local | Amir | Alikhanzadeh | [6 empty] | 1
78 | 458 | HINP-SEAB New Double Circuit | Hinkley Point (GB) | Seabank (GB) | Overhead Line | AC | 0 | 0 | AACSR Twin 400 kV Matthew 620mm2 | 620 | 0 | 60 | 0.018 | 0.29 | 0 | 0 | 400 | 0 |  | 2024 | Permitting | 814 | 0 | NGET | NGET | 0 | 0 | 0 | 0 |  | aalikhanzadeh@ENTSOE.local | Amir | Alikhanzadeh | [6 empty] | 1
81 | 462 | 462 | Woodland (IE) | Turleenan (NI) | Overhead Line | AC | 0 | 0 | TBD | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2020 | Permitting | 0 | 0 | EirGrid | SONI | 0 | 0 | 0 | 0 |  | mmcclure@entsoe.local | Michael | McClure | [6 empty] | 1
82 | 463 | Srananagh - South Donegal | Srananagh (IE) | New substation in South Donegal (IE) | Overhead Line | AC | 0 | 0 | TBD | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 220 | 0 |  | 2029 | Planned but not yet permitting | 0 | 0 | EirGrid | EirGrid | 0 | 0 | 0 | 0 |  | mmcclure@entsoe.local | Michael | McClure | [6 empty] | 1
82 | 896 | Omagh South to South Donegal | South Donegal (IE) | Omagh South (NI) | Overhead Line | AC | 0 | 0 | TBD | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 275 | 0 |  | 2029 | Planned but not yet permitting | 0 | 0 | EirGrid | SONI | 0 | 0 | 0 | 0 |  | mmcclure@entsoe.local | Michael | McClure | [6 empty] | 1
82 | 897 | Omagh South to Turleenan | Omagh South | Turleenan | Overhead Line | AC | 0 | 0 | TBD | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 275 | 0 |  | 2029 | Planned but not yet permitting | 0 | 0 | SONI | SONI | 0 | 0 | 0 | 0 |  | mmcclure@entsoe.local | Michael | McClure | [6 empty] | 1
85 | 779 | F.Alentejo-Ourique-Tavira | F. Alentejo (by Ourique) | Tavira (by Ourique) | Overhead Line | AC | 0 | 0 | ACSR 595 | 595 | 2 | 122 | 0 | 0 | 0 | 0 | 400 | 2680 |  | 2024-2026 | Planned but not yet permitting | 0 | 0 | REN | REN | 0 | 0 | 0 | 0 |  | fbatista@entsoe.local | Fernando | Batista | [6 empty] | 1
85 | 780 | Extension of Ourique substation | Ourique (PT) | - | Substation | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2024-2026 | Planned but not yet permitting | 0 | 0 | REN | - | 0 | 0 | 0 | 0 |  | fbatista@entsoe.local | Fernando | Batista | [6 empty] | 1
92 | 146 | ALEGrO | Oberzier (DE) | Lixhe (BE) | Underground Cable | DC | VSC | 300 | XLPE | 0 | 0 | 100 | 0 | 0 | 0 | TBD | 320 | 0 |  | 01/ 10/ 2020 | Permitting | 560 | 0 | AMPRION | ELIA | TBD | TBD | 1000 | 0 |  | hbackhaus@ENTSOE.local | Christian | Neus | [6 empty] | 1
94 | 139 | Krajnik-Vierraden | Vierraden (DE) | Krajnik (PL) | Overhead Line | AC | 0 | 0 | 2xAFL-8 525 | 525 | 2 | 25.68 | 0.0265 | 0.293 | 3.86 | 0 | 400 | 1800 |  | 31/12/2020 | Under construction | 12.5 | 0.0375 | 50Hertz | PSE S.A. | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | michael.heit@50Hertz.com | Michael | Heit |  |  |  | 1
94 | 796 | Krajnik | Krajnik (PL) | Krajnik (PL) | Substation | AC | 0 | 0 | n.a. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2019 | Under consideration | 36.5 | 1.095 | PSE S.A. | PSE S.A. | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | [6 empty] | 1
94 | 1492 | PST in Mikulowa | Mikulowa (PL) | Mikulowa (PL) | PST | AC | 0 | 0 | Cu | 0 | 0 | 0 | 0.132 | 12.278 | 0.7 | 0 | 400 | 1860 |  | 30/06/2016 | in operation | 65.7 | 1.971 | PSE | PSE | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | [6 empty] | 1
94 | 1493 | PST Vierraden | Vierraden | Vierraden | PST | AC | 0 | 0 | Cu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 31/12/2018 | Under construction | 110.8 | 2 | 50Hertz | 50Hertz | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | michael.heit@50Hertz.com | Michael | Heit |  |  |  | 1
96 | 801 | FI5 KI-PS | Keminmaa (FI) | Pyhanselka (FI) | Overhead Line | AC | 0 | 0 | 3-Finch | 850 | 3 | 156 | 0.0512 | 0.284 | 0 | 0 | 400 | 3150 |  | 1/ 1/ 2024 | Permitting | 60 | 0.1 | Fingrid | Fingrid | 0 | 0 | 0 | 0 |  | aharjula@entsoe.local | Antti | Harjula | [6 empty] | 1
103 | 1488 | Diemen-Lelystad-Ens | Diemen | Ens | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2020 | Under construction | 0 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
103 | 1490 | Ens-Zwolle | Ens | Zwolle | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2022 | Planned but not yet permitting | 30 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
103 | 1539 | Krimpen-Geertruidenberg | Krimpen | Geertruidenberg | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2020 | Permitting | 45 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
103 | 1540 | Eindhoven-Maasbracht | Eindhoven | Maasbracht | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2023 | Permitting | 50 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
103 | 1560 | Randstad380 noordring | Beverwijk | Bleiswijk | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2018 | Under construction | 0 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
107 | 810 | France Ireland Interconnector | West Wexford or East Cork (IE) | La Martyre (FR) | Subsea Cable | DC | VSC | 0 | TBD | 0 | 0 | 580 | 0 | 0 | 0 | TBD | 320 | 0 |  | 2026 | Under consideration | 920 | 0 | EIRGRID | RTE | TBD | TBD | 700 | 0 |  | pbodin@ENTSOE.local | Philippe | Bodin | [6 empty] | 1
110 | 424 | Norway - Great Britain | Kvilldal (NO) | Blythe (GB) | Subsea Cable | DC | VSC | 0 | Double circuit | 0 | 0 | 720 | 0.0101 | Not relevant for DC cable | Very small and not normally used for DC cables (order of 10-6 µS/km at 20 deg. C) | TBD | 500 | 0 |  | 2021 | Under construction | 1800 | 15.4 | Statnett | NHIGL | TBD | TBD | 1400 | 0 |  | apettersen@entsoe.local | Arne | Egil Pettersen | marta.navarrete@nationalgrid.com | Marta | Navarrete |  |  |  | 1
111 | 396 | 3rd AC Finland-Sweden north | Keminmaa (Finland) | Messaure (Sweden, bidding area SE1) | Overhead Line | AC | 0 | 0 | Al-59 910 | 910 | 3 | 200 | 0.0326 | 0.284 | 0 | 0 | 400 | 3150 |  | 2025 | Permitting | 160 | 0.24 | Fingrid | Svenska kraftnät | 0 | 0 | 0 | 150 |  | aharjula@entsoe.local | Antti | Harjula | [6 empty] | 1
113 | 145 | Doetinchem-Niederrhein | Niederrhein (DE) | Doetinchem (NL) | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2018 | Under construction | 220 | 0 | AMPRION | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Jorrit | Bos | ano@energinet.dk | Kedar | Kolharkar | Andre.Seack@amprion.net | Andre | Seack | 1
121 | 934 | Nautilus: 2nd interco UK - BE | Leiston (UK) | TBD (BE) | Subsea Cable | DC | VSC | 0 | TBD | 0 | 0 | 250 | 0 | 0 | 0 | TBD | 400 | 0 |  | 2028 | Under consideration | 850 | 6 | NGHIL | ELIA | TBD | TBD | 1000 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | marta.navarrete@nationalgrid.com | Marta | Navarrete |  |  |  | 1
123 | 373 | Ostroleka-Stanislawow | Ostroleka (PL) | Stanislawow (PL) | Overhead Line | AC | 0 | 0 | 3x3x408-AL1F/34-UHST | 408 | 3 | 106 | 0.0281 | 0.1982 | 3.9474 | 0 | 400 | 2970 |  | 31/ 12/ 2023 | Planned but not yet permitting | 0 | 0 | PSE | PSE | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
124 | 378 | 330 kV OHL Panevezys-Musa | Panevezys | Musa | Overhead Line | AC | 0 | 0 | Al | 400 | 2 | 80 | 0 | 0 | 0 | 0 | 330 | 1650 |  | 31/12/ 2023 | Planned but not yet permitting | 19 | 0 | LITGRID | LITGRID | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | Petter.Glantz@svk.se | Peter | Glantz |  |  |  | 1
124 | 385 | Grobina (LV) - Imanta (LV) | Grobina (LV) | Imanta (LV) | Overhead Line | AC | 0 | 0 | Single circuit/ Double circuit | 400 | 3 | 380 | 0.024 | 0.281 | 3.73 | 0 | 330 | 0 |  | 2019 | Under construction | 190.8 | 0 | AST | AST | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | Petter.Glantz@svk.se | Peter | Glantz |  |  |  | 1
124 | 733 | Ekhyddan-Nybro-Hemsjo | Ekhyddan (SE) | Nybro/Hemsjo (SE) | Overhead Line | AC | 0 | 0 | Al59 | 910 | 3 | 160 | 0.015 | 0.194 | 0 | 0 | 400 | 3150 |  | 2023 | Permitting | 159 | 0.1 | Svk | Svk | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | Petter.Glantz@svk.se | Peter | Glantz |  |  |  | 1
126 | 403 | Reinforcements SE2-SE3 in Sweden | SE2 | SE3 | Compensation | AC | 0 | 0 | - | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 400 | 3150 |  | 2030 | Under consideration | 550 | 0 | Svk | Svk | 0 | 0 | 0 | 0 |  | pglantz@ENTSOE.local | Petter | Glantz | Petter.Glantz@svk.se | Peter | Glantz |  |  |  | 1
127 | 86 | 86 | Foggia (IT) | Villanova (IT) | Overhead Line | AC | 0 | 0 | ACSR | 585 | 3 | 178 | 0.02 | 0.27 | 0.005 | 0 | 400 | 3000 |  | 1/ 1/ 2022 | Permitting | 0 | 0 | TERNA | TERNA | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
127 | 91 | 91 | Foggia (IT) | Benevento II (IT) | Overhead Line | AC | 0 | 0 | ACSR | 585 | 0 | 85 | 3 | 0 | 0 | 0 | 400 | 3000 |  | 30/ 06/ 2014 | Commissioned | 0 | 0 | TERNA | TERNA | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
127 | 96 | 96 | Deliceto (IT) | Bisaccia (IT) | Overhead Line | AC | 0 | 0 | ACSR | 585 | 3 | 30 | 0.02 | 0.31 | 0.004 | 0 | 400 | 3000 |  | 31/ 12/ 2022 | Permitting | 0 | 0 | TERNA | TERNA | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
127 | 645 | ITA-3 | Laino (IT) | Altomonte (IT) | Overhead Line | AC | 0 | 0 | ACSR | 585 | 3 | 50 | 0.01 | 0.1 | 0.01 | 0 | 400 | 3000 |  | 1/ 1/ 2022 | Permitting | 0 | 0 | TERNA | TERNA | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
130 | 665 | Wolmirstedt-Isar | Wolmirstedt (DE) | Isar (DE) | Underground Cable | DC | VSC | 0 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2025 | Planned but not yet permitting | 2800 | 22.4 | 50Hertz | TenneT DE | 0 | 0 | 0 | 0 | NO information? | mheit@entsoe.local | Michael | Heit | kedar.kolharkar@tennet.eu | Kedar | Kolharkar | robert.tempels@amprion.net | Robert | Tempels | 1
132 | 661 | HVDC Line A-North | Emden East (DE) | Osterath (DE) | Overhead Line | DC | VSC | 0 | cable | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 400 | 0 |  | 1/ 1/ 2025 | Planning | 0 | 0 | Amprion | Amprion | 0 | 0 | 0 | 0 |  | mfranz@ENTSOE.local | Marco | Franz | Christian.Neus@amprion.net | Christian | Neus |  |  |  | 1
134 | 176 | Daxlanden-Eichstetten | Daxlanden (DE) | Eichstetten (DE) | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 380 | 0 |  | 1/ 1/ 2021 | Planning | 0 | 0 | TransnetBW | TransnetBW | 0 | 0 | 0 | 0 |  | bgaillardon@entsoe.local | Boris | Gaillardon | [6 empty] | 1
134 | 680 | Urberach - Daxlanden | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 219 | 0 | 0 | 0 | 0 | 400 | 0 |  | 1/ 1/ 2022 | Planning | 0 | 0 | Amprion | TransnetBW | 0 | 0 | 0 | 0 |  | bgaillardon@entsoe.local | Boris | Gaillardon | [6 empty] | 1
135 | 179 | Rommerskirchen - Weißenthurm | Rommerskirchen (DE) | Weißenthurm (DE) | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 400 | 3600 |  | 1/ 1/ 2019 | Under Construction | 0 | 0 | Amprion | Amprion | 0 | 0 | 0 | 0 |  | mfranz@ENTSOE.local | Marco | Franz | Christian.Neus@amprion.net | Christian | Neus |  |  |  | 1
135 | 188 | Kruckel - Dauersberg | Kruckel (DE) | Dauersberg (DE) | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 380 | 3600 |  | 1/ 1/ 2021 | Permitting | 0 | 0 | Amprion | Amprion | 0 | 0 | 0 | 0 |  | mfranz@ENTSOE.local | Marco | Franz | Christian.Neus@amprion.net | Christian | Neus |  |  |  | 1
138 | 273 | 400kV OHL Cernavoda-Stalpu | Cernavoda (RO) | Stalpu (RO) | Overhead Line | AC | 0 | 0 | ALOL | 300 | 3 | 159 | 2.56 | 24.24 | 0.965 | 0 | 400 | 1741 |  | 2020 | Permitting | 0 | 0 | Transelectrica | Transelectrica | 0 | 0 | 0 | 0 |  | spetkov@entsoe.local | Stojan | Petkov | [6 empty] | 1
138 | 275 | 400 kV OHL Smardan-Gutinas | Smardan (RO) | Gutinas (RO) | Overhead Line | AC | 0 | 0 | ALOL | 300 | 3 | 140 | 4.28 | 40.608 | 1.617 | 0 | 400 | 1741 |  | 2020 | Permitting | 0 | 0 | Transelectrica | Transelectrica | 0 | 0 | 0 | 0 |  | spetkov@entsoe.local | Stojan | Petkov | [6 empty] | 1
138 | 715 | 220kV Stalpu substation upgrade to 400 kV | Stalpu (RO) | Stalpu (RO) | Substation | AC | 0 | 0 | GIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 250 |  | 2020 | Permitting | 0 | 0 | Transelectrica | Transelectrica | 0 | 0 | 0 | 0 |  | spetkov@entsoe.local | Stojan | Petkov | [6 empty] | 1
138 | 800 | 400 kV OHL Varna-Burgas | Varna(BG) | Burgas(BG) | Overhead Line | AC | 0 | 0 | Aluminum-steel | 400 | 3 | 140 | 0 | 0 | 0 | 0 | 400 | 0 |  | 31/ 03/ 2021 | Planned but not yet permitting | 0 | 0 | ESO-EAD | ESO-EAD | 0 | 0 | 0 | 0 |  | spetkov@entsoe.local | Stojan | Petkov | [6 empty] | 1
142 | 256 | 256 | Maritsa East 1 (BG) | N.Santa (GR) | Overhead Line | AC | 0 | 0 | Aluminum-Steel | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 400 | 0 |  | 30/01/ 2023 | Permitting | 0 | 0 | ESO-EAD | IPTO-SA | 0 | 0 | 0 | 0 |  | spetkov@entsoe.local | Stojan | Petkov | DBolashikova@ndc.bg | Dilyana | Bolashikova |  |  |  | 1
142 | 257 | 257 | Maritsa East 1 (BG) | Plovdiv (BG) | Overhead Line | AC | 0 | 0 | Aluminum-Steel | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 400 | 0 |  | 30/ 12/ 2020 | Design & Permitting | 0 | 0 | ESO-EAD | ESO-EAD | 0 | 0 | 0 | 0 |  | spetkov@entsoe.local | Stojan | Petkov | DBolashikova@ndc.bg | Dilyana | Bolashikova |  |  |  | 1
142 | 258 | 258 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | Overhead Line | AC | 0 | 0 | Aluminum-Steel | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 400 | 0 |  | 30/ 06/ 2019 | Design & Permitting | 0 | 0 | ESO-EAD | ESO-EAD | 0 | 0 | 0 | 0 |  | spetkov@entsoe.local | Stojan | Petkov | DBolashikova@ndc.bg | Dilyana | Bolashikova |  |  |  | 1
142 | 262 | 262 | Maritsa East 1 (BG) | Burgas (BG) | Overhead Line | AC | 0 | 0 | Aluminum-Steel | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 400 | 0 |  | 01/ 06/ 2021 | Design & Permitting | 0 | 0 | ESO-EAD | ESO-EAD | 0 | 0 | 0 | 0 |  | spetkov@entsoe.local | Stojan | Petkov | DBolashikova@ndc.bg | Dilyana | Bolashikova |  |  |  | 1
144 | 238 | New_400 kV OHL RO-RS | Resita (RO) | Pancevo (RS) | Overhead Line | AC | 0 | 0 | ALOL | 300 | 3 | 131 | 3.404 | 33.536 | 1.112 | 0 | 400 | 1741 |  | 2017 | Under construction | 0 | 0 | Transelectrica | EMS | 0 | 0 | 0 | 63 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | vzaharia@entsoe.local | Virginica | Zaharia | [6 empty] | 1
144 | 269 | 400 kV OHL Portile de Fier-Resita | Portile de Fier (RO) | Resita (RO) | Overhead Line | AC | 0 | 0 | ALOL | 300 | 3 | 116 | 3.712 | 35.148 | 1.4 | 0 | 400 | 1741 |  | 2019 | Under Construction | 0 | 0 | Transelectrica | Transelectrica | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | vzaharia@entsoe.local | Virginica | Zaharia | [6 empty] | 1
144 | 270 | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz - Arad to 400kV double circuit line | Resita (RO) | Arad (RO) | Overhead Line | AC | 0 | 0 | ALOL | 300 | 3 | 175 | 0 | 0 | 0 | 0 | 400 | 1741 |  | 2023 | Permitting | 0 | 0 | Transelectrica | Transelectrica | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | vzaharia@entsoe.local | Virginica | Zaharia | [6 empty] | 1
144 | 701 | 400 kV Substation Resita | Resita (RO) | Resita (RO) | Substation | AC | 0 | 0 | AIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 650 |  | 2019 | Permitting | 0 | 0 | Transelectrica | Transelectrica | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | vzaharia@entsoe.local | Virginica | Zaharia | [6 empty] | 1
144 | 705 | 400 kV Substation Timisoara | Timisoara (RO) | Timisoara (RO) | Substation | AC | 0 | 0 | AIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 900 |  | 2023 | Design | 0 | 0 | Transelectrica | Transelectrica | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | vzaharia@entsoe.local | Virginica | Zaharia | [6 empty] | 1
150 | 616 | Salgareda - Border IT-SI | Salgareda (IT) | Border IT-SI | Underground Cable | DC | VSC | 0 | Tbd | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 500 | 0 |  | 2022 | Permitting | 0 | 0 | TERNA | N/A | N/A | N/A | 1000 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | Klemen.Dragas@eles.si | Klemen | Dragas |  |  |  | 1
150 | 1616 | Beričevo - Border IT-SI | Beričevo (SI) | Border IT-SI | Underground Cable | DC | VSC | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 500 | 0 |  | 2022 | Under consideration | 0 | 0 | ELES | N/A | N/A | N/A | 1000 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | Klemen.Dragas@eles.si | Klemen | Dragas |  |  |  | 1
153 | 987 | France-Alderney-Britain | Menuel (FR) | Exeter (GB) | Subsea Cable | DC | VSC | 0 | TBD | 0 | 0 | 210 | 0 | 0 | 0 | TBD | 320 | 0 |  | 1/ 1/ 2022 | Permitting | 0 | 0 | RTE (FR) | NGIHL (UK) | TBD | TBD | 0 | 0 |  | pbodin@ENTSOE.local | Philippe | Bodin | [6 empty] | 1
164 | 149 | Dollern - Stade | Dollern (DE) | Stade (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
164 | 157 | Wahle - Mecklar | Wahle (DE) | Mecklar (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
164 | 677 | Dollern - Landesbergen | Dollern (DE) | Landesbergen (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2023 | Permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
164 | 685 | Mecklar - Grafenrheinfeld | Mecklar (DE) | Grafenrheinfeld (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2027 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
167 | 998 | Viking Link DKW-GB, TYNDP ID 167.998 | Revsing (DKW) | Bicker Fen (GB) | Subsea Cable | DC | VSC | 0 | Double Circuit | 0 | 0 | 770 | 0 | 0 | 0 | TBD | 515 | 1410 |  | 31/12/ 2022 | Permitting | 0 | 0 | Energinet.dk | National Grid | TBD | TBD | 1400 | 0 |  | aorths@entsoe.local | Antje | Orths | [6 empty] | 1
170 | 382 | 330 kV line Vilnius-Neris | Vilnius | Neris | Overhead Line | AC | 0 | 0 | AL | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 330 | 1650 |  | 1/ 1/ 2024 | Under construction | 36 | 0 | LITGRID | LITGRID | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | [6 empty] | 1
170 | 1004 | 330kV OHL Paide-Sindi (L346) | Sindi | Paide | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 330 | 0 |  | 01/01/2025 | Cancelled | 0 | 0 | ELERING | ELERING | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | [6 empty] | 1
170 | 1010 | 330 kV OHL Tartu-Valmiera | Tartu | Valmiera | Overhead Line | AC | 0 | 0 | Single circuit | 300 | 3 | 133 | 0.029 | 0.326 | 3.44 | 0 | 330 | 1650 |  | 1/ 1/ 2025 | Planned but not yet permitting | 0 | 0 | Elering | AST | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | [6 empty] | 1
170 | 1011 | Valmiera -Tsirguliina 330 kV | Tsirguliina | Valmiera | Overhead Line | AC | 0 | 0 | Single circuit | 300 | 3 | 60 | 0.029 | 0.326 | 3.44 | 0 | 330 | 1650 |  | 1/ 1/ 2025 | Planned but not yet permitting | 0 | 0 | Elering | AST | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | [6 empty] | 1
170 | 1012 | 330 kV OHL Tartu-Balti (L300) | Balti | Tartu | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 330 | 0 |  | 1/ 1/ 2024 | Planning | 0 | 0 | ELERING | ELERING | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | [6 empty] | 1
170 | 1013 | Eesti-Tsirguliina 330kV OHL | Eesti | Tsirguliina | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 243 | 0 | 0 | 0 | 0 | 330 | 0 |  | 1/ 1/ 2025 | Planning | 0 | 0 | ELERING | ELERING | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | [6 empty] | 1
170 | 1034 | New 400 kV interconnection line from Lithuania to state border | Marijampole | State border | Overhead Line | AC | 0 | 0 | Al | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 400 | 1361 |  | 01/01/2031 | Planned but not yet permitting | 43.7 | 0 | LITGRID | LITGRID | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | [6 empty] | 1
170 | 1117 | B2B at Narva | Eesti | - | Substation | DC | LCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 0 |  | 1/ 1/ 2024 | Planning | 0 | 0 | ELERING | - | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | [6 empty] | 1
170 | 1118 | SVC and control upgrades | Eesti 330 kV | - | Compensation | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 0 |  | 1/ 1/ 2024 | Planning | 0 | 0 | LITGRID; AST; ELERING | - | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | [6 empty] | 1
170 | 1564 | New 110 kV OHL Pagegiai-Bitenai | Pagegiai | Bitenai | Overhead Line | AC | 0 | 0 | Al | 150 | 1 | 17 | 0 | 0 | 0 | 0 | 110 | 450 |  | 2019 | Under construction | 4.3 | 0 | LITGRID | LITGRID | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
170 | 1565 | Reconstruction of 330 kV OHL LE-Vilnius | LE | Vilnius | Overhead Line | AC | 0 | 0 | Al | 300 | 2 | 41 | 0 | 0 | 0 | 0 | 330 | 1461 |  | 2018 | Under construction | 21 | 0 | LITGRID | LITGRID | 0 | 0 | 0 | 0 |  | Rimantas.Rutkauskas@litgrid.eu | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
170 | 1566 | Reconstructions in North Eastern Lithuania | Ignalina | Utena | Substation | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 0 |  | 2021 | Under construction | 21 | 0 | LITGRID | LITGRID | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
170 | 1567 | Reinforcements of 110 kV lines near LT-BY border | Didziasalis, Kalveliai, Salcininkai | - | Overhead Line | AC | 0 | 0 | Al | 150 | 0 | 64 | 0 | 0 | 0 | 0 | 110 | 450 |  | 2023 | Planned but not yet permitting | 31 | 0 | LITGRID | - | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
170 | 1568 | Construction of three new 400/330 kV autotransformers in Alytus substation | Alytus | - | Phase Shift Transformer | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 1050 |  | 2024 | Planned but not yet permitting | 18 | 0 | LITGRID | - | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
170 | 1569 | Rerouting of exicting HVDC converter in Alytus | Alytus | - | LCC converter station | DC | LCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024 | Planned but not yet permitting | 1 | 0 | LITGRID | - | 0 | 0 | 500 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
170 | 1570 | Construction of new HVDC converter in Bitenai | Bitenai | - | LCC converter station | DC | VSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024 | Planned but not yet permitting | 150 | 0 | LITGRID | - | 0 | 0 | 700 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
170 | 1571 | New voltage stabiliser units (SVC) in Baltics | - | - | Substation | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2023 | Planned but not yet permitting | 30 | 0 | LITGRID; AST; ELERING | - | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
170 | 1572 | Preparation works in Baltics: Baltic AGC system, frequency control monitoring system | - | - | Substation | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024 | Planned but not yet permitting | 2 | 0 | LITGRID; AST; ELERING | - | 0 | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas | andrzej.tymorek@pse.pl | Andrzej | Tymorek |  |  |  | 1
170 | 1573 | New 330 kV Musa substation | Musa | - | Substation | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 330 | 0 | 2023 |  | 2023 | Planned but not yet permitting | 4 | 0.004 |  | LITGRID | - | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas
170 | 1574 | Reconstruction of 330 kV OHL Klaipeda - Bitenai | Klaipeda | Bitenai | Overhead Line | AC | 0 | 0 | 0 | 0 | 92 | 0.0391 | 0.322 | 3.5102 | 2% | 330 | 1650 | 2024 |  | 2024 | Planned but not yet permitting | 19 | 0.06 |  | LITGRID | - | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas
170 | 1575 | Reconstruction of 330 kV OHL Bitėnai - Jurbarkas | Bitenai | Jurbarkas | Overhead Line | AC | 0 | 0 | 0 | 0 | 43.6 | 0.0391 | 0.322 | 3.5102 | 2% | 330 | 1650 | 2024 |  | 2024 | Planned but not yet permitting | 9 | 0.028 |  | LITGRID | - | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas
170 | 1576 | New 330 kV OHL Jurbarkas - KHAE | Jurbarkas | KHAE | Overhead Line | AC | 0 | 0 | 0 | 0 | 75 | 0.0391 | 0.322 | 3.5102 | 2% | 330 | 1650 | 2024 |  | 2024 | Planned but not yet permitting | 16 | 0.049 |  | LITGRID | - | 0 | 0 | 0 |  | rrutkauskas2@entsoe.local | Rimantas | Rutkauskas
172 | 1487 | ElecLink | Sellindge (UK) | Mandarins (FR) | Underground Cable | DC | VSC | 345 | Aluminium | 0 | 0 | 69 | 0 | 0 | 0 | 2% | 320 | 1600 |  | 2019 | Under construction | 580 | 4.5 | National Grid Electricty Transmission, the GB TSO | Reseau de Transport d'Electricite, the French TSO | 1.5% | 0.5% | 1000 | 28 |  | adeluca@ENTSOE.local | Alex De Luca | Alex | De Luca | [5 empty] | 1
173 | 1281 | Aubange-Moulaine: PSTs | Aubange (BE) | Moulaine (FR) | Phase Shift Transformer | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 |  | 31/12/2020 | Planned but not yet permitting | 20 | 0 | ELIA | RTE | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | [6 empty] | 1
174 | 1014 | Greenconnector | Verderio | Sils i.D. | Underground Cable | DC | LCC | 0 | Copper/Aluminum | 0 | 0 | 150 | 0 | 0 | 0 | 72 hours | 400 | 1350 |  | 2022 | Permitting | 609 | 1.9 | Terna | Swissgrid | 1 week/year/monopole | 0.2 faults/year/bipole | 1000 | 120 |  | cgianotti@ENTSOE.local | Claudio | Gianotti | [6 empty] | 1
175 | 1000 | Great Belt II | Not decided | Not decided | Subsea Cable | DC | LCC | 0 | not decided | 0 | 0 | 120 | 0 | 0 | 0 | 600 MW | 400 | 1.5 |  | 2030 | Under consideration | 320 | 6.4 | Energinet | Energinet | 4% | 4% | 600 | 10 |  | pborre@entsoe.local | Peter | Borre Eriksen | [6 empty] | 1
176 | 995 | Hansa PowerBridge | Hurva (SE4) | Guestrow (DE) | Subsea Cable | DC | VSC | 300 | not decided | 0 | 0 | 300 | 0 | 0 | 0 | n/a | 300 | 2400 |  | 2026 | Permitting | 660 | 22.4 | Svk | 50Hertz | 3.5 % (13 days) | 4 % (15 days) | 700 | 180 |  | pglantz@ENTSOE.local | Petter | Glantz |  |  |  | thomas.koebinger@50Hertz.com | Thomas | Köbinger | 1
179 | 1016 | DKE-DE (Kontek 2) | Bjæverskov (DK2) | Bentwisch (DE) | Subsea Cable | DC | LCC | 0 | Not decided | 0 | 0 | 170 | 0 | 0 | 0 | 4.5 | 400 | 1.5 |  | 2030 | Under consideration | 360 | 7.2 | Energinet | 50Hertz | 5 % | 5 % | 600 | 0 |  | mheit@entsoe.local | Michael | Heit | thomas.koebinger@50Hertz.com | Thomas | Köbinger |  |  |  | 1
183 | 1018 | DKW-DE, Westcoast, TYNDP ID 183.1018 | Klixbüll (DE) | Endrup (DKW) | Overhead Line | AC | 0 | 0 | Double Circuit | 36.2 | 3 | 92 | 1.82 | 15.48 | 454.25 | 0 | 380 | 4988 |  | 31/ 12/ 2022 | Permitting | 0 | 0 | TenneT-DE | Energinet.dk | 0 | 0 | 0 | 0 |  | aorths@entsoe.local | Antje | Orths | [6 empty] | 1
186 | 886 | 886 | Seyring | Neusiedl/Zaya | Overhead Line | AC | 0 | 0 | Tbd | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Permitting | 0 | 0 | APG | APG | 0 | 0 | 0 | 0 |  | dboehm@ENTSOE.local | david | boehm | [6 empty] | 1
187 | 997 | 997 Pleinting - St. Peter | Pleinting (DE) | St. Peter (AT) | Overhead Line | AC | 0 | 0 | Tbd | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2024 | Permitting | 0 | 0 | TenneT-DE | APG | 0 | 0 | 0 | 0 |  | dboehm@ENTSOE.local | david | boehm | [6 empty] | 1
190 | 1382 | NorthConnect | Sima | Peterhead | Subsea Cable | DC | VSC | 0 | Undecided | 0 | 0 | 655 | 0 | 0 | 0 | 1400MW | 500 | 0 |  | 2022 | Design | 1813 | 30 | Statnett | National Grid (SSEN is TO) | TBC | TBC | 1400 | 0 |  | aelder@ENTSOE.local | Adair | Elder | [6 empty] | 1
191 | 656 | BorWin3 | Cluster BorWin3 | Emden/East (DE) | Subsea Cable | DC | VSC | 0 | single circuit | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2019 | Under construction | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
191 | 952 | Cluster DolWin 5 (NOR 1-1) | Cluster DolWin 5 (NOR-1-1) | Emden/East (DE) | Subsea Cable | DC | VSC | 0 | single circuit | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
191 | 953 | Cluster DolWin6 | Cluster DolWin 6 (NOR-3-3) | Emden/East | Subsea Cable | DC | VSC | 0 | single circuit | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2023 | Under construction | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
191 | 1513 | DolWin3 | Cluster DolWin3 (DE) | Dörpen/West (DE) | Subsea Cable | DC | VSC | 0 | single circuit | 0 | 0 | 162 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2018 | Under construction | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 |  | nschindzielorz@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
192 | 211 | DolWin 4 (NOR-3-2) | Cluster DolWin 4 (NOR 3-2) | area of Cloppenburg | Subsea Cable | DC | VSC | 0 | single circuit | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2028 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
192 | 659 | SylWin2 | Cluster SylWin2 (DE) | Büttel (DE) | Subsea Cable | DC | VSC | 0 | single circuit | 0 | 0 | 205 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2025 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 536 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
192 | 954 | Cluster BorWin 5 (NOR-7-1) | Cluster BorWin 5 (NOR-7-1) | area of Cloppenburg/East | Subsea Cable | DC | VSC | 0 | single circuit | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2025 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 900 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
192 | 1485 | BorWin4 | Cluster BorWin4 (DE) | area of Cloppenburg/East | Subsea Cable | DC | VSC | 0 | single circuit | 0 | 0 | 272 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2030 | Planned but not yet permitting | 0 | 0 | TenneT DE | TenneT DE | 0 | 0 | 900 | 0 |  | nschindzielorz@entsoe.local | Kedar Kolharkar; Antje Orths | Kedar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
193 | 927 | La Plana/Morella-Godelleta | La Plana/Morella | Godelleta | Overhead Line | AC | 0 | 0 | Condor | 0 | 3 | 207.5 | 0.0256 | 0.2729 | 4.0993 | 0 | 400 | 2815 |  | 2025 | Under consideration | 67.62 | 1.0143 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
194 | 561 | New substation Cartuja | Cartuja (ES) | Cartuja (ES) | Substation | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2029 | Under consideration | 3.1 | 0.0465 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
194 | 929 | Cartuja-Arcos 400 kV | Cartuja | Arcos | Overhead Line | AC | 0 | 0 | Condor | 0 | 3 | 30 | 0.0128 | 0.1384 | 2.0794 | 0 | 400 | 2786 |  | 2029 | Under consideration | 20.2 | 0.303 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
197 | 742 | Pyhanselka-Petajavesi | Pyhanselka (FI) | Petajavesi (FI) | Overhead Line | AC | 0 | 0 | 3-Finch | 636.6 | 3 | 300 | 0.0171 | 0.284 | 0 | 0 | 400 | 3150 |  | 1/ 7/ 2022 | Permitting | 90 | 0.242 | Fingrid | Fingrid | 0 | 0 | 0 | 0 |  | aharjula@entsoe.local | Antti | Harjula | [6 empty] | 1
199 | 1051 | Cornier - Chavalon 400 kV | CORNIER (FR) | CHAVALON (CH) | Overhead Line | AC | 0 | 0 | To be defined | 0 | 0 | 63 | 0.02 | 0.296 | 3.66 | 0.9% | 400 | 0 |  | 2035 | Under consideration | 130 | 1 | RTE | SWISSGRID | 0.5% | 0.4% | 0 | 0 |  | gdudicourt@entsoe.local | Gabriel | Dudicourt | [6 empty] | 1
200 | 306 | R Vitkov | Vitkov (CZ) | N/A | Substation | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 30/ 11/ 2022 | Permitting | 0 | 0 | CEPS | N/A | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | akasembe@entsoe.local | Andrew | Kasembe | [6 empty] | 1
200 | 308 | Vernerov-Vitkov | Vernerov (CZ) | Vitkov (CZ) | Overhead Line | AC | 0 | 0 | 3x3x490-AL1/64-ST1A | 0 | 0 | 79 | 0.02 | 0.28 | 3.95 | 0 | 400 | 2445 |  | 30/ 07/ 2025 | Permitting | 0 | 0 | CEPS | CEPS | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | akasembe@entsoe.local | Andrew | Kasembe | [6 empty] | 1
200 | 309 | Vitkov-Prestice | Vitkov (CZ) | Prestice (CZ) | Overhead Line | AC | 0 | 0 | 3x3x490-AL1/64-ST1A | 0 | 0 | 86 | 0.02 | 0.28 | 3.95 | 0 | 400 | 2445 |  | 30/ 11/ 2022 | Permitting | 0 | 0 | CEPS | CEPS | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | akasembe@entsoe.local | Andrew | Kasembe | [6 empty] | 1
200 | 312 | R Mirovka | Mirovka (CZ) | N/A | Substation | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 30/ 09/ 2025 | Permitting | 0 | 0 | CEPS | N/A | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | akasembe@entsoe.local | Andrew | Kasembe | [6 empty] | 1
200 | 314 | Mirkovka-V413 | Mirovka (CZ) | V413 (CZ) | Overhead Line | AC | 0 | 0 | 3x3x490-AL1/64-ST1A | 0 | 0 | 27 | 0.02 | 0.28 | 3.95 | 0 | 400 | 2445 |  | 30/ 05/ 2019 | Permitting | 0 | 0 | CEPS | CEPS | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | akasembe@entsoe.local | Andrew | Kasembe | [6 empty] | 1
203 | 538 | Morella-La Plana | Morella (ES) | La Plana(ES) | Overhead Line | AC | 0 | 0 | Cardinal | 0 | 2 | 78 | 0.033 | 0.3227 | 3.528 | 0 | 400 | 2815 |  | 2020 | Permitting | 50.76 | 0.7614 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
206 | 682 | Großgartach - Endersbach | Großgartach (DE) | Endersbach (DE) | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2025 | Planned but not yet permitting | 0 | 0 | TransnetBW | TransnetBW | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
206 | 687 | Redwitz - Schwandorf | Redwitz (DE) | Schwandorf (DE) | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2023 | Permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
206 | 688 | Raitersaich-Altheim | Raitersaich (DE) | Altheim (DE) | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2026 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
206 | 990 | Grafenrheinfeld - Großgartach | Grafenrheinfeld (DE) | Großgartach (DE) | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2022 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TransnetBW | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
207 | 676 | Dollern - Elsfleth/West | Dollern (DE) | Elsfleht/West (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2026 | Permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
207 | 939 | Conneforde - Emden | Conneforde | Emden/Ost | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
207 | 940 | Emden - Halbemond | Emden/Ost | Halbemond | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2022 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
208 | 150 | Conneforde-Wilhelmshaven | Conneforde (DE) | Wilhelmshaven (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2020 | Permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
208 | 151 | Ganderkesee - Wehrendorf | Wehrendorf (DE) | Ganderkesee (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 95 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
208 | 156 | Niederrhein-Dörpen | Niederrhein (DE) | Dörpen/West (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Permitting | 0 | 0 | Amprion | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
209 | 935 | Kreis Segeberg - Siems | Kreis Segeberg | Göhl/Siems | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2022 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
210 | 1380 | Wurmlach (AT) - Somplago (IT) interconnection | SOMPLAGO | WURMLACH | Underground Cable | AC | 0 | 0 | Aluminum cable | 2000 | 1 | 51 | 0.0149 | 0.107 | 75.36 | 0 | 220 | 800 |  | 2021 | Permitting | 92 | 1.6 | TERNA SPA | Austrian Power Grid AG | 0 | 0 | 0 | 40 IT - 11 AT |  | fscaramuzza@ENTSOE.local | Fabrizio | Scaramuzza | [6 empty] | 1
214 | 1082 | Interco Iceland-UK | tbd | tbd | Subsea Cable | DC | VSC | 0 | XLPE ALUMINUM | 0 | 0 | 1000 | 0 | 0 | 0 | TBD | 500 | 0 |  | 2030 | Under consideration | 1800 | 21 | tbd | tbd | TBD | TBD | 1000 | 0 | Iceland not modelled | mnavarette@ENTSOE.local | Marta | Navarrete | [6 empty] | 1
219 | 1407 | EuroAsia Interconnector | Hadera Site | Kofinou Site | Subsea Cable | DC | 10 | 0 | XLPE | 0 | 0 | 330 | 0.0233 | ?? | 0 | 7.93% | 500 | 0 |  | 2020 | Permitting | 4590 | 53.5 | IEC | TSO Cyprus | 2% | 5.93% | 2000 | 0 | Israel not modelled | gkillas1@ENTSOE.local | George | Killas
219 | 1409 | EuroAsia Interconnector | Kofinou Site | Korakia (Crete)Site | Subsea Cable | DC | 10 | 0 | XLPE | 0 | 0 | 880 | 0.0233 | ?? | 0 | 7.93% | 500 | 0 |  | 2021 | Permitting | 4590 | 53.5 | TSO Cyprus | ADMHE | 2% | 5.93% | 2000 | 0 | Israel not modelled | gkillas1@ENTSOE.local | George | Killas
219 | 1410 | EuroAsia Interconnector | Korakia (Crete)Site | Athens Site | Subsea Cable | DC | 10 | 0 | XLPE | 0 | 0 | 310 | 0.0233 | ?? | 0 | 7.93% | 500 | 0 |  | 2020 | Permitting | 4590 | 53.5 | ADMHE | ADMHE | 2% | 5.93% | 2000 | 0 | Israel not modelled | gkillas1@ENTSOE.local | George | Killas
225 | 1107 | 2nd interconnecter between Belgium and Germany | to be defined (BE) | to be defined (DE) | Underground Cable | DC | VSC | 0 | XLPE | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 0 | 0 |  | 2028 | Under consideration | 600 | 0 | ELIA | AMPRION | TBD | TBD | 1000 | 0 |  | mfranz@ENTSOE.local | Marco | Franz | [6 empty] | 1
227 | 627 | 400kV interconnection RS-BA | Bajina Basta (RS) | Visegrad (BA) | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 45.2 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2024 | Permitting | 19.6 | 0.24 | EMS | NOSBIH | 1% | 1% | 0 | 26.2 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
227 | 628 | 400kV OHL B.Basta-Obrenovac | SS Bajina Basta (RS) | SS Obrenovac (RS) | Overhead Line | AC | 0 | 0 | ACSR | 2x490 | 2 | 109 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2024 | Permitting | 55 | 0.66 | EMS | EMS | 1% | 1% | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
227 | 630 | 400kV interconnection RS-ME | Bajina Basta (RS) | Pljevlja (ME) | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 100 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2024 | Permitting | 44.4 | 0.53 | EMS | CGES | 1% | 1% | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
227 | 631 | 400kV SS B.Basta upgrade | Bajina Basta (RS) | Bajina Basta (RS) | Substation | AC | 0 | 0 | ACSR | 490 | 2 | 0 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2024 | Permitting | 11 | 0.13 | EMS | EMS | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
227 | 1526 | 400 kV OHL Lastva - Pljevlja | SS Lastva | SS Pljevlja | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 151 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2019 | Under construction | 67.5 | 1.35 | CGES | CGES | 1% | 1% | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
227 | 1527 | 400 kV OHL Kragujevac-Kraljevo | SS Kragujevac | SS Kraljevo | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 60 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2020 | Under construction | 17 | 0.2 | EMS | EMS | 1% | 1% | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
227 | 1528 | Upgrade of SS Kraljevo | SS Kraljevo | SS Kraljevo | Substation | AC | 0 | 0 | ACSR | 490 | 2 | 0 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2020 | Under construction | 10.5 | 0.13 | EMS | EMS | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
228 | 1231 | Muhlbach Eichstetten | Muhlbach | Eichstetten | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2025 | Planned but not yet permitting | 50 | 0 | RTE | TransnetBW GmbH | 0 | 0 | 0 | 0 |  | tokraszewski@ENTSOE.local | Tomasz | Okraszewski | [6 empty] | 1
229 | 1270 | Baczyna-Zielona Góra | Baczyna-Plewiska indentation | Zielona Góra | Overhead Line | AC | 0 | 0 | 468/24-A1F/UHST-261 | 0 | 0 | 40 | 0.0216 | 0.2919 | 3.927 | 0 | 400 | 3200 |  | >2030 | Under Consideration | 19 | 0.057 | PSE S.A. | PSE S.A. | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | [6 empty] | 1
229 | 1271 | Zielona Góra - Plewiska | Zielona Góra | Baczyna-Plewiska indentation | Overhead Line | AC | 0 | 0 | 468/24-A1F/UHST-261 | 0 | 0 | 40 | 0.0216 | 0.2919 | 3.927 | 0 | 400 | 3200 |  | >2030 | Under Consideration | 19 | 0.057 | PSE S.A. | PSE S.A. | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | [6 empty] | 1
229 | 1272 | Zielona Góra | Zielona Góra | n.a. | Substation | AC | 0 | 0 | n.a. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | >2030 | Under Consideration | 23.7 | 0.711 | PSE S.A. | n.a. | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | [6 empty] | 1
229 | 1273 | Zielona Góra-Gubin | Zielona Góra | Gubin | Overhead Line | AC | 0 | 0 | 468/24-A1F/UHST-261 | 0 | 0 | 60 | 0.0216 | 0.2919 | 3.927 | 0 | 400 | 3200 |  | >2030 | Under Consideration | 28.4 | 0.085 | PSE S.A. | PSE S.A. | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | [6 empty] | 1
229 | 1274 | Gubin | Gubin | n.a. | Substation | AC | 0 | 0 | n.a. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | >2030 | Under Consideration | 66.7 | 2.001 | PSE S.A. | n.a. | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | [6 empty] | 1
229 | 1275 | Gubin - Eisenhuettenstadt | Gubin (PL) | Eisenhuettenstadt (DE) | Overhead Line | AC | 0 | 0 | 468/24-A1F/UHST-261 | 0 | 0 | 20 | 0.0216 | 0.2919 | 3.927 | 0 | 400 | 3200 |  | >2030 | Under consideration | 15 | 0.045 | PSE S.A. | 50Hertz | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit |  |  |  | michael.heit@50Hertz.com | Michael | Heit | 1
230 | 353 | Krajnik-Baczyna | Krajnik (PL) | Baczyna (PL) | Overhead Line | AC | 0 | 0 | 408-AL1F/34-UHST | 408 | 3 | 70 | 0.0245 | 0.2917 | 3.927 | 0 | 400 | 3200 |  | 2021 | Permitting | 38.7 | 0.116 | PSE S.A. | PSE S.A. | 0 | 0 | 0 | 0 |  | ktokarski@entsoe.local | Krzysztof | Tokarski | [6 empty] | 1
230 | 355 | Mikułowa - Świebodzice | Mikułowa (PL) | Świebodzice (PL) | Overhead Line | AC | 0 | 0 | 468/24-A1F/UHST-261 | 0 | 0 | 100 | 0.0216 | 0.2919 | 3.927 | 0 | 400 | 3200 |  | 2023 | Planned but not yet permitting | 102.27 | 0.307 | PSE S.A. | PSE S.A. | 0 | 0 | 0 | 0 |  | ktokarski@entsoe.local | Krzysztof | Tokarski | [6 empty] | 1
230 | 1035 | Baczyna | Baczyna | n.a. | Substation | AC | 0 | 0 | n.a. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2020 | Permitting | 22.5 | 0.675 | PSE S.A. | n.a. | 0 | 0 | 0 | 0 |  | ktokarski@entsoe.local | Krzysztof | Tokarski | [6 empty] | 1
230 | 1232 | Baczyna-Plewiska | Baczyna | Plewiska | Overhead Line | AC | 0 | 0 | 468/24-A1F/UHST-261 | 0 | 0 | 147 | 0.0216 | 0.2919 | 3.927 | 0 | 400 | 3200 |  | 2024 | Planned but not yet permitting | 107.22 | 0.7 | PSE S.A. | PSE S.A. | 0 | 0 | 0 | 0 |  | ktokarski@entsoe.local | Krzysztof | Tokarski | [6 empty] | 1
231 | 1282 | 380 kV Grid Reinforcement Beznau - Tiengen | Beznau (CH) | Tiengen (DE) | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 01/01/2030 | Under consideration | 0 | 0 | Swissgrid | Amprion | 0 | 0 | 0 | 0 |  | tokraszewski@ENTSOE.local | Tomasz | Okraszewski | [6 empty] | 1
231 | 1457 | Additional measures | Germany | Switzerland | Overhead Line | DC | VSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2035 | Under consideration | 0 | 0 | TransnetBW | Swissgrid | 0 | 0 | 0 | 0 |  | tokraszewski@ENTSOE.local | Tomasz | Okraszewski | [6 empty] | 1
233 | 1235 | Conceptual project | - | - | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2027 | Under consideration | 75 | 1.125 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | [6 empty] | 1
234 | 1236 | DKE-PL-1 | Avedøre (DKE) | Dunowo (PL) | Subsea Cable | DC | VSC | 200 | Not decided | 0 | 0 | 330 | 0 | 0 | 0 | 600 | 400 | 1.5 |  | >2030 | Under consideration | 700 | 14 | Energinet | PSE | 5 % | 5 % | 600 | 0 |  | pborre@entsoe.local | Peter | Borre Eriksen | [6 empty] | 1
235 | 664 | HVDC Line C | "Brunsbüttel, Wilster" | "Großgartach, Grafenrheinfeld" | Overhead Line | DC | VSC | 0 | - | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 520 | 0 |  | 2025 | Permitting | 0 | 0 | TenneT-DE | TransnetBW | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
236 | 608 | HTLS upgrade Horta-Mercator | Horta (BE) | Mercator (BE) | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 380 | 0 |  | 31/12/2019 | Under construction | 100 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | [6 empty] | 1
239 | 1241 | Fenno-Skan 1 renewal | Hjalta (SE2) | Tuovila (FI) | Subsea Cable | DC | VSC | 300 | not decided | 0 | 0 | 200 | 0 | 0 | 0 | not known | 300 | 2700 |  | 2029 | Under consideration | 380 | 0 | SVK | FINGRID | 3.5 % (13 days) | 4 % (15 days) | 800 | 100 |  | pglantz@ENTSOE.local | Petter | Glantz | [6 empty] | 1
240 | 1460 | AC Enhancement Güstrow-Wolmirstedt | Güstrow (DE) | Wolmirstedt (DE) | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 195 | 0.01877 | 0.2447 | 66.3 | 0 | 380 | 0 |  | 2021 | Planned but not yet permitting | 350 | 2.8 | 50Hertz Transmission | 50Hertz Transmission | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | martin.ruge@50hertz.de | Martin | Ruge |  |  |  | 1
241 | 1276 | Upgrading of existing 220 kV line between SS Dakovo (HR) and TPP Tuzla (BA) to 400 kV line | Dakovo | Tuzla | Overhead Line | AC | 0 | 0 | ACSR | 416.5 | 2 | 91 | 0.02971 | 0.341 | 3.371 | 0 | 400 | 0 |  | 31/12/2032 | Under consideration | 26 | 0.033 | HOPS | NOS BIH | 0 | 0 | 0 | 26 |  | scazin@entsoe.local | Sasa | Cazin | [6 empty] | 1
241 | 1277 | Upgrading of existing 220 kV line between SS Dakovo (HR) and Gradacac (BA) to 400 kV line | Dakovo | Gradacac | Overhead Line | AC | 0 | 0 | ACSR | 1107.8 | 2 | 46.2 | 0.031875 | 0.3243 | 3.4865 | 0 | 400 | 1905 |  | 31/12/2032 | Under consideration | 14.07 | 0.018 | HOPS | NOS BIH | 0 | 0 | 0 | 29.3 |  | scazin@entsoe.local | Sasa | Cazin | [6 empty] | 1
241 | 1278 | Upgrading existing 220 kV SS Dakovo to 400 kV | Dakovo | Dakovo | Substation | AC | 0 | 0 | ACSR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 31/12/2032 | Under consideration | 11 | 0.0141 | HOPS | HOPS | 0 | 0 | 0 | 0 |  | scazin@entsoe.local | Sasa | Cazin | [6 empty] | 1
241 | 1279 | New double 400 kV line between SS Dakovo and location Razbojiste | Dakovo | Razbojiste | Overhead Line | AC | 0 | 0 | ACSR | 1107.8 | 2 | 25 | 0.031875 | 0.3243 | 3.4865 | 0 | 400 | 1905 |  | 31/12/2032 | Under consideration | 10.375 | 0.0133 | HOPS | HOPS | 0 | 0 | 0 | 0 |  | scazin@entsoe.local | Sasa | Cazin | [6 empty] | 1
241 | 1530 | Upgrading of existing 220 kV line between SS Gradacac (BA) and TPP Tuzla (BA) to 400 kV line | SS Gradacac (BA) | TPP Tuzla (BA) | Overhead Line | AC | 0 | 0 | ACSR | 1107.8 | 2 | 47.8 | 0.031875 | 0.3243 | 3.4865 | 0 | 400 | 1905 |  | 2032 | Under consideration | 13.7 | 0.0176 | NOS BIH | NOS BIH | 0 | 0 | 0 | 0 |  | scazin@entsoe.local | Sasa | Cazin |  | Ljupko | Teklic |  |  |  | 1
241 | 1531 | Upgrading existing 220 kV SS Gradacac (BA) to 400 kV | SS Gradacac (BA) | SS Gradacac (BA) | Substation | AC | 0 | 0 | ACSR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2032 | Under consideration | 7.9 | 0.01 | NOS BIH | NOS BIH | 0 | 0 | 0 | 0 |  | scazin@entsoe.local | Sasa | Cazin |  | Ljupko | Teklic |  |  |  | 1
242 | 194 | Offshore Connection Cluster 1 | OWF Cluster Baltic Sea East (DE) | Lubmin (DE) | Subsea Cable | AC | 0 | 0 | Cu | 0 | 0 | 115 | 0.0243 | 0.119 | 61.26 | 0 | 220 | 0 |  | 2018 | Under construction | 1605 | 54.57 | 50Hertz | 50Hertz | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | martin.ruge@50hertz.de | Martin | Ruge |  |  |  | 1
243 | 1269 | New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | Ernestinovo | Sombor | Overhead Line | AC | 0 | 0 | ACSR | 1107.8 | 2 | 70 | 0.031875 | 0.3243 | 3.4865 | 0 | 400 | 1905 |  | 01/01/2035 | Under consideration | 19.04 | 0.0245 | HOPS | EMS | 1% | 1% | 0 | 38 |  | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
244 | 1245 | Vigy - Uchtelfangen (or beyond) | Vigy (FR) | Uchtelfangen (DE) | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 400 | 3600 |  | 2027 | Planned but not yet permitting | 60 | 0.48 | Rte | Amprion | 0 | 0 | 0 | 31 |  | mfranz@ENTSOE.local | Marco | Franz | [6 empty] | 1
244 | 1514 | Power flow control between Vigy - Uchtelfangen | Vigy (FR) | Uchtelfangen (DE) | Phase Shift Transformer | AC | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 3600 |  | 2027 | Planned but not yet permitting | 60 | 0.48 | Rte | Amprion | 0 | 0 | 0 | 0 |  | mfranz@ENTSOE.local | Marco | Franz | Christian.Neus@amprion.net | Christian | Neus |  |  |  | 1
245 | 1246 | Upgrade Meeden - Diele | Meeden [NL] | Diele [DE] | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2019 | Under construction | 35 | 0 | TENNET-NL | TENNET-DE | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Jorrit | Bos | [6 empty] | 1
247 | 1381 | AQUIND Interconnector | Lovedean (GB) | Barnabos (FR) | Subsea Cable | DC | VSC | 708 | XLPE | 0 | 0 | 250 | 0 | 0 | 0 | 1.66% | 320 | 1621.09 |  | 2022 | Permitting | 1400 | 29 | National Grid plc | Réseau de transport d'électricité | 48 hours/year | 24 hours/year | 2000 | 125 |  | kglukhovskoy@ENTSOE.local | Kirill | Glukhovskoy | vladimir.temerko@aquind.co.uk | Vladimir | Temerko |  |  |  | 1
248 | 1248 | Offshore Connection Cluster 2 | OWF Cluster Baltic Sea (DE) | Lubmin (DE) | Subsea Cable | AC | 0 | 0 | Cu | 0 | 0 | 115 | 0.0243 | 0.119 | 61.26 | 0 | 220 | 0 |  | 2022 | Under Consideration | 1605 | 54.57 | 50Hertz | 50Hertz | 0 | 0 | 0 | 0 |  | mheit@entsoe.local | Michael | Heit | martin.ruge@50hertz.de | Martin | Ruge |  |  |  | 1
248 | 1613 | Offshore Connection Cluster 1,2 and 4 | OWF Cluster Baltic Sea (DE) | Siedenbrünzow/Alt Telin/Bartow (DE) | Subsea Cable | DC | VSC | 0 | Cu | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 320 | 0 |  | 2027 | Permitting | 1461 | 49.67 | 50Hertz | 50Hertz | 0 | 0 | 0 | 110 |  | mheit@entsoe.local | Michael | Heit | martin.ruge@50hertz.de | Martin | Ruge |  |  |  | 1
250 | 1384 | "Merchant line ""Castasegna (CH) - Mese (IT)""" | Castasegna | Mese | Underground Cable | AC | 0 | 0 | 3 x XLPE Cu | 500 | 1 | 0 | 0.0366 | 0.25 | 27.3 | 0 | 220 | 766 |  | 2021 | Permitting | 90 | 0.1 | swissgrid | Terna | 0 | 0 | 0 | 0.4 |  | sbontadelli@ENTSOE.local | Samuel | Bontadelli | [6 empty] | 1
251 | 147 | Dollern - Hamburg/Nord | Dollern (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2018 | Under construction | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
251 | 148 | Audorf - Hamburg/Nord | Audorf (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2017 | Under construction | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
252 | 1050 | Van Eyck - Gramme: HTLS upgrade | Van Eyck | Gramme | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 380 | 0 |  | 31/12/2029 | Under consideration | 140 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | [6 empty] | 1
252 | 1456 | Massenhoven - Van Eyck: HTLS upgrade | Massenhoven (BE) | Van Eyck (BE) | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 380 | 0 |  | 31/12/2024 | Under consideration | 120 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | philippe.bodin@rte-france.com | Philippe | Bodin |  |  |  | 1
252 | 1515 | Gramme - Courcelles: HTLS upgrade | Gramme | Courcelles | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2033 | Under consideration | 150 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | philippe.bodin@rte-france.com | Philippe | Bodin |  |  |  | 1
252 | 1516 | Bruegel - Courcelles: HTLS upgrade | Bruegel | Courcelles | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2035 | Under consideration | 110 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | philippe.bodin@rte-france.com | Philippe | Bodin |  |  |  | 1
252 | 1517 | Mercator - Bruegel: HTLS upgrade | Mercator | Bruegel | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2025 | Under consideration | 80 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | philippe.bodin@rte-france.com | Philippe | Bodin |  |  |  | 1
253 | 1224 | Uprate of Creys-St Vulbas | Creys(FR) | Saint Vulbas (FR) | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 21 | 0.021 | 0.306 | 3.8 | 0.6% | 400 | 0 |  | 2031 | Under consideration | 45 | 0.5 | RTE | RTE | 0.5% | 0.1% | 0 | 0 |  | gdudicourt@entsoe.local | Gabriel | Dudicourt | [6 empty] | 1
253 | 1225 | PST in Cornier | Cornier (FR) | Cornier (FR) | Phase Shift Transformer | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 10.8 | 0 | 0.7% | 400 | 0 |  | 2031 | Under consideration | 15 | 0.1 | RTE | RTE | 0.5% | 0.2% | 0 | 0 |  | gdudicourt@entsoe.local | Gabriel | Dudicourt | [6 empty] | 1
254 | 660 | HVDC Line A South - Ultranet | Osterath (DE) | Philippsburg (DE) | Overhead Line | DC | VSC | 0 | line | 0 | 0 | 340 | 0 | 0 | 0 | 0 | 400 | 0 |  | 01/01/2021 | Permitting | 0 | 0 | Amprion | TransnetBW | 0 | 0 | 0 | 0 |  | bgaillardon@entsoe.local | Boris | Gaillardon | [6 empty] | 1
255 | 1251 | New line 400 kV Muruarte-Ichaso | Muruarte | Ichaso | Overhead Line | AC | 0 | 0 | Condor | 0 | 3 | 145 | 0.0263 | 0.2824 | 4.2448 | 0 | 400 | 2843 |  | 2023 | Permitting | 38 | 0.566 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
255 | 1455 | New line 400 kV Castejon-Ichaso | Castejon | Ichaso | Overhead Line | AC | 0 | 0 | Condor | 0 | 3 | 169 | 0.0262 | 0.2816 | 4.2326 | 0 | 400 | 2843 |  | 2023 | Permitting | 38 | 0.566 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
256 | 1252 | Long term upgrade interconnection DE-NL | to be defined (DE) | to be defined (NL) | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2040 | Under consideration | 0 | 0 | Amprion | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Jorrit | Bos | [6 empty] | 1
256 | 1529 | Upgrade interconnection DE-NL | tbd | tbd | Phase Shift Transformer | AC | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 380 | 3600 |  | 2030 | Under consideration | 0 | 0 | Amprion | TENNET-NL | 0 | 0 | 0 | 1 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
258 | 667 | Brunsbttel - Klixbüll | Brunsbüttel (DE) | Klixbüll (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2019 | Permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Nils | Schindzielorz | [6 empty] | 1
259 | 1205 | HU-RO | Józsa | Oradea | Overhead Line | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | >2030 | Under consideration | 200 | 0 | MAVIR | Transelectrica | 0 | 0 | 0 | 0 |  | vzaharia@entsoe.local | Virginica | Zaharia | [6 empty] | 1
260 | 1255 | Interconnector GB-NL | TBD | TBD | Subsea Cable | DC | VSC | 0 | o | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2030 | Under consideration | 850 | 6 | National Grid | TENNET-NL | 0 | 0 | 0 | 0 |  | mnavarette@ENTSOE.local | Marta | Navarette | [6 empty] | 1
262 | 1257 | Belgium-Netherlands: Zandvliet-Rilland | Zandvliet (BE) | Rilland (NL) | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2022 | Planned but not yet permitting | 50 | 0 | ELIA | TENNET-NL | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | [6 empty] | 1
263 | 1258 | Rüthi - Bonaduz/Grynau | Rüthi | Grynau & Bonaduz | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2035 | Under consideration | 0 | 0 | Swissgrid | Swissgrid | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
263 | 1583 | Vorarlberg | xx | xx | Compensation | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2035 | Under consideration | 0 | 0 | VUEN | VUEN | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
264 | 1259 | Beznau - Mettlen | Beznau | Mettlen | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2025 | Permitting | 0 | 0 | Swissgrid | Swissgrid | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
264 | 1284 | Pradella - La Punt | Pradella | La Punt | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Under construction | 0 | 0 | Swissgrid | Swissgrid | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
264 | 1287 | Bassecourt - Mhleberg | Bassecourt | Mhleberg | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 01/01/2025 | Under consideration | 0 | 0 | xx | xx | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
264 | 1288 | Mettlen - Ulrichen | Mettlen | Ulrichen | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 |  | 01/01/2025 | Design & Permitting | 0 | 0 | xx | xx | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
265 | 1260 | Grimsel connection | Innertkirchen | Ulrichen | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 01/01/2029 | Planning | 0 | 0 | xx | xx | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
265 | 1289 | Lago Bianco connection | xx | xx | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 01/01/2029 | Planning | 0 | 0 | xx | xx | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
265 | 1290 | Magadino - Ulrichen | xx | xx | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 01/01/2029 | Planning | 0 | 0 | xx | xx | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
266 | 1261 | Bickigen - Chippis - Chamoson | Bickigen | Chamoson | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Design & Permitting | 0 | 0 | Swissgrid | Swissgrid | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
266 | 1285 | Magadino | xx | xx | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 01/01/2019 | Design & Permitting | 0 | 0 | xx | xx | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
266 | 1286 | Chippis - Lavorgo | Chippis | Lavorgo | Overhead Line | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 01/01/2024 | Design & Permitting | 0 | 0 | xx | xx | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
267 | 1262 | Hansa PowerBridge II | Hurva (SE4) | Guestrow (DE) | Subsea Cable | DC | VSC | 300 | not decided | 0 | 0 | 300 | 0 | 0 | 0 | n/a | 300 | 0 |  | 2030 | Under consideration | 660 | 22.44 | Svenska Kraftnat | 50Hertz | 3.5 % (13 days) | 4 % (15 days) | 700 | 180 |  | mheit@entsoe.local | Michael | Heit | thomas.koebinger@50Hertz.com | Thomas | Köbinger |  |  |  | 1
269 | 1228 | Uprate D.Rodrigo-Aljarafe | "D.Rodrigo " | Aljarafe | Overhead Line | AC | 0 | 0 | Gull | 0 | 2 | 33.7 | 0.0639 | 0.3692 | 3.1994 | 0 | 220 | 1102 |  | 2019 | Under construction | 0.7 | 0.0105 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
269 | 1229 | Uprate Aljarafe-Santiponce | Aljarafe | Santiponce | Overhead Line | AC | 0 | 0 | Gull | 0 | 2 | 13 | 0.0849 | 0.4151 | 2.7495 | 0 | 220 | 1102 |  | 2019 | Permitting | 0.3 | 0.0045 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
270 | 1211 | HVDC Aragon region -Marsillon | "Aragon region" | Marsillon | Underground Cable | DC | VSC | 600 | TBD | 0 | 0 | 230 | 0 | 0 | 0 | 1000 MW | 320 | 0 |  | 01/01/2026 | Planned but not yet permitting | 0 | 0 | REE | RTE | TBD | TBD | 2000 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
270 | 1212 | New axis Ejea-Aragon region 400 kV | "Ejea de los Caballeros " | Arag¢n region | Overhead Line | AC | 0 | 0 | TBD | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 400 | 0 |  | 01/01/2026 | Planned but not yet permitting | 0 | 0 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
270 | 1214 | Ejea de los Caballeros subestation | "Ejea de los Caballeros " | "Ejea de los Caballeros" | Substation | AC | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 01/01/2025 | Planned but not yet permitting | 0 | 0 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
270 | 1215 | Aragon region subestation | Aragon region | Aragon region | Substation | AC | VSC | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 01/01/2025 | Planned but not yet permitting | 0 | 0 | REE | REE | 0 | 0 | 0 | 0 |  | llopez@entsoe.local | Laura | Lopez | plabra@ree.es | Patricia | Labra |  |  |  | 1
271 | 1264 | Investments to be created | 0 | 0 | Overhead Line | DC | VSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Under consideration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 0
276 | 1206 | HVDC Pamplona area -Cantegrit | Pamplona area | Cantegrit | Underground Cable | DC | VSC | 600 | TBD | 0 | 0 | 225 | 0 | 0 | 0 | 1000 MW | 320 | 0 |  | 01/12/2026 | Planned but not yet permitting | 0 | 0 | REE | RTE | TBD | TBD | 2000 | 0 |  | plabra@entsoe.local | Patricia | Labra |  |  |  | jean-gabriel.valentin@rte-france.com | Jean-Gabriel | Valentin | 1
276 | 1207 | Upgrade Cantegrit-Saucats | Cantegrit | Saucats | Overhead Line | AC | 0 | 0 | TBD | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2026 | Planned but not yet permitting | 0 | 0 | RTE | RTE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra |  |  |  | jean-gabriel.valentin@rte-france.com | Jean-Gabriel | Valentin | 1
276 | 1208 | Upgrade Cantegrit-Marsillon | Cantegrit | Marsillon | Overhead Line | AC | 0 | 0 | TBD | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2026 | Planned but not yet permitting | 0 | 0 | RTE | RTE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra |  |  |  | jean-gabriel.valentin@rte-france.com | Jean-Gabriel | Valentin | 1
276 | 1210 | New substation Pamplona area | "Pamplona area " | "Pamplona area" | Substation | AC | 0 | 0 | subestation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 01/01/2025 | Planned but not yet permitting | 0 | 0 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra |  |  |  | jean-gabriel.valentin@rte-france.com | Jean-Gabriel | Valentin | 1
280 | 1008 | Study Lonny-Achene-Gramme | Lonny (FR) | Gramme (BE) | Phase Shift Transformer | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2025-2030 | Under consideration | 100 | 0 | RTE | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | [6 empty] | 1
281 | 1379 | ANAI: Abengoa Northern Atlantic Interconnection | Soto de Ribera | Exeter | Subsea Cable | DC | VSC | 0 | XLPE | 0 | 0 | 1550 | n.a. | n.a. | n.a. | 50% | 525 | 70 |  | 2025 | Under consideration | 2700 | 10 | REE | National Grid | 1% | 0,5% | 2000 | 0 |  | pinfante@ENTSOE.local | Juan | Santos | [6 empty] | 1
282 | 1297 | ASEI: Abengoa Southern Europe Interconnection | Vandellos | La Spezia | Subsea Cable | DC | VSC | 0 | XLPE | 0 | 0 | 1000 | n.a. | n.a. | n.a. | 50% | 525 | 70 |  | 2024 | Under consideration | 2400 | 10 | REE | Terna | 1% | 0,5% | 2000 | 0 |  | pinfante@ENTSOE.local | Juan | Santos | ?????? | [5 empty] | 1
283 | 1378 | TuNur DC | Rejim Maatoug (TN) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Subsea Cable | DC | VSC | 1300 | Aluminium for deep water cable, copper for shallow water and land cable, aluminium for multiple conductor overhead lines | 0 | 0 | 1265 | 1270 | 0,007862 overhead line @ 2GW 0,012332 submarine cable @ 2GW 0,010114 average @ 2GW | n.a. | n.a. | 500 | 1100 |  | 2025 | Permitting | 2680 | 41 | TuNur Limited | TuNur Limited | 8 hours/year | 8 hours/year for overhead lines, 0.1 faults/year for cables, 2 hours/year for VSC HVDC converters | 2000 | 950 | Tunisia not modelled | mscaravaggi@ENTSOE.local | Maurizio | Scaravaggi | [6 empty] | 1
283 | 1430 | TuNur AC | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) Terna station 400 kV AC | Underground Cable | AC | 0 | 0 | Copper | 2500 | 2 | 2 | 2 | 0.0036 | 0.205 | n.a. | 400 | 2990 |  | 2025 | Permitting | 16 | 0.04 | TuNur Limited | Terna | 0 | 0 | 0 | 0 | Tunisia not modelled | mscaravaggi@ENTSOE.local | Maurizio | Scaravaggi | [6 empty] | 1
284 | 1619 | LEG1 | Tobrouk (Libya) | Linoperamata (Greece, Crete) | Subsea Cable | DC | VSC | 500 | Copper and aluminum for the deep water portion. | 0 | 0 | 370 | 0 | 0 | 0 | 1440 | 400 | 55 |  | 2021 | Planned but not yet permitting | 1600 | 2.6 | GECOL | ADMIE | 2.7 | 2.8 | 2000 | 340 | Libya is not modelled | dpowell@entsoe.eu | Dante | Powell | [6 empty] | 1
285 | 1383 | GridLink | Kingsnorth (UK) | "Warande (Gravelines, France)" | Subsea Cable | DC | VSC | 0 | XLPE or MI | 0 | 0 | 156 | 0 | 0 | 0 | 700MW | 525 | ??? | ??? | 2022 | Planning | 906 | 23.9 | National Grid | RTE | 98% | 2% | 1400 | 0 |  | thanlan@ENTSOE.local | Tony | Hanlan | [6 empty] | 1
286 | 1385 | Greenlink | Great Island | Pembroke | Subsea Cable | DC | VSC | 500 | Cable | 800 | 0 | 195 | 0.051 | n/a | n/a | 100% | 320 | 803 |  | 2023 | Planned but not yet permitting | 396 | 8 | National Grid | EirGrid | 2% | 1% | 500 | 94+101 |  | gnicholson@ENTSOE.local | Guy | Nicholson | [6 empty] | 1
293 | 1431 | Southern Aegean Interconnector | LAVRIO | LEVITHA | Subsea Cable | DC | VSC | 700 | cable | 1200 | 0 | 245 | 0.0079 | 0.035 | 71 | one pole | 320 | 2500 |  | 2024 | Permitting | 600 | 40 | yes | no | 2% | 3% | 800 | 0 |  | sgaryfalakis@ENTSOE.local | Stefanos | Garyfalakis | [6 empty] | 1
293 | 1432 | Southern Aegean Interconnector | LEVITHA | KORAKIA CRETE | Subsea Cable | DC | VSC | 600 | Cu | 800 | 0 | 250 | 0.0079 | 0.035 | 71 | one pole outage | 320 | 2500 |  | 2026 | Permitting | 600 | 40 | no | yes | 2% | 3% | 800 | 0 |  | sgaryfalakis@ENTSOE.local | Stefanos | Garyfalakis | [6 empty] | 1
293 | 1433 | Southern Aegean Interconnector | Levitha | Syrna | Subsea Cable | AC | 0 | 0 | Cu | 800 | 1 | 81 | 0.054 | 0.12 | 66 | 0 | 220 | 775 |  | 2025 | Permitting | 150 | 7 | no | no | 0 | 0 | 0 | 0 |  | sgaryfalakis@ENTSOE.local | Stefanos | Garyfalakis | [6 empty] | 1
293 | 1434 | Southern Aegean Interconnector | KINAROS | LEVITHA | Subsea Cable | AC | 0 | 0 | Cu | 800 | 1 | 14 | 0.054 | 0.12 | 66 | 0 | 220 | 775 |  | 2024 | Permitting | 30 | 1 | no | no | 0 | 0 | 0 | 0 |  | sgaryfalakis@ENTSOE.local | Stefanos | Garyfalakis | [6 empty] | 1
293 | 1435 | Southern Aegean Interconnector | Kandeliousa | Syrna | Subsea Cable | AC | 0 | 0 | Cu | 300 | 1 | 34 | 0.079 | 0.14 | 44 | 0 | 220 | 530 |  | 2025 | Permitting | 80 | 6 | no | no | 0 | 0 | 0 | 0 |  | sgaryfalakis@ENTSOE.local | Stefanos | Garyfalakis | [6 empty] | 1
293 | 1436 | Southern Aegean Interconnector | Kandeliousa | Pergousa | Subsea Cable | AC | 0 | 0 | Cu | 300 | 1 | 14 | 0.079 | 0.14 | 44 | 0 | 220 | 530 |  | 2025 | Permitting | 40 | 2 | no | no | 0 | 0 | 0 | 0 |  | sgaryfalakis@ENTSOE.local | Stefanos | Garyfalakis | [6 empty] | 1
294 | 1356 | Maali | Kergord Shetland | tba near Bergen-Mongstad or Karsto- Blafalli | Subsea Cable | DC | VSC | 700 | cable | 1200 | 0 | 400 | 0.035 | n/a | n/a | 100% | 320 | 1094 |  | 2025 | Under consideration | 612 | 10 | National Grid / Scottish Hydro Electric Transmission | Stattnett | 2% | 2% | 700 | 200+200 |  | gnicholson@ENTSOE.local | Guy | Nicholson | [6 empty] | 1
296 | 1437 | Britib | Gatica/Hernani, Cordemais and Langage/Indian Queens | Gatica/Hernani, Cordemais and Langage/Indian Queens | Subsea Cable | DC | VSC | 950 | 3000Al XLPE/ MI-PPL | 0 | 0 | 1330 | 0 | 0 | 0 | 950MW (Bipole configuration) | 500 | 3800 |  | 2023-2024 | Planned but not yet permitting | 0 | 0 | REE, RTE, NG | REE, RTE, NG | <0.5% per year | Forced bipolar outages are normaly neglictable. Forced unavailability per converter (single pole) is <1.0% per year. | 1900 | 1330 |  | dnavidad@ENTSOE.local | David | Navidad Mencía | [6 empty] | 1
297 | 445 | BRABO II: Zandvliet - Lillo - Liefkenshoek | Zandvliet | Lillo - Liefkenshoek | Overhead Line | AC | 0 | 0 | Two conductors: type 2*928 AMS | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 380 | 0 |  | 31/12/2020 | Permitting | 60 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | [6 empty] | 1
297 | 604 | BRABO III: Liefkenshoek - Mercator | Liefkenshoek (BE) | Mercator (BE) | Overhead Line | AC | 0 | 0 | One conductors: type 2*928 AMS | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 380 | 0 |  | 01/01/2023 | Permitting | 50 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | [6 empty] | 1
297 | 605 | BRABO II: Lillo 380 | Lillo (BE) | Lillo (BE) | Substation | AC | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 31/03/2019 | Under construction | 10 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | [6 empty] | 1
299 | 1458 | SACOI3 | Codrongianos - Lucciana | Suvereto | Subsea Cable | DC | VSC | 0 | TBD | 0 | 0 | 300 | 0 | 0 | 0 | N/A | 200 | 2000 |  | 2023 | Permitting | 0 | 0 | TERNA - EDF | TERNA | N/A | N/A | 400 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
300 | 1459 | Channel Cable | Ninfield (United Kingdom) | Paluel (France) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 137 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2019 | Permitting | 0 | 0 | National Grid | RTE | TBA | TBA | 1000 | 137 |  | bgreplova@ENTSOE.local | Bara | Greplova - bgreplova | [6 empty] | 1
301 | 1548 | Spain-France Route | Hernani (Spain) | La Martyre (France) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 805 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2021 | Permitting | 0 | 0 | Red Eléctrica de España | RTE | TBA | TBA | 500 | 805 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
301 | 1549 | France-United Kingdom Route | La Martyre (France) | Indian Queens (United Kingdom) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 245 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2021 | Permitting | 0 | 0 | RTE | National Grid | TBA | TBA | 1200 | 245 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
301 | 1550 | United Kingdom-Ireland Route | Indian Queens (United Kingdom) | Great Island (Ireland) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 276 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2021 | Permitting | 0 | 0 | National Grid | EirGrid | TBA | TBA | 1200 | 276 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
302 | 1551 | Tunisia-Italy Sicily Interconnector | El Haouaria (Tunisia) | Partanna (Sicily) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 226 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2021 | Permitting | 0 | 0 | STEG | Terna | TBA | TBA | 1000 | 226 | Tunisia not modelled | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
303 | 1553 | Spain-Morocco Interconnector | Haourai (Spain) | Tahaddart (Morocco) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 250 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2021 | Planned but not yet permitting | 0 | 0 | Red Eléctrica de España | Office National de l'Electricité et de l'Eau | TBA | TBA | 1000 | 250 | Morocco is not modelled | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
304 | 1554 | Algeria-Italy Interconnector | El Hadjar (Algeria) | Rumianca (Sardinia) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 388 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2022 | Planned but not yet permitting | 0 | 0 | Sonelgaz | Terna | TBA | TBA | 1000 | 388 | Algeria not modelled | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
305 | 1577 | Romania-Turkey Interconnector | Constanta Nord (Romania) | Alibeyköy (Turkey) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 446 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2023 | Planned but not yet permitting | 0 | 0 | Transelectrica | TEIAS | TBA | TBA | 1000 | 446 | Turkey grid model not detailed. | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
306 | 1578 | Algeria-Spain Interconnector | Hassi Ameur (Algeria) | Litoral De Almeria (Spain) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 203 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2023 | Planned but not yet permitting | 0 | 0 | Sonelgaz | Red Eléctrica de España | TBA | TBA | 1000 | 203 | no Algeria network model - no assessment feasible | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
307 | 1579 | East West 1 | Arklow (Ireland) | Pentir (United Kingdom) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 151 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | EirGrid | National Grid | TBA | TBA | 400 | 151 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
308 | 1580 | East West 2 | Great Island (Ireland) | Pembroke (United Kingdom) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 165 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | EirGrid | National Grid | TBA | TBA | 400 | 165 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
312 | 1472 | St. Peter - Tauern (AT internal) | St. Peter | Tauern | Overhead Line | AC | 0 | 0 | Tbd | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2022 | Permitting | 0 | 0 | APG | APG | 0 | 0 | 0 | 0 |  | dboehm@ENTSOE.local | Stefan | Führer | Christian.Neus@amprion.net | Christian | Neus | david.boehm@apg.at | David | Boehm | 1
313 | 1473 | Isar/Altheim/Ottenhofen - St. Peter | Isar/Altheim/Ottenhofen (DE) | St. Peter (AT) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Permitting | 0 | 0 | TenneT-DE | APG | 0 | 0 | 0 | 0 |  | dboehm@ENTSOE.local | Stefan | Führer | Christian.Neus@amprion.net | Christian | Neus | david.boehm@apg.at | David | Boehm | 1
316 | 1617 | Upgrade of 220 kV line Divaca-Bericevo to 400 kV | Divaca | Bericevo | Overhead Line | AC | 0 | 0 | ACSR | 490 | 0 | 80 | 0.03 | 0.32 | 3.5 | 0 | 400 | 1920 |  | 2030 | Under consideration | 0 | 0 | ELES | ELES | 0 | 0 | 0 | 0 |  | kdragas@entsoe.local | Klemen | Dragas | [6 empty] | 1
317 | 1615 | Upgrade of internal 220 kV line Podlog-Bericevo to 400 kV | Podlog | Bericevo | Overhead Line | AC | 0 | 0 | ACSR | 490 | 3 | 63 | 0.03 | 0.32 | 3.5 | 0 | 400 | 1920 |  | 2035 | Under consideration | 0 | 0 | ELES | ELES | 0 | 0 | 0 | 0 |  | kdragas@entsoe.local | Klemen | Dragas | [6 empty] | 1
318 | 1614 | Upgrade of 220 kV line Podlog-Cirkovce to 400 kV | Podlog | Cirkovce | Overhead Line | AC | 0 | 0 | ACSR | 490 | 3 | 50 | 0.03 | 0.32 | 3.5 | 0 | 400 | 1920 |  | 2035 | Under consideration | 0 | 0 | ELES | ELES | 0 | 0 | 0 | 0 |  | kdragas@entsoe.local | Klemen | Dragas | [6 empty] | 1
320 | 1558 | Double 400 kV OHL Cirkovce(SI)-Heviz(HU)/Zerjavinec(HR) | Cirkovce (SI) | Heviz (HU) \ Zerjavinec (HR) | Overhead Line | AC | 0 | 0 | ACSR | 495 | 3 | 80 | 0.03 | 0.32 | 3.5 | 0 | 400 | 3800 |  | 2018 | Permitting | 132.5 | 0 | ELES | MAVIR; HOPS | 0 | 0 | 0 | 80 | Multi border NTC project. Should be assessed by RG | kdragas@entsoe.local | Klemen | Dragas | [6 empty] | 1
321 | 1475 | Herbertingen - Tiengen | Herbertingen | Tiengen | Overhead Line | AC | 0 | 0 | - | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 380 | 3600 |  | 2025 | Planned but not yet permitting | 0 | 0 | Amprion / TransnetBW | Amprion / TransnetBW | 0 | 0 | 0 | 0 |  | mfranz@ENTSOE.local | Marco | Franz | Christian.Neus@amprion.net | Christian | Neus |  |  |  | 1
322 | 1476 | Wullenstetten - Border Area (DE-AT) | Wullenstetten (DE) | Austrian National border (AT) | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 380 | 3600 |  | 2020 | Permitting | 0 | 0 | Amprion | Amprion / vuen/ APG | 0 | 0 | 0 | 0 |  | mfranz@ENTSOE.local | Marco | Franz | Christian.Neus@amprion.net | Christian | Neus |  |  |  | 1
322 | 1477 | Herbertingen - Neuravensburg | Herbertingen | Neuravensburg | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 380 | 3600 |  | 2020 | Planned but not yet permitting | 0 | 0 | Amprion | Amprion | 0 | 0 | 0 | 0 |  | mfranz@ENTSOE.local | Marco | Franz | Christian.Neus@amprion.net | Christian | Neus |  |  |  | 1
323 | 1478 | Dekani (SI) - Zaule (IT) interconnection | DEKANI | ZAULE | Underground Cable | AC | 0 | 0 | XLPE ALUMINUM | 1000 | 1 | 11 | 0.0291 | 0.109 | 72.26 | 0 | 110 | 763 |  | 2020 | Permitting | 16 | 0.3 | ELES D.O.O. | TERNA SPA | 0 | 0 | 0 | 6 IT - 5 SI |  | fscaramuzza@ENTSOE.local | Fabrizio | Scaramuzza | [6 empty] | 1
324 | 1482 | Redipuglia (IT) - Vrtojba (SI) Interconnection | REDIPUGLIA | VRTOJBA | Underground Cable | AC | 0 | 0 | XLPE ALUMINUM | 1000 | 1 | 22.5 | 0.0291 | 0.109 | 72.26 | 0 | 110 | 763 |  | 2020 | Permitting | 24 | 0.4 | TERNA SPA | ELES D.O.O. | 0 | 0 | 0 | 20 IT - 2,5 SI |  | fscaramuzza@ENTSOE.local | Fabrizio | Scaramuzza | [6 empty] | 1
325 | 1483 | Upgrade Obersielach (AT) - Podlog (SI) (finalisation after approval of APG's Board Members) | Obersielach (AT) | Podlog (SI) | Overhead Line | AC | 0 | 0 | Tbd | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2035 | Under consideration | 0 | 0 | APG | ELES | 0 | 0 | 0 | 0 | Complex Multi-borders project to assess deltaNTC. Should be assessed by RG | dboehm@ENTSOE.local | Stefan | Führer | Christian.Neus@amprion.net | Christian | Neus |  |  |  | 1
329 | 1518 | Stevin-Izegem/Avelgem: new corridor | Stevin | Avelgem | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2028 | Under consideration | 400 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | philippe.bodin@rte-france.com | Philippe | Bodin |  |  |  | 1
330 | 1498 | New CZ-SK 400 kV interconnector | Otrokovice (CZ) | Ladce (SK) | Overhead Line | AC | 0 | 0 | SEPS side: 3x3xAlFe 450/52 CEPS side: 3x3x490-AL1/64-ST1A | 450 | 3 | 78 | 0.0225 | 0.284 | 3.945 | 0 | 400 | 2500 |  | 2035 | Under consideration | 0 | 0 | CEPS | SEPS | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | lsamsely@entsoe.local | Lubos | Samsely | lengyelz@mavir.hu | Zsolt | Lengyel |  |  |  | 1
330 | 1499 | New 400 kV substation Ladce | Ladce (SK) | Ladce (SK) | Substation | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2027 | Planned but not yet permitting | 0 | 0 | SEPS | SEPS | 0 | 0 | 0 | 0 | Data to assess the project in CBA phase will be calculated using new grid model BE2025 with PINT projects. Grid model collection expected in Jan2018. | lsamsely@entsoe.local | Lubos | Samsely | lengyelz@mavir.hu | Zsolt | Lengyel |  |  |  | 1
331 | 1494 | dpp1 | 54 | 54 | LCC converter station | DC | VSC | 76 | 45 | 0 | 0 | 45 | 0 | 0 | 0 | 22 | 45 | 4 |  | 54 | Under consideration | 54 | 54 | 54 | 54 | 76 | 76 | 6 | 45 | #N/A | dpowell@entsoe.eu | Dante Powell | Dante | Powell | [5 empty] | 0
332 | 1495 | ruskin | 65 | 65 | Overhead Line | AC | 0 | 0 | 56 | 56 | 56 | 565 | 56 | 56 | 56 | 0 | 65 | 6 |  | 565 | Planned but not yet permitting | 56 | 5 | 656 | 56 | 0 | 0 | 0 | 65 | #N/A | dpowell@entsoe.eu | Dante Powell | Dante | Powell | [5 empty] | 0
333 | 1496 | PST Foretaille | Foretaille | Foretaille | Phase Shift Transformer | AC | 0 | 0 | xx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2031 | Under consideration | 35 | 0 | Swissgrid | Swissgrid | 0 | 0 | 0 | 0 |  | dpowell@entsoe.eu | Dante Powell | Dante | Powell | [5 empty] | 1
335 | 1504 | Power Link Island | 0 | 0 | Substation | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2035-2040 | Under consideration | 0 | 0 | TenneT-NL, Energinet, TenneT-DE | TenneT-NL, Energinet, TenneT-DE | 0 | 0 | 0 | 0 |  | hthomsen@entsoe.local | Henrik | Thomsen | Nils.Schindzielorz@tennet.eu | Nils | Schindzielorz | kedar.kolharkar@tennet.eu | Kedar | Kolharkar | 1
335 | 1505 | Interconnection DKw to Power Link Island | Endrup, DKw | Power Link Island DKw | Subsea Cable | DC | VSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2035-2040 | Under consideration | 0 | 0 | Energinet | Energinet | 0 | 0 | 2000 | 0 |  | hthomsen@entsoe.local | Henrik | Thomsen | Nils.Schindzielorz@tennet.eu | Nils | Schindzielorz | kedar.kolharkar@tennet.eu | Kedar | Kolharkar | 1
335 | 1506 | Interconnection NL Maasvlakte to Power Link Island | Maasvlakte 380 kV | Power Link Island NL1 | Subsea Cable | DC | VSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2035-2040 | Under consideration | 0 | 0 | TenneT TSO NL | TenneT TSO NL | 0 | 0 | 2000 | 0 |  | hthomsen@entsoe.local | Henrik | Thomsen | Nils.Schindzielorz@tennet.eu | Nils | Schindzielorz | kedar.kolharkar@tennet.eu | Kedar | Kolharkar | 1
335 | 1507 | Interconnection NL Eemshaven to Power Link Island | Eemshaven 380 kV | Power Link Island NL2 | Subsea Cable | DC | VSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2035-2040 | Under consideration | 0 | 0 | TenneT TSO NL | TenneT TSO NL | 0 | 0 | 2000 | 0 |  | hthomsen@entsoe.local | Henrik | Thomsen | Nils.Schindzielorz@tennet.eu | Nils | Schindzielorz | kedar.kolharkar@tennet.eu | Kedar | Kolharkar | 1
335 | 1508 | Interconnection DE (area of Brunsbüttel) to Power Link Island | German substation located in the area of Brunsbüttel (north of the Elbe) | Power Link Island DE1 | Subsea Cable | DC | VSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2035-2040 | Under consideration | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 2000 | 0 |  | hthomsen@entsoe.local | Henrik | Thomsen | Nils.Schindzielorz@tennet.eu | Nils | Schindzielorz | kedar.kolharkar@tennet.eu | Kedar | Kolharkar | 1
335 | 1509 | Interconnection DE (area of Oldenburg) to Power Link Island | German substation located in the area of Oldenburg | Power Link Island DE2 | Subsea Cable | DC | VSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2035-2040 | Under consideration | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 2000 | 0 |  | hthomsen@entsoe.local | Henrik | Thomsen | Nils.Schindzielorz@tennet.eu | Nils | Schindzielorz |  | Kedar | Kolharkar | 1
335 | 1511 | Interconnection DE (area of Krümmel) to Power Link Island | German substation located in the area of Krümmel | Power Link Island DE3 | Subsea Cable | DC | VSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2035-2040 | Under consideration | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 2000 | 0 |  | hthomsen@entsoe.local | Henrik | Thomsen | Nils.Schindzielorz@tennet.eu | Nils | Schindzielorz | kedar.kolharkar@tennet.eu | Kedar | Kolharkar | 1
336 | 1556 | Prati (IT) – Steinach (AT) | Prati di Vizze (IT) | Steinach (AT) | Overhead Line | AC | 0 | 0 | N/A | 0 | 0 | 139 | 0.06 | 0.39 | 0.023 | 0 | 132 | 0 |  | 2019 | Under construction | 0 | 0 | TERNA | TINETZ | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
337 | 1510 | Cloppenburg East - Merzen | Cloppenburg East (DE) | Merzen (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | TenneT-DE | Amprion | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Henrik | Thomsen | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
337 | 1512 | Conneforde - Cloppenburg | Conneforde (DE) | Cloppenburg (DE) | Overhead Line | AC | 0 | 0 | double circuit | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2022 | Planned but not yet permitting | 0 | 0 | TenneT-DE | TenneT-DE | 0 | 0 | 0 | 0 |  | nschindzielorz@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
338 | 1521 | new HVDC line between Villanova and Fano existing 400 kV substations | Villanova | Fano | Subsea Cable | DC | VSC | 0 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 500 | 2400 |  | 2030 | Under consideration | 0 | 0 | Terna | Terna | N/A | N/A | 1000 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
339 | 1557 | Italian HVDC tri-terminal link | SARDINIA REGION | SICILY REGION - SOUTH OF ITALY | Subsea Cable | DC | VSC | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 |  | 2025 | Under consideration | 0 | 0 | TERNA | TERNA | N/A | N/A | 1000 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
340 | 1519 | Avelgem-Center: new corridor | Avelgem | Center (TBD) | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2028 | Under consideration | 500 | 0 | ELIA | ELIA | 0 | 0 | 0 | 0 |  | svcampenhout@entsoe.local | Steve | Van Campenhout | philippe.bodin@rte-france.com | Philippe | Bodin |  |  |  | 1
341 | 1536 | Portile de Fier (RO) - Djerdap (RS) 2nd | Portile de Fier | Djerdap | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 2 | 0.03 | 0.337 | 3.4189 | 0 | 400 | 1920 |  | 2030 | Under consideration | 3.5 | 0.03 | Transelektrica | EMS | 1% | 1% | 0 | 0.5 |  | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
341 | 1537 | New SS 400/110 kV Belgrade West | Belgrade West | Belgrade West | Substation | AC | 0 | 0 | ACSR | 490 | 2 | 0 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2030 | Under consideration | 27.5 | 0.33 | EMS | EMS | 0 | 0 | 0 | 0 |  | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
341 | 1538 | New OHL 400 kV WPP Cibuk - SS Belgrade West | WPP Cibuk | Belgrade West | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 60 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2030 | Under consideration | 12.5 | 0.15 | EMS | EMS | 1% | 1% | 0 | 0 |  | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
342 | 1520 | Sofia West (BG) - Nis 2 (RS) 2nd | SS Sofia West | SS Nis 2 | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 123 | 0.0294 | 0.341 | 3.371 | 0 | 40 | 1920 |  | 2034 | Under consideration | 56 | 0.78 | ESO | EMS | 1% | 1% | 0 | 38 |  | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
342 | 1522 | Upgrade of exsisting OHL 220 kV to 400 kV SS Nis 2 - SS Kruševac 1 | SS Nis 2 | SS Krusevac 1 | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 72 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2034 | Under consideration | 17 | 0.2 | EMS | EMS | 1% | 1% | 0 | 0 |  | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
342 | 1523 | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | SS Krusevac 1 | SS Krusevac 1 | Substation | AC | 0 | 0 | ACSR | 490 | 2 | 0 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2034 | Under consideration | 6.5 | 0.08 | EMS | EMS | 0 | 0 | 0 | 0 |  | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
342 | 1524 | Upgrading of exsisting OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | SS Krusevac 1 | SS Kraljevo 3 | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 48 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2034 | Under consideration | 11.5 | 0.14 | EMS | EMS | 1% | 1% | 0 | 0 |  | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
342 | 1525 | Uprading exsisting OHL 220 kV to 400 kV SS Kraljevo 3 - Vardiste | EMS | EMS | Overhead Line | AC | 0 | 0 | ACSR | 490 | 2 | 120 | 0.0294 | 0.341 | 3.371 | 0 | 400 | 1920 |  | 2033 | Under consideration | 65 | 0.8 | EMS | EMS | 1% | 1% | 0 | 0 |  | nvucinic@entsoe.local | Nebojsa | Vucinic | [6 empty] | 1
343 | 1532 | New OHL 400 kV Banja Luka - Lika | Banja Luka (BA) | Lika (HR) | Overhead Line | AC | 0 | 0 | ACSR | 1107.8 | 2 | 155 | 0.031875 | 0.3243 | 3.4865 | 0 | 400 | 1905 |  | 2030 | Planned but not yet permitting | 43 | 0.055 | NOS BIH | HOPS | 0 | 0 | 0 | 115 |  | scazin@entsoe.local | Sasa | Cazin |  | Ljupko | Teklic |  |  |  | 1
343 | 1533 | New OHL 400 kV Lika – Melina | Lika (HR) | Melina (HR) | Overhead Line | AC | 0 | 0 | ACSR | 1107.8 | 2 | 68 | 0.031875 | 0.3243 | 3.4865 | 0 | 400 | 1905 |  | 2030 | Planned but not yet permitting | 17.2 | 0.022 | HOPS | HOPS | 0 | 0 | 0 | 0 |  | scazin@entsoe.local | Sasa | Cazin |  | Ljupko | Teklic |  |  |  | 1
343 | 1534 | New OHL 400 kV Lika – Konjsko | Lika (HR) | Konjsko (HR) | Overhead Line | AC | 0 | 0 | ACSR | 1107.8 | 2 | 200 | 0.031875 | 0.3243 | 3.4865 | 0 | 400 | 1905 |  | 2030 | Planned but not yet permitting | 65.5 | 0.084 | HOPS | HOPS | 0 | 0 | 0 | 0 |  | scazin@entsoe.local | Sasa | Cazin |  | Ljupko | Teklic |  |  |  | 1
343 | 1535 | New Substation 400/110 kV Lika | Lika (HR) | Lika (HR) | Substation | AC | 0 | 0 | ACSR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 2029 | Planned but not yet permitting | 30 | 0.038 | HOPS | HOPS | 0 | 0 | 0 | 0 |  | scazin@entsoe.local | Sasa | Cazin |  | Ljupko | Teklic |  |  |  | 1
344 | 1541 | Zwolle-Hengelo-Doetinchem-Dodewaard | Zwolle | Dodewaard | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 165 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2035 | Under consideration | 215 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
345 | 1542 | Northern East-West connection NL | tbd | tbd | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2040 | Under consideration | 0 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
346 | 1543 | ZuidWest380 West | Borssele | Rilland | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Under construction | 400 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
346 | 1544 | ZuidWest3808 Oost | Rilland | Tilburg | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2025 | Permitting | 620 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
347 | 1545 | Maasvlakte – Noord Brabant connection | Krimpen | Geertruidenberg | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2040 | Under consideration | 0 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
348 | 1546 | NoordWest380 | Eemshaven Oude Schip | Vierverlaten | Overhead Line | AC | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2021 | Under construction | 420 | 0 | TENNET-NL | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
351 | 1547 | Eastern HVDC Link | Peterhead (GB) | Hawthorn Pit (GB) | Subsea Cable | DC | VSC | 0 | TBC | 0 | 0 | 365 | 0 | 0 | 0 | TBC | 500 | 0 |  | 2024 | Under consideration | 1460 | 0 | SHETL | NGET | TBC | TBC | 2000 | 0 |  | aalikhanzadeh@ENTSOE.local | Marta | Navarrete | steve.vancampenhout@elia.be | Steve | Van Campenhout |  |  |  | 1
353 | 1582 | United Kingdom-Germany Interconnector | Hawthorne Pit (United Kingdom) | Brokdorf (Germany) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 730 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | National Grid | Tennet | TBA | TBA | 1000 | 730 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
354 | 1585 | Irish Sea Offshore Export Cable | Poolbeg | Great Island | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 243 | 0 | 0 | 0 | TBA | 400220 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | EirGrid | EirGrid | TBA | TBA | 1500 | 243 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
358 | 1589 | Germany-Poland Interconnector | Lubmin (Germany) | Dunowo (Poland) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 175 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2025 | Planned but not yet permitting | 0 | 0 | 50Hertz Transmission GmbH | Polskie Sieci Elektroenergetyczne | TBA | TBA | 1000 | 175 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
359 | 1590 | Poland-Lithuania Interconnector | Gdańsk Błonia (Poland) | Klaipėda (Lithuania) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 258 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2025 | Planned but not yet permitting | 0 | 0 | Polskie Sieci Elektroenergetyczne | Litgrid | TBA | TBA | 400 | 258 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
362 | 1594 | France-Spain East Interconnector | Baixas (France) | Santa Llogaia (Spain) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 113 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | RTE | Red Eléctrica de España | TBA | TBA | 400 | 113 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
363 | 1596 | Spain-Portugal North Interconnector | Pazos de Borben (Spain) | Vermoim (Portugal) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 159 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | Red Eléctrica de España | Redes Energéticas Nacionais | TBA | TBA | 400 | 159 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
365 | 1599 | Italy-Croatia Interconnector | Candia (Italy) | Zakučac (Croatia) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 280 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2023 | Planned but not yet permitting | 0 | 0 | Terna | HOPS | TBA | TBA | 1000 | 280 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
366 | 1600 | Italy-Albania Interconnector | Brindisi North (Italy) | Vlore (Albania) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 127 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2023 | Planned but not yet permitting | 0 | 0 | Terna | OST | TBA | TBA | 400 | 127 |  | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
367 | 1601 | Greece-Turkey Interconnector | Pallinis (Greece) | Yeniköy (Turkey) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 393 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | ADMIE | TEİAŞ | TBA | TBA | 1000 | 393 | Turkey grid model not detailed. | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
369 | 1603 | Ukraine-Poland Interconnector | Dobrotvirska (Ukraine) | Rzeszów (Poland) | Underground Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 205 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2021 | Planned but not yet permitting | 0 | 0 | Ukrenergo | Polskie Sieci Elektroenergetyczne | TBA | TBA | 1000 | 205 | Ukraine is not included in the market model, therefore CBA assessment is not possible. (Also missing: technical data for line, terminals in PL and UA.) | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
370 | 1604 | Ukraine-Hungary Interconnector | Zakhidnoukrainska (Ukraine) | Albertirsa (Hungary) | Underground Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 520 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2021 | Planned but not yet permitting | 0 | 0 | Ukrenergo | MAVIR | TBA | TBA | 1000 | 520 | Ukraine is not included in the market model, therefore CBA assessment is not possible. (Also missing: technical data for line, terminals in HU and UA.) | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
371 | 1605 | Cyprus-Turkey Interconnector | Orounda (Cyprus) | Anamur (Turkey) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 112 | 0 | 0 | 0 | TBA | 220 | 0 |  | 2024 | Planned but not yet permitting | 0 | 0 | Cyprus TSO | TEİAŞ | TBA | TBA | 2000 | 112 | Turkey grid model not detailed. | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
372 | 1606 | Cyprus-Saudi Arabia Interconnector | TBA | TBA | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 0 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2024 | Under consideration | 0 | 0 | Cyprus TSO | Saudi Electricity Company | TBA | TBA | 2000 | 0 | Grid model not available for Saudi Arabia | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
374 | 1611 | Germany-Russia Interconnector | Lubmin (Germany) | Ochakovo (Russia) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 2000 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2026 | Under consideration | 0 | 0 | Tennet | RAO UES | TBA | TBA | 2000 | 2000 | no Russia model | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
375 | 1555 | Lienz (AT) - Veneto region (IT) | Lienz (AT) | Veneto region (IT) | Overhead Line | AC | 0 | 0 | N/A | 0 | 0 | 140 | 0.02 | 0.27 | 0.005 | 0 | 220 | 0 |  | 2024 | Permitting | 0 | 0 | APG | TERNA | 0 | 0 | 0 | 0 |  | atonti@ENTSOE.local | Alessio | Tonti | [6 empty] | 1
376 | 1559 | New investment | Bitola (MK) | Meliti (GR) | Overhead Line | AC | 0 | 0 | ACCC | 727 | 2 | 35.512 | 0.0242 | 0.3155 | 3.628 | 0 | 400 | 1990 |  | 2030 | Under consideration | 0 | 0 | MEPSO | IPTO | 0 | 0 | 0 | 18.12 |  | aneris@entsoe.local | Aristomenis | Neris | knaumoski@mepso.com.mk | Kliment | Naumovski |  |  |  | 1
377 | 1561 | BE-NL interconnector: upgrade VanEyck-Maasbracht | VanEyck | Maasbracht | Overhead Line | AC | 0 | 0 | HTLS | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 380 | 0 |  | 2030 | Under consideration | 0 | 0 | Elia | TENNET-NL | 0 | 0 | 0 | 0 |  | jbos@entsoe.local | Kedar | Kolharkar | ano@energinet.dk | Antje | Gesa Orths |  |  |  | 1
378 | 1584 | Transformer Gatica | GATICA 400 | GATICA 220 | Substation | AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 1575 |  | 2025 | Planned but not yet permitting | 8.16 | 0.1224 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
379 | 1593 | Uprate Gatica-Guenes | Gatica | Guenes | Overhead Line | AC | 0 | 0 | Cardinal | 0 | 2 | 38.8 | 0.0297 | 0.3237 | 3.5878 | 0 | 400 | 2454 |  | 2025 | Under consideration | 0.22 | 0.0033 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
379 | 1595 | Uprate Gatica-Amorebieta-Ichaso | Gatica | Ichaso | Overhead Line | AC | 0 | 0 | Cardinal | 0 | 2 | 69.12 | 0.029 | 0.32 | 3.6 | 0 | 400 | 2526 |  | REE | Under consideration | 1.65 | 0.02475 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
379 | 1597 | Uprate Gatica-Azpeitia | Gatica | Azpeitia | Overhead Line | AC | 0 | 0 | Cardinal | 0 | 2 | 57 | 0.0303 | 0.3192 | 3.5089 | 0 | 400 | 2454 |  | 2025 | Under consideration | 0.31 | 0.00465 | REE | REE | 0 | 0 | 0 | 0 |  | plabra@entsoe.local | Patricia | Labra | laura.lopez@ree.es | Laura | Lopez |  |  |  | 1
380 | 1576 | Tunisia-Italy Sardinia Interconnector | Mnihla (Tunisia) | Rumianca (Sardinia) | Subsea Cable | DC | VSC | 0 | Aluminium or Copper | 0 | 0 | 255 | 0 | 0 | 0 | TBA | 400 | 0 |  | 2021 | Permitting | 0 | 0 | STEG | Terna | TBA | TBA | 1000 | 255 | Tunisia not modelled | bgreplova@ENTSOE.local | Bara | Greplova | [6 empty] | 1
Note on N136: Heit Dr. Michael (50HzT MP): Not Available at the ENTSO-E plattform.
Note on O136: Heit Dr. Michael (50HzT MP): Not Available at the ENTSO-E plattform.
Note on P136: Heit Dr. Michael (50HzT MP): Not Available at the ENTSO-E plattform.
Note on N217: Heit Dr. Michael (50HzT MP): No availlable at ENTSO-E plattform.
Note on O217: Heit Dr. Michael (50HzT MP): No availlable at ENTSO-E plattform.
Note on P217: Heit Dr. Michael (50HzT MP): No availlable at ENTSO-E plattform.
Note on N249: Heit Dr. Michael (50HzT MP): Not available at ENTSO-E plattform
Note on O249: Heit Dr. Michael (50HzT MP): Not available at ENTSO-E plattform
Note on P249: Heit Dr. Michael (50HzT MP): Not available at ENTSO-E plattform

## Sheet2 (hidden)
Project ID | countif | id | project_id | name | _from | _to | elementstype | technology_type | total_route_length | voltage_level | expected_commissioning_year | status | tso_in_charge_from | tso_in_charge_to | third_party | country_1 | country_2 | country_3 | code | internal | regions
1 | #REF! | 4 | 1 | V.Minho -R.Pena-FridÃ£o-Feira | V.Minho (by Ribeira de Pena and FridÃ£o) | Feira (by Ribeira de Pena and FridÃ£o) | Overhead Line | AC | 131 | 400 | 2022-2024 | In Permitting | REN | REN | FALSE | Portugal |  |  |  | TRUE | CSW
|  | 474 | 1 | Substation Ribeira de Pena | Ribeira de Pena (PT) | - | Substation | AC | 0 | 400 | 2022-2024 | In Permitting | REN | - | FALSE | Portugal |  |  |  | TRUE | CSW
|  | 2 | 1 | Pedralva-Sobrado | Pedralva (PT) | Sobrado (PT) | Overhead Line | AC | 67 | 400 | 2022-2023 | Planned but not yet permitting | REN | REN | FALSE | Portugal |  |  |  | TRUE | CSW
|  | 941 | 1 | Switching station FridÃ£o | FridÃ£o | Fontefria (ES) | Substation | AC | 0 | 400 | 2026-2030 | In Permitting | REN | - | FALSE | Portugal |  |  |  | TRUE | CSW
4 | #REF! | 500 | 4 | Ponte de Lima (PT) | Ponte de Lima (PT) | La Ribina (ES) | Substation | AC | 0 | 400 | 44197 | In Permitting | REN | REN | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
|  | 498 | 4 | SE Fontefria 400/220kV | Fontefria (ES) | Beariz (ES) | Substation | AC | 0 | 400 | 44197 | In Permitting | REE | REE | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
|  | 496 | 4 | Fontefria (ES) - Vila Nova de FamalicÃ†o (PT) | Fontefria (ES) | REE | Overhead Line | AC | 135 | 400 | 44197 | In Permitting | REE | REN | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
|  | 18 | 4 | Beariz (ES) - Fontefria (ES) | Beariz (ES) | Vila Nova de FamalicÃ†o (PT) (By Ponte de Lima) | Overhead Line | AC | 32 | 400 | 44197 | In Permitting | REE | REE | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
|  | 499 | 4 | Beariz 400kV (ES) | Beariz (ES) | Ponte de Lima (PT) | Substation | AC | 0 | 400 | 44197 | In Permitting | REE | REE | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
13 | #REF! | 570 | 13 | New substation La Ribina | La Ribina (ES) | Cubnezais (FR) | Substation | AC | 0 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
|  | 31 | 13 | Axis Caparacena-Baza-La Ribina | Caparacena (ES) | Baza (ES) | Overhead Line | AC | 177 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
|  | 569 | 13 | New substation Baza | Baza (ES) | La Ribina (ES) | Substation | AC | 0 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
16 | #REF! | 38 | 16 | HVDC Gatica-Cubnezais | Gatica (ES) | Piossasco (IT) | Subsea Cable | DC | 370 | 320 | 45658 | In Permitting | REE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS
21 | #REF! | 55 | 21 | Savoie - PiÃ¨mont | Grande Ile (FR) | Horta (BE) | Underground Cable | DC | 190 | 320 | 2019 | Under Construction | RTE | TERNA | FALSE | France | Italy | 0 | FR - IT | FALSE | CSW,NS,CCS
23 | #REF! | 60 | 23 | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | Avelin/Mastaing (FR) | Chilling (GB) | Overhead Line | AC | 80 | 400 | 44562 | In Permitting | RTE | ELIA | FALSE | France | Belgium | 0 | FR - BE | FALSE | CSW,NS
25 | #REF! | 62 | 25 | IFA2 | Tourbe (FR) | Glorenza (IT) | Subsea Cable | DC | 250 | 320 | 43831 | Under Construction | RTE | NGIHL | FALSE | France | Great Britain | 0 | FR - GB | FALSE | CSW,NS
26 | #REF! | 614 | 26 | Reschenpass Interconnector | Nauders (AT) | Lastva (ME) | Underground Cable | AC | 26 | 220 | 2021 | In Permitting | APG | Terna | FALSE | Austria | Italy | 0 | AT - IT | FALSE | CCS,CCE
28 | #REF! | 70 | 28 | First HVDC Module IT-ME | Villanova (IT) |  | Subsea Cable | DC | 445 | 500 | 2019 | Under Construction | TERNA | CGES | FALSE | Italy | Montenegro | 0 | IT - ME | FALSE | CSE,CCS
|  | 624 | 28 | SS 400/110 kV Lastva | Lastva (ME) | Lastva (ME) | Substation | AC | 0 | 400 | 43465 | Under Construction | CGES |  | FALSE | Italy | Montenegro | 0 | IT - ME | FALSE | CSE,CCS
29 | #REF! | 635 | 29 | Elmed Project | Sicily Area (IT) | Pallanzeno(IT)-Baggio(IT) | Subsea Cable | DC | 200 | 400 | 2022 | In Permitting | TERNA | STEG | FALSE | Italy | Tunisia | 0 | IT - TN | FALSE | CSE,CCS
31 | #REF! | 642 | 31 | San Giacomo Project | All'Acqua (CH) | Colunga (IT) | Overhead Line | AC | 100 | 380 | 2025 | In Permitting | SWISSGRID | TERNA | FALSE | Switzerland | Italy | 0 | CH - IT | FALSE | CCS
33 | #REF! | 1041 | 33 | Rem. lim. in Central Italy | Villanova (IT) |  | Overhead Line | AC | 350 | 220 | 44562 | Planned but not yet permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
|  | 90 | 33 | 90 | Calenzano (IT) | S. Barbara (IT) | Overhead Line | AC | 80 | 400 | 2022 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
35 | #REF! | 311 | 35 | R Kocin | Kocin (CZ) | Mirovka (CZ) | Substation | AC | 0 | 400 | 45292 | Under Construction | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
|  | 313 | 35 | Kocin-Mirovka | Kocin (CZ) | Prestice (CZ) | Overhead Line | AC | 121 | 400 | 45292 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
|  | 315 | 35 | Kocin-Prestice | Kocin (CZ) | Bentwisch (DE) | Overhead Line | AC | 116 | 400 | 46753 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
36 | #REF! | 141 | 36 | Kriegers Flak CGS, TYNDP ID: 36.141 | IshÃ¸j / BjÃ¦verskov (DK) | Wilster (DE) | Subsea Cable | AC | 24 | 150 | 43465 | Under Construction | Energinet.dk | 50Hertz Transmission GmbH | FALSE | denmark | Germany | 0 | DK - DE | FALSE | BS,NS
37 | #REF!
39 | #REF! | 144 | 39 | Audorf - Kassoe | Audorf (DE) | LUX-DE (TBC) | Overhead Line | AC | 110 | 380 | 44196 | Under Construction | TenneT-DE | Energienet.dk | FALSE | denmark | Germany | 0 | DK - DE | FALSE | BS,NS
40 | #REF! | 650 | 40 | BE-LUX-DE Long-Term perspective | Aubange (TBC) | St. Peter (AT) | Overhead Line | AC | 0 | 0 | 2035 | Under Consideration | ELIA | CREOS; AMPRION | FALSE | Belgium | Germany | Luxembourg | BE - DE | FALSE | BS,NS,CCS
47 | #REF! | 219 | 47 | 219: Westtirol - Zell/Ziller (AT internal) | Westtirol (AT) | Westtirol (AT) | Overhead Line | AC | 105 | 380 | 2024 | Planned but not yet permitting | APG | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
|  | 689 | 47 | 689: VÃ¶hringen (DE) - Westtirol (AT) | VÃ¶hringen (DE) |  | Overhead Line | AC | 114 | 380 | 2024 | Planned but not yet permitting | Amprion | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
|  | 216 | 47 | (is a single investment project, please consider only content of project 312) 216 | St. Peter (AT) | Zell-Ziller (AT) | Overhead Line | AC | 128 | 400 | 2022 | In Permitting | APG | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
|  | 212 | 47 | (is a single investment project, please consider only content of project 313) 212 Isar/Altheim/Ottenhofen - St. Peter | Isar (DE) | Tauern (AT) | Overhead Line | AC | 90 | 400 | 2021 | In Permitting | TenneT-DE | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
48 | #REF! | 697 | 48 | Hunew 2 | SajÃ³ivÃ¡nka (HU) | Gonyu (HU) | Substation | AC | 0 | 400 | 2020 | In Permitting | MAVIR |  | FALSE | Slovakia | Hungary | 0 | SK - HU | FALSE | CCE
|  | 696 | 48 | Hunew 1 | SajÃ³ivÃ¡nka (HU) |  | Compensation | AC | 0 | 400 | 2020 | In Permitting | MAVIR |  | FALSE | Slovakia | Hungary | 0 | SK - HU | FALSE | CCE
|  | 1501 | 48 | 2. SK-HU interconnection | RimavskaÂ Sobota (SK) | Sajoivanka (HU) | Overhead Line | AC | 48 | 400 | 2020 | In Permitting | MAVIR |  | FALSE | Slovakia | Hungary |  | SK - HU | FALSE | CCE
|  | 1500 | 48 | 1. SK-HU interconnection | Gabcikovo (SK) | Gonyu (HU) | Overhead Line | AC | 110 | 400 | 2020 | In Permitting | SEPS | MAVIR | FALSE | Slovakia | Hungary |  | SK - HU | FALSE | CCE
62 | #REF! | 1062 | 62 | Riga CHP2 - Riga HPP | Riga CHP2 | Eemshaven (NL) | Overhead Line | AC | 15 | 330 | 43831 | In Permitting | AST | AST | FALSE | Estonia | Latvia | 0 | EE - LV | FALSE | BS
|  | 386 | 62 | 3rd EE-LV interconnection | Kilingi-Nomme (EE) | Sindi (EE) | Overhead Line | AC | 205 | 330 | 2020 | Under Construction | Elering | AST | FALSE | Estonia | Latvia | 0 | EE - LV | FALSE | BS
|  | 735 | 62 | Harku-Sindi 330kV OHL | Harku (EE) | Riga HPP | Overhead Line | AC | 175 | 330 | 44196 | Under Construction | Elering | Elering | FALSE | Estonia | Latvia | 0 | EE - LV | FALSE | BS
71 | #REF! | 427 | 71 | COBRA Cable | Endrup (DK) | Gezelle (BE) | Subsea Cable | DC | 325 | 320 | 2019 | Under Construction | Energinet | TENNET-NL | FALSE | denmark | Netherlands | 0 | DK - NL | FALSE | BS,NS
74 | #REF! | 450 | 74 | SELL - DUNG Reconductoring | Sellindge (GB) | Stevin (Zeebrugge) | Overhead Line | AC | 26 | 400 | 42704 | Under Construction | NGET | NGET | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
|  | 443 | 74 | NEMO | Richborough (GB) | Canterbury (GB) | Subsea Cable | DC | 140 | 400 | 43466 | Under Construction | NGET | ELIA | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
|  | 449 | 74 | Richborough - Canterbury | Richborough (GB) | Dungeness (GB) | Overhead Line | AC | 20 | 400 | 2018 | In Permitting | NGET | NGET | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
75 | #REF! | 752 | 75 | Modular Offshore Grid | Offshore platform | Deeside (GB) | Subsea Cable | AC | 50 | 220 | 43831 | In Permitting | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
77 | #REF! | 452 | 77 | Western HVDC Link | Hunterston (GB) | Seabank (GB) | Subsea Cable | DC | 360 | 500 | 2017 | Under Construction | SPT | NGET | FALSE | United Kingdom |  |  |  | TRUE | NS
78 | #REF! | 458 | 78 | HINP-SEAB New Double Circuit | Hinkley Point (GB) | Turleenan (NI) | Overhead Line | AC | 60 | 400 | 2024 | In Permitting | NGET | NGET | FALSE | United Kingdom |  |  |  | TRUE | NS
81 | #REF! | 462 | 81 | 462 | Woodland (IE) | New substation in South Donegal (IE) | Overhead Line | AC | 138 | 400 | 2020 | In Permitting | EirGrid | SONI | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
82 | #REF! | 463 | 82 | Srananagh - South Donegal | Srananagh (IE) | Omagh South (NI) | Overhead Line | AC | 76 | 220 | 2029 | Planned but not yet permitting | EirGrid | EirGrid | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
|  | 896 | 82 | Omagh South to South Donegal | South Donegal (IE) | Turleenan | Overhead Line | AC | 58 | 275 | 2029 | Planned but not yet permitting | EirGrid | SONI | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
|  | 897 | 82 | Omagh South to Turleenan | Omagh South | Tavira (by Ourique) | Overhead Line | AC | 63 | 275 | 2029 | Planned but not yet permitting | SONI | SONI | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
85 | #REF! | 780 | 85 | Extension of Ourique substation | Ourique (PT) | Lixhe (BE) | Substation | AC | 0 | 400 | 2024-2026 | Planned but not yet permitting | REN | - | FALSE | Portugal |  |  |  | TRUE | CSW
|  | 779 | 85 | F.Alentejo-Ourique-Tavira | F. Alentejo (by Ourique) | - | Overhead Line | AC | 122 | 400 | 2024-2026 | Planned but not yet permitting | REN | REN | FALSE | Portugal |  |  |  | TRUE | CSW
92 | #REF! | 146 | 92 | ALEGrO | Oberzier (DE) | Krajnik (PL) | Underground Cable | DC | 100 | 320 | 44105 | In Permitting | AMPRION | ELIA | FALSE | Belgium | Germany | 0 | BE - DE | FALSE | BS,NS,CCS
94 | #REF! | 139 | 94 | Krajnik-Vierraden | Vierraden (DE) | Krajnik (PL) | Overhead Line | AC | 26 | 400 | 44196 | Under Construction | 50Hertz | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
|  | 796 | 94 | Krajnik | Krajnik (PL) | Mikulowa (PL) | Substation | AC | 0 | 400 | 2019 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
96 | #REF! | 801 | 96 | FI5 KI-PS | Keminmaa (FI) | Ens | Overhead Line | AC | 156 | 400 | 45292 | In Permitting | Fingrid | Fingrid | FALSE | Finland |  |  |  | TRUE | BS
103 | #REF! | 1540 | 103 | Eindhoven-Maasbracht | Eindhoven | Maasbracht | Overhead Line | AC | 50 | 380 | 2023 | Planned but not yet permitting | TENNET - NL | TENNET - NL |  | Netherlands |  |  | NL | TRUE | NS
|  | 1488 | 103 | Diemen-Lelystad-Ens | Diemen | Ens | Overhead Line | AC | 75 | 380 | 2020 | Under Construction | TENNEL - NL | TENNET - NL | FALSE | Netherlands |  |  | NL | TRUE | NS
|  | 1488 | 103 | Diemen-Lelystad-Ens | Diemen | Ens | Overhead Line | AC | 75 | 380 | 2020 | Under Construction | TENNET - NL | TENNET - NL | FALSE | Germany |  |  | DE | TRUE | CCE,BS,NS,CCS
107 | #REF! | 810 | 107 | France Ireland Interconnector | West Wexford or East Cork (IE) | Blythe (GB) | Subsea Cable | DC | 580 | 320 | 2026 | Under Consideration | EIRGRID | RTE | FALSE | France | Ireland | 0 | FR - IE | FALSE | NS
110 | #REF! | 424 | 110 | Norway - Great Britain | Kvilldal (NO) | Messaure (Sweden, bidding area SE1) | Subsea Cable | DC | 720 | 500 | 2021 | Under Construction | Statnett | NHIGL | FALSE | United Kingdom | norway | 0 | GB - NO | FALSE | BS,NS
111 | #REF! | 396 | 111 | 3rd AC Finland-Sweden north | Keminmaa (Finland) | Doetinchem (NL) | Overhead Line | AC | 200 | 400 | 2025 | In Permitting | Fingrid | Svenska kraftnÃ¤t | FALSE | Finland | Sweden | 0 | FI - SE | FALSE | BS
113 | #REF! | 145 | 113 | Doetinchem-Niederrhein | Niederrhein (DE) | TBD (BE) | Overhead Line | AC | 57 | 380 | 2018 | Under Construction | AMPRION | TENNET-NL | FALSE | Netherlands | Germany | 0 | NL - DE | FALSE | NS,CCS
120 | #REF! | 1625 | 120 | MOG II: connection of up to 2 GW additional offshore wind Belgium | Offshore (TBD) | Onshore (TBD) | Subsea Cable | DC | 50 | 400 | 2030 | Under Consideration | Elia | Elia | FALSE | Belgium |  |  | BE | TRUE | NS
121 | #REF! | 934 | 121 | Nautilus: 2nd interco UK - BE | Leiston (UK) | Stanislawow (PL) | Subsea Cable | DC | 250 | 400 | 2028 | Under Consideration | NGHIL | ELIA | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
123 | #REF! | 373 | 123 | Ostroleka-Stanislawow | Ostroleka (PL) | Musa | Overhead Line | AC | 106 | 400 | 45291 | Planned but not yet permitting | PSE | PSE | FALSE | Poland | Lithuania | 0 | PL - LT | FALSE | BS
124 | #REF! | 378 | 124 | 330 kV OHL Panevezys-Musa | Panevezys | Imanta (LV) | Overhead Line | AC | 80 | 330 | 45291 | Planned but not yet permitting | LITGRID | LITGRID | FALSE | Lithuania | Sweden | 0 | LT - SE | FALSE | BS
|  | 385 | 124 | Grobina (LV) - Imanta (LV) | Grobina (LV) | Nybro/Hemsjo (SE) | Overhead Line | AC | 380 | 330 | 2019 | Under Construction | AST | AST | FALSE | Lithuania | Sweden | 0 | LT - SE | FALSE | BS
|  | 733 | 124 | Ekhyddan-Nybro-Hemsjo | Ekhyddan (SE) | SE3 | Overhead Line | AC | 160 | 400 | 2023 | In Permitting | Svk | Svk | FALSE | Lithuania | Sweden | 0 | LT - SE | FALSE | BS
126 | #REF! | 403 | 126 | Reinforcements SE2-SE3 in Sweden | SE2 | Villanova (IT) | Compensation | AC | 900 | 400 | 2030 | Under Consideration | Svk | Svk | FALSE | Sweden |  |  |  | TRUE | BS
127 | #REF! | 645 | 127 | ITA-3 | Laino (IT) | Isar (DE) | Overhead Line | AC | 50 | 400 | 44562 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
|  | 86 | 127 | 86 | Foggia (IT) | Benevento II (IT) | Overhead Line | AC | 178 | 400 | 44562 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
|  | 91 | 127 | 91 | Foggia (IT) | Bisaccia (IT) | Overhead Line | AC | 85 | 400 | 41820 | Commissioned | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
|  | 96 | 127 | 96 | Deliceto (IT) | Altomonte (IT) | Overhead Line | AC | 30 | 400 | 44926 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
130 | #REF! | 665 | 130 | Wolmirstedt-Isar | Wolmirstedt (DE) | Osterath (DE) | Underground Cable | DC | 540 | 0 | 2025 | In Permitting | 50Hertz | TenneT DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
132 | #REF! | 661 | 132 | HVDC Line A-North | Emden East (DE) | Eichstetten (DE) | Overhead Line | DC | 300 | 400 | 45658 | Under Consideration | Amprion | Amprion | FALSE | Germany |  | 0 | Internal | TRUE | CCE,BS,NS,CCS
|  | 661 | 132 | HVDC Line A-North | Emden East (DE) | Osterath (DE) | Overhead Line | DC | 300 | 400 | 2025 | Planned but not yet permitting | AMPRION | AMPRION | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
134 | #REF! | 680 | 134 | Urberach - Daxlanden | Urberach (DE) | WeiÃŸenthurm (DE) | Overhead Line | AC | 219 | 400 | 44562 | Under Consideration | Amprion | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 176 | 134 | Daxlanden-Eichstetten | Daxlanden (DE) | Daxlanden (DE) | Overhead Line | AC | 120 | 380 | 44197 | Under Consideration | TransnetBW | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
135 | #REF! | 179 | 135 | Rommerskirchen - WeiÃŸenthurm | Rommerskirchen (DE) | Dauersberg (DE) | Overhead Line | AC | 94 | 400 | 43466 | Under Construction | Amprion | Amprion | FALSE | Germany |  | 0 | Internal | TRUE | CCE,BS,NS,CCS
|  | 188 | 135 | Kruckel - Dauersberg | Kruckel (DE) | Stalpu (RO) | Overhead Line | AC | 110 | 380 | 44197 | In Permitting | Amprion | Amprion | FALSE | Germany |  | 0 | Internal | TRUE | CCE,BS,NS,CCS
138 | #REF! | 800 | 138 | 400 kV OHL Varna-Burgas | Varna(BG) | N.Santa (GR) | Overhead Line | AC | 140 | 400 | 44286 | Planned but not yet permitting | ESO-EAD | ESO-EAD | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE
|  | 715 | 138 | 220kV Stalpu substation upgrade to 400 kV | Stalpu (RO) | Burgas(BG) | Substation | AC | 0 | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE
|  | 275 | 138 | 400 kV OHL Smardan-Gutinas | Smardan (RO) | Stalpu (RO) | Overhead Line | AC | 140 | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE,CCE
|  | 273 | 138 | 400kV OHL Cernavoda-Stalpu | Cernavoda (RO) | Gutinas (RO) | Overhead Line | AC | 159 | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE
142 | #REF! | 256 | 142 | 256 | Maritsa East 1 (BG) | Plovdiv (BG) | Overhead Line | AC | 130 | 400 | 44956 | In Permitting | ESO-EAD | IPTO-SA | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
|  | 257 | 142 | 257 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | Overhead Line | AC | 100 | 400 | 44195 | Under Consideration | ESO-EAD | ESO-EAD | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
|  | 258 | 142 | 258 | Maritsa East 1 (BG) | Burgas (BG) | Overhead Line | AC | 13 | 400 | 43646 | Under Consideration | ESO-EAD | ESO-EAD | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
|  | 262 | 142 | 262 | Maritsa East 1 (BG) | Pancevo (RS) | Overhead Line | AC | 150 | 400 | 44348 | Under Consideration | ESO-EAD | ESO-EAD | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
144 | #REF! | 705 | 144 | 400 kV Substation Timisoara | Timisoara (RO) | Border IT-SI | Substation | AC | 0 | 400 | 2023 | Under Consideration | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
|  | 270 | 144 | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz - Arad to 400kV double circuit line | Resita (RO) | Resita (RO) | Overhead Line | AC | 175 | 400 | 2023 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
|  | 701 | 144 | 400 kV Substation Resita | Resita (RO) | Timisoara (RO) | Substation | AC | 0 | 400 | 2019 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
|  | 238 | 144 | New_400 kV OHL RO-RS | Resita (RO) | Resita (RO) | Overhead Line | AC | 131 | 400 | 2017 | Under Construction | Transelectrica | EMS | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE,CCE
|  | 269 | 144 | 400 kV OHL Portile de Fier-Resita | Portile de Fier (RO) | Arad (RO) | Overhead Line | AC | 116 | 400 | 2019 | Under Construction | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
150 | #REF! | 616 | 150 | Salgareda - Border IT-SI | Salgareda (IT) | Border IT-SI | Underground Cable | DC | 0 | 500 | 2022 | Under Consideration | TERNA |  | FALSE | Slovenia | Italy | 0 | SI - IT | FALSE | CCE,CCS
|  | 1616 | 150 | BeriÄevo - Border IT-SI | BeriÄevo (SI) | Border IT-SI | Underground Cable | DC | 140 | 400 | 2022 | In Permitting | ELES | TERNA |  | Slovenia | Italy |  |  | FALSE | CCE,CCS
153 | #REF! | 987 | 153 | France-Alderney-Britain | Menuel (FR) | Stade (DE) | Subsea Cable | DC | 210 | 320 | 44562 | In Permitting | RTE (FR) | NGIHL (UK) | FALSE | France | Great Britain | 0 | FR - GB | FALSE | CSW,NS
164 | #REF! | 157 | 164 | Wahle - Mecklar | Wahle (DE) | Landesbergen (DE) | Overhead Line | AC | 210 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 685 | 164 | Mecklar - Grafenrheinfeld | Mecklar (DE) | Bicker Fen (GB) | Overhead Line | AC | 130 | 380 | 2027 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 149 | 164 | Dollern - Stade | Dollern (DE) | Mecklar (DE) | Overhead Line | AC | 14 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 677 | 164 | Dollern - Landesbergen | Dollern (DE) | Grafenrheinfeld (DE) | Overhead Line | AC | 130 | 380 | 2023 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
167 | #REF! | 998 | 167 | Viking Link DKW-GB, TYNDP ID 167.998 | Revsing (DKW) | Neris | Subsea Cable | DC | 770 | 515 | 44926 | In Permitting | Energinet.dk | National Grid | FALSE | Denmark | United Kingdom | 0 | DK - GB | FALSE | BS,NS
170 | #REF! | 382 | 170 | 330 kV line Vilnius-Neris | Vilnius | Paide | Overhead Line | AC | 80 | 330 | 45292 | Planned but not yet permitting | LITGRID | LITGRID | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
|  | 1011 | 170 | Valmiera -Tsirguliina 330 kV | Tsirguliina | Tartu | Overhead Line | AC | 60 | 330 | 45658 | Planned but not yet permitting | Elering | AST | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
|  | 1010 | 170 | 330 kV OHL Tartu-Valmiera | Tartu | Valmiera | Overhead Line | AC | 133 | 330 | 45658 | Planned but not yet permitting | Elering | AST | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
|  | 1034 | 170 | New 400 kV interconnection line from Lithuania to state border | Marijampole | - | Overhead Line | AC | 51 | 400 | 47849 | Under Consideration | LITGRID | LITGRID | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
|  | 1013 | 170 | Eesti-Tsirguliina 330kV OHL | Eesti | State border | Overhead Line | AC | 243 | 330 | 45658 | Under Consideration | ELERING | ELERING | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
|  | 1117 | 170 | B2B at Narva | Eesti | - | Substation | DC | 0 | 330 | 45292 | Under Consideration | ELERING | - | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
|  | 1012 | 170 | 330 kV OHL Tartu-Balti (L300) | Balti | Tsirguliina | Overhead Line | AC | 168 | 330 | 45292 | Under Consideration | ELERING | ELERING | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
172 | #REF! | 1487 | 172 | Eleclink | Sellindge | Mandarins | Subsea Cable | DC | 69 | 400 | 2019 | Under Construction | National Grid | Reseau de Transport d'Electricite, the French TSO | FALSE | United Kingdom | France |  | GB - FR | FALSE | NS
173 | #REF! | 1281 | 173 | Aubange-Moulaine: PSTs | Aubange (BE) | Sils i.D. | Phase Shift Transformer | AC | 0 | 220 | 44196 | Planned but not yet permitting | ELIA | RTE | FALSE | France | Belgium | 0 | FR - BE | FALSE | CSW,NS
174 | #REF! | 1014 | 174 | Greenconnector | Verderio | Not decided | Underground Cable | DC | 150 | 400 | 2022 | In Permitting | Terna | Swissgrid | TRUE | Italy | Switzerland | 0 | IT - CH | FALSE | CSE,CCS
175 | #REF! | 1000 | 175 | Great Belt II | Not decided | GueÂstrow (DE) | Subsea Cable | DC | 50 | 400 | 2030 | Under Consideration | Energinet | Energinet | FALSE | Denmark | Denmark | 0 | DK - DK | FALSE | BS
176 | #REF! | 995 | 176 | Hansa PowerBridge | Hurva (SE4) | Bentwisch (DE) | Subsea Cable | DC | 300 | 300 | 2026 | In Permitting | Svk | 50Hertz | FALSE | Germany | Sweden | 0 | DE - SE | FALSE | BS,NS,CCE
179 | #REF! | 1016 | 179 | DKE-DE (Kontek 2) | BjÃ¦verskov (DK2) | Endrup (DKW) | Subsea Cable | DC | 170 | 400 | 2030 | Under Consideration | Energinet | 50Hertz | FALSE | Denmark | Germany | 0 | DK - DE | FALSE | BS,NS
183 | #REF! | 1018 | 183 | DKW-DE, Westcoast, TYNDP ID 183.1018 | KlixbÃ¼ll (DE) | Neusiedl/Zaya | Overhead Line | AC | 92 | 380 | 44926 | In Permitting | TenneT-DE | Energinet.dk | FALSE | Denmark | Germany | 0 | DK - DE | FALSE | BS,NS
186 | #REF! | 886 | 186 | 886 | Seyring | St. Peter (AT) | Overhead Line | AC | 60 | 380 | 2021 | In Permitting | APG | APG | FALSE | Austria |  |  |  | TRUE | CCE,CCS,CCE
187 | #REF! | 997 | 187 | 997 Pleinting - St. Peter | Pleinting (DE) | Peterhead | Overhead Line | AC | 60 | 380 | 2024 | In Permitting | TenneT-DE | APG | FALSE | Austria | Germany | 0 | AT - DE | FALSE | CCE,CCS,CCE
190 | #REF! | 1382 | 190 | NorthConnect | Sima | Emden/East (DE) | Subsea Cable | DC | 655 | 500 | 2022 | In Permitting | Statnett | National Grid (SSEN is TO) | TRUE | Great Britain | Norway | 0 | GB - NO | FALSE | BS,NS
191 | #REF! | 953 | 191 | Cluster DolWin6 | Cluster DolWin 6 (NOR-3-3) | DÃ¶rpen/West (DE) | Subsea Cable | DC | 90 | 320 | 2023 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 952 | 191 | Cluster DolWin 5 (NOR 1-1) | Cluster DolWin 5 (NOR-1-1) | Emden/East | Subsea Cable | DC | 130 | 320 | 2024 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 656 | 191 | BorWin3 | Cluster BorWin3 | Emden/East (DE) | Subsea Cable | DC | 160 | 320 | 2019 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 659 | 192 | SylWin2 | Cluster SylWin2 (DE) | area of Cloppenburg/East | Subsea Cable | DC | 205 | 320 | 2025 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
192 | #REF! | 211 | 192 | DolWin 4 (NOR-3-2) | Cluster DolWin 4 (NOR 3-2) | BÂÃ¼ttel (DE) | Subsea Cable | DC | 190 | 320 | 2028 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 954 | 192 | Cluster BorWin 5 (NOR-7-1) | Cluster BorWin 5 (NOR-7-1) | area of Cloppenburg/East | Subsea Cable | DC | 250 | 320 | 2025 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
193 | #REF! | 927 | 193 | La Plana/Morella-Godelleta | La Plana/Morella | Cartuja (ES) | Overhead Line | AC | 207.5 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
194 | #REF! | 561 | 194 | New substation Cartuja | Cartuja (ES) | Arcos | Substation | AC | 0 | 400 | 2029 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
|  | 929 | 194 | Cartuja-Arcos 400 kV | Cartuja | Petajavesi (FI) | Overhead Line | AC | 30 | 400 | 2029 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
197 | #REF! | 742 | 197 | Pyhanselka-Petajavesi | Pyhanselka (FI) | CHAVALON (CH) | Overhead Line | AC | 300 | 400 | 44743 | In Permitting | Fingrid | Fingrid | FALSE | Finland |  |  |  | TRUE | BS
199 | #REF! | 1051 | 199 | Cornier - Chavalon 400 kV | CORNIER (FR) |  | Overhead Line | AC | 65 | 400 | 2035 | Under Consideration | RTE | SWISSGRID | FALSE | France | Switzerland | 0 | FR - CH | FALSE | CSW,NS,CCS
200 | #REF! | 306 | 200 | R Vitkov | Vitkov (CZ) | Vitkov (CZ) | Substation | AC | 0 | 400 | 44895 | In Permitting | CEPS |  | FALSE | Czech Republic |  |  |  | TRUE | CCE
|  | 309 | 200 | Vitkov-Prestice | Vitkov (CZ) |  | Overhead Line | AC | 86 | 400 | 44895 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
|  | 308 | 200 | Vernerov-Vitkov | Vernerov (CZ) | Prestice (CZ) | Overhead Line | AC | 71 | 400 | 45868 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
|  | 312 | 200 | R Mirovka | Mirovka (CZ) | V413 (CZ) | Substation | AC | 0 | 400 | 45930 | In Permitting | CEPS |  | FALSE | Czech Republic |  |  |  | TRUE | CCE
|  | 314 | 200 | Mirkovka-V413 | Mirovka (CZ) | La Plana(ES) | Overhead Line | AC | 27 | 400 | 43615 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
203 | #REF! | 538 | 203 | Morella-La Plana | Morella (ES) | Endersbach (DE) | Overhead Line | AC | 78 | 400 | 2020 | In Permitting | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
206 | #REF! | 687 | 206 | Redwitz - Schwandorf | Redwitz (DE) | Altheim (DE) | Overhead Line | AC | 185 | 380 | 2023 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 688 | 206 | Raitersaich-Altheim | Raitersaich (DE) | GroÃŸgartach (DE) | Overhead Line | AC | 160 | 380 | 2026 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 682 | 206 | GroÃŸgartach - Endersbach | GroÃŸgartach (DE) | Schwandorf (DE) | Overhead Line | AC | 0 | 380 | 2025 | Planned but not yet permitting | TransnetBW | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 990 | 206 | Grafenrheinfeld - GroÃŸgartach | Grafenrheinfeld (DE) | Elsfleht/West (DE) | Overhead Line | AC | 168 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 990 | 206 | Grafenrheinfeld - GroÃŸgartach |  |  | Overhead Line | AC |  |  |  | Planned but not yet permitting
207 | #REF! | 940 | 207 | Emden - Halbemond | Emden/Ost | Wilhelmshaven (DE) | Overhead Line | AC | 30 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 676 | 207 | Dollern - Elsfleth/West | Dollern (DE) | Emden/Ost | Overhead Line | AC | 100 | 380 | 2026 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 939 | 207 | Conneforde - Emden | Conneforde | Halbemond | Overhead Line | AC | 60 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
208 | #REF! | 151 | 208 | Ganderkesee - Wehrendorf | Wehrendorf (DE) | DÃ¶rpen/West (DE) | Overhead Line | AC | 95 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 156 | 208 | Niederrhein-DÃ¶rpen | Niederrhein (DE) | GÃ¶hl/Siems | Overhead Line | AC | 182 | 380 | 2021 | In Permitting | Amprion | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 150 | 208 | Conneforde-Wilhelmshaven | Conneforde (DE) | Ganderkesee (DE) | Overhead Line | AC | 30 | 380 | 2020 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
209 | #REF! | 935 | 209 | Kreis Segeberg - Siems | Kreis Segeberg | WURMLACH | Overhead Line | AC | 110 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
210 | #REF! | 1380 | 210 | Wurmlach (AT) - Somplago (IT) interconnection | SOMPLAGO | tbd | Underground Cable | AC | 51 | 220 | 2021 | In Permitting | TERNA SPA | Austrian Power Grid AG | TRUE | Austria | Italy | 0 | AT - IT | FALSE | CSE,CCE,CCE
214 | #REF! | 1082 | 214 | Interco Iceland-UK | tbd | Kofinou Site | Subsea Cable | DC | 1000 | 500 | 2030 | Under Consideration | tbd | tbd | FALSE | Iceland | Great Britain | 0 | IS - GB | FALSE | NS
219 | #REF! | 1410 | 219 | EuroAsia Interconnector | Korakia (Crete)Site | to be defined (DE) | Subsea Cable | DC | 0 | 500 | 2020 | In Permitting | ADMHE | ADMHE | FALSE | Cyprus | Greece | Isreal | CY - GR | FALSE | CSE
|  | 1409 | 219 | EuroAsia Interconnector | Kofinou Site | Athens Site | Subsea Cable | DC | 0 | 0 | 2021 | In Permitting | TSO Cyprus | ADMHE | FALSE | Cyprus | Greece | Isreal | CY - GR | FALSE | CSE
|  | 1407 | 219 | EuroAsia Interconnector | Hadera Site | Korakia (Crete)Site | Subsea Cable | DC | 0 | 500 | 2020 | In Permitting | IEC | TSO Cyprus | FALSE | Cyprus | Greece | Isreal | CY - GR | FALSE | CSE
225 | #REF! | 1107 | 225 | 2nd interconnecter between Belgium and Germany | to be defined (BE) | Visegrad (BA) | Underground Cable | DC | 0 | 0 | 2028 | Under Consideration | ELIA | AMPRION | FALSE | Belgium | Germany | 0 | BE - DE | FALSE | BS,NS,CCS
227 | #REF! | 628 | 227 | 400kV OHL B.Basta-Obrenovac | SS Bajina Basta (RS) | Pljevlja (ME) | Overhead Line | AC | 115 | 400 | 2024 | In Permitting | EMS | EMS | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
|  | 631 | 227 | 400kV SS B.Basta upgrade | Bajina Basta (RS) | SS Pljevlja | Substation | AC | 0 | 400 | 2024 | In Permitting | EMS | EMS | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
|  | 630 | 227 | 400kV interconnection RS-ME | Bajina Basta (RS) | Bajina Basta (RS) | Overhead Line | AC | 100 | 400 | 2024 | In Permitting | EMS | CGES | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
|  | 627 | 227 | 400kV interconnection RS-BA | Bajina Basta (RS) | SS Obrenovac (RS) | Overhead Line | AC | 65 | 400 | 2024 | In Permitting | EMS | NOSBIH | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
|  | 1527 | 227 | 400 kV OHL Kragujevac-Kraljevo | SS Kragujevac | SS Kraljevo | Overhead Line | AC | 60 | 400 | 2020 | Under Construction | EMS | EMS | FALSE | Serbia | Montenegro |  | RS - MO | TRUE | CSE
228 | #REF! | 1231 | 228 | Muhlbach Eichstetten | Muhlbach | Zielona GÃ³ra | Overhead Line | AC | 32 | 400 | 2025 | Planned but not yet permitting | RTE | TransnetBW GmbH | FALSE | France | Germany | 0 | FR - DE | FALSE | CSW,NS,CCS
229 | #REF! | 1271 | 229 | Zielona GÃ³ra - Plewiska | Zielona GÃ³ra | n.a. | Overhead Line | AC | 40 | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
|  | 1272 | 229 | Zielona GÃ³ra | Zielona GÃ³ra | Gubin | Substation | AC | 0 | 400 | >2030 | Under Consideration | PSE S.A. | n.a. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
|  | 1273 | 229 | Zielona GÃ³ra-Gubin | Zielona GÃ³ra | n.a. | Overhead Line | AC | 60 | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
|  | 1275 | 229 | Gubin - Eisenhuettenstadt | Gubin (PL) | Baczyna (PL) | Overhead Line | AC | 20 | 400 | >2030 | Under Consideration | PSE S.A. | 50Hertz | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
|  | 1274 | 229 | Gubin | Gubin | Eisenhuettenstadt (DE) | Substation | AC | 0 | 400 | >2030 | Under Consideration | PSE S.A. | n.a. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
|  | 1270 | 229 | Baczyna-Zielona GÃ³ra | Baczyna-Plewiska indentation | Baczyna-Plewiska indentation | Overhead Line | AC | 40 | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
230 | #REF! | 355 | 230 | MikuÅ‚owa - Åšwiebodzice | MikuÅ‚owa (PL) | n.a. | Overhead Line | AC | 100 | 400 | 2023 | Planned but not yet permitting | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
|  | 353 | 230 | Krajnik-Baczyna | Krajnik (PL) | Åšwiebodzice (PL) | Overhead Line | AC | 70 | 400 | 2021 | In Permitting | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
|  | 1035 | 230 | Baczyna | Baczyna | Plewiska | Substation | AC | 0 | 400 | 2020 | Under Construction | PSE S.A. | n.a. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
|  | 1232 | 230 | Baczyna-Plewiska | Baczyna | Tiengen (DE) | Overhead Line | AC | 142 | 400 | 2024 | Planned but not yet permitting | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
231 | #REF! | 1235 | 233 | Conceptual project | - | Dunowo (PL) | Overhead Line | AC | 0 | 400 | 2027 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
|  | 1236 | 234 | DKE-PL-1 | AvedÃ¸re (DKE) | "GroÃŸgartach, Grafenrheinfeld" | Subsea Cable | DC | 330 | 400 | >2030 | Under Consideration | Energinet | PSE | FALSE | Denmark | Poland | 0 | DK - PL | FALSE | BS,NS
233 | #REF! | 664 | 235 | HVDC Line C | "BrunsbÃ¼Âttel, Wilster" | Mercator (BE) | Overhead Line | DC | 700 | 520 | 2025 | In Permitting | TenneT-DE | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
234 | #REF! | 608 | 236 | HTLS upgrade Horta-Mercator | Horta (BE) | Tuovila (FI) | Overhead Line | AC | 50 | 380 | 43830 | Under Construction | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
235 | #REF! | 1241 | 239 | Fenno-Skan 1 renewal | Hjalta (SE2) | Wolmirstedt (DE) | Subsea Cable | DC | 200 | 300 | 2029 | Under Consideration | SVK | FINGRID | FALSE | Finland | Sweden | 0 | FI - SE | FALSE | BS
236 | #REF! |  | 240 | AC Enhancement GÃ¼strow-Wolmirstedt |  |  | Underground Cable | AC |  |  |  | In Permitting |  |  | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
239 | #REF! | 1276 | 241 | Upgrading of existing 220 kV line between SS Dakovo (HR) and TPP Tuzla (BA) to 400 kV line | Dakovo | Gradacac | Overhead Line | AC | 91 | 400 | 48579 | Under Consideration | HOPS | NOS BIH | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
240 | #REF! | 1277 | 241 | Upgrading of existing 220 kV line between SS Dakovo (HR) and Gradacac (BA) to 400 kV line | Dakovo | Dakovo | Overhead Line | AC | 46.2 | 400 | 48579 | Under Consideration | HOPS | NOS BIH | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
241 | #REF! | 1278 | 241 | Upgrading existing 220 kV SS Dakovo to 400 kV | Dakovo | Razbojiste | Substation | AC | 0 | 400 | 48579 | Under Consideration | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
|  | 1279 | 241 | New double 400 kV line between SS Dakovo and location Razbojiste | Dakovo | TPP Tuzla (BA) | Overhead Line | AC | 25 | 400 | 48579 | Under Consideration | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
|  | 194 | 242 | Offshore Connection Cluster 1 | OWF Cluster Baltic Sea East (DE) | Sombor | Subsea Cable | AC | 115 | 220 | 2018 | Under Construction | 50Hertz | 50Hertz | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 1269 | 243 | New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | Ernestinovo | Uchtelfangen (DE) | Overhead Line | AC | 70 | 400 | 49310 | Under Consideration | HOPS | EMS | FALSE | Croatia | Serbia | 0 | HR - RS | FALSE | CSE
|  | 1245 | 244 | Vigy - Uchtelfangen (or beyond) | Vigy (FR) | Uchtelfangen (DE) | Overhead Line | AC | 65 | 400 | 2027 | Planned but not yet permitting | Rte | Amprion | FALSE | France | Germany | 0 | FR - DE | FALSE | CSW,NS,CCS
|  | 1246 | 245 | Upgrade Meeden - Diele | Meeden [NL] | Barnabos (FR) | Overhead Line | AC | 27 | 380 | 2019 | Under Construction | TENNET-NL | TENNET-DE | FALSE | Netherlands | Germany | 0 | NL - DE | FALSE | NS,CCS
242 | #REF! | 1381 | 247 | AQUIND Interconnector | Lovedean (GB) | Lubmin (DE) | Subsea Cable | DC | 250 | 320 | 2022 | In Permitting | National Grid plc | RÃ©seau de transport d'Ã©lectricitÃ© | TRUE | France | Great Britain | 0 | FR - GB | FALSE | CSW,NS
243 | #REF! | 1248 | 248 | Offshore Connection Cluster 2 | OWF Cluster Baltic Sea (DE) | SiedenbrÃ¼nzow/Alt Telin/Bartow (DE) | Subsea Cable | AC | 115 | 220 | 2022 | In Permitting | 50Hertz | 50Hertz | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
244 | #REF! | 1384 | 250 | "Merchant line ""Castasegna (CH) - Mese (IT)""" | Castasegna | Hamburg/Nord (DE) | Underground Cable | AC | 0 | 220 | 2021 | In Permitting | swissgrid | Terna | TRUE | Italy | Switzerland | 0 | IT - CH | FALSE | CSE,CCS
|  | 147 | 251 | Dollern - Hamburg/Nord | Dollern (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 45 | 380 | 2018 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
245 | #REF! | 148 | 251 | Audorf - Hamburg/Nord | Audorf (DE) | Gramme | Overhead Line | AC | 65 | 380 | 2017 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
247 | #REF! | 1050 | 252 | Van Eyck - Gramme: HTLS upgrade | Van Eyck | Van Eyck (BE) | Overhead Line | AC | 90 | 380 | 47483 | Under Consideration | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
248 | #REF! |  | 252
|  | 1224 | 253 | Uprate of Creys-St Vulbas | Creys(FR) | Cornier (FR) | Overhead Line | AC | 21 | 400 | 2031 | Under Consideration | RTE | RTE | FALSE | France | Switzerland | 0 | FR - CH | FALSE | CSW,NS,CCS
|  | 1225 | 253 | PST in Cornier | Cornier (FR) | Philippsburg (DE) | Phase Shift Transformer | AC | 0 | 400 | 2031 | Under Consideration | RTE | RTE | FALSE | France | Switzerland | 0 | FR - CH | FALSE | CSW,NS,CCS
250 | #REF! | 660 | 254 | HVDC Line A South - Ultranet | Osterath (DE) | Ichaso | Overhead Line | DC | 340 | 400 | 44197 | In Permitting | Amprion | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
251 | #REF! | 1251 | 255 | New line 400 kV Muruarte-Ichaso | Muruarte | Ichaso | Overhead Line | AC | 145 | 400 | 2023 | In Permitting | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
|  | 667 | 258 | BrunsbÂttel - KlixbÃ¼ll | BrunsbÂÃ¼ttel (DE) | Oradea | Overhead Line | AC | 125 | 380 | 2019 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
252 | #REF! | 1205 | 259 | HU-RO | JÃ³zsa | TBD | Overhead Line | AC | 0 | 400 | >2030 | Under Consideration | MAVIR | Transelectrica | FALSE | Hungary | romania | 0 | HU - RO | FALSE | CSE,CCE
|  | 1255 | 260 | Interconnector GB-NL | TBD | Rilland (NL) | Subsea Cable | DC | 0 | 0 | 2030 | Under Consideration | National Grid | TENNET-NL | FALSE | Great Britain | Netherlands | 0 | GB - NL | FALSE | NS
|  | 1257 | 262 | Belgium-Netherlands: Zandvliet-Rilland | Zandvliet (BE) | Grynau & Bonaduz | Overhead Line | AC | 10 | 380 | 2022 | Planned but not yet permitting | ELIA | TENNET-NL | FALSE | Belgium | Netherlands | 0 | BE - NL | FALSE | NS
|  | 1258 | 263 | RÃ¼Âthi - Bonaduz/Grynau | RÃ¼Âthi | xx | Overhead Line | AC | 0 | 380 | 2035 | Under Consideration | Swissgrid | Swissgrid | FALSE | Switzerland | austria | germany | CH - AT | FALSE | NS,CCS
|  | 1583 | 263 | Vorarlberg | Rüthi | Border area (DE-AT) | Overhead Line | AC | 1 | 380 | 2035 | Under Consideration | Swissgrid | VUEN | FALSE | Switzerland | austria |  | CH - AT | FALSE | CCS
253 | #REF! | 1284 | 264 | Pradella - La Punt | Pradella | MÂhleberg | Overhead Line | AC | 49 | 380 | 2021 | Under Construction | Swissgrid | Swissgrid | FALSE | Switzerland |  |  |  | TRUE | CCS
|  | 1288 | 264 | Mettlen - Ulrichen | Mettlen | Ulrichen | Overhead Line | AC | 0 | 220 | 45658 | Planned but not yet permitting | xx | xx | FALSE | Switzerland |  |  |  | TRUE | CCS
254 | #REF! | 1259 | 264 | Beznau - Mettlen | Beznau | La Punt | Overhead Line | AC | 64 | 380 | 2025 | In Permitting | Swissgrid | Swissgrid | FALSE | Switzerland |  |  |  | TRUE | CCS
255 | #REF! | 1287 | 264 | Bassecourt - MÂhleberg | Bassecourt | Ulrichen | Overhead Line | AC | 0 | 380 | 45658 | In Permitting | xx | xx | FALSE | Switzerland |  |  |  | TRUE | CCS
|  | 1289 | 265 | Lago Bianco connection | xx | xx | Overhead Line | AC | 0 | 380 | 47119 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
256 | #REF! | 1290 | 265 | Magadino - Ulrichen | xx | Chamoson | Overhead Line | AC | 0 | 380 | 47119 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
|  | 1260 | 265 | Grimsel connection | Innertkirchen | xx | Overhead Line | AC | 0 | 380 | 47119 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
258 | #REF! | 1285 | 266 | Magadino | xx | Lavorgo | Overhead Line | AC | 0 | 0 | 43466 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
259 | #REF! | 1286 | 266 | Chippis - Lavorgo | Chippis | GueÂstrow (DE) | Overhead Line | AC | 0 | 380 | 45292 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
260 | #REF! | 1261 | 266 | Bickigen - Chippis - Chamoson | Bickigen | xx | Overhead Line | AC | 0 | 380 | 2021 | Under Consideration | Swissgrid | Swissgrid | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
262 | #REF! | 1262 | 267 | Hansa PowerBridge II | Hurva (SE4) | Aljarafe | Subsea Cable | DC | 300 | 300 | 2030 | Under Consideration | Svenska Kraftnat | 50Hertz | FALSE | Sweden | Germany | 0 | SE - DE | FALSE | BS,NS
263 | #REF! | 1229 | 269 | Uprate Aljarafe-Santiponce | Aljarafe | Marsillon | Overhead Line | AC | 13 | 220 | 2019 | In Permitting | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
|  | 1228 | 269 | Uprate D.Rodrigo-Aljarafe | "D.Rodrigo " | Santiponce | Overhead Line | AC | 33.7 | 220 | 2019 | Under Construction | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
264 | #REF! | 1215 | 270 | Aragon region subestation | Aragon region | 0 | Substation | AC | 0 | 400 | 45658 | Planned but not yet permitting | REE | REE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS,CCS
|  | 1214 | 270 | Ejea de los Caballeros subestation | "Ejea de los Caballeros " | Aragon region | Substation | AC | 0 | 400 | 45658 | Planned but not yet permitting | REE | REE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS,CCS
|  | 1212 | 270 | New axis Ejea-Aragon region 400 kV | "Ejea de los Caballeros " | "Ejea de los Caballeros" | Overhead Line | AC | 110 | 400 | 46023 | Planned but not yet permitting | REE | REE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS
|  | 1211 | 270 | HVDC Aragon region -Marsillon | "Aragon region" | AragÂ¢n region | Underground Cable | DC | 230 | 320 | 46023 | Planned but not yet permitting | REE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS
265 | #REF! | 1206 | 276 | HVDC Pamplona area -Cantegrit | Pamplona area | Saucats | Underground Cable | DC | 225 | 320 | 46357 | Planned but not yet permitting | REE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW
266 | #REF! | 1208 | 276 | Upgrade Cantegrit-Marsillon | Cantegrit | "Pamplona area" | Overhead Line | AC | 80 | 400 | 2026 | Planned but not yet permitting | RTE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW
|  | 1207 | 276 | Upgrade Cantegrit-Saucats | Cantegrit | Marsillon | Overhead Line | AC | 70 | 400 | 2026 | Planned but not yet permitting | RTE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW
|  | 1210 | 276 | New substation Pamplona area | "Pamplona area " | Gramme (BE) | Substation | AC | 0 | 400 | 45658 | Planned but not yet permitting | REE | REE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW
267 | #REF! | 1008 | 280 | Study Lonny-Achene-Gramme | Lonny (FR) | Exeter | Phase Shift Transformer | AC | 0 | 400 | 2025-2030 | Under Consideration | RTE | ELIA | FALSE | France | Belgium | 0 | FR - BE | FALSE | CSW,NS
269 | #REF! | 1378 | 283 | TuNur DC | Rejim Maatoug (TN) VSC HVDC - 400 kV AC +/- 500 kV DC â€“ 2x 1GW | Montalto di Castro (IT) Terna station 400 kV AC | Subsea Cable | DC | 1265 | 500 | 2025 | In Permitting | TuNur Limited | TuNur Limited | TRUE | Tunisia | Italy | 0 | TN - IT | FALSE | CSE,CCS
|  | 1383 | 285 | GridLink | Kingsnorth (UK) | Pembroke | Subsea Cable | DC | 156 | 0 | 2022 | In Permitting | National Grid | RTE | TRUE | United Kingdom | France | 0 | GB - FR | FALSE | NS
270 | #REF! | 1385 | 286 | Greenlink | Great Island | LEVITHA | Subsea Cable | DC | 195 | 320 | 2023 | Planned but not yet permitting | National Grid | EirGrid | TRUE | Ireland | United Kingdom | 0 | IE - GB | FALSE | NS
|  | 1432 | 293 | Southern Aegean Interconnector | LEVITHA | Syrna | Subsea Cable | DC | 250 | 320 | 2026 | In Permitting | no | yes | TRUE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
|  | 1433 | 293 | Southern Aegean Interconnector | Levitha | LEVITHA | Subsea Cable | AC | 81 | 220 | 2025 | In Permitting | no | no | TRUE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
|  | 1431 | 293 | Southern Aegean Interconnector | LAVRIO | KORAKIA CRETE | Subsea Cable | DC | 245 | 320 | 2024 | In Permitting | yes | no | FALSE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
271 | #REF! | 1434 | 293 | Southern Aegean Interconnector | KINAROS | Syrna | Subsea Cable | AC | 14 | 220 | 2024 | In Permitting | no | no | TRUE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
276 | #REF! | 1435 | 293 | Southern Aegean Interconnector | Kandeliousa | Pergousa | Subsea Cable | AC | 34 | 220 | 2025 | In Permitting | no | no | FALSE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
|  | 1436 | 293 | Southern Aegean Interconnector | Kandeliousa | tba near Bergen-Mongstad or Karsto- Blafalli | Subsea Cable | AC | 14 | 220 | 2025 | In Permitting | no | no | FALSE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
|  | 1356 | 294 | Maali | Kergord Shetland | Gatica/Hernani, Cordemais and Langage/Indian Queens | Subsea Cable | DC | 400 | 320 | 2025 | Under Consideration | National Grid / Scottish Hydro Electric Transmission | Stattnett | TRUE | United Kingdom | Norway | 0 | GB - NO | FALSE | BS,NS
|  | 445 | 297 | BRABO II: Zandvliet - Lillo - Liefkenshoek | Zandvliet | Mercator (BE) | Overhead Line | AC | 18 | 380 | 44196 | In Permitting | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
280 | #REF! | 605 | 297 | BRABO II: Lillo 380 | Lillo (BE) | Suvereto | Substation | AC | 0 | 380 | 43555 | Under Construction | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
283 | #REF! | 604 | 297 | BRABO III: Liefkenshoek - Mercator | Liefkenshoek (BE) | Lillo (BE) | Overhead Line | AC | 19 | 380 | 44927 | In Permitting | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
|  | 1458 | 299 | SACOI3 | Codrongianos - Lucciana | Suvereto | Subsea Cable | DC | 300 | 200 | 2023 | In Permitting | TERNA | RTE | FALSE | Italy | France |  | IT - FR | FALSE | CCS
284 | #REF! |  | 309 | Neuconnect |  |  | Subsea Cable | DC | 680 | 400 | 2023 | In Permitting |  |  | TRUE | United Kingdom | Germany |  | GB - DE | FALSE | NS,CCS
285 | #REF! | 1472 | 312 | St. Peter - Tauern (AT internal) | St. Peter | Tauern | Overhead Line | AC | 128 | 380 | 2022 | In Permitting | APG | APG | FALSE | Austria |  |  |  | TRUE | CCE,CCS,CCE
286 | #REF! | 1473 | 313 | Isar/Altheim/Ottenhofen - St. Peter | Isar/Altheim/Ottenhofen (DE) | St. Peter (AT) | Overhead Line | AC | 90 | 380 | 2021 | In Permitting | TenneT-DE | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CCE,NS,CCS
|  | 1617 | 316 | Upgrade of 220 kV line Divaca-Bericevo to 400 kV | Divaca | Bericevo | Overhead Line | AC | 80 | 400 | 2030 | Under Consideration | ELES | ELES | FALSE | Slovenia | 0 | 0 |  | FALSE | CCE
293 | #REF! | 1615 | 317 | Upgrade of internal 220 kV line Podlog-Bericevo to 400 kV | Podlog | Bericevo | Overhead Line | AC | 63 | 400 | 2035 | Under Consideration | ELES | ELES | FALSE | Slovenia | 0 | 0 |  | FALSE | CCE
|  | 1614 | 318 | Upgrade of 220 kV line Podlog-Cirkovce to 400 kV | Podlog | Cirkovce | Overhead Line | AC | 50 | 400 | 2035 | Under Consideration | ELES | ELES | FALSE | Slovenia | 0 | 0 |  | FALSE | CCE
|  | 1475 | 321 | Herbertingen - Tiengen | Herbertingen | Tiengen | Overhead Line | AC | 138 | 380 | 2025 | Planned but not yet permitting | Amprion / TransnetBW | Amprion / TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
|  | 1476 | 322 | Wullenstetten - Border Area (DE-AT) | Wullenstetten (DE) | Austrian National border (AT) | Overhead Line | AC | 88 | 380 | 2020 | In Permitting | Amprion | Amprion / vuen/ APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CCE, CCS
|  | 1477 | 322 | Herbertingen - Neuravensburg | Herbertingen | Neuravensburg | Overhead Line | AC | 56 | 380 | 2020 | Planned but not yet permitting | Amprion | Amprion | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CCE, CCS
|  | 1478 | 323 | Dekani (SI) - Zaule (IT) interconnection | DEKANI | ZAULE | Underground Cable | AC | 11 | 110 | 2020 | In Permitting | ELES D.O.O. | TERNA SPA | FALSE | Slovenia | Italy | 0 | SI - IT | FALSE | CCE
294 | #REF! | 1482 | 324 | Redipuglia (IT) - Vrtojba (SI) Interconnection | REDIPUGLIA | VRTOJBA | Underground Cable | AC | 22.5 | 110 | 2020 | In Permitting | TERNA SPA | ELES D.O.O. | FALSE | Italy | Slovenia | 0 | IT - SI | FALSE | CSE,CCS
297 | #REF! | 1483 | 325 | Upgrade Obersielach (AT) - Podlog (SI) (finalisation after approval of APG's Board Members) | Obersielach (AT) | Podlog (SI) | Overhead Line | AC | 70 | 380 | 2035 | Under Consideration | APG | ELES | FALSE | Italy | Austria | 0 | IT - AT | FALSE | CCE, CCS,CCE
|  | 1800 | 325 | Lienz - Obersielach (AT Internal, mandatory requirement for NTC increases on AT-IT and AT-SI border) | Lienz (AT) | Obersielach (AT) |  | AC | 170 | 380 | 2027 | Planned but not yet permitting | APG | APG | FALSE | Austria |  |  | AT | TRUE | CCE, CCS,CCE
|  | 1631 | 325 | Lienz - Italy (AT - IT) | Lienz | Veneto Region | Overhead Line | AC | 140 | 380 | 2035 | Under Consideration | TERNA | APG | FALSE | ITALY | Austria |  | IT - AT | FALSE | CCE, CCS,CCE
299 | #REF! | 1630 | 328 | AC Overhead Line Aach-Bofferdange | Aach (DE) | Bofferdange (LU) | Overhead Line | AC | 38 | 400 | 2026 | Planned but not yet permitting | AMPRION | CREOS | FALSE | Germany | Switzerland |  | DE - CH | FALSE | CCS,CCE
309 | #REF! | 1518 | 329 | Stevin-Izegem/Avelgem: new corridor | Stevin | Avelgem | Overhead Line | AC | 60 | 380 | 2028 | Under Consideration | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
312 | #REF! | 1498 | 330 | New CZ-SK 400 kV interconnector | Otrokovice (CZ) | Ladce (SK) | Overhead Line | AC | 78 | 400 | 2035 | Under Consideration | CEPS | SEPS | FALSE | Czech Republic | slovakia | 0 | CZ - SK | FALSE | CCE
313 | #REF! | 1506 | 335 | Interconnection NL Maasvlakte to Power Link Island | Maasvlakte 380 kV | Power Link Island NL1 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT TSO NL | TenneT TSO NL | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
316 | #REF! | 1509 | 335 | Interconnection DE (area of Oldenburg) to Power Link Island | German substation located in the area of Oldenburg | Power Link Island DE2 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT-DE | TenneT-DE | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
317 | #REF! | 1511 | 335 | Interconnection DE (area of KrÃ¼mmel) to Power Link Island | German substation located in the area of KrÃ¼mmel | Power Link Island DE3 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT-DE | TenneT-DE | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
318 | #REF! | 1508 | 335 | Interconnection DE (area of BrunsbÃ¼ttel) to Power Link Island | German substation located in the area of BrunsbÃ¼ttel (north of the Elbe) | Power Link Island DE1 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT-DE | TenneT-DE | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
320 | #REF! | 1505 | 335 | Interconnection DKw to Power Link Island | Endrup, DKw | Power Link Island DKw | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | Energinet | Energinet | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
321 | #REF! | 1507 | 335 | Interconnection NL Eemshaven to Power Link Island | Eemshaven 380 kV | Power Link Island NL2 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT TSO NL | TenneT TSO NL | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
322 | #REF! | 1556 | 336 | Prati (IT) Â– Steinach (AT) | Prati di Vizze (IT) | Steinach (AT) | Overhead Line | AC | 139 | 132 | 2019 | Under Construction | TERNA | TINETZ | FALSE | ITALY | austria | 0 | IT - AT | FALSE | CSE,CCS
|  | 1512 | 337 | Conneforde - Cloppenburg | Conneforde (DE) | Cloppenburg (DE) | Overhead Line | AC | 60 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
323 | #REF! | 1510 | 337 | Cloppenburg East - Merzen | Cloppenburg East (DE) | Merzen (DE) | Overhead Line | AC | 55 | 380 | 2024 | Planned but not yet permitting | TenneT-DE | Amprion | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
324 | #REF! | 1521 | 338 | new HVDC line between Villanova and Fano existing 400 kV substations | Villanova | Fano | Subsea Cable | DC | 0 | 500 | 2030 | Under Consideration | Terna | Terna | FALSE | Italy |  |  |  | FALSE | CSE,CCS
325 | #REF! | 1557 | 339 | Italian HVDC tri-terminal link | SARDINIA REGION | SICILY REGION - SOUTH OF ITALY | Subsea Cable | DC | 0 | 0 | 2025 | Under Consideration | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
|  | 1519 | 340 | Avelgem-Center: new corridor | Avelgem | Center (TBD) | Overhead Line | AC | 100 | 380 | 2028 | Under Consideration | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
|  | 1538 | 341 | New OHL 400 kV WPP Cibuk - SS Belgrade West | WPP Cibuk | Belgrade West | Overhead Line | AC | 60 | 400 | 2030 | Under Consideration | EMS | EMS | FALSE | Romania | serbia | 0 | RO - RS | FALSE | CSE,CCE
328 | #REF! | 1536 | 341 | Portile de Fier (RO) - Djerdap (RS) 2nd | Portile de Fier | Djerdap | Overhead Line | AC | 4 | 400 | 2030 | Under Consideration | Transelektrica | EMS | FALSE | Romania | serbia | 0 | RO - RS | FALSE | CSE,CCE
|  | 1520 | 342 | Sofia West (BG) - Nis 2 (RS) 2nd | SS Sofia West | SS Nis 2 | Overhead Line | AC | 80 | 40 | 2034 | Under Consideration | ESO | EMS | FALSE | Bulgaria | serbia | 0 | BG - RS | FALSE | CSE
|  | 1522 | 342 | Upgrade of exsisting OHL 220 kV to 400 kV SS Nis 2 - SS KruÂševac 1 | SS Nis 2 | SS Krusevac 1 | Overhead Line | AC | 40 | 400 | 2034 | Under Consideration | EMS | EMS | FALSE | Bulgaria | serbia | 0 | BG - RS | FALSE | CSE
329 | #REF! | 1524 | 342 | Upgrading of exsisting OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | SS Krusevac 1 | SS Kraljevo 3 | Overhead Line | AC | 50 | 400 | 2034 | Under Consideration | EMS | EMS | FALSE | Bulgaria | serbia | 0 | BG - RS | FALSE | CSE
330 | #REF! | 1533 | 343 | New OHL 400 kV Lika Â Â– Melina | Lika (HR) | Melina (HR) | Overhead Line | AC | 68 | 400 | 2030 | Planned but not yet permitting | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
|  | 1534 | 343 | New OHL 400 kV Lika Â Â– Konjsko | Lika (HR) | Konjsko (HR) | Overhead Line | AC | 200 | 400 | 2030 | Planned but not yet permitting | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
331 | #REF! | 1532 | 343 | New OHL 400 kV Banja Luka - Lika | Banja Luka (BA) | Lika (HR) | Overhead Line | AC | 155 | 400 | 2030 | Planned but not yet permitting | NOS BIH | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
332 | #REF! | 1541 | 344 | Zwolle-Hengelo-Doetinchem-Dodewaard | Zwolle | Dodewaard | Overhead Line | AC | 165 | 380 | 2035 | Under Consideration | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
333 | #REF! | 1542 | 345 | Northern East-West connection NL | tbd | tbd | Overhead Line | AC | 0 | 0 | 2040 | Under Consideration | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
335 | #REF! | 1544 | 346 | ZuidWest3808 Oost | Rilland | Tilburg | Overhead Line | AC | 80 | 380 | 2025 | In Permitting | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
|  | 1543 | 346 | ZuidWest380 West | Borssele | Rilland | Overhead Line | AC | 40 | 380 | 2021 | Under Construction | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
|  | 1545 | 347 | Maasvlakte Â– Noord Brabant connection | Krimpen | Geertruidenberg | Overhead Line | AC | 0 | 0 | 2040 | Under Consideration | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
|  | 1546 | 348 | NoordWest380 | Eemshaven Oude Schip | Vierverlaten | Overhead Line | AC | 40 | 380 | 2021 | Under Construction | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
|  | 1622 | 350 | 400kV OHL SS Bitola - SS Elbasan | Bitola | Elbasan | Overhead Line | AC | 161 | 400 | 2020 | In Permitting | MEPSO | OST | FALSE | GREECE | Albania |  | GR - AL | FALSE | CSE
|  | 1547 | 351 | Eastern HVDC Link | Peterhead (GB) | Hawthorn Pit (GB) | Subsea Cable | DC | 365 | 500 | 2024 | Under Consideration | SHETL | NGET | FALSE | United Kingdom |  |  |  | TRUE | NS
|  | 1555 | 375 | Lienz (AT) - Veneto region (IT) | Lienz (AT) | Veneto region (IT) | Overhead Line | AC | 140 | 220 | 2024 | In Permitting | APG | TERNA | FALSE | Italy | austria | 0 | IT - AT | FALSE | CSE,CCS
336 | #REF! | 1555 | 375 | Lienz (AT) - Veneto region (IT) | Lienz (AT) | Veneto region (IT) | Overhead Line | AC | 140 | 220 | 2024 | In Permitting | APG | TERNA | FALSE | Austria | Italy |  | AT - IT |  | CSE,CCE
337 | #REF! | 1559 | 376 | New investment | Bitola (MK) | Meliti (GR) | Overhead Line | AC | 35.512 | 400 | 2030 | Under Consideration | MEPSO | IPTO | FALSE | Greece | macedonia | 0 | GR - MK | FALSE | CSE
|  | 1561 | 377 | BE-NL interconnector: upgrade VanEyck-Maasbracht | VanEyck | Maasbracht | Overhead Line | AC | 12 | 380 | 2030 | Under Consideration | Elia | TENNET-NL | FALSE | Belgium | netherlands | 0 | BE - NL | FALSE | NS
338 | #REF! | 1597 | 379 | Uprate Gatica-Azpeitia | Gatica | Azpeitia | Overhead Line | AC | 57 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
339 | #REF! | 1593 | 379 | Uprate Gatica-Guenes | Gatica | Guenes | Overhead Line | AC | 38.8 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
340 | #REF! | 1595 | 379 | Uprate Gatica-Amorebieta-Ichaso | Gatica | Ichaso | Overhead Line | AC | 69.12 | 400 | 2021 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
341 | #REF!
342 | #REF!
343 | #REF!
344 | #REF!
345 | #REF!
346 | #REF!
347 | #REF!
348 | #REF!
349 | #REF!
350 | #REF!
351 | #REF!
375 | #REF!
376 | #REF!
377 | #REF!
378 | #REF!
379 | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Sheet6 (hidden)
Id | Name | Description | SubmissionId | CreatedAt | UpdatedAt | IsCrossBorder | CountryList | ExpectedCommissioningDate | Motivation | UsefulInformation | Capex | Opex | EnvironmentalImpact | ProjectPromoter1 | ExpectedCapicityTransfer | PCI | NationalPlanAdvanced | NationalPlanConsideration | AgreementFileName | AgreementValidated | ExemptionProcessValidated | TsoAgreement | StudiesUnderConstructionFileName | TimelineForImplement | ExemptionProcessFileName | AttachmentFileName | InternalProject | ExpectedCapicityTransferExplanation | PCIValidated | NationalPlanAdvancedValidated | NationalPlanConsiderationValidated | StudiesUnderConstruction | TsoAgreementFilename | TsoAgreementValidated | StudiesUnderConstructionValidated | LocationFilename | IsSubmitted | SpocName | SpocEmail | SpocNumber | CreatedBy | UpdatedBy | Status | ReadyToSubmit | HaveEmptyMandatory | LocationUrl | AttachmentUrl | AgreementUrl | ExemptionProcessUrl | StudiesUnderConstructionUrl | TsoAgreementUrl
1 | RES in north of Portugal | The main objective of this project consists in introducing the network reinforcements that are needed to allow the connection of new RES generation (hydro with pumping and also wind) that is foreseen in the north of Portugal, where the RES potential is high. The project includes a set of new 400 kV OHL that will form a new axis between V. Minho-R. Pena-Fridão-Feira. A new 400 kV OHL Pedralva-Sobrado (PCI 2.16.1) is also included in this cluster, in order to ensure the maintenance of the NTC values between PT and ES that were available prior to the connection of these new power plants. | 221 | 1899-12-31 | 2018-01-11 15:53 | FALSE | Internal boundary in Portugal inside-outside | 2022 | This project integrates new amounts of hydro power plants in the northern region of Portugal and at same time creates better conditions to evacuate wind power that is already in operation and also new wind farms with authorization for connection. These new amounts of power will increase the flows in the region, and it is expected that the new flows could reach 3500 MW in the future, which must be evacuated to the littoral strip and south of Portugal, where the major consumption areas are located, through three new 400 kV independent routes as the existing network supported in the 150 kV and 220 kV is not adequate. Part of these flows will interfere and accumulate with the already existent flows entering in Portugal through the international interconnections with Spain on the north, namely the 400 kV Cartelle (ES)-Alto Lindoso (PT)-Riba d’Ave (PT)-Recarei (PT). This project includes a set of new 400 kV OHL that will form a new axis between V. Minho-R. Pena-Fridão-Feira, ensuring the network capacity to evacuate the new amounts of generation, while taking into consideration the N-1 security criteria. The new substations of R. Pena and Fridão are also included in this axis for the direct connection of the new power plants. A new OHL between the already in service substation of Pedralva and the future of Sobrado (PCI 2.16.1 Internal line between Pedralva and Sobrado) is also included in this cluster, in order to ensure the maintenance of the NTC values between PT and ES that were available prior to the connection of these new power plants (1400 MW of installed power). In fact, due to the location of these new hydro power plants (near the PT-ES border) as well as the location of their network connection points (near existing interconnection axis between Minho (PT) and Galiza (ES)) it was identified that additional congestions may occur in some situations due to the new production. These congestions would lead to a reduction in the NTC values between Portugal and Spain (-500 MW ES->PT) not compatible with the needs of the Iberian Market and the Internal Energy Market (IEM). | Portuguese National Development Plan http://www.erse.pt/pt/consultaspublicas/consultas/Documents/53_Proposta%20PDIRT-E_2015/PDIRT%202016-2025%20-%20Junho%202015%20-%20Relat%C3%B3rio.pdf PCI page – link to EC platform: http://ec.europa.eu/energy/infrastructure/transparency_platform/map-viewer/m/main.html Clustering: This project includes a set of new 400 kV OHL that will form a new axis between P. Lima-Pedralva-V. Minho-R. Pena-Fridão-Feira, ensuring the network capacity to evacuate the new amounts of generation, taking also into consideration the n-1 security criteria. The new substations of R. Pena and Fridão are also considered in this axis for direct connection of generation. A new line between Pedralva and Sobrado is also included in this cluster, in order to ensure the maintenance of the NTC values between PT and ES that were available prior to the connection of the new generation. | 2011 | 200 | Negligible or less than 15km | REN | Direction A: 2500-2900 - Direction B: 3100-4200 | 2.16.1 and 2.16.3 |  | PDIRT 2018-27, reference PR0911 and PR0914 |  | FALSE | FALSE |  |  |  |  | 63c23ebc-0a53-4e87-8bdd-5e5abf61bd51.docx | TRUE | RES integration, Market integration | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Fernando Batista | fernando.batista@ren.pt | +351 210013419 |  | fbatista@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/1/download/Attachment
4 | Interconnection Portugal-Spain | In order to reach a complete operational Iberian Electricity Market (MIBEL), and strengthening the Internal Energy Market (IEM), the increase of the interconnection between Spain and Portugal is needed. A new OHL 400kV interconnection between Fontefría (Spain) and Ponte de Lima (Portugal). Internal reinforcements complement the cross border section, such as the axis in Spain between Fontefría and Beariz and in Portugal between Ponte de Lima (previously Viana do Castelo) and Vila Nova de Famalicão (previously Vila doConde).This project was included in the 2013, 2015 and 2017 PCI list (PCI 2.17). | 225 | 1899-12-31 | 2018-01-15 10:53 | TRUE | Portugal - Spain | 2020-2021 | In 2006 the Spanish and Portuguese governments set the goal to reach 3000 MW of exchange capacity in the ES-PT border (in both directions) in order to reach a complete operational Iberian Electricity Market (MIBEL). It has been identified the need to have, in 2010, two new interconnections, one in the south and another in the north. In 2014 the new Southern interconnection Puebla de Guzmán (ES) – Tavira (PT) entered into full operation, reinforcing the capacity, mainly in the direction from Portugal to Spain, and reducing the congestion level in around 6%. However, the Spain to Portugal direction still needs to overcome existing (and future) restrictions in the northern part of the border. In fact according to the market studies performed in TYNDP 2016 framework it is expected that this direction will be the most used in the following decade. Although the congestion rate in the Spain to Portugal direction in 2014 was low (4%), without this new project it can increase up to 17%-53% in 2030 (depending on the scenario), while with the new project the congestions are limited to 3%-9% in 2030 (depending on the scenario). The Declaration of Madrid of the Energy Interconnection Links Summit among the Governments of France, Spain and Portugal, the EC and the EIB, highlights the urgency of implementing the already planned interconnections Portugal-Spain and Spain-France and conduct further investigations aiming at developing electrical interconnection projects in order to reach 8 GW capacity for the France-Spain border in order to meet the ambitious deadline of achieving the interconnection objective by 2020. | Clustering: the project consists on a set of investments in the same transport corridor, based on a 400 kV OHL axis linking the substations of Beariz and Fontefría, in Spain, with P. Lima-V. N. Famalicão-Recarei/Vermoim, in Portugal. These reinforcements are all needed (as they are in series) to achieve the main objectives of the project: reinforcement of the interconnection capacity between Portugal and Spain having in mind the MIBEL targets agreed by the Portuguese and Spanish governments and also to allow Portugal to achieve the 10% interconnection ratio defined by the EC, both contributing for the IEM.? Project website http://www.ree.es/es/actividades/gestor-de-la-red-y-transportista/proyectos-de-interes-comun-europeos-pic ; http://www.ren.pt/pt-PT/o_que_fazemos/projetos_interesse_2015/ PCI page – link to EC platform http://ec.europa.eu/energy/infrastructure/transparency_platform/map-viewer/m/main.html Other links: Spanish National Development Planhttp://www.minetur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx Portuguese National Development Plan http://www.erse.pt/pt/consultaspublicas/consultas/Documents/53_Proposta%20PDIRT-E_2015/PDIRT%202016-2025%20-%20Junho%202015%20-%20Relat%C3%B3rio.pdf Inter-Governmental agreement (Madrid Declaration) https://ec.europa.eu/energy/sites/ener/files/documents/Madrid%20declaration.pdf Constitution of the High Level Group on Interconnections for South West Europe The High Level Group is responsible to prepare a plan to implement the Madrid Declaration and ensure regular monitoring of progress of the projects and provide adequate technical assistance to the Member states. The group will deal with both gas and electricity infrastructure. http://europa.eu/rapid/press-release_IP-15-5187_en.htm XXII Portuguese-Spanish Summit (main conclusions) Main conclusions from the XXII Portuguese-Spanish summit where both governments agreed to continue working on the definition and routes for two new interconnection in order to reach a interconnection capacity of 3000 MW by 2010 between both countries. http://www.erse.pt/pt/mibel/construcaoedesenvolvimento/Documents/CONCLUS%C3%95ES%20CIMEIRA_BADAJOZ_2006.pdf | 111.9 | 1.09 | Negligible or less than 15km | REE;REN | ES->PT 1300-1900 MW and PT->ES 700-1000 MW | 2.17 | in Spain 2015 NDP (reference TI-1, page 532); in Portugal PDIRT 2018-2027, (refrenece PR0709). |  |  | FALSE | FALSE |  |  |  |  | 15f95f28-60dc-4597-8634-c00da2d0c672.docx | FALSE | Cross border impact, Market integration, REs integration | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Patricia Labra (Laura Lopez as substitute) | plabra@ree.es (laura.lopez@ree.es) | 00346267774 (916508500 - Ext. 3192) |  | llopez@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/4/download/Attachment
13 | Baza project | " This Project includes a new double circuit Caparacena-Baza-La Ribina 400 kV OHL, in Spain with two new 400 kV substations in Baza and La Ribina. " | 225 | 1899-12-31 | 2018-01-15 11:26 | FALSE | inside-outside | 2025 | Needed to connect new RES generation in an área without transmission network. It will also alliviate congestion in a parallel transmission axis. | "Useful link: Spanish National Development Planhttp://www.minetur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx Clustering: the project consists of a new substation (Baza) and 2 double circuits that connect this new substation to the existing network (Baza-Caparacena and Baza La RIbina), as only one would not allow evacuation of generation in case of contingency or solving constraints in the parallel axis. La Ribina is a new subestion required to connect to the existing axis Litoral-Rocamora with the lowest impact in the territory. All the investments are in series so a lack of any of them do not allow to get the full GTC increase of the project." | 119.16 | 1.7874 | Negligible or less than 15km | REE | Direction A: 550-770 - Direction B: 3280-3630 |  | Spain NDP Planificación Energética.2015-2020 (Anexo II.1. Página 5) |  |  | FALSE | FALSE |  |  |  |  | d099d8e5-9501-4fe8-8bf5-1252b5ae8f08.docx | TRUE | Generation connection | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Laura López (REE) / Patricia Labra (REE) as substitute | laura.lopez@ree.es (plabra@ree.es) | 916508500 - Ext. 3192 |  | llopez@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/13/download/Attachment
16 | Biscay Gulf | " The project consist of 370 km HVDC-VSC link (2 bipoles of 1000 MW each) mainly subsea in the Biscay Gulf, between Gatica (Basque Counrty, ES) and Cubnezais (Aquitaine, FR). Included in the Madrid Declaration, this project aims at improving the interconnection" | 225 | 1899-12-31 | 2018-01-15 09:33 | TRUE | Spain - France | 2025 | Lack of cross border capacity between France and Spain is a historical need. this new interconnection will allow market integration as it will reduce Price differences and congestions between both countries, it will allow RES integration in the Iberian Peninsula, and it will secure system operation as with higher Cross border capacity the isolation of the iberian península will be improved, and therefore the strenght to overcome major incidents. This project was included in the 2013, 2015 and 2017 PCI list (PCI 2.7). | " Project website http://www.ree.es/es/actividades/gestor-de-la-red-y-transportista/proyectos-de-interes-comun-europeos-pic ; PCI page – link to EC platformhttp://ec.europa.eu/energy/infrastructure/transparency_platform/map-viewer/m/main.html Other links Spanish National Development Planhttp://www.minetur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx French National Development Planhttp://www.rte-france.com/fr/article/schema-decennal-de-developpement-de-reseau Inter-Governmental agreement (Madrid Declaration) https://ec.europa.eu/energy/sites/ener/files/documents/Madrid%20declaration.pdf Constitution of the High Level Group on Interconnections for South West Europe http://europa.eu/rapid/press-release_IP-15-5187_en.htm " | 1750 | 10.2 | Negligible or less than 15km | REE;RTE | Direction A: 2600 - Direction B: 2200 | 2.7 | Spain NDP Planificación Energética.2015-2020 (reference TI-2); France SDDR2016 Page 278 |  |  | FALSE | FALSE |  |  |  |  | d3a66b6c-ce0e-4823-ba5d-edfac69fe3f6.pdf | FALSE | cross border impact, market integration, res integration | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Patricia Labra (REE) (jean gabriel valentin in RTE) | plabra@ree.es (jean-gabriel.valentin@rte-france.com) | 00376267774 |  | llopez@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/16/download/Attachment
21 | Italy-France | "The Project comprises a new 320 kV HVDC interconnection between France and Italy. The new HVDC link will connect the substations of Piossasco and Grand Ile mainly along motor way infrastructures and the Fréjus tunnel." | 238 | 1899-12-31 | 2018-01-15 15:36 | TRUE | France - Italy | 2019 |  | "Link to Project page on RTE website http://www.rte-france.com/fr/projet/savoie-piemont-190-km-de-solidarite-europeenne-entre-chambery-et-turin Link to last release of the French National Development Plan http://www.rte-france.com/fr/article/schema-decennal-de-developpement-de-reseau Link to the last release of the Italian National Development Plan http://www.terna.it/it-it/sistemaelettrico/pianodisviluppodellarete/pianidisviluppo.aspx Link to EC Transparency Platform http://ec.europa.eu/energy/infrastructure/transparency_platform/map-viewer/m/main.html " | 1200 | 4.8 | Negligible or less than 15km | RTE;TERNA | Direction A (FR-IT): 1200 - Direction B (IT-FR): 1000 | Included in Third PCI list with label 2.5.1 |  |  |  | FALSE | FALSE |  |  |  |  | f2669a29-a5f8-49eb-861d-9cfbe14e5105.pdf | FALSE | The project will allow the increase of the energy flows between Italy and France via 1000-1200 MW of additional capacity | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +039 0683138020 |  | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/21/download/Attachment
23 | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | The project consists in the reconductoring of the existing 80km double-circuit 400kV AC cross-border line between Lille (Avelin/Mastaing, FR) - Avelgem (BE) and onwards to Zomergem (Horta, BE) with High Temperature Low Sag conductors to double its capacity. | 64 | 1899-12-31 | 2018-01-15 14:38 | TRUE | France - Belgium | 2022 |  | The project is integrated in RTE's 2016 National Development Plan:https://www.connaissancedesenergies.org/sites/default/files/pdf-pt-vue/sddr-2016_volet_national.pdf The project is integrated in Elia's National Development Plan 2015-2025:http://www.elia.be/fr/grid-data/grid-development/plans-d-investissements/federal-development-plan-2015-2025 | 140 | 0.4 | Negligible or less than 15km | ELIA; RTE | 1000 |  | Investment is integrated in national development plans RTE & ELIA |  |  | FALSE | FALSE |  |  |  |  | 24837495-8266-4b8c-be79-4b039611200a.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhout (Elia); Philippe Bodin (RTE) | steve.vancampenhout@elia.be; philippe.bodin@rte-france.com | +3225467226; +33320226795 |  | pbodin@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/23/download/Attachment
25 | IFA2 | IFA2 is a new HVDC VSC subsea interconnector that will develop between Tourbe in France (area of Caen) and Chilling in Great Britain (area of Southampton). | 209 | 1899-12-31 | 2018-01-12 13:12 | TRUE | France - Great Britain | 2020 |  | More information related to the project can be found on IFA2 project website. Added to general project statements, specific information are given for both sides of the Channel (Public consultation, phases of the project...). The project is also part of both French and British National Development Plans. In addition IFA2 project has been confirmed on 23 November 2017 as Project of Common Interest in the priority corridor Northern Seas Offshore Grid (NSOG), included in cluster 1.7. | 685 | 8.4 | 15-50km | NGIHL,RTE | 1000 | PCI 1.7.2 confirmed on 23/11/2017 | Project under construction |  |  | FALSE | FALSE |  |  |  |  | 69da12bf-5789-4709-8464-e6a00796a123.xlsx | FALSE | Market integration and RES integration | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Philippe Bodin | philippe.bodin@rte-france.com | +33320226795 |  | pbodin@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/25/download/Attachment
26 | Reschenpass Interconnector Project | New 220kV interconnector between the substations Nauders (AT) and Glorenza (IT) | 238 | 1899-12-31 | 2018-01-15 15:37 | TRUE | Austria - Italy | 2021 |  | National development plan APG: http://www.apg.at/de/netz/netzausbau/Netzentwicklungsplan National development plan Terna: http://www.terna.it/it-it/sistemaelettrico/pianodisviluppodellarete/pianidisviluppo.aspx | 180 | 2.7 | Negligible or less than 15km | APG; TERNA | AT-IT 300 MW, IT-AT 300 MW |  | http://download.terna.it/terna/0000/0109/45.pdf, http://www.apg.at/~/media/2B6A483B17124B949827750CD8A49840.pdf |  | 02f0119c-c278-4442-b98c-26b5ae4067a5.pdf | TRUE | FALSE |  |  |  |  | f8e92fd5-5ffb-4d49-aa1e-a2afed175a9d.pdf | FALSE | The project will allow the increase of the energy flows between Italy and Austria via 300MW of additional capacity | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | AGP: Stefan Führer / TERNA: Alessio Tonti | APG: stefan.fuehrer@apg.at / TERNA: alessio.tonti@terna.it | APG: +43 (1) 50 320 / 56361 / TERNA: +039 0683138020 |  | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/26/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/26/download/Agreement
28 | Italy-Montenegro | " The Italy-Montenegro interconnection project includes a new HVDC subsea cable between Villanova (Italy) and Lastva (Montenegro) and the DC converter stations. The HVDC link between Italy and Balkansis correlated with the Transbalkan Corridor (projects 146 and 227) and the Mid Continental East Corridor (project 144)." | 238 | 1899-12-31 | 2018-01-15 15:39 | TRUE | Italy - Montenegro | 2019/2026 |  | "PCI information: https://www.terna.it/it-it/sistemaelettrico/pianodisviluppodellarete/progettidiinteressecomune.aspx Link to the last release of the Italian National Development Plan: http://www.terna.it/it-it/sistemaelettrico/pianodisviluppodellarete/pianidisviluppo.aspx" | 1250 | 6.25 | Negligible or less than 15km | CGES;TERNA | 1200 | Included in Third PCI list with label 3.22.5 |  |  |  | FALSE | FALSE |  |  |  |  | 78e7e7f6-a8f4-421a-adef-e62adb595612.pdf | FALSE | The project will allow the increase of the energy flows between Italy and Montenegro via 1200 MW of new capacity | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 |  | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/28/download/Attachment
29 | Italy-Tunisia | "The project consists in a new interconnection between Tunisia and Sicily to be realized through an HVDC submarine cable. The realization of the project is supported by the Italian and Tunisian Governments to increase the interconnection capacity of the Euro-Mediterranean system. Moreover, the project will contribute to reduce, under specific conditions, present and future limitations to the power exchanges on the northern Italian border, with France, Switzerland, Austria and Slovenia, and therefore it will allow to significantly increase the transmission capacity and its exploitation by at least 500 MW on that boundary." | 238 | 1899-12-31 | 2018-01-15 15:40 | TRUE | Italy - Tunisia | 2025 |  | "Link to the last release of the Italian National Development Plan http://www.terna.it/en-gb/sistemaelettrico/pianodisviluppodellarete.aspx" | 600 | 3 | NA | TERNA; STEG | IT-TN: 600 MW; TN-IT: 600 MW | Included in Third PCI list with label 3.27 |  |  |  | FALSE | FALSE |  |  |  |  | a55ee0d2-c696-4bc2-990a-92f026e5c3ae.pdf | FALSE | The project will allow the increase of the energy flows between Italy and Tunisia via 600 MW of new capacity | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 |  | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/29/download/Attachment
31 | Italy-Switzerland | " The project consists of a new 400 kV line San Giacomo-Pallanzeno, conversion from AC to DC of the 220 kV line between Pallanzeno and Milan area, including the realization of the 2 AC/DC converter stations and 220 kV to 400 KV substation upgrade. Additional internal lines in Italy and in Switzerland are required to get the full advantage from the interconnection capacity provided by the cross-border line" | 238 | 1899-12-31 | 2018-01-15 15:41 | TRUE | Switzerland - Italy | 2025 |  | "PCI information: https://www.terna.it/it-it/sistemaelettrico/pianodisviluppodellarete/progettidiinteressecomune.aspx? " | 1100 | 5 | Negligible or less than 15km | SWISSGRID;TERNA | Direction A: 1000 - Direction B: 950 | Included in Third PCI list with label 2.15.1 |  |  |  | FALSE | FALSE |  |  |  |  | ef1dc2cb-c52d-4898-904e-446015e0acad.pdf | FALSE | The project will allow the increase of the energy flows between Italy and Switzerland via the additional transfer capacity | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 |  | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/31/download/Attachment
33 | Central Northern Italy | "The project consists in the strengthening of interconnection between the northern and the central part of Italy. It will involve the upgrading of existing 220 kV over-head line to 400 kV between Colunga and Calenzano substations as well as the removing of limitations on the existing 220 kV network in Central Italy" | 238 | 1899-12-31 | 2018-01-15 15:43 | FALSE | Italy Center- Italy South | 2022 |  | "Link to the last release of the Italian National Development Plan http://www.terna.it/en-gb/sistemaelettrico/pianodisviluppodellarete.aspx" | 360 | 5.4 | 15-50km | TERNA | 600 |  | http://download.terna.it/terna/0000/0109/45.pdf |  |  | FALSE | FALSE |  |  |  |  | 4440b4fa-22f0-4a9b-8ff6-2099f18b3c49.pdf | TRUE | The project will allow the increase of the energy flows between Italy North and Italy Central south via 400 - 600 MW of additional capacity | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 |  | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/33/download/Attachment
35 | CZ Southwest-east corridor | "A corridor of internal 400 kV overhead lines inside the Czech Republic connecting existing 420 kV substations between Prestice, Kocin, Mirovka and Cebin in the southwest-east direction. The project consists of buidling a new AC 400 kV overhead line which connects 420 kV substations Kocin and Mirovka with double circuit line of about 120.5 km lenght and a capacity of 2x1730 MVA, building of a 400 kV overhead lines that involves changing of a 400 kV existing single-ciruit line to double-circuit line with a capacity of 2x1730 MVA between Kocin-Prestice. The upgrading of the existing 420 kV substation Kocin is also a part of the project" | 218 | 1899-12-31 | 2018-01-12 14:44 | FALSE | Czech - Germany | 2028 | Part of the corridor North-South electricity interconnections in central Eastern and South Eastern Europe aiming at facilation of the power flow in the north-south-west-east direction, reducing of infrastructure vulnerability in the southwest-east direction in the Czech grid, ensuring the security of supply in the southern regions and provision of additional transmission capacity for connection of potential power generation capacities in the southern part of the Czech republic. | "Information about PCI can be found? on the CEPS website: http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrostatni-vedeni-Vernerov-Vitkov-PCI-3.11.1.aspx http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrost%C3%A1tn%C3%AD-veden%C3%AD-V%C3%ADtkov-P%C5%99e%C5%A1tice-PCI-3.11.2.aspx http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrost%C3%A1tn%C3%AD-veden%C3%AD-P%C5%99e%C5%A1tice-Ko%C4%8D%C3%ADn-PCI-3.11.3.aspx http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrost%C3%A1tn%C3%AD-veden%C3%AD-Ko%C4%8D%C3%ADn-M%C3%ADrovka-PCI-3.11.4.aspx http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrost%C3%A1tn%C3%AD-veden%C3%AD-M%C3%ADrovka-%C4%8Ceb%C3%ADn-PCI-3.11.5.aspx" | 422.31 | 1.98 | NA | CEPS | 500 | 3.11.3, 3.11.4 | Included in the current national plan 2017-2026 which was approved by Energy Regulatory Office on 27th February 2017 | N/A | 21b01a58-16f9-47eb-8aa9-b6174c2a9e96.pdf | FALSE | FALSE | N/A |  |  |  | 0ba97137-4e35-4671-99fb-7544dda5c7a4.pdf | TRUE | Facilitation of the north-south and west-east power exchange, sustainability, flexibility and security of supply | FALSE | FALSE | FALSE | N/A |  | FALSE | FALSE |  | TRUE | Andrew Gayo KASEMBE | kasembe@ceps.cz | +420602870734 |  | jmajkus@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/35/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/35/download/Agreement
36 | Kriegers Flak CGS | The Combined Grid Solution (CGS) is new a AC offshore connection between Denmark and Germany with back to back stations placed in Germany. The project is a combined grid connection of the offshore wind farms Kriegers Flak, Baltic 1, 2 and an interconnection between both countries. | 226 | 1899-12-31 | 2018-01-15 14:27 | TRUE | Denmark-East - Germany | 31/12/2018 | This is the world's first combined solution of offshore wind connection AND interconnection of countries in one integrated solution. | 'Project Websites: https://energinet.dk/Anlaeg-og-projekter/Projektliste/KriegersFlakCGS http://www.50hertz.com/en/Grid-Extension/Offshore-projects/Projects/Combined-Grid-Solution 3rd PCI list https://ec.europa.eu/energy/sites/ener/files/documents/annex_to_pci_list_final_2017_en.pdf | 349 | 16 | Negligible or less than 15km | 50Hertz Transmission, Energinet.dk | 400 | 4.1 |  |  |  | FALSE | FALSE |  |  |  |  | d9b7d8b2-157c-4920-8c56-7f460a7178be.docx | FALSE | The project increases thus security of supply for offshore wind power plants and provides new transmission capacity for trading electricity in an integrated infrastructure as well. The usage of cable capacity is optimised, thereby increasing the project's socio-economic value. | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | 1. Antje Orths, 2. Thomas Köbinger | 1. ano@energinet.dk 2. Thomas.Koebinger@50hertz.com | Antje: +45 2333 8742 Thomas: +493051502388 |  | aorths@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/36/download/Attachment
37 | "Norway - Germany, NordLink" | NordLink: a new HVDC connection between Southern Norway and Northern Germany. Estimated subsea cable length: 514km. Capacity: 1400 MW. | 170 | 1899-12-31 | 2018-01-15 12:29 | TRUE | Germany - Norway | 2020 |  | http://www.tennet.eu/de; http://statnett.no | 1850 | 15 | 50-100km | STATNETT;TENNET-DE | 1400 | 1.8.1 |  |  |  | FALSE | FALSE |  |  |  |  | d1ff47a3-1d8e-4c1e-a6a3-f7c5761d08aa.pub | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar; Arne Pettersen | kedar.kolharkar@tennet.eu; arne.pettersen@statnett.no | +49 (921) 50740 - 4166 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/37/download/Attachment
39 | "DKW-DE, step 3" | New double circuit 380kV line from Kassoe (DK) to Audorf (DE). As third phase of the Danish-German agreement to upgrade cross border transfere capacity. The project is labelled by the EC as project of common interes (PCI 1.4.1) | 169 | 1899-12-31 | 2018-01-15 14:27 | TRUE | Denmark-West - Germany | 31.12.2020 |  | http://kassoe-audorf.eu/ | 536 | 4 | 15-50km | Energinet.dk; TENNET-DE | Direction A: 720 - Direction B: 1000 | PCI 1.4.1 |  |  |  | FALSE | FALSE |  |  |  |  | 88a54967-8b02-4e6e-b8b1-e9eecac17f77.pdf | FALSE | increased cross border market integration to facilitate EU Energy targets Project ensures security of supply and system stability in DK in a changing environment. | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar; Antje Orths | kedar.kolharkar@tennet.eu; ano@energienet.dk | +49 (921) 50740 - 4166; +45 2333 8742 |  | aorths@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/39/download/Attachment
40 | Belgium-Luxemburg-Germany: long-term perspective | An increase of transfer capacity across the BE-LU-DE corridor is envisioned towards the 2030-2040 time horizon. Further studies will determine the appropriate implementation option and timing, taking into account - the recent evolutions with installation of PST in Schifflange and creation of the LuxRing as reported in previous TYNDPs - the expected evolution on the LU-DE border as presented in project 328 | 217 | 1899-12-31 | 2018-01-15 13:45 | TRUE | Belgium-Luxemburg-Germany | 2035 | The 2040 GCA scenario has indicated a potential for developing additional transfer capacity along the BE-LU-DE corridor. | internal reinforcements to be added to current CAPEX estimate | 210 | 0.6 | N/A | CREOS; ELIA; AMPRION | 500-1000 |  |  |  |  | FALSE | FALSE |  |  |  |  | 0c379452-f285-4f3e-b1ec-d539880e1737.docx | FALSE | Capacity increase available to the operational processes dealing with market coupling and system security | FALSE | FALSE | FALSE | Identification of system needs 2040 |  | FALSE | FALSE |  | TRUE | Louis Philippe | louis.philippe@creos.net | +352 621 360 156 |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/40/download/Attachment
47 | Amprion - APG | Westtirol (AT) - Zell/Ziller (AT) Westtirol (AT) - Vöhringen (DE) | 224 | 1899-12-31 | 2018-01-15 15:38 | TRUE | Germany - Austria | 2024 |  | Detailed information to Investment 212 / PCI 3.1.1 can be found under:http://www.apg.at/en/projects/Deutschlandleitung Detailed information to Investment 216 / PCI 3.1.2 can be found under:http://www.apg.at/en/projects/380-kV-salzburg-line http://www.netzentwicklungsplan.de/en (German network development plan in German) http://www.apg.at/de/netz/netzausbau/Netzentwicklungsplan (Austrian Network development plan in German) Third PCI-List https://ec.europa.eu/energy/sites/ener/files/documents/annex_to_pci_list_final_2017_en.pdf | 0 | 0 | 15-50km | AMPRION; APG | AT-DE 600 MW, DE-AT 600 MW | Austrian internal investment (upgrade of Westtirol - Zell/Ziller): 3.1.4 | The project is part of the German NDP (project 74) and part of the Austrian NDP (projects 13-2 and 14-3) |  |  | FALSE | FALSE |  |  |  |  | 50e54ebe-94b7-4057-901f-8a547ba8f162.xlsx | TRUE | - | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | AGP: Stefan Führer / Amprion: Christian Neus | APG: stefan.fuehrer@apg.at / Amprion: christian.neus@amprion.net | APG: +43 (1) 50 320 / 56361 / Amprion: +49 231 5849 12305 |  | sfuhrer@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/47/download/Attachment
48 | New SK-HU intercon. - phase 1 | This project will increase the transfer capacity between Slovak and Hungarian transmission systems, improve security and reliability of operation both transmission systems and support North - South RES power flows in CCE region. Main investments of this project are double circuit AC OHL 400 kV from new Gabcikovo (Slovakia) substation to Gonyu (Hungary) substation, with one circuit connected to the Velky Dur (Slovakia) substation and double circuit AC OHL (preliminary armed only with one circuit on Hungarian side) 400 kV from Rimavska Sobota (Slovakia) substation to Sajoivanka (Hungary) substation. | 159 | 1899-12-31 | 2018-01-15 14:57 | TRUE | Slovakia - Hungary | 2020 |  | Project PCI website: https://ec.europa.eu/energy/sites/ener/files/documents/pci_3_16_1_en.pdf https://ec.europa.eu/energy/sites/ener/files/documents/pci_3_16_2_en.pdf https://ec.europa.eu/energy/sites/ener/files/documents/pci_3_16_3_en.pdf https://ec.europa.eu/energy/sites/ener/files/documents/pci_3_17_en.pdf Slovak website for the PCI projects 3.16 and 3.17: http://www.economy.gov.sk/3161-medzistatne-vedenie-medzi-stanicami-gabcikovo--sk--a-g/144266s http://www.economy.gov.sk/3162-vnutrostatne-vedenie-medzi-stanicami-velky-dur--sk--a-gabcikovo--sk--/144272s http://www.economy.gov.sk/317-2x400kv-vedenie-est-rimavska-sobota-/144273s Hungarian website for the PCI projects 3.16 and 3.17: http://www.mavir.hu/web/mavir/pci-jeloltek http://www.mavir.hu/web/mavir-en/eu-projects-of-common-interest-to-be-implemented-by-mavir 2nd PCI list: https://ec.europa.eu/energy/sites/ener/files/documents/5_2%20PCI%20annex.pdf Slovak TYNDP document: http://www.sepsas.sk/seps/Dokumenty/ProgRozvoj/2015/04/DPR_PS_2015_2024_en.pdf Hungarian National Development Plan (only in Hungarian): http://www.mavir.hu/documents/10258/15454/HFT_2016.pdf The costs of investments "HUnew1" and "HUnew2" are inclued in "2. SK-HU interconnection" (same as in the PCI process). | 82 | 1.48 | Negligible or less than 15km | MAVIR,SEPS | 2020: HU-SK: 200 MW, SK-HU: 1550 MW; 2030: HU-SK: 950 MW, SK-HU: 2400 MW | 3.16.1,3.17 | Included in MAVIR and SEPS NDPs |  |  | FALSE | FALSE |  |  |  |  | 0f91eb4a-c808-4c5d-b06f-ef8f414bc402.pdf | FALSE | Market intergration and increasing security and reliability of the both transmission systems operation | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Lubos Samsely / Zsolt Lengyel | lubos.samsely@sepsas.sk / lengyelz@mavir.hu | +421 905 412 135 / +361 304 1804 |  | lsamsely@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/48/download/Attachment
62 | Estonia-Latvia 3rd IC | Project nr 62 is a planned third 330 kV interconnection between Estonia and Latvia. The project consists of 3 investments of which nr 386 is the main inter-area investment, AC 330 kV OHL between Kilingi-Nõmme substation in Estonia and Riga CHP2 substations | 219 | 1899-12-31 | 2018-01-11 09:34 | TRUE | Estonia - Latvia | 2020 | Cluster Estonia – Latvia between Kilingi - Nõmme and Riga [currently known as the 3rd interconnection or the Harku-Sindi-Riga 330 kV line] is an important future infrastructure project for the whole Baltic region, providing enhanced security of supply in the region, effective operation and competitiveness of the energy market both within the Baltics and between Nordic countries, the Baltics and Central Europe. The most congested cross-section of the Baltic States transmission corridor is at the Estonian – Latvian border and therefore, for market integration it is an important step for increasing transmission capacity and removing an existing bottleneck. | Project website: http://elering.ee/general-information/ http://www.ast.lv/eng/transmission_network/latvian_estonian_3rd_interconnection/ PCI link: https://ec.europa.eu/energy/sites/ener/files/documents/pci_4_2_1_en.pdf https://ec.europa.eu/energy/sites/ener/files/documents/pci_4_2_2_en.pdf National development plans: http://elering.ee/varustuskindluse-aruanded/ http://www.ast.lv/eng/par_ast/public_reports/development_plan_of_transmission_power_system/? " | 176 | 0 | More than 100 km | AST; ELERING | 450-600 |  |  |  |  | FALSE | FALSE |  |  |  |  | 30efb6d9-6a53-40f7-88f3-d4faf6d11110.docx | FALSE | Improve security of supply, market integration and cross-border capacity increase for elimination of bottleneck | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Oleg Tsernobrovkin | oleg.tsernobrovkin@elering.ee | +3727151207 |  | azbanovs@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/62/download/Attachment
71 | COBRA cable | The project is an interconnection between Endrup (Denmark) and Eemshaven (The Netherlands). The project consists of a 320 kV DC subsea cable and related substations on both ends, 325 km apart, applying VSC DC technology. | 154 | 1899-12-31 | 2018-01-15 15:30 | TRUE | Denmark-West - Netherlands | 2019 | Project analysis shows that the project improves the SoS of the region (esp. DKW and Dutch System), due to the choice of technology, which facilitates to support system stability. Overall RES integration (mainly wind energy, both on- and offshore) in this local area keeps on increasing, thus the grid infrastructure needs to be upgraded respectively. The project bypasses a congested onshore grid area and contributes to release bottlenecks. Investment needs The technology used facilitates significant improvement of the security of supply of the countries involved. Active and reactive power can be controlled independently; meaning that the project can significantly contribute to ensure voltage stability . | http://www.cobracable.eu/ | 685 | 14 |  | Energinet,TENNET-NL | 700 |  | Kwaliteits- en Capaciteitsplan 2017 |  |  | FALSE | FALSE |  |  |  |  | 8e7652da-137b-4f84-ae2a-79def8b56e0a.docx | FALSE | Better market integration and facilitation of increased RES exchange across borders, thus increasing the value of RES in order to facilitate reaching the EU energy targets. Project ensures security of supply and system stability in a changing environment. | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar (TENNET-NL); Antje Gesa Orths (Energinet) | kedar.kolharkar@tennet.eu (TENNET-NL); ANO@energinet.dk (Energinet) | Kedar (+49 (151) 40267054); Antje (+45-23-338742) |  | aorths@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/71/download/Attachment
74 | Thames Estuary Cluster (NEMO-Link) | This project envisions the realization of NEMO-Link – the first interconnector between Great Britain and Belgium – as a 1 GW HVDC link of ~140km with technical commissioning by 2018 and operation in 2019, including a number of onshore UK reinforcements to facilitate this and other potential interconnector connections within the Thames Estuary region.The NEMO interconnector is promoted by NGIHL and Elia. The reinforcements to the internal GB network are the responsibility of NGET. | 173 | 1899-12-31 | 2018-01-15 13:40 | TRUE | Belgium - Great Britain | 2019 |  | The project is integrated in Elia's National Development Plan 2015-2025:http://www.elia.be/en/grid-data/grid-development/investment-plan/federal-development-plan-2015-2025 There is also a dedicated project website:http://www.nemo-link.com/" | 650 | 25 | Negligible or less than 15km | ELIA; NGIHL | 1000 | NEMO Link interconnector is a PCI |  |  |  | FALSE | FALSE |  |  |  |  | 3845a8e3-5399-4423-8f1e-cd1b26bce66e.docx | FALSE | The elaboration of a project implementation plan, including the assessment of commissioning date, is subject to further studies | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | MARTA NAVARRETE; Steve Van Campenhout | marta.navarrete@nationalgrid.com; steve.vancampenhout@elia.be | +32 493 504 993 |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/74/download/Attachment
75 | Modular Offshore Grid (MOG) | The Modular Offshore Grid aims at centralizing the offshore wind of four offshore future wind farms in Belgium in an offshore hub and transporting it via three 220 kV AC cables to the new substation Stevin at Zeebrugge. Via the substation Stevin the MOG makes the connection to the STEVIN link (new 400kV axis between Zeebrugge & Zomergem). The MOG is expected to be fully operational by 2020. | 59 | 1899-12-31 | 2018-01-14 15:17 | FALSE | Belgium (offshore - inland) | 2020 |  | The project is integrated in Elia's National Development Plan 2015-2025:http://www.elia.be/en/grid-data/grid-development/investment-plan/federal-development-plan-2015-2025 | 400 | 8.5 | Negligible or less than 15km | ELIA | 1000 |  | MOG integrated in Elia's national development plan 2015-2015 |  |  | FALSE | FALSE |  |  |  |  | b06f6360-5b6e-4755-a3c7-7842eb697f07.docx | TRUE | Evacuation of 1000 MW offshore wind | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhout | steve.vancampenhout@elia.be | +3225467226 |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/75/download/Attachment
77 | Anglo-Scottish -1 | A new 2.4GW (short term rating) submarine HVDC cable route from Hunterston to Deeside with associated AC network reinforcement works at both ends. | 173 | 1899-12-31 | 2018-01-15 11:27 | FALSE | North-South | 2017 | Increase the RES integration and SoS |  | 1220 | 0 | NA | NGET; SPT | 2400 |  |  |  |  | FALSE | FALSE |  |  |  |  | 8d2d4ab8-ad69-4fa1-9f71-491b76c7ff17.docx | TRUE | Facilitate the connection of RES and increase SoS | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Le Fu, Richard Woodwards | Le.Fu@nationalgrid.com; Richard.Woodward@nationalgrid.com | +44(0)1926656596 |  | aalikhanzadeh@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/77/download/Attachment
78 | South West Cluster | New 400kV substation at Hinkley Point. New 400kV transmission route from Hinkley Point to Seabank. Reconstruction of Bridgewater substation for 400kV operation. Uprate Bridgewater - Melksham to 400kV. | 173 | 1899-12-31 | 2018-01-15 12:35 | FALSE | West-East | 2024 |  |  | 814 | 0 | Negligible | NGET | 3200 |  |  |  |  | FALSE | FALSE |  |  |  |  | 57a96108-9690-4ec8-96a1-3a098d5fec2f.docx | TRUE | Project needed for renewables off of the South West peninsula, the replanting of Hinkley Point nuclear power station and further CCGT at Seabank. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Le Fu; Richard Woodward | Le.Fu@nationalgrid.com; Richard.Woodward@nationalgrid.com | +44(0)1926656596 |  | aalikhanzadeh@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/78/download/Attachment
81 | North South Interconnector | A new 400 kV interconnector between Woodland in Ireland and Turleenan in Northern Ireland. | 223 | 1899-12-31 | 2018-01-15 15:36 | TRUE | Ireland - Northern Ireland | 2020 |  | "Project website: http://www.eirgridgroup.com/the-grid/projects/north-south/the-project/ PCI page: https://ec.europa.eu/energy/sites/ener/files/documents/pci_2_13_1_en_2017.pdf This circuit will establish a second interconnector between Ireland and Northern Ireland, effectively eliminating the ongoing risk of system separation, thus allowing an increased transfer capacity. The project is being supported through the consents processes in both jurisdictions by SONI and EirGrid. Upon receipt of consents the project will be implimented by the respecting transmission asset owners with an expected completion date of Q4 2020." | 349 | 0.6 | Negligible or less than 15km | EIRGRID, SONI | 1120 | PCI 2.13.1 |  |  |  | FALSE | FALSE |  |  |  |  | 39585a2c-75f9-49c8-86ad-3a277ab5f9e7.xlsx | FALSE | Market integration, RES integration and Security of Supply | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Michael McClure | michael.mcclure@soni.ltd.uk | 00442890707577 |  | mmcclure@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/81/download/Attachment
82 | RIDP I | The infrastructure development is required to facilitate connection of renewable generation in the North and West of the Island. It will further integrate the Ireland and Northern Ireland transmission systems and provide capacity for substantial demand growth. | 223 | 1899-12-31 | 2018-01-15 14:16 | TRUE | Ireland - Northern Ireland | 2029 |  | "Project website: http://www.eirgridgroup.com/how-the-grid-works/ridp/ PCI page: https://ec.europa.eu/energy/sites/ener/files/documents/pci_2_13_2_en_2017.pdf" | 412 | 0 | Negligible or less than 15km | EIRGRID, SONI | 570 | PCI 2.13.2 |  |  |  | FALSE | FALSE |  |  |  |  | e4fef5d0-fcf8-4bde-94f2-a465567ef558.xlsx | FALSE | RES Integration | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Michael McClure | michael.mcclure@soni.ltd.uk | 00442890707577 |  | mmcclure@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/82/download/Attachment
85 | Integration of RES in Alentejo | The main objective of this project consists in introducing the network reinforcements that are needed to allow the connection of new RES generation (mostly solar but also some wind) that is foreseen for the south region of Portugal, where the solar potential is considerably high. The project includes two new 400 kV OHL that will constitute a new axis between F. Alentejo-Ourique-Tavira substations. It is also included the expansion of the Ourique substation to include the 400 kV voltage level. | 221 | 1899-12-31 | 2018-01-11 15:54 | FALSE | Internal boundary in Portugal inside-outside | 2025 | This project integrates new amounts of solar (and also some wind) generation in the south regions of Portugal. The existing network at 150 kV is not sufficient to integrate the expected new significant amounts of power and a new 400 kV axis should be launched in this region, establishing a connection between the two southern interconnections between Portugal and Spain: the Ferreira do Alentejo-Alqueva (PT) to Brovales (ES), and the Tavira (PT) to Puebla de Guzmán (ES). This axis will also close a 400 kV ring in the southern part of Portugal that will guarantee the network integration of the new RES and at the same time the load growth in the region (Algarve is one of the regions that presents the biggest growth rate in Portugal), in a safe and quality manner. This project includes a new 400 kV axis between the two already in service F. Alentejo and Tavira substations, together with the expansion of Ourique substation to introduce the 400 kV voltage level, where new generation will be connected directly. The new axis F. Alentejo-Ourique-Tavira, constitutes a new transport corridor that increases network capacity and also ensures n-1 security in case of a failure. | Portuguese National Development Plan: http://www.erse.pt/pt/consultaspublicas/consultas/Documents/53_Proposta%20PDIRT-E_2015/PDIRT%202016-2025%20-%20Junho%202015%20-%20Relat%C3%B3rio.pdf Clustering: the project consists of a new axis connecting Ferreira do Alentejo and Tavira substations, with an intermediate substation (Ourique) that will need to be expand to include the 400 kV voltage level. All investments are in series so a lack of any of them will not allow to get the full GTC increase of the project. | 70.3 | 0 | Negligible or less than 15km | REN | Direction A: 1600 - Direction B: 0 |  |  | PDIRT 2018-27, reference PR1208 and PR 1209 |  | FALSE | FALSE |  |  |  |  | e7c7b981-670a-4904-a55c-96a78b63a2b5.docx | TRUE | RES integration | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Fernando Batista | fernando.batista@ren.pt | +351210013419 |  | fbatista@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/85/download/Attachment
92 | ALEGrO | This project realizes the first interconnection between Belgium (Lixhe) and Germany (Oberzier) as a 100 km HVDC link with a bidirectional rated power of 1.000 MW capacity | 71 | 1899-12-31 | 2018-01-14 15:19 | TRUE | Belgium - Germany | 2020 |  | The project is integrated in Elia's National Development Plan 2015-2025:http://www.elia.be/en/grid-data/grid-development/investment-plan/federal-development-plan-2015-2025 Dedicated project websites:http://netzausbau.amprion.net/projekte/alegro-deutschland-belgien andhttp://www.elia.be/nl/projecten/netprojecten/alegro/alegro-content | 560 | 4.2 | Negligible or less than 15km | AMPRION;ELIA | 1000 | Project is PCI | Project is integrated in both BE & DE national development plans as 'advanced' project |  |  | FALSE | FALSE |  |  |  |  | 108c84fa-821c-4520-bfb3-f37d56b86aaf.xlsx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhout; Christian Neus | steve.vancampenhout@elia.be; christian.neus@amprion.net | 3225467226 |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/92/download/Attachment
94 | GerPol Improvements | Upgrade of the existing 220 kV double interconnection line between Krajnik and Vierraden to 400 kV double line in the same direction together with installation of Phase Shifting Transformers on two existing interconnection lines (Krajnik-Vierraden by 50Hertz | 227 | 1899-12-31 | 2018-01-15 13:28 | TRUE | Poland - Germany | 2020 |  | Link to PSE S.A. Development Plan where this project is included: https://www.pse.pl/documents/31287/c1eca7ac-5ec1-4f7a-a7cb-a487cdf5cf9f?safeargs=646f776e6c6f61643d74727565 https://ec.europa.eu/energy/en/topics/infrastructure/projects-common-interest Description of PCI projects on PSE website:http://www.pse.pl/index.php?dzid=256&did=2063 | 85 | 0 | Negligible or less than 15km | 50Hertz Transmission, PSE | Direction A: 0-1500 - Direction B: 0-500 |  |  |  |  | FALSE | FALSE |  |  |  |  | 83bd060f-7600-4360-9248-45aad4cdbc04.xlsx | FALSE | Provision of additional capacity to the market. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 029f0cdc-da6b-4c74-8b08-92d15184c190.geojson | TRUE | Michael Heit | michael.heit@50Hertz.com | +493051503537 |  | mheit@entsoe.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/94/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/94/download/Attachment
96 | Keminmaa-Pyhänselkä | The project is 400 kV overhead line in North Finland. It is part of the 3rd AC cross border project between Finland and Sweden. Will also allow integration of new RES generation at Bothnian bay. | 38 | 1899-12-31 | 2018-01-15 11:35 | FALSE | Finland North-South | 2024 |  | The project consist of 400 kV overhead line, series compensation of the line and substation extensions at the terminal substations. Fingrid has published a national development plan in 2015. The investment plan presents a detailed look of the projects. The plan is available in Finnish: http://www.fingrid.fi/fi/asiakkaat/asiakasliitteet/Kehittämissuunnitelma/Kantaverkon_kehittämissuunnitelma%202015%20-%202025.pdf | 50 | 0.15 | Negligible or less than 15km | FINGRID | 800 |  | Project is in the national plan |  |  | FALSE | FALSE |  |  |  |  | 0eb4ca26-b2f4-44b7-a37e-fdb9a5c54bb6.xlsx | TRUE | Allows 800 MW increased capacity for market on the Finland-Sweden border after 3rd AC FI-SE1 project is finished. | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Antti Harjula | antti.harjula@fingrid.fi | +358400409779 |  | aharjula@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/96/download/Attachment
103 | Reinforcements Ring NL phase I | Upgrade of existing 380kV circuits in the Dutch main ring from 2,5 kA to 4 kA. | 179 | 1899-12-31 | 2017-11-30 13:42 | FALSE | Netherlands - Germany | 2023 | The project reinforces the Dutch grid to accommodate new conventional and renewable generation, to handle regional flow patterns and to facilitate the cross-border capacity increase with neighbouring countries. The project investments are spanning over the time period | All investements in this project are related to the upgrade of the main 380 kV ring structure in the Netherlands. https://www.tennet.eu/nl/ons-hoogspanningsnet/onshore-projecten-nederland/diemen-lelystad-ens/ | 0 | 0 | More than 100km | TENNET-NL | 750 |  | Project is described in Dutch NDP (Kwaliteits- en Capaciteitsplan 2017) |  |  | FALSE | FALSE |  |  |  |  | 328a391c-c79b-441f-a846-bf255eabf0a9.docx | TRUE | Expansion of onshore AC capacity to mitigate internal congestions | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (151) 40267054 |  | jbos@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/103/download/Attachment
107 | Celtic Interconnector | Celtic Interconnector will be the first interconnection between Ireland and France. A survey of the route of the HVDC (VSC) link with 700 MW capacity has been done from the southern coast of Ireland to La Martyre (Finistère) in France. | 156 | 1899-12-31 | 2018-01-12 13:30 | TRUE | France - Ireland | 2026 |  | More information can be found on the Project Website. The project is also part of both RTE and Eirgrid National Development plans. In addition, CELTIC project has been confirmed on 23 November 2017 as a Project of Common Interest 1.6 in the priority corridor Northern Seas Offshore Grid (NSOG). | 920 | 8.5 | NA | EIRGRID,RTE | 700 | PCI 1.6 confirmed on 23/11/2017 |  |  |  | FALSE | FALSE |  |  |  |  | 4d407de5-e72f-4796-949c-cec9306b1569.xlsx | FALSE | Market integration and RES integration | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Philippe BODIN (RTE) ; Gary NOLAN (EIRGRID) | philippe.bodin@rte-france.com ; gary.nolan@eirgrid.com | +33320226795 ; +35312370212 |  | pbodin@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/107/download/Attachment
110 | Norway-Great Britain NSN | North Sea Link, 1400 MW and 720 km long interconnector between Norway and England. | 168 | 1899-12-31 | 2017-11-30 13:33 | TRUE | Great Britain Norway | 2021 |  | "www.nsn-link.com; www.statnett.no; www.NationalGrid.com" | 1800 | 15.4 |  | NGIHL;STATNETT | 1400 | PCI 1.10.1 |  |  |  | FALSE | FALSE |  |  |  |  | 2a74dfee-f50b-47fc-9bc6-b7d3b39989d6.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | MARTA NAVARRETE; Arne Pettersen | marta.navarrete@nationalgrid.com; arne.pettersen@statnett.no | +44 7812 063 912 |  | apettersen@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/110/download/Attachment
111 | 3rd AC Finland-Sweden north | Third AC 400 kV overhead line interconnector between Finland north and Sweden SE1. Strengthening the AC connection between Finland and Sweden is necessary due to market needs, security of supply in Finland, new wind power generation and larger conventional units. | 129 | 1899-12-31 | 2018-01-15 11:36 | TRUE | Finland - Sweden | 2025 |  | "Svenska kraftnät has published a national development plan in 2015. The purpose of the plan is to be an investment plan for the following ten years, 2016-2025. The investment plan presents a detailed look of the projects Svenska kraftnät intends to realize under the stated time period. The plan is available in Swedish through the following link: http://www.svk.se/siteassets/om-oss/rapporter/natutvecklingsplan-2016-2025.pdf (Swedish) Fingrid has published a national development plan in 2015. The investment plan presents a detailed look of the projects. The plan is available in Finnish: http://www.fingrid.fi/fi/asiakkaat/asiakasliitteet/Kehittämissuunnitelma/Kantaverkon_kehittämissuunnitelma%202015%20-%202025.pdf " | 154 | 0.24 | Negligible or less than 15km | FINGRID;SVK | Direction FI-SE: 900 - Direction SE-FI: 800 |  | Project is in the national plan |  |  | FALSE | FALSE | Agreement to go forward with the project has been signed in 2017 between Fingrid and Svenska Kraftnät |  |  |  | c73da28c-7b58-410a-bdd1-8309621c6870.xlsx | FALSE | Capacity will be given to market. | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Antti Harjula | antti.harjula@fingrid.fi | +358400409779 |  | aharjula@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/111/download/Attachment
113 | Doetinchem - Niederrhein | This new AC 380-kV double circuit overhead line will interconnect The Netherlands and Germany (Rhine-Ruhr area). Upon realisation of the project there will be four double circuit interconnections between The Netherlands and Germany. The project will increase the cross border capacity and will facilitate the further integration of the European Energy market especially in Central West Europe. The new line will also increase the security of supply. | 73 | 1899-12-31 | 2018-01-15 11:26 | TRUE | Netherlands - Germany | 2018 | The North Sea Region is characterised by a significant increase in RES generation (especially offshore wind). The grid has to be developed in order to support these new exchange possibilities, facilitating the access to the most economic energy mix, while minimising grid congestions. High flows in both directions West-East and North-South are expected. The project strengthens the European single market especially in the CWE-Region. It also increases the number of interconnectors between The Netherlands and Germany and therefore the security of supply. | "More detailed information on the project can be find here (in German)?: http://netzausbau.amprion.net/projekte/wesel-niederlande/projektbeschreibung And here (in English): https://www.tennet.eu/our-grid/onshore-projects-netherlands/doetinchem-wesel-380-kv/ | 220 | 0 | 15-50km | AMPRION;TENNET-NL | 1500 |  | This project is part of the german NDP. |  |  | FALSE | FALSE |  |  |  |  | c7c9b2a9-a7f7-4461-88a3-7c03ad7b60e9.pdf | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar (TENNET-NL); André Seack (AMPRION) | kedar.kolharkar@tennet.eu (TENNET-NL); Andre.Seack@amprion.net (AMPRION) | Kedar (+49 (151) 40267054); André (+49 172 7490743) |  | mbechmann@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/113/download/Attachment
120 | MOG II: connection of up to 2 GW additional offshore wind Belgium | As per the concept of MOG (project 75), the MOG II aims at centralizing the offshore wind farms in an offshore hub and transporting it via 220 kV AC cables to a substation along a new corridor Stevin-Avelgem (see project 329). Current hypothesis is to apply this concept in two-fold thus two platforms and cable sets centralizing ~1000 MW each Structure, capacity, timing etc. are all subject to the identification of new offshore concession zones in the Belgian part of the North Sea and subsequent proces to translate this into an implementation plan with all involved stakeholders. | 77 | 1899-12-31 | 2018-01-14 15:48 | FALSE | Belgium (offshore - inland) | 2030 | Additional offshore wind is anticipated in the future energy mix for Belgium. Through the development of a MOG II, the efficient connection of additional offshore wind farms will be allowed. |  | 800 | 17 | NA | ELIA | 2000 |  |  | Integration of additional offshore wind beyond 2020 has been considered in Elia's national development plan 2015-2025 |  | FALSE | FALSE |  |  |  |  | 4170969f-9455-4459-b6df-68e61567be09.docx | TRUE | Connection of additional offshore wind in Belgium, on top of the 2.3 GW planned by 2020 | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhot | steve.vancampenhout@elia.be | +3225467226 |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/120/download/Attachment
121 | Nautilus: 2nd interconnector Belgium - UK | This project considers the possibility of a ~1 - 1.4 GW second HVDC connection between UK and Belgium at the earliest by 2028 (indicative timing). The timing as well as location, routing, capacity are subject to further studies. In this context, Elia and NGIHL are conducting a bilateral feasibility study. | 75 | 1899-12-31 | 2018-01-15 13:45 | TRUE | Belgium - Great Britain | 2028 |  | The project is integrated as project under consideration in Elia's National Developmen Plan 2015-2025:http://www.elia.be/en/grid-data/grid-development/investment-plan/federal-development-plan-2015-2025 | 1000 | 8 | NA | ELIA;NGIHL | 1000 | 2nd interconnector BE-UK is a PCI |  |  |  | FALSE | FALSE |  |  |  |  | 64e71c8f-ff57-4701-8643-5608ba1ec371.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhout; Marta Navarette | steve.vancampenhout@elia.be;Marta.Navarrete@nationalgrid.com | +3225467226 |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/121/download/Attachment
123 | LitPol Link Stage 2 | The LitPol Link Stage 2 is a continuation of building of the interconnection between Poland and Lithuania in order to achieve the planned transmission capacity of 1000 MW in both directions. Building of additional internal investments in Poland and Lithuania are necessary. Project will help to further strenghten of Baltics integration into European market. | 48 | 1899-12-31 | 2018-01-03 08:40 | TRUE | Poland - Lithuania | 2023 |  | Link to PSE S.A. Development Plan: https://www.pse.pl/documents/31287/c1eca7ac-5ec1-4f7a-a7cb-a487cdf5cf9f?safeargs=646f776e6c6f61643d74727565 Description of PCI projects on PSE website: https://www.pse.pl/obszary-dzialalnosci/inwestycje-infrastrukturalne/informacje-o-projektach-wspolnego-zainsteresowania-pci?safeargs=696e686572697452656469726563743d74727565 2nd PCI list:https://ec.europa.eu/energy/sites/ener/files/documents/5_2%20PCI%20annex.pdf Link to project web page:http://www.litpol-link.com/ In 2nd PCI list there is position: 4.5.2 Internal line between Stanisławów and Olsztyn Mątki (PL) which corresponds functionally to investments included in project 123. | 335 | 1 | 15-50 km | LITGRID,PSE | 500-1000 MW |  |  |  |  | FALSE | FALSE |  |  |  |  | 1b2e7a2d-22a6-4d28-a9d9-67a35ae11b1b.xlsx | FALSE | In the PL – LT Direction 1000MW of Delta GTC Was used and in the LT- PL direction 500 MW was used. This is because during the Litpol Link Stage 1 project, a 500 MW DC connection was built, but there will be no power flow in the PL-LT direction, the 500 MW will be in the LT-PL direction. The Litpol Link Stage 2 project add another 500 MW in 2020 and due to improvements in the Polish grid, there will be a power flow of 1000 MW GTC in both directions. The GTC in the LT-PL direction will therefore be 500 MW (1000MW – 500MW) and for the PL-LT direction it will be 1000MW (1000MW – 0MW). | TRUE | TRUE | FALSE |  |  | FALSE | FALSE | b2fbe226-c8d4-4243-9641-4a53712b04e0.geojson | TRUE | Andrzej Tymorek | andrzej.tymorek@pse.pl | +48222422121 |  | atymorek@entsoe.local |  | FALSE | TRUE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/123/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/123/download/Attachment
124 | NordBalt phase 2 | Second phase includes the internal network reinforcements in Sweden, Lithuania and Latvia, a key investments to accomplish full utilization of the NordBalt cable between Lithuania and Sweden | 207 | 1899-12-31 | 2018-01-15 12:45 | TRUE | Lithuania - Sweden | 2023 |  | "Svenska kraftnät has published a national development plan in 2015. The purpose of the plan is to be an investment plan for the following ten years, 2016-2025. The investment plan presents a detailed look of the projects Svenska kraftnät intends to realize under the stated time period. The plan is available in Swedish through the following link: http://www.svk.se/siteassets/om-oss/rapporter/natutvecklingsplan-2016-2025.pdf (Swedish) Main characteristics about project: NordBalt project information (LITGRID)" | 294 | 0 | NA | AST;LITGRID;SVK | 0 |  |  |  |  | FALSE | FALSE |  |  |  |  | e62235c3-ea24-46de-b190-3b34f104a341.xlsx | FALSE | To be able to fully utilize the interconnector between Lithuania and Sweden. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Petter Glantz | petter.glantz@svk.se | +46104758481 |  | rrutkauskas2@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/124/download/Attachment
126 | SE North-south reinforcements | Reactive measures in substations and series compensations in order to increase capacity between SE2 and SE3. Replacement of ageing overhead lines that also will contribute to the increased capacity. | 131 | 1899-12-31 | 2017-11-29 16:09 | FALSE | North-South | 2030 |  |  | 550 | 0 | NA | SVK | 1500 |  |  | included in draft och Swedish national plan |  | FALSE | FALSE |  |  |  |  | ca3e2767-1d8e-4b7d-bfa1-42cf3936ef92.xlsx | TRUE | increased power flow from north to south | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Petter Glantz | petter.glantz@svk.se | +46104758481 |  | pglantz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/126/download/Attachment
127 | Central Southern Italy | "The project consists in the reinforcement of southern Italy 400 kV network through new 400 kV lines. The activities will involve the network portions between the substation of Villanova and Foggia, Deliceto and Bisaccia as well as Laino and Altomonte" | 238 | 1899-12-31 | 2018-01-15 15:46 | FALSE | Italy South - Italy Center | 2022 |  | "Link to the last release of the Italian National Development Plan http://www.terna.it/en-gb/sistemaelettrico/pianodisviluppodellarete.aspx" | 750 | 11.25 | Negligible or less than 15km | TERNA | Direction A: 0 - Direction B: 1000 |  | http://download.terna.it/terna/0000/0109/45.pdf |  |  | FALSE | FALSE |  |  |  |  | b0d2eabd-419a-4ce9-8271-e1813e011faa.pdf | TRUE | The project will allow the increase of the energy flows between Italy South and Italy Central south via 1100 MW of additional capacity | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 |  | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/127/download/Attachment
130 | HVDC Wolmirstedt to area Isar | 2 GW HVDC-connection from North-East Germany (Area of Wolmirstedt), an area with high installed capacities of RES, to the South of Bavaria (area of Isar), an area with high consumption and connections to storage capabilities. A Capacity extension to 4 GW is under investigation. | 232 | 1899-12-31 | 2018-01-12 12:36 | FALSE | Internal Project | 2025 | In order to meet the goals of the European and especially German energy policy (German Energiewende) the RES generation in Germany will be increasing strongly. With the current grid, this would lead to internal bottlenecks which occur due to high power flows mainly in the north-south direction. To reduce the related necessary amount of RES generation curtailment as well as conventional redispatch additional North-South transmission capacities in Germany are needed. Moreover, due to the nuclear phase out in Germany, the amount of reliable available generation capacity in southern Germany will decrease. To retain the security of supply (SOS) of this area at an acceptable level, additional transmission capacities towards areas with conventional generation units, RES and connections to storage (for example Scandinavia) are required. The project connects Sachsen-Anhalt, an area with high installed capacities of RES and Bavaria, an area with high consumption and connections to storage capabilities (RES integration/Austria). It also helps to avoid unscheduled transit flows to neighboring countries and therefore creates possibility to use the relieved interconnectors for energy trading (market integration). Due to used DC-Technology the project is able to provide reactive power and therefore helps to improve the voltage stability | German grid development plan: http://www.netzentwicklungsplan.de/en Project Homepage: http://www.50hertz.com/en/Grid-Extension/Projects/SuedOstLink 3rd PCI-list: https://ec.europa.eu/energy/sites/ener/files/documents/annex_to_pci_list_final_2017_en.pdf | 2800 | 0 | NA | 50Hertz Transmission, TenneT DE | 2000 (Internal GTC) & 650 (NTC DE-AT/CZ/PL both directions) | PCI 3.12 | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | eab338b1-d8a2-47a3-be57-c7995b16927d.pdf | TRUE | Integration of RES; retain the security of supply in southern Germany at an acceptable level | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar; Robert Tempels | kedar.kolharkar@tennet.eu; Robert.Tempels@50hertz.com | +49 (921) 50740 - 4166; 0049 30 5150 2379 |  | mruge@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/130/download/Attachment
132 | HVDC Line A-North | Project 132 consists of a new HVDC cable from Emden-East to Osterath. This HVDC has a transfer capacity of 2 GW. | 171 | 1899-12-31 | 2018-01-15 14:27 | TRUE | Internal Project | 2025 |  | Further information on the project, its investments and their necessity particularly for the German Energiewende can be found in the German grid development plan (in German): http://www.netzentwicklungsplan.de/content/der-netzentwicklungsplan-0 More detailed information on Investment 663 can be found on the investment websites (in German): http://netzausbau.amprion.net/projekte/cloppenburg-merzen/projektbeschreibung http://www.tennet.eu/de/netz-und-projekte/onshore-projekte/conneforde-cloppenburg-merzen.html | 1400 | 11.2 | NA | Amprion | 2000 |  | This project is part of the German NDP. (Project DC1) |  |  | FALSE | FALSE |  |  |  |  | a37588bd-7ba6-471d-a873-ce339277a06b.xlsx | FALSE | RES Integration | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Christian Neus | christian.neus@amprion.net | +49 231 5849-12305 |  | mfranz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/132/download/Attachment
134 | N-S Western DE_section South | Project 134 provides significant North-South transmission capacity in Western Germany. The project consists of AC reinforcements and upgrades of existing corridors towards the load centers of Baden-Württemberg and Switzerland. | 196 | 1899-12-31 | 2018-01-15 14:23 | FALSE | Internal Project | 2023 |  | "Further information on the project, its investments and their necessity particularly for the German Energiewende can be found in the German grid development plan (in German): http://www.netzentwicklungsplan.de/content/der-netzentwicklungsplan-0 More detailed information on investment 680 can be found on the investment website (in German): http://netzausbau.amprion.net/projekte/urberach-weinheim/projektbeschreibung https://www.transnetbw.de/de/uebertragungsnetz/dialog-netzbau/netzverstaerkung-weinheim-karlsruhe More detailed information on investment 176 can be found on the investment website (in German): https://www.transnetbw.de/de/uebertragungsnetz/dialog-netzbau/daxlanden-eichstetten | 780 | 6.2 | NA | AMPRION;TRANSNET-BW | - |  | Both investments are part of the German NDP. |  |  | FALSE | FALSE |  |  |  |  | 64ce629e-8fb1-4d73-b8f5-2a2b39d8ee1f.xlsx | TRUE | - | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Tomasz Okraszewski | t.okraszewski@transnetbw.de | +49 711 21858-3436 |  | mfranz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/134/download/Attachment
135 | N-S Western DE_parallel lines | Project 135 provides significant grid reinforcement between Cologne and the Ruhr district (North-West-Germany) and Koblenz/Frankfurt (South-West-Germany) to integrate RES. | 194 | 1899-12-31 | 2018-01-15 14:25 | TRUE | Internal Project | 2022 |  | "Further information on the project, its investments and their necessity particularly for the German Energiewende can be found in the German grid development plan (in German): http://www.netzentwicklungsplan.de/content/der-netzentwicklungsplan-0 Detailed information on Investment 179 can be found on the investment website (in German): http://netzausbau.amprion.net/projekte/osterath-weissenthurm/projektbeschreibung Detailed information on Investment 188 can be found on the investment website (in German): http://netzausbau.amprion.net/projekte/dortmund-frankfurt/projektbeschreibung " | 900 | 7.2 | NA | AMPRION | - |  | The project is part of the German NDP. |  |  | FALSE | FALSE |  |  |  |  | 2831b950-4c3d-4a00-9f23-5cbecb2082c5.xlsx | FALSE | - | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Christian Neus | christian.neus@amprion.net | +49 231 5849-12305 |  | mfranz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/135/download/Attachment
138 | Black Sea Corridor | The project consists of one 400kV double circuit OHL Cernavoda-Stalpu with in/out connection of one circuit in Gura Ialomitei, one 400 kV double circuit OHL Smardan-Gutinas in Romania and also the new 400 kV OHL Dobrujda-Burgas in Bulgaria. | 97 | 1899-12-31 | 2018-01-15 10:15 | FALSE | North-South | 2021 |  | In the second PCI list are included the following investments: 3.8.1 Internal line between Dobrudja and Burgas (BG) 3.8.4 Internal line between Cernavoda and Stalpu(RO) 3.8.5 Internal line between Gutinas and Smardan(RO) http://www.transelectrica.ro/web/tel/proiecte-de-interes-comun Clustering approach: The investments are completely dependent on each other as the main enhancements in Romania and Bulgaria which remove bottlenecks and integrate RES to the network. Clustering of investments had the purpose to identify investments contributing to the increase of transfer capacity on the same corridor. Proposed Project supports market development in South East Europe which is less developed. Based on upper mentioned information it is crucial to cluster all these investment together, to fully utilize the possible benefits. Romanian National Development Plan (only in Romanian):https://www.transelectrica.ro/web/tel/plan-perspectiva" Project included in the 3rd PCI list. | 193 | 1.5 | Negligible or less than 15km | "TRANSELECTRICA, ESO-EAD" | Direction RO-BG: 1350MW ; Direction BG-RO: 800 MW | 3.8 Cluster Bulgaria-Romania capacity increase [currently knows as "Black Sea Corridor"]. Project included in the 3rd PCI list. | National Development Plan for period 2016-2025; Project codes:D2+D4+D5+D6 |  |  | FALSE | FALSE |  |  |  |  | 515a6eef-06ab-422b-b40d-f128f7a7b7e4.txt | TRUE | Cross-border impact, RES integration, market integration, security of supply | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Virginica Zaharia / Milena Tsoleva | virginica.zaharia@transelectrica.ro / m.toleva@eso.bg | +40213035657 / +35929696731 |  | vzaharia@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/138/download/Attachment
142 | CSE4 | The project concerns the construction of a new AC 400kV interconnection between Bulgaria and Greece and new AC 400kV overhead lines at the south part of Bulgaria. This project will increase cross border transfer capacity between Bulgaria and Greece | 146 | 1899-12-31 | 2018-01-08 13:27 | TRUE | North-South | 2023 |  | Project website ESO (http://projects.eso.bg/maritsa-east-nea-santa/?en#PROJECT%20OF%20COMMON%20INTEREST) - Project website IPTO (http://www.admie.gr/en/transmission-system/system-development/projects-of-common-interest/project/article/2194/) Project 142 includes a new interconnection between Bulgaria and Greece and relevant reinforcements in the 400kV network at the south part of Bulgaria. The later are necessary in order to alleviate congestions in the area of south Bulgaria that are restricting power exchanges through the new interconnector. | 224.4 | 3 | 15-50km | ESO,IPTO-SA | Direction A: 648 - Direction B: 82 |  |  |  |  | FALSE | FALSE |  |  |  |  | 6f0bfb36-a1a7-43dc-9af6-a0fc38fa003b.xlsx | FALSE | Cross-border impact, market integration, security of supply | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Dilyana Bolashikova-Georgieva | dbolashikova@ndc.bg | +35929213729 |  | spetkov@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/142/download/Attachment
144 | Mid Continental East corridor | The project consists of one double circuit 400 kV line between Serbia and Romania and reinforcement of the network along the western border in Romania: one new simple circuit 400 kV line from Portile de Fier to Resita and upgrade from 220 kV double circuit to 400 kV double circuit of the axis between Resita and Arad, including upgrade to 400 kV of three substations along this path: Resita, Timisoara, Sacalaz. | 97 | 1899-12-31 | 2018-01-15 10:20 | TRUE | Romania - Serbia | 2023 |  | On the second PCI list are included the following investments: PCI 3.22.1 Interconnection between Resita (RO) and Pancevo (RS) PCI 3.22.2 Internal line between Portile de Fier and Resita (RO) PCI 3.22.3 Internal line between Resita and Timisoara/Sacalaz (RO) PCI 3.22.4 Internal line between Arad and Timisoara/Sacalaz (RO) http://www.transelectrica.ro/web/tel/proiecte-de-interes-comun Clustering approach: Project 144 aims to enhance the transmission capacity along the East-West corridor in the South-Eastern and Central Europe. GTC was calculated for a common boundary in South East region, between the West borders of Romania and Bulgaria which are main exporters of the area on one hand and Serbia and Hungary on the other hand. The investments 238, 269, 270,701 and 705 are complementing each other as the main enhancements in Romania which remove bottlenecks and integrate RES to the network. Based on upper mentioned information it is crucial to cluster all these investments together, to utilize the possible benefits. Romanian National development Plan (only in Romanian):http://www.transelectrica.ro/web/tel/plan-perspectiva Project included in the 3rd PCI list. | 179 | 1.2 | 15-50km | TRANSELECTRICA; EMS | Direction RO-RS=950 MW - Direction RS-RO=750 MW | 3.22 Cluster Romania- Serbia between Resita and Pancevo [currently known as "Mid Continental East Corridor"]. Project included in the 3rd PCI list. | National Development Plan for period 2016-2025; Project codes:F1+F2+F3 |  |  | FALSE | FALSE |  |  |  |  | 18b6de80-7b39-41cf-abb6-0e37ac79aeec.txt | TRUE | Cross-border impact, RES integration, Market integration | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Virginica Zaharia / Ivan Trkulja | virginica.zaharia@transelectrica.ro / ivan.trkulja@ems.rs | +40213035657 / +381113330767 |  | vzaharia@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/144/download/Attachment
150 | Italy-Slovenia | "The project consists in a new HVDC link between Salgareda (Italy) and Beričevo (Slovenia) which will strengthen the connection between Slovenia and Italy. On italian side the project is under permitting since 2012. Terna and ELES are evaluating the opportunity to implement the project according to the following two phases: • phase 1 reinforcement of existing grid (PSTs, upgrade of existing lines) o Commissioning date: 2020 o Delta GTC contribution: 400 MW • phase 2 HVDC link (two separate investments: one for the IT side and one for the SI side) o Substation 1: Beričevo o Rated power: 800/600 MW o Commissioning date: 2022/2025 o Delta GTC contribution: 600 MW | 238 | 1899-12-31 | 2018-01-15 15:47 | TRUE | Slovenia - Italy | 2022 |  | "PCI website: https://ec.europa.eu/energy/sites/ener/files/documents/pci_3_21_en.pdf 2nd PCI list: https://ec.europa.eu/energy/sites/ener/files/documents/5_2%20PCI%20annex.pdf Clustering approach: HVDC line represents an international commercial connection and is considered as cluster of one investment. Slovenian NDP (only in slovenian): http://www.eles.si/za-poslovne-uporabnike/razvoj-in-uporaba-prenosnega-omrezja/strategija-razvoja-elektroenergetskega-sistema-rs.aspx" | 0 | 0 | NA | TERNA;ELES | Direction A (SI-IT): 1000 - Direction B (IT-SI): 1000 | Included in Third PCI list with label 3.21 |  |  |  | FALSE | FALSE |  |  |  |  | 1af01b98-d0be-475b-8c99-248fa0a01c2a.pdf | FALSE | The project will allow the increase of the energy flows between Italy and Slovenia via the additional trasfer capacity | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti \ ELES: Dragaš Klemen | TERNA: alessio.tonti@terna.it \ ELES: Klemen.Dragas@eles.si | TERNA: +39 0683138020 \ ELES: +38614743510 |  | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/150/download/Attachment
153 | France-Alderney-Britain | France-Alderney-Britain (FAB) is a new HVDC subsea interconnector between Exeter (UK) and Menuel (France) with 1,4 GW capacity. | 153 | 1899-12-31 | 2018-01-12 13:27 | TRUE | France - Great Britain | 2022 |  | More information related to the project can be found on internet platforms : www.fablink.net and www.rte-france.com/fr/projet/interconnexion-france-aurigny-grande-bretagne-fab. The project is also part of both System Operator National Development Plans. In addition, FAB project has been confirmed on 23 November 2017 as Project of Common Interest 1.7.1 in the priority corridor Northern Seas Offshore Grid (NSOG). | 850 | 7.6 | Negligible or less than 15km | RTE,FAB Link Ltd | 1400 | PCI 1.7.1 confirmed on 23/11/2017 |  |  |  | FALSE | FALSE |  |  |  |  | bfd5bcc8-93ba-45ae-b967-be14511fd5c6.xlsx | FALSE | Market Integration and RES integration | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Philippe BODIN (RTE) and James DICKSON (FAB Link Ltd) | philippe.bodin@rte-france.com | +33320226795 |  | pbodin@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/153/download/Attachment
164 | N-S Eastern DE_central section | North-South transmission in Germany. AC links from Northern Germany towards the load centers of Bavaria and Baden-Württemberg. | 175 | 1899-12-31 | 2018-01-12 13:51 | FALSE | inside-inside | 2027 |  | " German grid development plan: http://www.netzentwicklungsplan.de/en Information on Investments 149 and 677 (in German) http://www.tennet.eu/de/netz-und-projekte/onshore-projekte/stade-landesbergen.html Information on Investment 157 (in German) http://www.tennet.eu/de/netz-und-projekte/onshore-projekte/wahle-mecklar.html " | 0 | 0 | NA | TENNET-DE | tbd |  | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | a2e952c1-e584-4869-99d8-fb001e876bc1.pdf | TRUE | Integration of RES; retain the security of supply in southern Germany at an acceptable level | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (921) 50740 - 4166 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/164/download/Attachment
167 | Viking DKW-GB | 2x700 MW HVDC subsea link across the North Seas. New substations on both sides; Bicker Fen (GB); Revsing (DK) | 177 | 1899-12-31 | 2018-01-15 15:40 | TRUE | Denmark- West - Great Britain | 31/12/2022 |  | "Project Website: http://viking-link.com" | 1970 | 16 | NA | Energinet.dk, NGIHL | 1400 | applied for 3rd list, included in EC's November publication | included in NG's ETYS: https://www.nationalgrid.com/uk/publications/electricity-ten-year-statement-etys |  |  | FALSE | FALSE |  |  |  |  | 7e3581f5-f21f-49a4-b048-075b2c2fbff6.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | 1. Antje Orths, 2. Marta Navarrete | 1. ano@energinet.dk, 2. marta.navarrete@nationalgrid.com | +45 2333 8742 |  | aorths@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/167/download/Attachment
170 | Baltics synchro with CE | The power system of the Baltic States which includes Estonia, Latvia, Lithuania (Baltic Integrated Power System) currently is operating in parallel with the Integrated/Unified Power System (IPS/UPS) of Russia and Belarus. The aim of this project is to remove the energy isolation of the Baltic States from the rest of the EU and connect their power systems with systems using the same technical standards and developing in the same European legal framework. This strategic goal has been set by the Prime Ministers of the Baltic States in 2007. | 219 | 1899-12-31 | 2018-01-15 12:15 | TRUE | Baltics - Nordic - Continental Europe | 2025 | This strategic goal has been set by the Prime Ministers of the Baltic States in 2007. |  | 1069 | 0 | NA | AST;ELERING;LITGRID | 500 |  |  |  |  | FALSE | FALSE |  |  |  |  | 42745892-14f2-473d-8a59-8384df74641d.xlsx | FALSE | Baltic States desinchronization from IPS/UPS power system | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Oleg Tšernobrovkin | oleg.tsernobrovkin@elering.ee | +3725033639 |  | rrutkauskas2@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/170/download/Attachment
172 | ElecLink | ElecLink is a new FR – UK interconnection cable with 1000 MW capacity through the Channel Tunnel between Sellindge (UK) and Mandarins (FR). Converter stations will be located on Eurotunnel concession at Folkestone and Coquelles. This HVDC interconnection is a PCI project (Project of Common Interest) no. 1.7.3 | 125 | 1899-12-31 | 2018-01-10 17:01 | TRUE | France - Great Britain | 2019 |  |  | 580 | 4.5 | Negligible or less than 15km | ElecLink | 1000 | 1.7.3 |  |  |  | FALSE | FALSE |  |  |  |  | d1f2f795-7015-4ccd-9f1d-b4b33f67beef.pdf | FALSE | ElecLink will increase interconnection capacity between Great Britain and the continent. The connection points on both the French and British transmission grid will allow a safe operation in 2020 and 2030 and the full capacity (1000MW) can be used without leading to unmanageable critical system failure. | TRUE | FALSE | FALSE |  |  | FALSE | FALSE | dc6f4c28-7e3f-4258-8fcb-819bc55892a7.pdf | TRUE | Alex De Luca | alex.deluca@eleclink.co.uk | +44 (0)203 871 2572 |  | adeluca@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/172/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/172/download/Attachment
173 | FR-BE II: PSTs Aubange-Moulaine | Installation of two phase shifting transformers in Aubange, one on each of the 225kV circuits of the Aubange-Moulaine interconnector. | 65 | 1899-12-31 | 2018-01-14 15:23 | TRUE | France - Belgium | 2020 |  | The project is integrated as project under consideration in Elia's National Development Plan 2015-2025:http://www.elia.be/en/grid-data/grid-development/investment-plan/federal-development-plan-2015-2025 | 20 | 0.1 | NA | ELIA;RTE | 500 |  |  | Integrated as investment under consideration in Elia national development plan 2015-2025 |  | FALSE | FALSE | Investment part of MoU RTE-ELIA governing evolution FR-BE interconnectors |  |  |  | 81096783-9cef-4ffd-8eb8-d243a9ec4543.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | FALSE | FALSE | TRUE |  |  | TRUE | FALSE |  | TRUE | Steve Van Campenhout (Elia) | steve.vancampenhout@elia.be | +3225467226 |  | pjmarsboom@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/173/download/Attachment
174 | Greenconnector | Greenconnector is an HVDC interconnector project between Italy and Switzerland for power transport using DC cables rather than overhead lines. The route length is about 150 km. The design power is 1000 MW (1200 MW in overload condition), while the DC voltage is +/- 400 kV DC. Two cables will be installed, working with a bipolar scheme. Great part of the cables route will exploit a section of an existing oil pipeline, no longer in service since January 1997. This pipeline crosses the Italian and Switzerland border at Splügenpass and is running close by the two end stations of the Greenconnector project (Sils in Graubunden Canton and Verderio Inferiore, Lecco). The cables will be pulled inside the pipeline itself, reducing the amount of civil works required before and after cable laying and therefore limiting even temporary environmental impact. For about 47 km the cables will run across the Como lake. | 241 | 1899-12-31 | 2017-11-30 21:45 | TRUE | Italy - Switzerland | 2022 |  |  | 609 | 1.9 | Negligible or less than 15km | Worldenergy SA | 1000 | 2.14 |  |  |  | FALSE | FALSE |  |  |  |  | 26e7fd35-6f3c-4c3e-a772-5084a8d1bd49.pdf | FALSE | cross border impact; connection of renewables | TRUE | FALSE | FALSE |  |  | FALSE | FALSE | d5c51d1c-b18a-4416-a213-7e6d33141117.xlsx | TRUE | Claudio Gianotti | c.gianotti@wdenergy.com | +41793541348 |  | cgianotti@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/174/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/174/download/Attachment
175 | Great Belt II | This project candidate includes an HVDC connector between Denmark-West (DKW) and Denmark-East (DKE). The connector is called Great Belt-2. | 89 | 1899-12-31 | 2018-01-03 09:15 | TRUE | Denmark-West (DK1) - Denmark-East (DK2) | 2030 | Security of supply for DKE (Denmark East) | Project was also assessed in TYNDP2016. Project in planning phase | 300 | 6 | Not assessed | Energinet.dk | 600 |  |  |  |  | FALSE | FALSE |  |  |  |  | 0ec0ed5f-3aac-4c6d-90e8-0864ed38535c.docx | FALSE | Security of supply and market integration | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 734b6aa9-70d5-4607-9468-e6a283d9d2a3.docx | TRUE | Peter Børre Eriksen | pbe@energinet.dk | +4523338523 |  | pborre@entsoe.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/175/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/175/download/Attachment
176 | Hansa PowerBridge I | New HVDC interconnector between Sweden (SE4) and Germany (50 Hertz, Continental) aiming to enhance the integration of the Nordic and the continental power market. Moreover the interconnector facilitates RES integration and increases the system adequacy in both systems. | 239 | 1899-12-31 | 2017-11-30 20:06 | TRUE | Germany - Sweden | 2026 |  |  | 660 | 0 | Negligible or less than 15km | 50Hertz Transmission, Svenska Kraftnät (SvK) | 700 |  |  |  |  | FALSE | FALSE |  |  |  |  | 0a79bc3b-8f82-4b9a-8bdd-cfa9396b4116.xlsx | FALSE | enhance the integration of the Nordic and the continental power market | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Thomas Köbinger | Thomas.Koebinger@50hertz.com | "+493051502388" |  | pglantz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/176/download/Attachment
179 | DKE - DE (Kontek2) | This project includes a HVDC subsea interconnector between Denmark-East (DKE) and Germany (DE) and is called Kontek-2. A final grid-connection solution is not prepared yet. | 231 | 1899-12-31 | 2018-01-09 15:06 | TRUE | Denmark - Germany | 2030 | Market integration; SoS for DK2 | A project candidate identified in the TYNDP14 process which was carried over into the TYNDP16 project as a potential future project. Now it is carried into TYNDP 2018. Project was also assessed in TYNDP 2016 Project also called Kontek 2 | 360 | 7.2 | Not assessed | 50Hertz Transmission; Energinet | 600 MW |  |  |  |  | FALSE | FALSE |  |  |  |  | 030e222d-2fb8-4490-b004-485df0b8f6bb.docx | FALSE | Security of supply and market integration | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 846524d9-6377-4654-9f49-368c9d93e630.docx | TRUE | Peter Børre Eriksen | pbe@energinet.dk | +4523338523 |  | pborre@entsoe.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/179/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/179/download/Attachment
183 | "DKW-DE, Westcoast" | New 400 kV line from Endrup (DK) to Klixbüll (DE), increasing the transfer capacity at the West Coast between these countries. The project is labelled by the EC as project of common interest (PCI 1.3.1). | 191 | 1899-12-31 | 2018-01-15 15:05 | TRUE | Denmark-West - Germany | 31/12/2022 |  | - new joint homepage expected in January 2018, until then refer to homepages published in TYNDP16 | 313 | 2 | Negligible or less than 15km | Energinet.dk,TENNET-DE | 500 | 1.3.1 |  |  |  | FALSE | FALSE |  |  |  |  | 0952e34b-8ea3-409d-a5ed-a9c56f46e789.docx | FALSE | • necessary to ensure system stability in DK in case Viking cable to GB trips (based on bilateral dynamic study results), Sharing of reserves with DE | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | 1. Antje Orths, 2. Kedar Kolharkar | 1. ano@energinet.dk, 2. Kedar.Kolharkar@tennet.eu | 1. +45 2333 8742, 2. +49 (151) 4026 7054 |  | aorths@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/183/download/Attachment
186 | east of Austria | To allow the grid integration of the planned renewable energy generation (mainly wind power) in the north-eastern part of Austria ("Weinviertel") the transmission grid infrastructure (currently a rather weak 220kV line) has to be enforced and new substation for the connection needs to be erected. | 224 | 1899-12-31 | 2018-01-15 09:49 | FALSE | outside-inside | 2021 |  | Project homepage (only in german) https://www.apg.at/de/projekte/Weinviertelleitung National development plan: http://www.apg.at/de/netz/netzausbau/Netzentwicklungsplan | 0 | 0 | Negligible or less than 15km | APG | 1500 |  | 11-8 |  | 37f9af0e-166a-4675-aa7b-0f801b643000.pdf | TRUE | FALSE |  |  |  |  | 990ac1b9-19e8-426a-956b-de4ca5cbc09e.pdf | TRUE | RES integration | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Stefan Führer | stefan.fuehrer@apg.at | +43 (1) 50 320 / 56361 |  | sfuhrer@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/186/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/186/download/Agreement
187 | St. Peter (AT) - Pleinting (DE) | Increase of the cross border transmission capacity by erecting a new 380kV line between St. Peter (Austria) and Pleinting (Germany). This leads to an improved connection of the very high amount of RES in Germany and the pump storages in the Austrian Alps. | 224 | 1899-12-31 | 2018-01-12 16:29 | TRUE | Austria - Germany | 2024 |  | This project is highly connected to and partly based on TYNDP 2016 Project 47/Investment 212. German grid development plan: http://www.netzentwicklungsplan.de/content/der-netzentwicklungsplan-0 Austrian grid development plan: http://www.apg.at/de/netz/netzausbau/Netzentwicklungsplan | 0 | 0 | Negligible or less than 15km | APG;TENNET-DE | 1500 |  | it is part of the German NDP; it is part of the Austrian NDP (11-7) |  |  | FALSE | FALSE |  |  |  |  | 6d7765bc-0597-4022-b9e2-2a7503fd1511.pdf | FALSE | improved connection of the very high amount of RES in Germany and the pump storages in the Austrian Alps | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | TenneT-DE: Kedar Kolharkar / AGP: Stefan Führer | TenneT-DE: kedar.kolharkar@tennet.eu / APG: stefan.fuehrer@apg.at | TenneT-DE: +49 (921) 50740 - 4166 / APG: +43 (1) 50 320 / 56361 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/187/download/Attachment
190 | NorthConnect | "A 650 km long subsea interconnector between Norway and Scotland is planned to be realised in 2022. The interconnector is planned to be a 500 kV, 1400 MW HVDC subsea interconnector between western Norway (Simadalen) and eastern Scotland (Peterhead), UK." | 148 | 1899-12-31 | 2017-11-30 08:54 | TRUE | Great Britain - Norway | 2022 |  |  | 1813 | 30 |  | NorthConnect KS | 1400MW | 1.10B |  |  |  | FALSE | FALSE |  |  |  |  | 9c788ebc-3e10-49dd-9d5e-65d5c500582d.pdf | FALSE | 1400MW is design capacity of link. | TRUE | FALSE | FALSE |  |  | FALSE | FALSE | d01ba7a1-1ff7-4b81-ab3b-b2864aa6c3f7.shp | TRUE | Adair Elder | adair.elder@northconnect.no | +4748260866 |  | aelder@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/190/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/190/download/Attachment
191 | OWP TenneT Northsea Part 2 | Connection of offshore wind parks in the North Sea to Germany. Mainly subsea DC cable. The OWP will help to reach the European goal of CO2 reduction and RES integration | 198 | 1899-12-31 | 2018-01-12 14:29 | FALSE | inside-DE | 2022 | Germany is planning to build a big amount of offshore wind power plants in the North- and Baltic Sea. The OWP will help to reach the European goal of CO2 reduction and RES integration. These offshore infrastructure projects in the North- and Baltic Seas areas, will deliver benefits for the regional society by pooling generation portfolios, integrating markets, lowering CO2 emissions, facilitating the integration of renewables (both onshore as well as offshore) and ensuring sufficient system resilience. The development of off-shore wind farms in the North of Germany induces needs for undersea connections to these wind farms as well as reinforcements of the grid capacity. | Information on offshore projects within the northern sea promoted by TenneT TSO GmbH (http://www.tennet.eu/de/netz-und-projekte/offshore-projekte.html)in German | 0 | 0 | More than 100km | TENNET-DE | 3600 |  | it is part of the German offshore NDP |  |  | FALSE | FALSE |  |  |  |  | ea1b9c51-346c-4e31-94e9-29d74f415adc.pdf | TRUE | RES integration of offshore wind | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (921) 50740 - 4166 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/191/download/Attachment
192 | OWP Northsea TenneT Part 3 | Connection of offshore wind parks in the North Sea to Germany. Mainly subsea DC cable. The OWP will help to reach the European goal of CO2 reduction and RES integration | 199 | 1899-12-31 | 2018-01-12 14:32 | FALSE | inside-DE | 2027 | Germany is planning to build a big amount of offshore wind power plants in the North- and Baltic Sea. The OWP will help to reach the European goal of CO2 reduction and RES integration. These offshore infrastructure projects in the North- and Baltic Seas areas, will deliver benefits for the regional society by pooling generation portfolios, integrating markets, lowering CO2 emissions, facilitating the integration of renewables (both onshore as well as offshore) and ensuring sufficient system resilience. The development of off-shore wind farms in the North of Germany induces needs for undersea connections to these wind farms as well as reinforcements of the grid capacity | Information on offshore projects within the northern sea promoted by TenneT TSO GmbH (http://www.tennet.eu/de/netz-und-projekte/offshore-projekte.html)in German |  |  | NA | TENNET-DE | 3236 |  | it is part of the German offshore NDP |  |  | FALSE | FALSE |  |  |  |  | c4335be3-4496-4b2f-877a-456276134cab.pdf | TRUE | RES integration of offshore wind | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (921) 50740 - 4166 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/192/download/Attachment
193 | Godelleta-Morella/La Plana | " This project consist of a new OHL 400 kV AC axis Godelleta-Morella/La Plana (Spain)." | 225 | 1899-12-31 | 2018-01-15 11:27 | FALSE | North-South | 2025 | Needed to solve the congestion in the mediterranean axis. it is not directly linked to the cross border, that with higher flows north-south due to higher cross border flows in the long term the reinforcement of this axis is required | "Useful link: Spanish National Development Planhttp://www.minetur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx Clustering: the project consists of a unique investment. A double circuit, one circuit connecting Godelleta and Morella and the other Godelleta and La Plana. new substation (Baza) and 2 double circuits that connect this new substation to the existing network. This intersection allows minimizing the impact in the territory." | 67.62 | 1.0143 | Negligible or less than 15km | REE | Direction A: 670-850 - Direction B: 1400-1500 | it was PCI in the 2nd list, not in the 3rd list | Spain NDP Planificación Energética.2015-2020 (Anexo II.1. Página 12) |  |  | FALSE | FALSE |  |  |  |  | 2b325391-d4ea-4289-9504-cb99ac8c8f24.docx | TRUE | Market integration;RES integration | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Laura López (REE) / Patricia Labra (REE) as substitute | laura.lopez@ree.es (plabra@ree.es) | 916508500 - Ext. 3192 |  | llopez@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/193/download/Attachment
194 | Cartuja | This project includes a new 400 kV double circuit Cartuja-Arcos de la Frontera and a new substation Cartuja 400 kV. | 225 | 1899-12-31 | 2018-01-15 11:01 | FALSE | South-North | 2029 | Needed to connect new RES generation (onshore wind and offshore wind) | "Useful link: Spanish National Development Planhttp://www.minetur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx Clustering: the project consists of a new substation (Cartuja) and a double circuit that connect this new substation to the existing network (Arcos-Cartuja). Both investments are necessary to get the full GTC increase of the project. Possible connection to 220kV network in the area is not included in the project." | 23.3 | 0.3495 | Negligible or less than 15km | REE | Direction A: 425-600 - Direction B: 1560-2700 |  | Spain NDP Planificación Energética.2015-2020 (reference TS-2 Anexo III. Página 87) |  |  | FALSE | FALSE |  |  |  |  | aa656f08-ade1-41f4-8932-3920eeefdbdc.docx | TRUE | Generation connection | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Laura López (REE) / Patricia Labra (REE) as substitute | laura.lopez@ree.es (plabra@ree.es) | 916508500 - Ext. 3192 |  | llopez@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/194/download/Attachment
197 | N-S Finland P1 stage 2 | Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission capacity thusenabling the integration of new renewable and conventional generation in northern Finland and to compensate dismantling of obsolescent existing 220 kV lines. This project is fifth 400 kV overhead line connecting North Finland to South Finland. | 38 | 1899-12-31 | 2018-01-15 11:36 | FALSE | Finland North-South | 2022 |  | The project consist of 400 kV overhead line, series compensation of the line and substation extensions at the terminal substations. Fingrid has published a national development plan in 2015. The investment plan presents a detailed look of the projects. The plan is available in English: http://www.fingrid.fi/fi/asiakkaat/asiakasliitteet/Kehitt%C3%A4missuunnitelma/Kehittamissuunnitelma%202017_2027/Main%20grid%20development%20plan%202017-2027.pdf and in Finnish: http://www.fingrid.fi/fi/asiakkaat/asiakasliitteet/Kehitt%C3%A4missuunnitelma/Kehittamissuunnitelma%202017_2027/Kantaverkon%20kehitt%C3%A4missuunnitelma%202017-2027.pdf | 90 | 0.24 | NA | FINGRID | 1000 |  | Project is in the national plan |  |  | FALSE | FALSE |  |  |  |  | 37a65082-ec3f-4a0e-a244-b53e8bbe51f8.xlsx | TRUE | Capacity will allow the higher cross border capacity between Finland and Sweden (SE1) to be utilized. | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Antti Harjula | antti.harjula@fingrid.fi | +358400409779 |  | aharjula@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/197/download/Attachment
199 | Lake Geneva South | This project comes on top of "PST Foretaille" and "upstream grid reinforcement in France" projects. It consists in upgrading the existing 225-kV overhead line south of Lake Geneva, possibly to 400-kV. | 202 | 1899-12-31 | 2018-01-14 20:46 | TRUE | France - Switzerland | 2035 |  | Link to the latest Fench National Development Plan http://www.rte-france.com/fr/article/schema-decennal-de-developpement-de-reseau | 130 | 1 | NA | RTE,SWISSGRID | FR-> CH 750 ; CH -> FR 1300 |  |  | Mentioned in the finalised French National Plan 2016 (ID of project = 445) as project under consideration. |  | FALSE | FALSE |  |  |  |  | c4de781a-2256-4f19-bff0-bbb8eb30f6e8.xlsx | FALSE | Market integration and RES integration | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Gabriel Dudicourt | gabriel.dudicourt@rte-france.com | +33 3 20 22 68 20 |  | gdudicourt@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/199/download/Attachment
200 | CZ Northwest-South corridor | "A corridor of internal 400 kV overhead lines inside the Czech Republic connecting new 420 kV substations between Vernerov, Vitkov and existing substation Prestice in the northwest-south direction incuding looping of existing 400 kV overheadline (V413: Reporyje-Prosenice) into the existing substation 420 kV Mirovka. The project consists of building of two new 420 kV substations Vernerov and Vitkov, building of two 400 kV overhead lines involving changing a 220 kV double-circuit lines to 400 kV double-circuit lines with a capacity of 2x1730 MVA between Vernerov-Vitkov and Vitkov-Prestice and building a new double-circuit overhead line between Mirovka and V413" | 218 | 1899-12-31 | 2018-01-12 14:45 | FALSE | Czech - Germany | 2025 | Part of the corridor North-South electricity interconnections in central Eastern and South Eastern Europe aiming at increasing the transmission capacity in the western part of the Czech grid and therefore enabling the accomodation of the prevailing power flows in the north-west and west-east direction for the entire Central Eastern Europe. Moreover, the project will enable the connection of Renewable Energy Sources in the Karlovary region, reduce infrastructure vulnerability and ensure security of supply in the western region of the Czech Republic. The transmission capacity of the 220 kV grid in the western part of the Czech grid has already exhausted which in some operation cases cause violation of the security criteria N - 1. The project which involves the changing of the current 220 kV grid (substations and overhead lines) to 400 kV grid ensure to eliminate the congestion in this part of the grid. Moreover, it is also planned that the operation of the 220 kV will be decommissioned step-by-step between 2019 - 2040, so reinforcement brough by the project not only eliminates the congestion in this part of the grid but also replaces the 220 kV grid to be decommisioned. | "Information about PCI can be found on the CEPS website: http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrostatni-vedeni-Vernerov-Vitkov-PCI-3.11.1.aspxPCI http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrost%C3%A1tn%C3%AD-veden%C3%AD-V%C3%ADtkov-P%C5%99e%C5%A1tice-PCI-3.11.2.aspx http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrost%C3%A1tn%C3%AD-veden%C3%AD-P%C5%99e%C5%A1tice-Ko%C4%8D%C3%ADn-PCI-3.11.3.aspx http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrost%C3%A1tn%C3%AD-veden%C3%AD-Ko%C4%8D%C3%ADn-M%C3%ADrovka-PCI-3.11.4.aspx http://www.ceps.cz/CZE/Cinnosti/Technicka-infrastruktura/projekty-spolecneho-zajmu/Stranky/Vnitrost%C3%A1tn%C3%AD-veden%C3%AD-M%C3%ADrovka-%C4%8Ceb%C3%ADn-PCI-3.11.5.aspx" | 261.21 | 5.04 | 15-50km | CEPS | 500 | 3.11.1, 3.11.2, 3.11.4 | Included in the current national plan 2017-2026 which was approved by Energy Regulatory Office on 27th February 2017 | N/A | de11e94f-cfe2-4dff-80c0-260bc301faa3.pdf | FALSE | FALSE | N/A |  |  |  | 2c038dc7-07fa-478d-900d-7283e6e3b60b.pdf | TRUE | Facilitation of the north-south and west-east power exchange, sustainability, flexibility and security of supply | FALSE | FALSE | FALSE | N/A |  | FALSE | FALSE |  | TRUE | Andrew Gayo KASEMBE | kasembe@ceps.cz | +420602870734 |  | jmajkus@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/200/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/200/download/Agreement
203 | Morella-La Plana (previosly Aragón-Castellon) | "The project consists of a 400kV axis Morella-La Plana". The previous project already considered additional investments that are already in service, that is Mudejar-Morella , Mezquita-Morella and a new 400kV substation Mudejar with connection to the axis Aragón-Teruel (Spain)." | 225 | 1899-12-31 | 2018-01-15 11:34 | FALSE | West-East | 2020 | Needed to solve the congestion in the cantabric- mediterranean axis. It is not directly linked to the cross border Spain-France, but with higher flows north-south due to higher cross border flows in the long term, the reinforcement of this axis is required. | "Useful link: Spanish National Development Planhttp://www.minetur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx? Clustering: The objective of this project is to solve the congestion in the existing line Aragón-Morella-La Plana 400kV, which can not be uprated . Therefore a new parallel axis with higher capacity will be built and the old line will be decommissioned. For such a purpose as Aragón subestation can not be extended to be an extreme of the new double circuit, a new subestation in Mudejar is required. The whole axis is in series so that all is required for the GTC increase. The other investment Mezquita-Morella 400kV gathers RES in Muniesa and Mezquita area. This investment need to be clustered because without it the flows could go up to Aragón (causing overloads in the 220kV Mezquita-Aragón) to go down in the Aragón-Morella axis increasing the load of it, and increasing losses." | 50.76 | 0.7614 | 15-50km | REE | Direction A: 100-900 - Direction B: 1900-2600 |  | Spain NDP Planificación Energética.2015-2020 (reference TL-2 Anexo III. Página 77) |  |  | FALSE | FALSE |  |  |  |  | 2ec3fe8b-da22-4aec-8c83-6abf117429dd.docx | TRUE | market integration; RES integration | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Laura López (REE) / Patricia Labra (REE) as substitute | laura.lopez@ree.es (plabra@ree.es) | 916508500 - Ext. 3192 |  | llopez@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/203/download/Attachment
206 | Reinforcement Southern DE | AC-busbar"" in Southern Germany for energy dispatching within Bavaria and Baden-Württemberg and gathering solar energy. | 203 | 1899-12-31 | 2018-01-12 14:43 | FALSE | inside-inside | 2024 |  | "German grid development plan: http://www.netzentwicklungsplan.de/en Information on investment 687 (in German) http://www.tennet.eu/de/netz-und-projekte/onshore-projekte/ostbayernring.html Information on investment 990 (in German) https://www.transnetbw.de/de/uebertragungsnetz/dialog-netzbau/grafenrheinfeld-kupferzell–grossgartach " | 0 | 0 | NA | TENNET-DE;TRANSNET-BW | - |  | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | 8e43e377-f783-4262-9986-4dceffeee568.xlsx | TRUE | - | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (921) 50740 - 4166 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/206/download/Attachment
207 | Reinforcement Northwestern DE | Integration of on- and offshore RES in Lower Saxony | 161 | 1899-12-31 | 2018-01-12 14:48 | FALSE | inside-inside | 2024 |  | " German grid development plan: http://www.netzentwicklungsplan.de/en Information on Investment 939 (in German) http://www.tennet.eu/de/netz-und-projekte/onshore-projekte/emden-conneforde.html Information on Investment 940 (in German) http://www.tennet.eu/de/netz-und-projekte/onshore-projekte/halbemond-emdenost.html " | 0 | 0 | NA | TENNET-DE | tbd |  | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | a317b3e9-f720-4cb2-a9cb-6760cd348c3f.pdf | TRUE | Integration of RES; retain the security of supply in southern Germany at an acceptable level | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (921) 50740 - 4166 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/207/download/Attachment
208 | N-S Western DE_section North_1 | Project 208 consists of new 380 kV overhead line s(partly in existing corridor). The project is needed for integration of on- and offshore wind energy and transport to the load centres in western and southern parts of Germany. | 180 | 1899-12-31 | 2018-01-15 14:31 | FALSE | Internal Project | 2021 |  | "Further information on the project, its investments and their necessity particularly for the German Energiewende can be found in the German grid development plan (in German): http://www.netzentwicklungsplan.de/content/der-netzentwicklungsplan-0 More detailed information on Investment 156 can be found on the investment website (in German): http://netzausbau.amprion.net/projekte/wesel-meppen/projektbeschreibung " | 1010 | 8 | NA | AMPRION;TENNET-DE | tbd |  | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | 2f647f45-8e00-4ca1-b9af-c6997716dab2.pdf | TRUE | Integration of RES; retain the security of supply in southern Germany at an acceptable level | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar; Christian Neus | kedar.kolharkar@tennet.eu; christian.neus@amprion.net | +49 (921) 50740 - 4107; +49 231 5849-12305 |  | mfranz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/208/download/Attachment
209 | Reinforcement Northeastern DE | New 380-kV-lines in the area of Schleswig-Holstein mainly for integration of Onshore-Wind. | 167 | 1899-12-31 | 2018-01-12 16:41 | FALSE | inside-inside | 2021 |  | " German grid development plan: http://www.netzentwicklungsplan.de/en Project webpage (in German) http://www.tennet.eu/de/netz-und-projekte/onshore-projekte/ostkuestenleitung.html " | 0 | 0 | NA | TENNET-DE | tbd |  | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | acd418f7-98a0-4cc1-90dd-00c8a4bc6a47.pdf | TRUE | Integration of RES; retain the security of supply in southern Germany at an acceptable level | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (921) 50740 - 4166 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/209/download/Attachment
210 | Wurmlach (AT) - Somplago (IT) interconnection | Somplago - Wurmlach interconnection is a cross-border electrical line promoted by Alpe Adria Energia Srl. The project concerns a 220kV a.c. merchant line, about 300 MW from Somplago substation to new Wurmlach substation, including Phase Shifter Transformer located in Austria". | 107 | 1899-12-31 | 2017-11-29 14:03 | TRUE | Austria - Italy | 2021 | The Somplago – Wűrmlach merchant line project (the Project) is promoted by the company Alpe Adria Energia S.r.l. (AAE). The project was implemented in the framework of the European Regulation that allows private enterprises to build and manage new electrical interconnections, in order to strengthen competitiveness of the European energy markets and to increase the cross-border capacity among Member Countries. | No other information | 92 | 1.6 | Negligible or less than 15km | Alpe Adria Energia Srl | 300 MW | PCI 3.4 - interconnection Somplago (IT) - Wurmlach (AT) |  |  |  | FALSE | FALSE |  |  |  |  | f033962a-9807-494f-8cec-b4087b4ecc1c.jpg | FALSE | The Wurmlach (AT) – Somplago (IT) Interconnection is a private project foreseen under the Reg (EC) 714/2009. The use of the transfer capacity will be defined by the exemption of the art. 17, Reg. (EU) 347/2013 issued by the EC for private purposes. | TRUE | FALSE | FALSE |  |  | FALSE | FALSE | 69733639-bcdf-43fb-9b11-d0a0cb0a4041.kml | TRUE | Fabrizio Scaramuzza | fabrizio.scaramuzza@enel.com | +393290184625 |  | fscaramuzza@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/210/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/210/download/Attachment
214 | Interco Iceland-UK | Interconnector (Sea cable) between Iceland and Great Britain. The Cable is DC with 800-1200 MW capacity and over 1.000 km long. 99.98% of the generation in Iceland is RES. Icelands hydro generation is highly flexible and ideal for complementing intermittency of GB´s growing wind sector. | 127 | 1899-12-31 | 2017-11-29 15:40 | TRUE | Iceland - Great Britain | 2030 |  |  | 1800 | 21 |  | LANDSNET;NGIHL | 1000 | The project is in the 3rd PCI list adopted by the European Commission - Project 1.13 |  |  |  | FALSE | FALSE |  |  |  |  | edc3b34b-10cd-4711-b5b5-a6d6f0a7a369.pdf | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security. | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | MARTA NAVARRETE | marta.navarrete@nationalgrid.com | +44 7812 063 912 |  | mnavarette@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/214/download/Attachment
219 | EuroAsia Interconnector | "The Euro Asia Interconnector consists of a 500 kV DC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot, Israeli and the Greek transmission networks (offshore). The Interconnector will have a capacity of 2000 MW and a total length of around 820 nautical miles/around 1518 km (approx. 329 km between CY and IL, 879 km between CY and Crete and 310 km between Crete and Athens) and allow for reverse transmission of electricity." | 204 | 1899-12-31 | 2018-01-15 13:50 | TRUE | Cyprus - Greece - Israel | "PCI 3.10.1 12/2019, PCI 3.10.2 12/2022, PCI 3.10.3 12/2020 " |  |  | 5765 | 53.5 |  | EuroAsia Interconnector | 2000 |  |  |  |  | FALSE | FALSE |  |  |  |  | faa7102b-f088-4291-a4e7-c720440943e8.pdf | FALSE | Cheaper energy will be transferred due to higher integration of renewable energy sources | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | George Killas | gkillas@euroasia-interconnector.com | 0035722792000 |  | gkillas1@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/219/download/Attachment
225 | 2nd interconnector Belgium - Germany | This project considers the possibility of a second ~1GW HVDC interconnection between Belgium and Germany at the earliest by 2028 (indicative timing). The timing as well as location, routing, capacity are subject to further studies. In this context, Elia and Amprion are conducting a bilateral feasibility study. | 160 | 1899-12-31 | 2018-01-15 13:28 | TRUE | Belgium - Germany | 2028 | Preliminary studies have indicated potential for further regional welfare increase by further increasing the interconnection capacity between Belgium and Germany. |  | 600 | 4.8 | NA | AMPRION;ELIA | 1000 |  | this project is part of the German NDP as project 313 |  |  | FALSE | FALSE |  |  |  |  | 59c713c8-67b9-4985-9dfd-dd851887af84.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhout; Christian Neus | steve.vancampenhout@elia.be; christian.neus@amprion.net | +3225467226 |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/225/download/Attachment
227 | Transbalkan Corridor | The project aim is to increase transmission capacity within Serbia and facilitate exchange of energy between north-east part of Europe and south-west of Europe. | 140 | 1899-12-31 | 2018-01-15 09:22 | TRUE | inside-outside | 2024 |  | "The Muhlbach - Eichstetten project is part of the2015 French National Development Plan and of the German Grid development plan (http://www.netzentwicklungsplan.de) " | 42 | 0 | Negligible or less than 15km | EMS, CGES, NOSBiH | 300 |  | Yes | Yes | b4fc93ca-fd49-4f7e-a1e8-ca3f861d1677.pdf | FALSE | FALSE |  |  |  |  | 0ecc65fd-3895-424e-9c1c-5cdb6b967bd6.xlsx | FALSE | This project will enable export energy toward Italy from north of Balkan region | FALSE | FALSE | TRUE | Pre-Feasibilty Studies, Feasibility Studies with general design |  | FALSE | TRUE |  | TRUE | Nebojsa Vucinic | nebojsa.vucinic | 00381648029424 |  | itrkulja@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/227/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/227/download/Agreement
228 | Muhlbach - Eichstetten | Reinforcement of the existing 400kV OHL: Deployment of a second 400kV circuit at existing double circuit OHL Muhlbach - Eichstetten, instead of the currently operated circuit Eichstetten - Vogelgruen (currently operated with 225kV). Some topological adjustments of the existing grid in the area might prove to be necessary. | 139 | 1899-12-31 | 2018-01-15 15:02 | TRUE | France - Germany | 2025 |  |  | 50 | 0.75 |  | RTE; TransnetBW; Amprion | 300MW |  |  |  |  | FALSE | FALSE |  |  |  |  | 7d15de36-b903-4f6f-acc9-8a365ce3f76c.xlsx | FALSE | Market Integration | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Tomasz Okraszewski | t.okraszewski@transnetbw.de | +49 711 21858-3436 |  | pbodin@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/228/download/Attachment
229 | GerPol Power Bridge II | Project consist from following investments: indentation to the 2x400 kV line Baczyna-Plewiska (new routes: Baczyna-Zielona Góra, Zielona Góra-Plewiska), 2x400 kV line Zielona Góra - Gubin, crossborder line 2x400 kV line Gubin (PL)-Eisenhuettenstadt (DE) | 48 | 1899-12-31 | 2018-01-12 13:16 | TRUE | Poland - Germany | 2030 | The project contributes to the following: • Increase of market integration between member states - additional NTC of 1500 MW import on PL-DE/SK/CZ synchronous profile, • Integration of additional Renewable Energy Sources on the area of western and north-western Poland as well as eastern part of Germany. | Link to PSE S.A. Development Plan where investments of this project are included : https://www.pse.pl/documents/31287/c1eca7ac-5ec1-4f7a-a7cb-a487cdf5cf9f?safeargs=646f776e6c6f61643d74727565 The implementation of the project GerPol I is a prerequisite to achieve the increase of transfer capability brought by project GerPol II. | 171.8 | 2.956 | More than 100km | 50Hertz Transmission, PSE | 1500 (import to Poland) |  |  |  |  | FALSE | FALSE |  |  |  |  | 3d3347c6-a66f-4d65-afcd-820165bd1834.xlsx | FALSE | Increase of market integration between member states. Integration of additional RES. | FALSE | FALSE | TRUE |  |  | FALSE | TRUE |  | TRUE | Krzysztof Tokarski | krzysztof.tokarski@pse.pl | +48-22-242-23-86 |  | ktokarski@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/229/download/Attachment
230 | GerPol Power Bridge I | The reinforcements in the Polish transmission network in western part of the country near Polish/German border. Construction new AC 2x400 kV lines Mikułowa - Świebodzice, Krajnik - Baczyna and Baczyna - Plewiska. | 48 | 1899-12-31 | 2018-01-12 13:20 | TRUE | Poland - Germany | 2024 | All investments in the 230 project complement each other in bringing the desired increase of Grid Transfer Capability on the Polish-German border. Vast majority of investents in this cluster connect directly to border substations and have direct impact on border flows. Project contributes to the following: • Increase of market integration between member states - additional NTC of 1500 import and 500 MW export on PL-DE/SK/CZ synchronous profile, • Integration of additional Renewable Energy Sources on the area of western and north-western Poland as well as eastern part of Germany, • Improving network security - project contributes to increase of security of supply and flexibility of the transmission network (security of supply of Poznań agglomeration area). | Link to PSE S.A. Development Plan where investments of this project are included : https://www.pse.pl/documents/31287/c1eca7ac-5ec1-4f7a-a7cb-a487cdf5cf9f?safeargs=646f776e6c6f61643d74727565 The following investments from cluster are included in 3rd PCI list : 3.14.2 Internal line between Krajnik and Baczyna (PL), 3.14.3 Internal line between Mikułowa and Świebodzice (PL), 3.14.4 Internal line between Baczyna and Plewiska (PL) | 270.69 | 1.798 | NA | 50Hertz Transmission;PSE | 1500 (import to Poland) / 500 (export from Poland) |  |  |  |  | FALSE | FALSE |  |  |  |  | 0a6c74db-cca7-40e3-9829-0b027d8d421a.xlsx | TRUE | like in TYNDP 2016 | TRUE | TRUE | FALSE |  |  | FALSE | FALSE | 97cd259c-3050-4a56-832a-426f860f9125.geojson | TRUE | Krzysztof Tokarski | krzysztof.tokarski@pse.pl | +48-22-242-23-86 |  | ktokarski@entsoe.local |  | FALSE | TRUE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/230/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/230/download/Attachment
231 | Concept project Germany-Switzerland | "This concept project focuses on increasing the transmission capacity between Germany and Switzerland. One already identified investment is the upgrade of a 220 kV crossborder line to 380 kV between the substations of Tiengen (DE) and Beznau (CH)." | 142 | 1899-12-31 | 2018-01-12 18:23 | TRUE | Germany - Switzerland | 2030 |  |  | 58 | 0.304 | NA | swissgrid; TransnetBW; Amprion | 1000 |  | The project has been approved January 2018 in the German NDP by Bundesnetzagentur. Project 204. |  |  | FALSE | FALSE |  |  |  |  | 039c65a4-5404-4bdd-95e1-7783f7a50531.xlsx | FALSE | RES Integration, | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Christian Neus | christian.neus@amprion.net | +49 231 5849 12305 |  | memery@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/231/download/Attachment
233 | Connection of Aragon Pumping hydro | Potential necessary transmission development for the connection of 3rd party storage project (pumping hydro) that has received a PCI label in the 3rd list 2017. No details about the required network are known yet. | 225 | 1899-12-31 | 2018-01-12 12:17 | FALSE | Internal boundary in Spain (generation) | 2027 | Allow the connection to the transmission system of a storage project (pumping hydro) included in the 3rd PCI list of 2017 |  | 75 | 1.125 | NA | REE | 3000 |  |  |  |  | FALSE | FALSE | Already available to ENTSOE |  |  |  | 38c7bbfd-8a08-46b8-9969-6c4558784e9b.docx | TRUE | generation connection | FALSE | FALSE | FALSE |  |  | TRUE | FALSE |  | TRUE | Laura López (REE) / Patricia Labra (REE) as substitute | laura.lopez@ree.es (plabra@ree.es) | 916508500 - Ext. 3192 |  | plabra@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/233/download/Attachment
234 | DKE - PL-1 | HVDC connection DKE-PL; | 157 | 1899-12-31 | 2018-01-03 09:16 | TRUE | Denmark-East (DK2) - Poland | >2030 | The motivation for the project is -RES integration. -SoS in DKE -Market integration | The project was CBA assessed in TYNDP 2016 | 700 | 14 | Not assessed | Energinet; PSE | 600 |  |  |  |  | FALSE | FALSE |  |  |  |  | ca2c7d0f-0f3e-4fe1-84f0-c62a869a83de.xlsx | FALSE | SOS in DKE; RES integration | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 02069f8f-f2e0-499b-b0cf-6a6e2f37c5c4.geojson | TRUE | Peter Børre Eriksen | pbe@energinet.dk | +4523338523 |  | pborre@entsoe.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/234/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/234/download/Attachment
235 | HVDC Brunsbüttel/Wilster to Großgartach/Grafenrheinfeld | 4 GW HVDC connection from Northern Germany (areas of Brunsbüttel/Wilster) to Bavaria / Baden-Württemberg (areas of Großgartach/Grafenrheinfeld).North Germany is characterised by a high amount of RES, the feed-in exceeds the local load and therefore there is a high demand for transfer to the load centres in southern parts of Germany. With the further installation of additional renewable energy, the relevance of this projects increases | 208 | 1899-12-31 | 2018-01-12 15:01 | FALSE | Internal boundary in Germany | 2025 | In order to meet the goals of the European and especially German energy policy (German Energiewende) the RES generation in Germany will be increasing strongly. With the current grid, this would lead to internal bottlenecks which occur due to high power flows mainly in the north-south direction. To reduce the related necessary amount of RES generation curtailment as well as conventional redispatch additional North-South transmission capacities in Germany are needed. Moreover, due to the nuclear phase out in Germany, the amount of reliable available generation capacity in southern Germany will decrease. To retain the security of supply (SOS) of this area at an acceptable level, additional transmission capacities towards areas with conventional generation units, RES and connections to storage (for example Scandinavia or Switzerland) are required. Due to used DC-Technology the project is able to provide reactive power and therefore helps to improve the voltage stability. This project will both directly connect Schleswig-Holstein and Lower Saxony, areas with huge amount of installed onshore wind turbines and big amounts of offshore wind farms with the southern part of Germany, an area with high consumption and connection to storage capabilities in the Alps. Furthermore it will in general significantly increase the transmission capacity to Norway, Sweden and Denmark, areas with high amounts of RES and storage plants. | German grid development plan: http://www.netzentwicklungsplan.de/content/der-netzentwicklungsplan-0 Project specific web page (in German): http://suedlink.tennet.eu/home.html https://www.transnetbw.de/de/uebertragungsnetz/dialog-netzbau/sued-link Second PCI-list: https://ec.europa.eu/energy/sites/ener/files/documents/5_2%20PCI%20annex.pdf | 0 | 0 | 0 | TenneT-DE; TransnetBW | 4000 (internal GTC); 1800 (NTC to NO and DKw) | PCI 2.10 | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | 3c602b57-b635-4c61-a4e3-cfb953239677.xlsx | TRUE | Integration of RES; retain the security of supply in southern Germany at an acceptable level | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar; Boris Gaillardon | kedar.kolharkar@tennet.eu; b.gaillardon@transnetbw.de | +49 (921) 50740 - 4166; +49 711 21858 - 3216 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/235/download/Attachment
236 | Internal Belgian Backbone West: HTLS upgrade Horta-Mercator | Project consists of replacing the conductors of the ~50km double circuit 380 kV overhead line between the substations of Horta and Mercator with high performance conductors, hereby doubling the transport capacity of the Horta-Mercator corridor. | 74 | 1899-12-31 | 2018-01-14 15:27 | FALSE | Internal Belgium Backbone West | 2019 |  | http://www.elia.be/nl/projecten/netprojecten/Mercator-Horta | 100 | 0.2 |  | ELIA | 1500 | Project is a PCI | Listed as investment in Elia's national development plan 2015-2025 |  |  | FALSE | FALSE |  |  |  |  | 6f3c670f-5c6c-4417-9c26-263967ad58ba.docx | TRUE | Capacity increase available to the operational processes dealing with market coupling and system security | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhout | steve.vancampenhout@elia.be | +3225467226 |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/236/download/Attachment
239 | Fenno-Skan 1 renewal | Replacement of the existing 400 kV HVDC cable interconnection between Finland and Sweden. Fennoskan 1 will be decomissioned at the same time with this project being commisioned, which reduces capacity between FI and SE3 by 400 MW while increasing SE2-FI by 800 MW. | 130 | 1899-12-31 | 2018-01-12 17:52 | TRUE | Finland (FI) -Sweden (SE2) | 2029 |  |  | 380 | 0.75 | NA | Fingrid;Svenska Kraftnät | 800MW(SE2<-->FI), -400MW(SE3<-->FI) |  |  | Project in draft of Swedish national plan |  | FALSE | FALSE |  |  |  |  | 8ea1b472-a4b1-4868-bcbb-337c44b4b41d.xlsx | FALSE | The capacity will be given to market. | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Petter Glantz | petter.glantz@svk.se | +46104758481 |  | pglantz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/239/download/Attachment
240 | 380-kV-grid enhancement between Area Güstrow and Wolmirstedt | 380-kV-grid enhancement between Area Güstrow and Wolmirstedt | 233 | 1899-12-31 | 2018-01-12 12:17 | FALSE | Internal Project | 2020 |  |  | 62 | 0 | Negligible or less than 15km | 50Hertz Transmission | 3300 |  | Part of German Grid Development Plan |  |  | FALSE | FALSE |  |  |  |  | 5d21d153-8f19-433c-88a0-d348ae1b382c.docx | TRUE | Integration of RES; retain the security of supply in southern Germany at an acceptable level | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Martin Ruge | martin.ruge@50hertz.com | + 49 30 5150 2030 |  | mruge@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/240/download/Attachment
241 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV lines between SS Dakovo (HR) and SS Tuzla/Gradacac (BA) to 400 kV lines. The project 241, has been proposed assessed in the TYNDP 2016, based on the results of common planning studies performed in the CSE Region during preparation of Regional investment plan 2015. The project assumes upgrade of existing 220 kV lines between SS Đakovo (HR) and SS Tuzla (BH) and SS Gradačac (BH) to 400 kV, with additional internal new double 400 kV line connecting SS Đakovo to existing 400 kV line Žerjavinec - Ernestinovo. This project is under consideration and there is a need for pre-feasibility study. | 123 | 1899-12-31 | 2018-01-09 12:50 | TRUE | Croatia - Bosnia Herzegovina | 2032 |  |  | 83.435 | 0.107 | Negligible or less than 15km | HOPS;NOS BiH | 500 |  |  |  |  | FALSE | FALSE |  |  |  |  | dea7e91b-eced-4485-b214-186f65fc00e3.xlsx | FALSE | This project will enable exporting energy from east to west part of the region. | FALSE | FALSE | FALSE | Studies performed under TYNDP2018 process |  | FALSE | TRUE |  | TRUE | Ljupko Teklic | ljupko.teklic@hops.hr | +385998023261 |  | scazin@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/241/download/Attachment
242 | Offshore Wind Baltic Sea (I) | AC grid connections connecting Offshore Wind Farms in Cluster 1 of the Baltic Sea (see German Offshore Grid Development Plan). Cluster 1 is located north east of Ruegen in the German Exclusive Economic Zone. | 234 | 1899-12-31 | 2018-01-15 08:30 | FALSE | Internal Boundary in North-East Germany | 2018 |  | The project 243, as new candidate transmission project has been proposed to be assessed in the TYNDP 2016, based on the results of common planning studies performed in the CSE Region during preparation of Regional investment plan 2015. The project assumes construcion of new single 400 kV interconnection line between Croatia and Serbia (length is approximatly 70 km). This project is under consideration and there is a need for pre-feasibility study. | 1605 | 54.57 | NA | 50Hertz Transmission | 750 |  |  |  |  | FALSE | FALSE |  |  |  |  | b9f379c8-0f45-4120-aa7d-9a13b949bdd0.docx | TRUE | Integration of RES | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Martin Ruge | martin.ruge@50hertz.com | +49 30 5150 2030 |  | mheit@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/242/download/Attachment
243 | New 400 kV interconnection line between Serbia and Croatia | Construction of new 400 kV interconnection line Sombor (RS) - Ernestinovo (HR) | 120 | 1899-12-31 | 2018-01-09 10:11 | TRUE | Croatia - Serbia | 2035 |  |  | 19.04 | 0.0245 | Negligible or less than 15km | EMS, HOPS | 500 |  |  |  |  | FALSE | FALSE |  |  |  |  | 78dc0bdd-5f51-47fa-adbf-f6cfe839a53e.xlsx | FALSE | This project will enable exporting energy from east to west part of the region. | FALSE | FALSE | FALSE | Studies performed under TYNDP2018 process |  | FALSE | TRUE |  | TRUE | Ljupko Teklic | ljupko.teklic@hops.hr | +385998023261 |  | scazin@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/243/download/Attachment
244 | Vigy - Uchtelfangen area | An upgrade of the existing over headline between the substations Ensdorf, Uchtelfangen and Vigy is planned to increase the thermal cross-border capacity. For this reinforcement the options are either the implementation of High Temperature Low Sag (HTLS) conductors or a reconstruction of the tie-line in the existing route. To allow an optimal use of the capacity increase the installation of phase shifter transformers (PSTs) is necessary. For these measures the substations have to be adjusted accordingly. | 141 | 1899-12-31 | 2018-01-11 08:54 | TRUE | France - Germany | 2027 |  | The project is part of the German National Grid Development Plan 2030, Version 2017, 2nd draft. The two investments are listed under the following projects numbers: P170: Netzverstärkung zur Erhöhung der grenzüberschreitenden Transportkapazität zwischen Deutschland und Frankreich P314: Leistungsflusssteuerung zwischen Uchtelfangen und Vigy | 120 | 0.96 | Negligible or less than 15km | Amprion;Rte | 1500 MW |  | This project is part of the French and German NDP. |  |  | FALSE | FALSE |  |  |  |  | 0a3f166e-5fac-405a-941e-00963b4971de.xlsx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security. | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Christian Neus | Christian.Neus@amprion.net | +49-231-5849-12305 |  | cstrotmann@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/244/download/Attachment
245 | Upgrade Meeden - Diele | Increase of the interconnection capacity between The Netherlands and Germany by adding one new phase shifting transformer and apply dynamic line rating on the existing 380 kV double circuit tie line between Meeden and Diele. | 176 | 1899-12-31 | 2017-11-30 13:57 | TRUE | Netherlands - Germany | 2019 | The project will increase the cross border capacity and hence increase the market capacity between the two countries. This will lead to better price convergence in the region. Furthermore the energy from RES sources can better be integrated in the Dutch and German system, avoiding spillage and in extreme cases the increase of the interconnection capacity and controllability helps in increasing the security of supply. | https://www.tennet.eu/news/detail/tennet-starts-expansion-of-the-meeden-diele-interconnector-between-the-netherlands-and-germany/ | 35 | 0 | NA | TENNET-NL;TENNET-DE | 300 |  | project described in German and Dutch NDP's |  |  | FALSE | FALSE |  |  |  |  | ae0f3cbf-fa0f-4061-a9f7-2ba21978183e.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (151) 40267054 |  | jbos@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/245/download/Attachment
247 | AQUIND Interconnector | AQUIND Interconnector is a proposed High Voltage Direct Current (HVDC) subsea and underground electric power transmission link between the South of England and Normandy in France with a net nominal power capacity of 2 GW. The Proposed Development shall consist of two independent 1000 MW interconnector links. • The 320 kV DC subsea cable route will be between 170 km to 190 km in length, spanning between the two landfall sites at Eastney (UK) and near Dieppe (France). • The British 320 kV DC terrestrial cables will be approximately 20 km long. • The French 320 kV DC terrestrial cables will be approximately 40 km long. • The 400 kV AC cable routes are not anticipated to exceed 2 km in UK. • The 400 kV AC cable routes are not anticipated to exceed 2 km in France. The main investment items are listed above, additional items will include the procurement of spare parts for the cables and converter stations. | 135 | 1899-12-31 | 2018-01-12 09:27 | TRUE | France - Great Britain | 2022 |  | http://aquind.co.uk/ | 1400 | 29 | NA | Aquind Limited | 2000MW | 1.7.4 |  |  |  | FALSE | TRUE |  |  |  | 05e5bd44-b748-43a6-a6d7-7d1b465db4c8.pdf | 8af0c987-095a-471c-9309-2484a6f63862.pdf | FALSE | With a nominal rating of 2000 MW, the AQUIND HVDC interconnector will significantly increase the cross-border capacity between GB and France, increasing competition and improving security of the electricity supply in each of the respective countries. Promoting greater competition across domestic energy markets could, in turn, help lower energy prices for consumers and businesses. AQUIND Interconnector will also help foster greater renewable energy integration and supply ancillary services, which will provide greater flexibility in managing the electricity grid. | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kirill Glukhovskoy | kirill.glukhovskoy@aquind.co.uk | +44(0)2037098094 |  | kglukhovskoy@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/247/download/Attachment |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/247/download/ExemptionProcess
248 | Offshore Wind Baltic Sea (II) | AC and DC grid connections connecting Offshore Wind Farms in Cluster 1, 2, 4 and 6 of the Baltic Sea (see German Offshore Grid Development Plan) | 235 | 1899-12-31 | 2018-01-15 08:38 | FALSE | Internal Boundary in North-East Germany | 2027 |  | Changes can occur after the auctioning procedure from 2018. The Federal Agency can change the commissioning year and capacity after 2018. | 2161 | 73.47 | Negligible or less than 15km | 50Hertz Transmission | 1650 |  |  |  |  | FALSE | FALSE |  |  |  |  | ae9586ab-074c-4f62-a481-e7c2923ac2bb.docx | TRUE | Integration of RES | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Martin Ruge | martin.ruge@50hertz.com | +49 30 5150 2030 |  | mheit@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/248/download/Attachment
250 | "Merchant line ""Castasegna (CH) - Mese (IT)""" | The planned Transmission project is a merchant line on the swiss-italian border between Castasegna (CH) and Mese (IT). The planned Cable connection in 220 kV AC has a length of around 14 km, 13.5 of witch in Italy. In connection with the realisation of the project a Ra-tionalisation of the 380 and 132 kV Grid in the region Mese (Provincia di Sondrio) is planned. The expected NTC increase is around 200-250 MW. | 243 | 1899-12-31 | 2018-01-12 17:34 | TRUE | Italy - Switzerland | 2021 | The project has a relevant impact on the 3 pillars of EU energy policy: • Address the market integration increasing the interconnection capacity between CWE and Italy; • Improve significantly the sustainability promoting a better dispatching of the existing hydro generation in the region as well as the rationalisation of the existing HV Grid in Mese --> substi-tution of existing 132 kV overhead transmission line with underground transmission cables and unlock valuable municipal land; • Improve the security of system operation removing existing bottlenecks in the north Italian HVG and easing dispatching of local hydro Generation. | TYNDP 2016 PDS Terna | 90 | 0.1 | 14 | Mera srl (a 100% subsidiary of Repower AG) | 200 |  |  |  |  | FALSE | FALSE |  |  |  |  | 8cbb12ba-5789-43e1-a81d-4dddfbc2966b.pptx | FALSE | commercial purpose | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Samuel Bontadelli | samuel.bontadelli@repower.com | +41796288777 |  | sbontadelli@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/250/download/Attachment
251 | Audorf-Dollern | New 380-kV-line Audorf – Hamburg/Nord – Dollern” in existing 220-kV-corridor. Main focus of the project is the integration of onshore-RES – mainly wind – in Schleswig-Holstein. The project is labeled as PCI 1.4.2. and 1.4.3. It is the southbound connection of PCI 1.4.1. and is necessary to increase the GTC between Dänemark/West and Germany by 720/1000 MW. | 165 | 1899-12-31 | 2018-01-12 15:07 | FALSE | Inside Germany | 2017 |  | ?The project is integrated as project under consideration in Elia's National Development Plan 2015-2025:http://www.elia.be/fr/grid-data/grid-development/plans-d-investissements/federal-development-plan-2015-2025 | 0 | 0 | 15-50km | TenneT-DE | tbd | PCI 1.4.2 and PCI 1.4.3 | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | cc3c3656-e64a-47cf-bc86-2683dfa3ab72.pdf | TRUE | integration of RES; retain the security of supply in southern Germany at an acceptable level | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (921) 50740 - 4166 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/251/download/Attachment
252 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | This project structurally strenghtens the central & eastern part of the internal Belgian backbone. The current conductors on the 380kV ring Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator will be replaced by HTLS conductors, doubling the capacity. The implementation starts with the upgrade of the Massenhoven-VanEyck section by 2024 as this is the weakest link only having 1 conductor at the moment. It then follows a phased approach running up to 2035. Phasing is subject to optimalisation in function of outage constraints (operational secutiry) and the evolution of the production park. | 82 | 1899-12-31 | 2018-01-14 15:33 | FALSE | Internal Belgian Backbone East | 2025-2035 | This upgrade will be key to sustain price convergence whilst the power flows become increasingly more volatile and international. Where in the past the location of generation and load centers was quite stable over time, this will be much less the case with the future energy mix characterized by RES geographically spread out over Europe. Depending on the climatic conditions, flows can come from the north, east, south or west, and even change several times per day as wind fronts and clouds move from one hour to the next. Upgrading the existing internal corridors also ensures the potential to integrate new large power plants domestically. |  | 600 | 1.4 | NA | ELIA | 1500 |  |  | Partly covered in Elia's national development plan 2015-2025 |  | FALSE | FALSE |  |  |  |  | 3892f0e9-1b17-4e0f-a04f-54fb4ff4cacb.docx | TRUE | Capacity increase available to the operational processes dealing with market coupling and system security | FALSE | FALSE | TRUE | Network analysis in TYNDP18 |  | FALSE | TRUE |  | TRUE | Steve Van Campenhout | steve.vancampenhout@elia.be | +3225467226 |  | pjmarsboom@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/252/download/Attachment
253 | Upstream reinforcement in France to increase FR-CH capacity | The project consists in attracting the flows to the interconnection south of Lake Geneva in order to alleviate the congestion on the link west to Lake Geneva. It is necessary before implementing Project 199 ""Lake Geneva South"" project. This project is coupled with the "PST Foretaille" project and will be implemented right after the implementation of PST in Foretaille. | 202 | 1899-12-31 | 2018-01-15 08:06 | TRUE | France - Switzerland | 2031 |  |  | 60 | 2 | Negligible or less than 15km | RTE | FR->CH 600; CH->FR 100 |  |  | Mentioned in the finalised French National Plan 2016 (ID of the project = 446) as project under consideration |  | FALSE | FALSE |  |  |  |  | 21f5d38d-324d-4dcd-b6ce-18dfe6440769.xlsx | FALSE | Market integration and RES integration | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Gabriel Dudicourt | gabriel.dudicourt@rte-france.com | +33 3 20 22 68 20 |  | gdudicourt@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/253/download/Attachment
254 | Ultranet | The Ultranet project consists of a 2 GW HVDC-connection from the Region of Osterath (Rhineland) to the Region of Philippsburg (Baden-Württemberg). It's a pilot project with DC circuits on the same pylons as AC lines and will therefore deliver profund knowledge. | 197 | 1899-12-31 | 2018-01-15 14:34 | FALSE | Internal Project | 2021 |  |  | 1070 | 8.6 |  | Amprion;TransnetBW | 2000 (internal GTC); DE-CH & DE-NL: 600 | 2.9 | The Project is part of the german NDP (Project DC2) |  |  | FALSE | FALSE |  |  |  |  | 796caa0d-cfec-415e-8fba-2a1b66efd99d.xlsx | TRUE | - | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Christian Neus | christian.neus@amprion.net | +49 231 5849-12305 |  | mfranz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/254/download/Attachment
255 | Connection Navarra-Basque Country | New AC OHL 400kV double circuit Ichaso-Castejón/Muruarte 400kV (one circuit Castejon-Ichaso, second circuit Muruarte-Ichaso) | 225 | 1899-12-31 | 2018-01-15 11:02 | FALSE | Internal boundary in Spain Navarra-Basque Country or ES-FR | 2023 | Needed to solve existing and future congestion in the parallel existing axis, mainly due to RES integration. it is part of the cantabric-mediterranean axis. in teh long term it is the network to connect the future cross border Project Navarra-Landes between France and Spain |  | 75.5 | 1.1325 | NA | REE | 1500-2000 |  | Spain NDP Planificación Energética.2015-2020 (reference TNE-2 Anexo III. Página 23) |  |  | FALSE | FALSE |  |  |  |  | e780da51-574a-48ac-b655-fa879044a51a.docx | TRUE | market integration;RES Integration; cross border impact | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Laura López (REE) / Patricia Labra (REE) as substitute | laura.lopez@ree.es (plabra@ree.es) | 916508500 - Ext. 3192 |  | llopez@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/255/download/Attachment
256 | Study to upgrade interconnection DE-NL | Market analysis revealed the need for additional cross-border capacity between Germany and The Netherlands. Therefore, a bilateral study is started to investigate options for a further increase in addition to existing and planned interconnections. | 179 | 1899-12-31 | 2018-01-12 12:43 | TRUE | Germany - Netherlands | 2035 | Amprion and TenneT are conducting technical studies on the optimisation of the existing grid near the border. For the medium-term investments in phaseshifters, upgrade of existing HV-lines and substation reconfiguration are analysed. These measures may lead to an improvement of the existing crossborder capacity in the medium-term. The necessity of a new interconnector in the long term perspective to increase the capacity between Germany and the Netherlands will be investigated in further studies. Elia is involved in the discussions of the studies. |  | 0 | 0 | NA | Amprion;TENNET-NL | 500-1000 |  |  |  |  | FALSE | FALSE |  |  |  |  | 3be05d99-1f23-40b6-9cd7-2a48c102c011.xlsx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | FALSE | FALSE | FALSE | based on bilteratel study between Amprion and Tennet NL |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar; Christian Neus | kedar.kolharkar@tennet.eu; christian.neus@amprion.net | +49 151 4026 7054; +49 231 5849-12305 |  | mbechmann@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/256/download/Attachment
258 | Westcoast line | New 380-kV-line Brunsbüttel – Niebül inside Schleswig – Holstein. Main focus of the project is the integration of onshoreRES – mainly wind – in Western Schleswig-Holstein. The project is labeled as PCI 1.3.2. It is the southbound connection of PCI 1.3.1. and is necessary to increase the GTC between Dänemark/West and Germany by 500 MW. | 164 | 1899-12-31 | 2018-01-12 15:09 | FALSE | Inside Germany | 2019 |  | German grid development plan: http://www.netzentwicklungsplan.de/en Project webpage (in German) http://www.tennet.eu/de/netz-und-projekte/onshore-projekte/westkuestenleitung.html Second PCI-list https://ec.europa.eu/energy/sites/ener/files/documents/5_2%20PCI%20annex.pdf | 198 | 0 | NA | TenneT-DE | 500 | PCI 1.3.2 | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | 5b9a141f-00d3-4ba8-b5d3-df3d9422bd8d.pdf | TRUE | Integration of RES; retain the security of supply in southern Germany at an acceptable level; increasing the capacity between DK and DE | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (921) 50740 - 4166 |  | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/258/download/Attachment
259 | HU-RO | 400 kV OHL between Hungary and Romania. In Romania, the following internal investments are necessary associated to this project: -new 400/220 kV transformer in substation Rosiori -reconductoring 220 kV OH line Urechesti-Tg. Jiu-Paroseni- Baru Mare-Hasdat -new 400/220 kV transformer in substation Resita | 97 | 1899-12-31 | 2018-01-15 10:14 | TRUE | Hungary-Romania | >2030 |  | The project was originally proposed by the ENTSO-E Common Planning Study performed during TYNDP 2016, which found potential when assessing against TYNDP 2014 Vision 4. The need was confirmed during the IoSN process of TYNDP 2018, in scenarios DG2040 and GCA2040. | 200 | 0.818 | N/A | MAVIR,Transelectrica | RO-HU : 500 MW ; HU-RO: 500 MW |  |  | Not included in the Romanian Development Plan for period 2016-2025; |  | FALSE | FALSE |  |  |  |  | f4ac2cb3-8aef-44ef-a126-68bdbeb213ca.txt | FALSE | market auction | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Virginica Zaharia / Zsolt Lengyel | virginica.zaharia@transelectrica.ro / lengyelz@mavir.hu | +40 21 30 35 657 / +36 1 304 1804 |  | vzaharia@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/259/download/Attachment
260 | New Great Britain - Netherlands interconnection | This project considers the possibility of a second 1- 2GW interconnector between GB and the Netherlands. The project will also consider UK / NL offshore wind connection optionality. | 126 | 1899-12-31 | 2017-11-29 15:28 | TRUE | Great Britain - Netherlands | 2030 | The project contributes to further integration of the UK and Central European power systems, which are characterized by different production mix structures and subsequent wholesale market price deltas. Also the time difference in wind and solar generation between UK and continent gives opportunities to further optimise the use of RES in the EU energy system. The interconnector further improves the Security of Supply, especially when the production share of RES in the UK and NL increases. As both NL and UK intend to develop large offshore wind farms in the North Sea, connection of windfarms to the interconnector will be investigated as this might optimise the use of the infrastructure between NL and UK. |  | 850 | 6 | NA | NGIHL;TENNET-NL | 1000-2000 | The project is in the 3rd PCI list - Project 1.16 |  |  |  | FALSE | FALSE |  |  |  |  | de3c09ee-d4a3-41bb-a4c8-466be1bb78af.docx | FALSE | The interconnection capacity will be available for market coupling. As synergies with offshore wind are being investigated, the use of the interconnection capacity could compete with transmission of offshore wind. | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | MARTA NAVARRETE (National Grid); Kedar Kolharkar (TENNET-NL) | marta.navarrete@nationalgrid.com (National Grid); Kedar.kolkarhar@tennet.eu (TENNET-NL) | Kedar (+49 (151) 40267054); Marta (+44 (0)7812 063 912) |  | mnavarette@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/260/download/Attachment
262 | Belgium-Netherlands: Zandvliet-Rilland | Bilateral study has assessed multiple reinforcement options. The study concluded that an upgrade of the existing corridor Zandvliet-Rilland via the installation of two additional PSTs in Zandvliet and the upgrade of Zandvliet-Rilland line to high capacity conductors is the most appropriate solution. The constuction of the substation Rilland is part of TenneT's project "Zuid-West 380", id XXX. | 21 | 1899-12-31 | 2018-01-14 15:35 | TRUE | Belgium - Netherlands | 2022 | A need has been identified during TYNDP16 to develop additional interconnection capacity between Belgium and The Netherlands. |  | 50 | 0.1 | Negligible or less than 15km | ELIA; TENNET-NL | 1000 |  |  | Project listed in Elia's national development plan edition 2015-2025 |  | FALSE | FALSE |  |  |  |  | 6c80335d-467f-4fad-b697-5388799ee089.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhout (Elia); Kedar Kolharkar (TENNET-NL) | steve.vancampenhout@elia.be; kedar.kolharkar@tennet.eu | Steve (+3225467226); Kedar (+49 (151) 40267054) |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/262/download/Attachment
263 | Lake Constance East | This project increases the capacity between CH and its neighbours DE and AT. This enables to connect large renewable generation in Northern Europe to consumers and pump storage devices in the Alps, thus noticeably increasing the mutual balancing between both regions. | 245 | 1899-12-31 | 2018-01-15 11:37 | TRUE | Switzerland, Austria, Germany | 2035 |  | This project further integrates Alpine storage and pump storage power plants. | 353 | 1.5 |  | Swissgrid, VUEN | CH > DE + AT: + 0.8 GW /// DE + AT => CH: + 0.35 GW // AT > DE: +1 GW // DE>AT: +1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | ab328750-5ab3-4e60-96d0-4738dee3f38c.xlsx | FALSE | This project increasea the capacity between on the one hand Switzerland and on the other hand Austria and Germany as well as between Austria and Germany. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Marc Emery | marc.emery@swissgrid.ch | +41 58 580 24 21 |  | memery@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/263/download/Attachment
264 | Swiss Roof I | This project increases the capacity between CH and its neighbours DE and AT. This enables to connect large renewable generation in Northern Europe to pump storage devices in the Alps, thus noticeably increasing the mutual balancing between both regions. | 245 | 1899-12-31 | 2018-01-12 16:23 | FALSE | Switzerland - Germany; and Switzerland - Austria | 2025 |  |  | 497 | 0 |  | Swissgrid | DE > CH: + 1600 MW AT > CH: + 500 MW CH > DE: + 1600 MW CH > AT: + 500 MW |  |  |  |  | FALSE | FALSE |  |  |  |  | 6e80e5c2-f127-405b-8076-fb19a61fe092.xlsx | TRUE | This project increases the capacity between on the one hand Switzerland and on the other hand Germany and Austria. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Marc Emery | marc.emery@swissgrid.ch | +41 58 580 24 21 |  | memery@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/264/download/Attachment
265 | Tessin | reinforcement of the infrastructure in canton Tessin | 245 | 1899-12-31 | 2018-01-15 09:35 | FALSE | Switzerland | 2035 |  |  | 160 | 0 |  | Swissgrid | +0.2 GW (dedicated Swiss Network Nodes => Market Nodes AT, DE, ITn and FR) |  |  |  |  | FALSE | FALSE |  |  |  |  | 2b1a71bf-3bf8-414f-8ce7-6a35900290e9.bmp | TRUE | improvement of the evacuation of hydro power | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Marc Emery | marc.emery@swissgrid.ch | +41 58 580 24 21 |  | memery@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/265/download/Attachment
266 | Swiss Ellipse I | The project helps accommodate new pump storage units which mainly support the increasing RES generation in the European areas with solar and wind generation. | 245 | 1899-12-31 | 2018-01-15 09:35 | TRUE | Switzerland | 2022 | [5 empty] | Swissgrid | +2 GW (dedicated Swiss Network Nodes => Market Nodes AT, DE, ITn and FR) |  |  |  |  | FALSE | FALSE |  |  |  |  | 093ac818-52ba-470c-aec8-5334fbb2b4b1.bmp | FALSE | xx | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Marc Emery | marc.emery@swissgrid.ch | +41 58 580 24 21 |  | memery@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/266/download/Attachment
267 | Hansa PowerBridge II | Possible second HVDC cable interconnector between southern Sweden (Bidding area SE4) and Germany (50Hertz). This project candidate is driven by market based target capacities found in the Common Planning Studies by Regional Group Baltic Sea. | 239 | 1899-12-31 | 2017-11-30 17:26 | TRUE | Sweden (SE4)-Germany | 2030 |  |  | 660 | 0 | Negligible or less than 15km | 50Hertz Transmission, Svenska Kraftnät (SvK) | 700 |  |  |  |  | FALSE | FALSE |  |  |  |  | c3c8e8c9-87fb-44a0-bdc8-ed72984cff7a.xlsx | FALSE | enhance the integration of the Nordic and the continental power market | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Thomas Koebinger | Thomas.Koebinger@50Hertz.com | "+493051502388" |  | mheit@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/267/download/Attachment
269 | Uprate the western 220kV Sevilla Ring | Uprate the 220 kV lines D.Rodrigo-Aljarafe and Aljarafe-Santiponce to increase their capacity. as commission is by end 2019, it is not expected to assess the CBA of this project | 225 | 1899-12-31 | 2018-01-15 11:28 | FALSE | Spain - Portugal | 2019 | solve some congestion that limit in certain conditions the NTC ES-PT |  | 1 | 0.015 | less than 15 km | REE | 500 PT-->ES |  | Spain NDP Planificación Energética.2015-2020 (reference TS-3 Anexo I.1. Página 7) |  |  | FALSE | FALSE |  |  |  |  | 0737bdcc-6acc-42cf-a59f-ad08a5c42afc.docx | TRUE | cross border impact | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Laura López (REE) / Patricia Labra (REE) as substitute | laura.lopez@ree.es (plabra@ree.es) | 916508500 - Ext. 3192 |  | llopez@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/269/download/Attachment
270 | FR-ES project -Aragón-Atlantic Pyrenees | " This project consist of a new HVDC interconnection between France and Spain located in the Central part of the Pyrenees between Aragón region (Spain) and Marsillón (France). Internal AC reinforcements in Spain complement the cross border section, in order to connect the new converter station to the existing network. This project was included in the 2015 and 2017 PCI list (PCI 2.27.1)" | 225 | 1899-12-31 | 2018-01-15 14:21 | TRUE | Spain - France | 2026 | Lack of cross border capacity between France and Spain is a historical need. this new interconnection will allow market integration as it will reduce Price differences and congestions between both countries, it will allow RES integration in the Iberian Peninsula, and it will secure system operation as with higher Cross border capacity the isolation of the iberian península will be improved, and therefore the strenght to overcome major incidents This project was included in the 2015 and 2017 PCI list. | Spanish National Development Planhttp://www.minetur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx French National Development Planhttp://www.rte-france.com/fr/article/schema-decennal-de-developpement-de-reseau Inter-Governmental agreement (Madrid Declaration) https://ec.europa.eu/energy/sites/ener/files/documents/Madrid%20declaration.pdf Constitution of the High Level Group on Interconnections for South West Europe http://europa.eu/rapid/press-release_IP-15-5187_en.htm " | 1200 | 3.5 | NA | REE;RTE | 1500-2000 in both directions | 2.27.1 | Spain NDP Planificación Energética.2015-2020 (reference: Anexo II.1. Página 6) France SDDR2016 Page 278 |  |  | FALSE | FALSE |  |  |  |  | ea62d50c-4ee0-42a0-b0ce-5a67ae2fe3e3.docx | FALSE | cross border impact, market integration, RES integration | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | patricia Labra in REE (jean gabriel valentin in RTE) | plabra@ree.es (jean-gabriel.valentin@rte-france.com) | 00346267774 |  | pbodin@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/270/download/Attachment
271 | "Northern Seas Offshore Grid infrastructure" - a Long Term Conceptual Project | A list of individual projects of the TYNDP projects will develop into a global scheme for Offshore Grid Infrastructure in the Northern Seas. The individual projects will be described one by one on individual project sheets. | 213 | 1899-12-31 | 2018-01-15 15:23 | TRUE | Countries around the Northern Seas | >2030 | Joint analysis of all elements together as requested by the EC. The projects (elements) get individual analysis during the CBA phase. | Insight Report TYNDP16. | 0 | 0 | NA | EirGrid, Elia System Operator, Energinet.dk, Creos Luxembourg, National Grid, RTE,TenneT TSO GmbH, SONI, Statnett, TenneT TSO B.V. | TBD |  |  |  |  | FALSE | FALSE |  |  |  |  | f3a17e05-00d9-458d-9612-8f8d5f4e3835.docx | FALSE | Market and RES integration | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Antje Orths | ano@energinet.dk; Mark.Norton@Eirgrid.com; Steve.VanCampenhout@elia.be; louis.philippe@creos.net; Amir.Alikhanzadeh@nationalgrid.com; philippe.bodin@rte-france.com; Nils.Schindzielorz@tennet.eu; Michael.McClure@soni.ltd.uk; arne.pettersen@statnett.no; Wouter.vanden.Akker@tennet.eu | +45 2333 8742 |  | aorths@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/271/download/Attachment
276 | FR-ES project -Navarra-Landes | " This Project consist of a new HVDC interconnection between France and Spain in the Western part of the Pyrenees between Pamplona area (Spain) and Cantegrit (France). The project is considered as a HVDC project of 2x1000 MW. Internal reinforcements complement the cross border section. This project was included in the 2015 and 2017 PCI list (PCI 2.27.2)"" | 225 | 1899-12-31 | 2018-01-15 14:17 | TRUE | Spain - France | 2026 | Lack of cross border capacity between France and Spain is a historical need. this new interconnection will allow market integration as it will reduce Price differences and congestions between both countries, it will allow RES integration in the Iberian Peninsula, and it will secure system operation as with higher Cross border capacity the isolation of the iberian península will be improved, and therefore the strenght to overcome major incidents This project was included in the , 2015 and 2017 PCI list | Spanish National Development Planhttp://www.minetur.gob.es/energia/planificacion/Planificacionelectricidadygas/desarrollo2015-2020/Paginas/desarrollo.aspx French National Development Planhttp://www.rte-france.com/fr/article/schema-decennal-de-developpement-de-reseau Inter-Governmental agreement (Madrid Declaration) https://ec.europa.eu/energy/sites/ener/files/documents/Madrid%20declaration.pdf Constitution of the High Level Group on Interconnections for South West Europe http://europa.eu/rapid/press-release_IP-15-5187_en.htm " | 1470 | 5.5 | less than 15 km | REE;RTE | 1500-2000 in both directions | 2.27.2 | Spain NDP Planificación Energética.2015-2020 (reference Anexo II.1. Página 18). France SDDR2016 Page 278 |  |  | FALSE | FALSE |  |  |  |  | 0b4917d0-b6f3-4325-b263-0b40517051ed.docx | FALSE | cross border impact, market integration, RES integration | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | patricia Labra in REE (jean gabriel valentin in RTE) | plabra@ree.es (jean-gabriel.valentin@rte-france.com) | 00346267774 |  | pbodin@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/276/download/Attachment
280 | FR-BE III: study Lonny-Achene-Gramme | The project aims at sustaining further market integration within the long-term perspective of the energy transition and subsequent need to develop interconnection capacity on the French-Belgium border whilst alleviating Lonny-Achene-Gramme as bottleneck. The reinforcement strategy consists of maximizing the potential of the 400kV interconnector Lonny-Achene-Gramme (1 circuit) through the use of cost-efficient technologies such as PSTs and HTLS as well as the possibility to rebuild Lonny-Achene-Gramme as a 2-circuit solution. The bilateral study will determine the appropriate implementation option and phasing of this implementation (for example: first install a PST, then upgrade the line capacity), taking into account 1) the interaction between the 400kV interconnectors Avelin-Avelgem-Horta & Lonny-Achene-Gramme in optimizing interconnection capacity 2) the required time to implement the solution 3) that by 2025 Lonny-Achene-Gramme is a structural bottleneck due to the planned nuclear phase out in Belgium | 66 | 1899-12-31 | 2018-01-14 15:37 | TRUE | France - Belgium | 2025-2030 |  |  | 100 | 0.1 | NA | ELIA; RTE | 1000 |  |  | Project under consideration listed in Elia's national development plan 2015-2025 |  | FALSE | FALSE | Study on interconnector is part of MoU between RTE & ELIA |  |  |  | 8867ec30-a1f0-489c-adab-0b71fb02e9b4.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | FALSE | FALSE | TRUE | Bottleneck structurally identified in TYNDP planning studies |  | FALSE | TRUE |  | TRUE | Steve Van Campenhout (Elia); Philippe Bodin (RTE) | steve.vancampenhout@elia.be; philippe.bodin@rte-france.com | +3225467226: +33 320 22 67 95 |  | pjmarsboom@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/280/download/Attachment
281 | ANAI: Abengoa Northern Atlantic Interconnection | "??ANAI project is a new interconnection line proposed by Inabensa (Abengoa). ANAI project will connect Spain - France - United Kingdom with a subsea multiterminal (with Voltage Source Converters) High Voltage Direct Current cable with 2,000 Megawatt of po" | 133 | 1899-12-31 | 2017-11-29 16:42 | TRUE | Spain - France - United Kingdom | 2025/2027 |  |  | 2700 | 10 | NA | Abengoa | 2000 |  |  |  |  | FALSE | FALSE |  | bffbe12a-6843-4ed3-b5a5-50b2ce1d0666.pdf |  |  | acdf9270-1f34-47fa-be59-d3543d29993e.pdf | FALSE | To meet the current interconnection needs in the Iberian Peninsula and UK, Abengoa is promoting the interconnection between Spain, France and United Kingdom. | FALSE | FALSE | FALSE |  |  | FALSE | TRUE |  | TRUE | Juan Santos | juan.santos@abengoa.com | +34 671035282 |  | pinfante@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/281/download/Attachment |  |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/281/download/StudiesUnderConstruction
282 | ASEI: Abengoa Southern Europe Interconnection | "??ASEI project is a new interconecnnection line developed by Inabensa (Abengoa). ASEI will connect Spain - France - Italy with a subsea HVDC VSC technology with 2GW power grid transfer capability." | 133 | 1899-12-31 | 2017-11-29 16:47 | TRUE | Spain - France - Italy | 2023/2025 |  |  | 1015 | 10 | NA | Abengoa | 2000 |  |  |  |  | FALSE | FALSE |  | 83b219bb-3931-4d93-96ed-148bc3787a32.pdf |  |  | 0017be69-9d55-45d1-9356-2779d480cab4.pdf | FALSE | To meet the current interconnection needs in the Iberian Peninsula and Italy, Abengoa is promoting the interconnection between Spain, France and Italy. | FALSE | FALSE | FALSE |  |  | FALSE | TRUE |  | TRUE | Juan Santos | juan.santos@abengoa.com | +34 671035282 |  | pinfante@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/282/download/Attachment |  |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/282/download/StudiesUnderConstruction
283 | TuNur | TuNur is aimed to connect to the European network a Concentrated Solar Power plant with storage to be located in Rejim Maatoug, Kebili, Tunisia, with an overall capacity exceeding 2000 MW. The connection point to the ENTSO-E network is located in Montalto di Castro, North of Rome, Italy. The transmission project will comprise: +/- 500 kV DC DC overhead line in Tunisia from the power plant to the shoring point, submarine cables from the Tunisian Northern coast to Montalto di Castro, VSC HVDC converter stations at both terminal points, short 400 kV AC cables from the HVDC converter in Montalto to Terna 400 kV station. No sea electrode is forecast. | 137 | 1899-12-31 | 2017-11-29 18:32 | TRUE | Tunisia, Italy | 2025 | The economics of the project are compelling: the site in the Sahara receives twice as much solar energy compared to sites in central Europe, thus, for the same investment, we can produce twice as much electricity. In a subsidy-free world, we will always be a low cost producer, even when transmission costs are factored in. | On July 31, 2017 TuNur Limited has filed its request for authorization with the Tunisian Ministry of Energy, Mines and Renewable Energy for a total of up to 4.5 GW solar export project in 3 tranches. A newly established solar complex in the Sahara Desert in Southwest Tunisia, near Réjim Maâtoug (Kébili Governorate) would supply the growing European market for carbon-free electricity, and stimulate much needed economic development in the interior region of the country. The project includes programs for local development and Tunisian industrial participation in the supply chain. Part of the production will be available for local and national consumption, at the option of the Tunisian government. The project is part of the solution to Europe’s increasingly urgent challenges in the energy sector: meeting the Paris Climate Agreement emissions reduction targets, replacing obsolete fossil fuel and nuclear power plants, reducing reliance on imported fossil fuels, and meeting the expected surge in electricity demand from electric vehicles. Three HVDC submarine cables systems are under development, which will allow the transport of power to Europe with low losses. The first cable links Tunisia and Malta, as Malta is already connected to the European grid, and this connection will help reinforce Malta’s position as an energy hub in the center of the Mediterranean. The second cable system will link Tunisia to central Italy, with a shoring point in Montalto, North of Rome. This second cable system has been under development for several years and is included in the TYNDP 2016 shortlist by ENTSO-E. A third cable is under study and will link Tunisia directly to the South of France. The aplication included: Submission Letter for Minister Annex A: - TuNur Legal Note Annex B: - TuNur Detailed Project Description Annex C: Supporting Documentation - Social and Economic Benefits Documents [01] Socio-Economic Study_Comete Engineering (2010). [02] Job Creation Memorandum_TuNur (2015). [03] Supply Chain Presentation_TuNur (2017). - Technical Documents [04] LoI_SEPCO3 (2017). [05] English translation of connection right in Montalto by Terna TSO (2011). [06] Validity confirmation of connection right in Montalto_Terna TSO (2015). [07] Cooperation agreement with Enemalta (2014). [08] EU Grid Integration of Tunisia Based CSP Plant_DNV KEMA_Imperial College (2012). - Economic Rationale Documents [09] LoI_MIGA (2013). [10] 500MW PPA for UK_update_Centrica (2016). [11] 500MW PPA for Germany_Centrica (2017). [12] Letter_Director General Energy EC to TuNur (19 April 2016). [13] Letter_TuNur to Commissioner Energy EC (26 February 2016). [14] LoI_State Grid International Development (2017). [15] Estimating the Value of Utility-Scale Solar Technologies in California_NREL (2014). [16] Presentation_European Energy Market (February 2017). - Environmental Aspects Documents [17] Land Requirement_Technical and Financial Analysis_TuNur (November 2013). [18] Rjim Maatoug Site Analysis Update (July 2017). [19] Rjim Maatoug Solar Resource Assessment Report_Nur Energie (2016). [20] 1 Choix du Site_Comete Engineering (2010). [21] 2 Etude du Site Retenu_Comete Engineering (2010). [22] 3 Etude d'Impact Environnementale_Comete Engineering (2010). [23] Etude de Lutte Contre l’Ensablement du Site_Comete Engineering (2010). [24] Etude des Besoins en Eau_ Dr Mamou (2012). [25] Letter_Support of Project_Gouverneur Kebili (1 November 2012). [26] Letter_Support and Status of Land Kebili_Ministre Domaines de l'Etats et Affaires Foncieres (08/01/13). [27] Letter_Support of Project_General Energy Manager to TuNur (16 February 2016). [28] Letters to and from conseil de gestion de la Tribu El Ghrib (2017). [29] Letters to and from Governorate of Kebili (2017). | 2700 | 41 | No sea return, no sea electrodes. | TuNur Limited | 2000 |  | TuNur is included in Terna 2017 network development plan, excerpt attached as "studies" |  |  | FALSE | FALSE |  | 8f235315-a474-4ad1-ad0e-79a9bc2d210b.pdf |  |  | b92103a6-0156-484a-b799-9cd10b756ee6.pdf | FALSE | mainly allow the import of 2GW CSP with storage dispatchable renewable power from Tunisia in Europe | FALSE | TRUE | FALSE |  | e0ed0e31-30cd-40c3-9b3e-684eea3cefb4.pdf | TRUE | TRUE | 9aceff06-8b01-49b6-a4ac-f50c98fa0f1c.pdf | TRUE | Maurizio Scaravaggi | ms@tunur.tn | +393383004203 |  | mscaravaggi@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/283/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/283/download/Attachment |  |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/283/download/StudiesUnderConstruction | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/283/download/TsoAgreement
284 | LEG1 | LEG1 is a Subsea HVDC Interconnection cable project of minimum 2 000 MW allowing for an electricity exchange between Europe and the South-Eastern Mediterranean Countries. The bidirectional interconnector will link Libya (Tobruk) to Greece (Linoperamata, Crete). LEG1 also comprises the development and operation of a solar power generation plant in Tobrouk. The pilot plant, currently sized at 150 MW, will identify the optimal technological combination to be implemented in the two (2) full-scale power generation plant, 1 000 MW each. Both landing points have been discussed and agreed with GECOL (General Electricity Company of Libya) and ADMIE (Hellenic TSO). LEG1 is currently being evaluated by both Hellenic and Bulgarian authorities to envisage a clustering with an existing Greece-Bulgaria interconnection project. GreenPower2020 and ADMIE are coordinating their efforts to allow for simultaneous commissioning of LEG1 and of the HVDC Crete to Greece mainland interconnector. | 244 | 1899-12-31 | 2017-12-01 15:02 | TRUE | Greece, Libya | 2021 | GreenPower2020's motivations are of social and economical nature. LEG1 will contribute to strong social enhancements by providing affordable electrical power to the Southeast European region. Simultaneously, LEG1 will also allow, depending on seasonnal needs, Libya to benefit from much needed stable power supply, as the country has initiated an internal plan to upgrade its electrical network. LEG1 will contribute to migration control towards Europe as its facilities will be implemented on one (1) of the routes chosen by migrants. As these people meet with available electrical power, facilities requiring skilled and less skilled personnel, some may wish to settle. The area will become more inclined to industrial and social development. This has already started with the recent METKA - GENERAL ELECTRIC 800 MW gas power plant. GreenPower2020 also ambitions to contribute to strong renewable energy intergation by linking LEG1 to future solar power generation plants. LEG1 will aid to reduce fossil fuels dependancy, hence CO2 emissions. | GreenPower2020 held meetings early November in Greece with ADMIE, the Ministry of Energy, the Ministry of Economy & Development and the Ministry of Foreign Affairs. The latter was supportive of the approach by previously cited Ministries. All three (3), i.e.: ADMIE, the Ministry of Energy, the Ministry of Economy were very supportive of LEG1. The Ministry of Economy is currently implementing a workgroup to progress LEG1 as soon as possible. Support letters have been requested and shall be forwarded as soon as they made available to us. Please note that GreenPower2020 holds valid Memorandums of Understanding (MoUs) with: ADMIE, GECOL, ESO (Bulgarian TSO). GreenPower2020 also has identified deep water concepts to reach the 2 700 meters cable water depth installation required for the shortest cable route. The consortium is created and is finalising cooperation agreements. Non-Disclosure Agreements (NDAs) have been signed with all involved global class companies. R&D project details shall be shortly released, as soon as cooperation framework is finalised. Project financing is well underway. Notably, the African Development Bank has shown great interest in LEG1 and have initiated the formal process which could lead to financing one third (1/3) of the project's costs. Final confirmation is expected by May 2018. | 1600 | 2.6 | Main impact as expected and assessed (cf. our CBA report) is very high RES integration. | GreenPower 2020 | 2000 |  | LEG1 is to be included in Greece's national development plan shortly. | LEG1 is being considered for clustering with existing Greece - Bulgaria and Greece internal projects. |  | FALSE | FALSE |  |  |  |  | dc6d7fb4-56f9-43aa-be6a-09f7c91faa9b.pdf | FALSE | The results of GTC calculation confirmed that full cable capacity i.e. 2000 MW can be used for power exchanges. Additionally, GTC was calculated on the boundary between Greece and neighbouring power systems (Italy, Albania Macedonia, Bulgaria, and Turkey). | FALSE | TRUE | TRUE |  |  | FALSE | FALSE | 4bba83f7-d284-4016-a614-893af3cd23d8.png | TRUE | Jean-Luc Saquet | jlsaquet@greenpower2020.net | +33 6 88 95 33 77 |  | dpowell@entsoe.eu |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/284/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/284/download/Attachment
285 | GridLink | UK (KIngsnorth sub-station) - France (Warande sub-station) 1.4 GW HVDC (VSC) electricity interconnector Connection points (substations name): Kingsnorth (UK) to Warande (France) Type of conductor: copper/aluminium (stranded or keystone, Mass Impregnated or Cross-Linked Polyethylene) Type of converters (VSC/LCC): Voltage Source Converter (VSC) Nominal voltage: ±525 kV Capacity: 1,400 MW km to each border if the infrastructure is a tie-line: Not applicable (cable length is 160 km from sub-station to sub-station, comprising 112 km in UK territory and 48 km in French territory) Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.5% (33 MW) full load; 0% (0 MW) at zero load Expected yearly unavailability, differentiating between planned and forced outages, and the maximum single failure according to the design: 2% planned outages (98% availability); 0% forced outages; maximum single failure according to the design: 1400MW In case of projects other than in the “under consideration” phase the list and features of the internal reinforcements required to connect the project in the transmission network based on the affected TSO analysis: None Main environmental impact: operational reduction of 1.6m tCO2 emissions per year from transmission of renewable and nuclear power; construction environmental effects during subsea cable installation | 57 | 1899-12-31 | 2018-01-14 13:28 | TRUE | United Kingdom, France | Q4 2022 | Security of supply Reduction in CO2 emissions Facilitate transfer of renewable energy | Project web-site: www.gridlinkinterconnector.com/ Statement on unbundling pursuant to Appendix 6.1.1 of the Practical Implementation Guide dated 2 October 2017: "GridLink Interconnector will abide by the European rules governing unbundling pursuant to the 3rd Energy Package". | 906 | 23.9 | Reduction in CO2 emissions (Average of 1.6mt/year for 25 years); construction environmental effects during subsea cable installation | iCON Infrastructure LLP | 1400 |  |  |  |  | FALSE | FALSE |  |  |  |  | 5698a4cc-8780-4e7b-80da-4cde62b0e79e.docx | FALSE | Cross border transfer of electricity | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Tony Hanlan | thanlan@elan-energy.com | +44 7799 472 366 |  | thanlan@ENTSOE.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/285/download/Attachment
286 | Greenlink | "An interconnector link between Ireland and Wales. Using subsea and onshore underground cables. Connecting EirGrid and National Grid networks / systems. Utilising high voltage direct current subsea and onshore cable. " | 215 | 1899-12-31 | 2017-11-30 15:53 | TRUE | Ireland - Wales UK | 2023 |  |  | 400 | 10 | NA | Element Power | 500 |  |  |  |  | FALSE | FALSE |  |  |  |  | c4fa5e17-1d73-4150-9c22-0a25ce2c8afb.pdf | FALSE | cross-border impact, | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Guy Nicholson | Guy.nicholson@elpower.com | +447824145479 |  | gnicholson@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/286/download/Attachment
293 | Southern Aegean Interconnector | The project refers to the construction of a submarine DC transmission link to connect the licensed RES plants at the South Aegean Sea to mainland Greece and the islands of Crete, Kos and the Dodecanese. The main link will be an HVDC link connecting the island of Levitha to both the metropolitan area of Athens and the island of Crete; the 400kV substation at Lavrion area will be the connection point in the Athens area and Korakia will be the connection point in Crete (located in the north coast). Both links will consist of two parallel cables in order to increase the reliability of each link; two converter stations are foreseen in Levitha and relevant converter stations in Lavrion and Korakia. Illustrative routing of the links is shown in the attached Entso-e map. The capacity of each link will be 600 to 800MW both directions using HVDC (High Voltage Direct Current) technology. VSA conversion technology in conjunction with plastic (XLPE) cables will be used. The licensed RES projects consist of wind and solar power plants located on 23 small uninhabited islands. The link will be used for transmitting electricity from the RES plants mentioned above to the mainland and the island of Crete. More specifically, the power produced in each island will be transferred to the island of Levitha where the main conversion station will be built acting as a hub. These connections (with the other islands) will be AC submarine cables (150 kV or 220 kV). The connection to Crete gives further possibilities for power transmission to Cyprus and further to Israel through the "EuroAsia Interconnector" (already accepted as a PCI by the E.C.). It is also possible to further extend this link to the main islands of the Dodecanese complex (namely Kos, Leros, Kalymnos, Nisyros, Tilos) in order to allow the supply of these islands and at the same time the supply of a complex of other smaller islands already connected to the main ones. This is a short link (10km to 15km long) and more likely it will be an AC one. All the installations on the islands (converter stations, substations etc) will be of closed type using GIS technology. The project increases the transfer capacity between Mainland Greece and Crete-Kos Islands and further on to Cyprus (through EuroAsia Interconnector). The project will provide the system with 1.9 TWh/year wind energy. o List of studies carried out so far for the project;  1. Wind measurements (completed)  2. Wind potential evaluation on the islands (completed)  3. Digital representation of each island terrain/relief (completed)  4. Orthophoto/Photomapping (completed)  5. Topographic drawings (completed)  6. Road Works preliminary design (completed)  7. Ports preliminary design (completed)  8. Desktop study of the cable route between Lavrio and Levitha (completed)  9. Desktop study of the cable route between Levitha and Crete (ongoing)  10. Single Line electrical drawings (competed)  11. Preliminary layout of underground cables. (completed)  12. Enviromental impact assessment (completed) | 242 | 1899-12-31 | 2018-01-12 10:08 | TRUE | Greece - Cyprus | 2024 | The Logic and Philosophy of the project It is a huge energy investment, with power 582 MW that will interconnect electrically with mainland Greece with a capacity of 600 MW cable, which plans to carry out a purely Greek company in uninhabited islets and rocks of Cyclades and Dodecanese. The philosophy is about a project, whose beneficial effects extend beyond the narrow limits of an ordinary financial investment, since they positively affect many different areas of the country, as indicative as the energy, environment and economy. The strategic location of the country, the specificity and sensitivity of the area of the Dodecanese and the use of first uninhabited islands and islets, combined with the size of the project, the overall energy needs of Greece and the current difficult economic climate, make Aegean project unique and give it a national dimension which surely in the issue of electricity interconnection can expand to European and Worldwide levels. It is a huge integrated energy investment, which consists of two sub-projects:  The project of construction of wind power plants and the abundant transformation and renewable wind energy into electrical Aegean.  The project of the produced energy transmission and in particular the interconnection project and the Cyclades and the Dodecanese in general with mainland Greece. More specifically, the production project includes the construction of a huge wind farm of a total capacity of 582 MW, which is covered by three production licenses RAE and are to be installed in uninhabited islets and rocks of the Cyclades and the Dodecanese. Electricity production is expected to rise to 1.786 GWh, surpassing the energy needs of the Cyclades and the Dodecanese, including major tourist destinations of Rhodes and Kos, with annual energy requirements amount to approximately 1.000 GWh. The transport project includes the electrical interconnection project and the region with mainland Greece and in particular with the National Interconnected Electrical System of Attica, after the energy production exceeds local needs. Energy benefits  A large improvement in the energy balance of the country because of RES and potential electricity export power, through the European and international interconnection, in all countries of the Middle East, but also to Italy mainly in the morning hours, with serious economic and wider benefits. •  The electrical interconnection project with mainland Greece and by extension the interface of the Cyclades and the Dodecanese with the electric system of the mainland, will balance the single most of the country's energy system by minimizing the risk of black out during the summer months.  The integration of the interface to the European Management Network transmission System Operators (European Network of Transmission System Operators. Entso-e), apart from the European perspective and security that gives the interface to the project and the region in general, provides the connectivity with Israel pipeline - Cyprus - Greece (EuroAsia Interconnector) 2.000 MW transfer capacity.  Thus, a unique energy system is created, which will transform the region and Greece in general a large energy hub of Southeast Europe and the Mediterranean. It can additionally be provided for further utilization of the electrical interface both with the service and other adjacent plant and stations of electricity, as well as servicing international connections from Cyprus, Egypt, Libya and other countries of the Middle East to Europe.  An ability to export electricity from RES, through the European and international interconnection, in all countries of the Middle East, but also in Italy, with serious economic and wider benefits.  Disengagement of the power from polluting lignite, imported stone and oil and gas. | "From Aegean, for Greece and the World" When Group Eunice started its course, in 2001, Greece, Europe, the World, functioned economically in an environment of accelerating growth and existed socially conditions of prosperity and positive expectations. Evaluating the development of the environment and the conditions of first years of our operation, we achieved to create a Greek Group in the space of renewable sources of energy, that was developed very rapidly, but with careful and sure steps, creating at the same time a robust infrastructure. A Group that invested in the innovation, and sought always as Greece is part of world energy map, having always a complete sense of particularities and reality of our country. These are the characteristics, that allowed in Group Eunice to continue its positive course and when Greece and the world entered in storm of crisis, unfortunately we have all experienced in the past few years. Our choice was to face the crisis not as a problem, but as occasion. We insisted in the innovation and the extraversion, because only the combination the two can only create a positive prospect. We invest in project pioneering, as “Tilos”.We advance in the production of small wind generators, because we can only contribute productively in the developmental effort. It is only with the materialization of planning’s of nodal importance, as «Aegean”, that we can only achieve growth, with profit for all. “Aegean”, an international scale energy investment of capacity 582MW, in deserted rocky islands of Dodecanese’s and Cyclades, the data change in local and in National level. The electric interconnection, the creation of 390 places of project and the aid of local economy and the reduction of atmospheric pollution, becomes a big energy node of South-Eastern Mediterranean. It is characteristic that the electric energy that will be produced will cover the energy needs 450.000 households, and will decrease the emissions of dioxide of coal at 850.000T/per year and will limit the import of oil and natural gas at 130.000.000€ per year . Along with the positive path and the breadth of its activities, the Group classifies Eunice Energy Group in dynamically developing business groups in Greece. The full harmonization with the vision of the Green Energy and innovation, classifies the Group guide developments in specific areas, as is the case with the autonomous hybrid systems. The presence of the path and our action, are based on clear assumptions as such: 1. We act and invest in an unstable social and economic International, European and Greek environment. 2. We act and invest in an International, European and Greek Energy environment in which we place enormous changes, which will determine the socioeconomic data of future generations worldwide. 3. We act and invest in a country with a deep economic crisis, trying to blend in with the upcoming energy changes in Europe. 4. We act and invest in our country, because more than any other time in its history, there has been a huge lack and need large investments. 5. We act and invest with an emphasis on innovation, which is a crucial challenge for Greece and Europe. 6. We act and invest boldly, proper planning, determination, systematic effort and faith in achieving our objectives. All projects and actions that we have implemented up to date, in combination with the projects that are now being implemented and the projects we design, place the Eunice Energy Group at the forefront of developments and changes that come in particular: In prevalence of RES with the great project of the Aegean. In autonomy, storage and saving, with "Tilos" program. The involvement of small wind turbines in the autonomous hybrid systems and beyond. On interfaces with the integration of the priorities of the European net project of the next decade, according to relevant ENTSO-e eligibility decision, the interconnection of the major project of the Aegean. It is estimated that the construction time of the entire project will be (5) five years from the issue of the installation permit, yet the gradual operation is expected to start on the third year of construction. National benefits The installation of wind power stations in uninhabited islands and rocky islets, will strengthen our national interests since under paragraph 3 of Article 121 of the law of the Sea, any rocky island that can sustain human habitation or their own economic life, have continental shelf and EEZ. This means that the installation of wind farms, and islands which cannot sustain human habitation, gain economic life and thus acquire EEZ. • Possibility of infrastructure use (ports and other installations) by the State. • Reduction of import of oil and natural gas, with a corresponding reduction of the country's dependence. • Significant strengthening and boost of the Greek economy since the materials used and the work required for the construction of the project, 61% will be covered by domestic products and Greek hands. • Improvement in the trade balance due to the corresponding reduction in imports of oil and gas. • Increase of gross domestic product. It is estimated that the direct and indirect benefits will amount to a total of 5.5 billion euros. • Reduction of excessive electricity costs in the non-interconnected islands, which with the interface will become more interconnected, thereby ensuring the uninterrupted supply of energy, while simultaneously the SGI will be reset, up to the amount of 1,020 million euro per year during the profitable duration of the project. The benefits for the Cyclades and Dodecanese islands and their inhabitant’s. Key benefits relating to the Cyclades and the Dodecanese and especially the residents of these areas are the following: • Uninterrupted supply of energy (since most islands interconnection becomes connected) and minimization of the risk of black out during the summer months. • Revitalization of the area of the Cyclades and the Dodecanese and insular area in general, whereas local communities responded positively and embraced the project. • Creation of new employment. It is estimated that during the construction will be required 2,405 man-years and rewards will amount up to € 100,000,000, while the (20) twenty-year operation and maintenance of the park will require 390 jobs, where € 17.000.000 per year will be deposited. These new posts will set in motion and a growth trend the local and regional economies, which afterwards will take off as the ensuring uninterrupted electricity flow, will favor further investments. • A tremendous significant strengthening of the local authorities, since the statutory rates of 1.7% for local authorities and 1% for residents, represent huge amounts by themselves and are able to change the economics of the wider region (about 6 cm . per year). • Ability to develop new technologies in the energy sector, and implementation of such investments. A first feature is provided for activation of SMEs and private investors in power generation and energy products. | 1500 | 96 | The project will have minor impact as the most of the installations will be located on uninhabited islands. On the contrary it will have numerous environmental benefits, as described next. Reduction of air pollutants, particularly carbon dioxide, which is emitted by burning fossil fuels, while reducing air pollution. Reduction of emissions, particularly carbon dioxide, which is emitted by burning fossil fuels, by reducing in the meantime air pollution. The "greenhouse" issue is serious, the risk is real and marginally reversible, forcing the eminently responsible, in the last meeting of G7 to reach an agreement to limit polluting gases by 40% to 70% by 2050 and to overcome the use of fossil fuels, which are responsible for the emission of carbon dioxide. Climate protection through the promotion of RES electricity production, environmental and energy is of high priority for the country. The Aegean project improves the correlation of renewables to fossil fuels. It is of great importance the fact, as can be seen by the enclosed areas tables that occupancy rates over the islets are ranging from 4.4% to 6.7%. | Kykladika Meltemia SA | 600 |  |  |  |  | FALSE | FALSE |  |  |  |  | 10197d4c-7df5-4831-b314-175fa91011a0.pdf | TRUE | The additional transfer capacity will: 1. allow the release of significant RES power such as contributing to the sustainability of the electricity sector in the islands. 2. allow the connection of Dodecanese complex to the mainland of Greece. 3. increase the transfer capacity between the Greek mainland and the island of Crete by 600-800 MW but also the transfer capacity of the first branch of the "Euroasia Interconnector" having significant cross-border impact. 4. further integrate the electricity market in Greece to include a number of isolated islands. 5. Increase the transfer capacity between Crete and Cyprus in the view of the "EuroAsia Interconnection" project | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Stefanos Garyfalakis | sg@eunice-group.com | +302103242020 |  | sgaryfalakis@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/293/download/Attachment
294 | Maali | An interconnector link between Shetland Scotland UK and Norway. Using subsea and onshore underground cables. Connecting Statnett and National Grid networks / systems. Utilising high voltage direct current subsea and onshore cable. | 216 | 1899-12-31 | 2017-11-30 15:57 | TRUE | Shetland - Norway | 2025 |  | ?? | 600 | 10 | NA | Element Power | 600 |  |  |  |  | FALSE | FALSE |  |  |  |  | f973846a-d344-496f-aebc-f9b4bfb35519.pdf | FALSE | cross-border impact, | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Guy Nicholson | guy.nicholson@elpower.com | +447824145479 |  | gnicholson@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/294/download/Attachment
296 | Britib | Interconnection project between South-West England (United Kingdom), Cordemais (France) and Basque Country (Spain) in a multiterminal HVDC configuration of 525-600 kV with 3 inputs/outputs of 1800 MW each, and a mostly subsea route from Spain to Great Britain along the French coast of about 1330 km in total. Bretagne-Britain-Iberia (BritIb). | 150 | 1899-12-31 | 2017-11-30 09:00 | TRUE | Spain, France, United Kingdom | 2023-2024 | BRITIB aims at the accomplishment of the main pillars of the European Energy Policy in both Security of supply, Solidarity and Trust, creation of the Internal Market; Efficiency; R&I and Competitiveness, and Decarbonisation: 1. Key piece of North-South Electricity corridor in Western Europe (2nd priority of EU Reg. 347/2013). Advance towards the completion of the Internal Energy Market. 2. Linking two isolated regions (UK-Ireland and Spain-Portugal) with high share of intermittent renewables (and low weather correlation) between them and with the Central Europe Grid through the strong Northern France grid. 3. Strongly contributes to the urgent implementation of the 10% interconnection target of the Iberian Peninsula by 2020 called by the European Council in October 2014. 4. High complementarity enables solar power from Spain-Portugal towards Northern Europe in summer and significant interchange of wind power between the Northern Sea region and Spain-Portugal, particularly in winter. 5. Technological breakthrough for the European industry: longest subsea power cable in the world, flexible Multiterminal configuration and highest voltage level at VSC conversion technology. 6. Convenient connecting points with little need of grid reinforcement and very low environmental impact. 7. Possible use of back-up from Spain based on strong natural gas Fired CC Plants and gas supply (LNG and CNG) and storage existing idle infrastructure. Firm production capacity could be offered avoiding investment in new generation: 8. Allows balancing services and mutual help in case of major incidents for grids' operation, among the three connected systems. Including frequency and reactive response, black start, boundary capability and constraint management: • Increased Manageability of the systems seriously affected by forecasts' volatility and uncertainty. VSC provides additional controllability • Enhanced perturbations response: Wind over-speed protection Wind and Solar voltage dips protection • Participation in ancillary services between countries | The following studies were performed and partially financed by the European Commission through the TEN-E 2011 program: • Connection points and network feasibility studies • Facilities electromechanical implementation • Configuration and converter technology assessment • Cable technology, lossess and deployment assessments • Land environmental study • Cable route high-level feasibility study • Cable route desktop evaluation and sea environmental assessment • Economic analysis and financial modeling • Cost-Benefit Analysis • Legal and regulatory analysis | 0 | 0 | Very limited environmental impact as most of the route goes through a subsea corridor. Assessment available. | ACS Cobra | 1800 | Under assessment |  |  |  | FALSE | TRUE |  | 76ff46b5-b750-49d1-b265-55dedbd2a0eb.pdf |  | 10ab8d24-19a5-425b-afb2-1ec4c7bbcf42.zip | 75666191-1fdf-40ee-a905-78ebf9313fcf.pdf | FALSE | The project will allow for power tranfer in 6 different flow directions among 3 countries: FR<->ES, FR<->UK and UK<->SP | TRUE | FALSE | FALSE |  | f318d92d-307d-4e02-beed-69f7c4b22e7b.zip | TRUE | TRUE | 434710d6-2ca4-43e3-bcd4-70b265f1815f.pdf | TRUE | David Navidad Mencía | dnavidad@acsindustria.com | Central Office: 0034914569500; Line: 0034913429022 |  | dnavidad@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/296/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/296/download/Attachment |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/296/download/ExemptionProcess | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/296/download/StudiesUnderConstruction | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/296/download/TsoAgreement
297 | BRABO II + III | Realization of a new 380 kV corridor between Zandvliet and Mercator consisting of a double-circuit AC overhead line, including a new substation 380kV in Lillo. | 81 | 1899-12-31 | 2018-01-14 15:41 | FALSE | Zandvliet-Mercator | 2020 | BRABO II and III sustain the development of interconnection capacity on the Belgian North Border towards a broader scenario framework, hereby securing the supply of electricity around the Antwerp harbour area in light of the increasing industrial demand (mainly applicable to BRABO II), as well as developing capacity for the potential integration of new production in the Antwerp area (mainly aplicable to BRABO III). |  | 120 | 0.33 | NA | ELIA | 1000 | Project is a PCI | BRABO is integrated in Elia's national development plan 2015-2025 |  |  | FALSE | FALSE |  |  |  |  | 88bc1f4f-5ea4-42d9-aac8-a433d7110f62.docx | TRUE | Capacity increase available to the operational processes dealing with market coupling and system security | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhout | steve.vancampenhout@elia.be | +3225467226 |  | pjmarsboom@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/297/download/Attachment
299 | SACOI3 | New HVDC line between Italy mainland, Corsica and Sardinia replacing existing link SACOI2 | 238 | 1899-12-31 | 2018-01-15 15:48 | TRUE | Italy-France (Corsica) | 2023 |  |  | 700 | 7 | NA | Terna; EDF | ITsar - ITcn: 400 MW; ITcn - ITsar: 400 MW; IT-FR(Corsica): 100 MW; FR(Corsica)-IT: 100 MW | Included in Third PCI list with label 2.4 |  |  |  | FALSE | FALSE |  |  |  |  | 47a95ad7-142a-45b1-b011-aec5626c4c54.pdf | FALSE | the project will allow the increase of the energy flows among Sardegna - Cordica and Italy mainland via 400 MW of additional capacity | TRUE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 |  | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/299/download/Attachment
300 | Channel Cable | Channel Cable is a new 1,000 MW high voltage direct current interconnection line to be built between the United Kingdom and France via a 137 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-10-09 11:18 | 2018-01-15 13:54 | TRUE | United Kingdom, France | 2019 |  |  | 546 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | d96a9201-f0f4-4915-8ddf-81dc3407d8b6.pdf | FALSE | Even though Channel Cable is small in comparison with the size of the UK and French electricity market (a bit less than 1 % of the market), it will significantly contribute in helping both the UK and France to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity (there is currently only one interconnection between the UK and the continent), and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | efe627c3-83f2-4fbd-8e94-a16dfddc8e1e.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 |  | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/300/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/300/download/Attachment
301 | Atlantic Link | Atlantic Link is a multi-terminal infrastructure combining 500 MW and 1,200 MW high voltage direct current interconnection projects to be built between the substations in Spain, France, United Kingdom and Ireland, creating an energy ring along the Western coasts of Europe. | 237 | 2017-10-09 11:18 | 2018-01-15 14:11 | TRUE | Spain, France, United Kingdom, Ireland | 2021 |  |  | 2786 | 20 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1.2 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | c7598fac-2c2c-4229-bd1c-950008fd1b31.pdf | FALSE | Atlantic Link will better integrate the Iberian Peninsula and Ireland with the rest of Europe and put a definite end to their isolation from the rest of the internal energy market. It will enable the integration of a greater volume of renewable energy into the grid, especially wind energy from the Iberian system. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 29f5aec5-d1df-4895-b5d0-c5259bbee590.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 |  | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/301/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/301/download/Attachment
302 | Tunisia - Italy Sicily Interconnector | Tunisia—Italy Sicily Interconnector is a new 1,000 MW high voltage direct current interconnection line connecting Tunisia with the Italian island of Sicily via a 226 km 400 kV subsea cable and with a converter station at both ends. | 237 | 2017-10-09 11:19 | 2018-01-15 13:56 | TRUE | Tunisia, Sicily | 2021 |  |  | 692 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | bee8adea-5e75-4abf-a63f-53a34cfc504b.pdf | FALSE | The interconnection will allow the two continents to exchange power and increase the use of renewable energy, tapping into the vast solar energy sources of the North Africa. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 5d07b76e-db62-41e8-a44b-8eb04eb59abf.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 |  | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/302/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/302/download/Attachment
303 | Spain - Morocco Interconnector | Spain—Morocco Interconnector is a new 1,000 MW high voltage direct current interconnection line to be built between Spain and Morocco via a 250 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-10-09 11:19 | 2018-01-15 13:56 | TRUE | Spain, Morocco | 2021 |  |  | 732 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | 58f9a116-2969-413b-951b-bc83ac5ba0d2.pdf | FALSE | The interconnection will allow the two continents to exchange power and increase the use of renewable energy, especially the wind energy from Spain. With Morocco being almost entirely reliant on imports for energy, the interconnector will provide security of supply. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | ee881945-cbc4-4698-bd7e-ea08029aa219.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 |  | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/303/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/303/download/Attachment
304 | Algeria - Italy Interconnector | Algeria—Italy Interconnector is a new 1,000 MW high voltage direct current interconnection line to be built between Algeria and the Italian island of Sardinia via a 388 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-10-09 11:19 | 2018-01-15 13:57 | TRUE | Algeria, Sardinia | 2022 |  |  | 960 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | b50a6d60-75df-45a9-b363-43d4a60eafea.pdf | FALSE | The interconnection will allow the two continents to exchange power and increase the use of renewable energy, tapping into the vast solar energy sources of the North Africa. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | e6019dc6-2212-4fe8-8783-98c5ca77a056.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 |  | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/304/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/304/download/Attachment
305 | Romania - Turkey Interconnector | Romania—Turkey Interconnector is a new 1,000 MW high voltage direct current interconnection line to be built between Romania and Turkey via a 446 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-10-09 11:20 | 2018-01-15 13:57 | TRUE | Romania, Turkey | 2023 |  |  | 1055 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | fe1ee9aa-77eb-44fe-9b9b-6acd165a3b01.pdf | FALSE | he interconnection will allow to make better use of Romania’s energy surplus, as the country is an important electricity producer, but one that needs external markets and infrastructure that would transport energy to external partners. The project will also bring a significant contribution to the development of the regional markets in South-East Europe and is in line with the Romanian policy to increase the interconnection capacity of the country. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 4af48571-6667-4e25-b629-b511ef5560ae.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 |  | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/305/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/305/download/Attachment
306 | Algeria - Spain Interconnector | Algeria—Spain Interconnector is a new 1,000 MW high voltage direct current interconnection line to be built between Algeria and Spain via a 203 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-10-09 11:20 | 2018-01-15 13:58 | TRUE | Algeria, Spain | 2023 |  |  | 655 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | b011610c-6d7d-4a42-b7bf-be677bc7200f.pdf | FALSE | The interconnection will allow the two continents to exchange power and increase the use of renewable energy, tapping into the vast solar energy sources of the North Africa. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 3d06572b-e396-4cca-b759-e3667ee0ce2f.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 |  | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/306/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/306/download/Attachment
307 | East West 1 | East West 1 is a new 400 MW high voltage direct current interconnection line to be built between Ireland and the United Kingdom via a 151 km 400 kV subsea cable and with converter stations at both ending points. East West 1 holds the exemption from third party access. | 237 | 2017-10-09 11:20 | 2018-01-15 13:58 | TRUE | Ireland, United Kingdom | 2024 |  |  | 419 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 400 MW |  |  |  |  | FALSE | FALSE |  |  |  |  | 67d7269d-8412-4cc7-9496-2c17171f9ef5.pdf | FALSE | East West 1 will better integrate Ireland with the rest of Europe and put an end to its isolation from the rest of the internal energy market. It will enable the integration of a greater volume of renewable energy into the grid, especially wind energy. It will significantly contribute in helping both countries to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 3e67888a-ea3b-4348-ab4b-2328a4db51f9.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 |  | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/307/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/307/download/Attachment
308 | East West 2 | East West 2 is a new 400 MW high voltage direct current interconnection line to be built between Ireland and the United Kingdom via a 165 km 400 kV subsea cable and with converter stations at both ending points. East West 2 holds the exemption from third party access. | 237 | 2017-10-09 11:21 | 2018-01-15 13:59 | TRUE | Ireland, United Kingdom | 2024 |  |  | 443 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 400 MW |  |  |  |  | FALSE | FALSE |  |  |  |  | e6cfd5e1-25b3-41bc-a8cf-e0de5c2fd766.pdf | FALSE | East West 2 will better integrate Ireland with the rest of Europe and put an end to its isolation from the rest of the internal energy market. It will enable the integration of a greater volume of renewable energy into the grid, especially wind energy. It will significantly contribute in helping both countries to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | f2674494-21e1-4d9c-b98b-822befab9edb.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 |  | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/308/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/308/download/Attachment
309 | NeuConnect | NeuConnect will be the first subsea HVDC electricity interconnector to connect the GB and German electricity markets. It will be approximately 680km long with a capacity of 1.4GW. | 172 | 2017-10-20 07:53 | 2018-01-12 11:43 | TRUE | Development | 2022 | This first link between the UK and Germany will provide security of supply, cost benefits to consumers and net welfare benefits. NeuConnect will also facilitate the addition of material volumes of renewable generation in GB and in Germany over the next ten years. NeuConnect has the potential to reduce carbon emissions in the UK by some 34MTCO2e. NeuConnect will improve the ability of both countries to manage intermittency associated with renewables and resultant system balancing. It will also improve the penetration of renewable generation. | NeuConnect has successfully completed the OFGEM IPA (Initial Project Assessment) for their regulated Cap and Floor Scheme and has a signed connection agreement with National Grid and initial offer from Tennet for the preferred location. |  |  | NeuConnect has the potential to reduce carbon emissions in the UK by some 34MTCO2e. This would accelerate the achievement of the UK’s legally binding CO2 reduction targets | Meridiam, Greenage Power, Frontier Power. | 1.4GW | NeuConnect will consider the PCI process after inclusion in the TYNDP due to Permitting implications. Details sent to tyndy2018@entsoe.com | See UK and German connection offer Information attached to this application from National Grid and Tennet | See UK and German connection offer information attached to this application from National Grid and Tennet | 2d613684-3187-4db2-9822-3e237861a8e5.pdf | TRUE | TRUE |  | 4c2957d0-3166-48f7-aba0-d51bd5be69ac.pdf |  | dbbc1417-320b-438d-8c82-9954f885646f.pdf | c04d00e4-e042-48b7-91a6-6a55c98f5b53.pdf | FALSE | NeuConnect Will provide a net 1400MW transfer capacity which will provide price driven cross border flows between the UK and Germany. | TRUE | TRUE | TRUE |  | 5d0808b3-ad24-4e31-986a-a1ef1db10f05.pdf | TRUE | TRUE | 914389e2-77ec-4804-9da2-e93cb46eac0f.pdf | TRUE | Jonathan Wheatley | jonathan.wheatley@frontierpower.biz | +44(0) 7976518860 | jwheatley@ENTSOE.local | jwheatley@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/309/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/309/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/309/download/Agreement | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/309/download/ExemptionProcess | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/309/download/StudiesUnderConstruction | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/309/download/TsoAgreement
312 | St. Peter - Tauern (AT internal) | St. Peter - Tauern | 224 | 2017-11-17 12:02 | 2017-11-30 17:07 |  |  | 2022 |  | PCI 3.1.2 https://ec.europa.eu/energy/sites/ener/files/documents/annex_to_pci_list_final_2017_en.pdf national development plan http://www.apg.at/de/netz/netzausbau/Netzentwicklungsplan |  |  | Negligible or less than 15km | APG | 2000 | 3.1.2 | 11-10 |  | 5ca2baa3-710c-4284-809d-4faf602494f8.pdf | TRUE | FALSE |  |  |  |  | e6d37c48-73cf-4194-9e42-c2672379c1a4.pdf | TRUE | RES integration, market integration, Security of supply | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Stefan Führer | stefan.fuehrer@apg.at | +43 (1) 50 320 / 56361 | sfuhrer@entsoe.local | dboehm@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/312/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/312/download/Agreement
313 | Isar/Altheim/Ottenhofen (DE) - St.Peter (AT) | New 380kV Line between TenneT-DE and APG (Isar/Altheim/Ottenhofen - St. Peter). This project reinforces the interconnection capacity between Austria and Germany. It supports the interaction of RES in Northern Europe (mainly in Germany) and in the eastern part of Austria with the pump storages in the Austrian Alps and therewith facilitates their utilisation. | 224 | 2017-11-17 12:09 | 2018-01-12 16:29 | TRUE | Germany, Austria | 2021 |  | Third PCI List: https://ec.europa.eu/energy/sites/ener/files/documents/annex_to_pci_list_final_2017_en.pdf NDP Austria: http://www.apg.at/de/netz/netzausbau/Netzentwicklungsplan NDP Germany: www.netzentwicklungsplan.de | 0 | 0 | Negligible or less than 15km | TenneT-DE; APG | 2000 | PCI 3.1.1 | AT: project 11-7 |  | cc559779-20a8-4529-b571-7335ebe04954.pdf | TRUE | FALSE |  |  |  |  | 0a78fbfd-1137-4819-b40d-4021b6e0129e.pdf | FALSE | The Project ensures the transmission of high RES amounts mainly coming from the northern parts of Germany to the DE-AT border and therefore helps to strengthen the connection capacity at the DE-AT border to ensure the connection to the hydro power plants in Austria | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | TenneT-DE: Kedar Kolharkar / AGP: Stefan Führer | TenneT-DE: kedar.kolharkar@tennet.eu / APG: stefan.fuehrer@apg.at | TenneT-DE: +49 (921) 50740 - 4166 / APG: +43 (1) 50 320 / 56361 | sfuhrer@entsoe.local | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/313/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/313/download/Agreement
316 | Upgrade of 220 kV line Bericevo-Divaca to 400 kV | Upgrade of existing 220 kV OHL Bericevo-Divaca to 400 kV voltage level (approximate length 80 km). | 240 | 2017-11-21 11:30 | 2018-01-15 09:43 |  |  | 2030 |  |  | 56 | 0.4 |  | ELES | 800 |  | Project included in Slovenian NDP 2017-2026 - investment no. I121-552 |  | d124608c-f31f-423b-91b0-b8f6d98a60ce.pdf | TRUE | FALSE | not relevant according to guideline - Project is internal |  |  |  | cf9e0350-6820-4fd9-a903-9bfb779aed4e.pdf | TRUE | The project will allow an increase of energy flows in predomitant east-west direction and will increase security of operation | FALSE | TRUE | FALSE | not relevant according to guideline - Project is internal |  | FALSE | FALSE |  | TRUE | Klemen Dragas | klemen.dragas@eles.si | +38614743510 | kdragas@entsoe.local | kdragas@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/316/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/316/download/Agreement
317 | Upgrade of 220 kV line Podlog-Bericevo to 400 kV | Upgrade of existing internal 220 kV OHL Podlog-Beričevo to 400 kV voltage level (approximate length 63 km). | 240 | 2017-11-21 11:31 | 2018-01-15 09:44 |  |  | 2035 |  |  | 44 | 0.3 |  | ELES | 800 |  | Project included in Slovenian NDP 2017-2026 as a future project (after year 2026) |  | b41af805-0f29-4483-91bc-d43b13aba5b2.pdf | TRUE | FALSE | not relevant according to guideline - Project is internal |  |  |  | 2a9761ff-ea38-4c8a-9094-931952fe2bf9.pdf | TRUE | The project will allow an increase of energy flows in predomitant east-west direction and will increase security of operation | FALSE | TRUE | FALSE | not relevant according to guideline - Project is internal |  | FALSE | FALSE |  | TRUE | Klemen Dragas | klemen.dragas@eles.si | +386 1 474 3510 | kdragas@entsoe.local | kdragas@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/317/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/317/download/Agreement
318 | Upgrade of 220 kV line Podlog-Cirkovce to 400 kV | Upgrade of existing internal 220 kV OHL Podlog-Cirkovce to 400 kV voltage level (approximate length 50km). | 240 | 2017-11-21 11:32 | 2018-01-15 09:44 |  |  | 2035 |  |  | 35 | 0.25 |  | ELES | 800 |  | Project included in Slovenian NDP 2017-2026 as a future project (after year 2026) |  | eab33673-71e3-4bfe-8ade-6d11b1667d37.pdf | TRUE | FALSE | not relevant according to guideline - Project is internal |  |  |  | 2e2ae912-29a2-4583-b649-27d7ff155b44.pdf | TRUE | The project will allow an increase of energy flows in predomitant east-west direction and will increase security of operation | FALSE | TRUE | FALSE | not relevant according to guideline - Project is internal |  | FALSE | FALSE |  | TRUE | Klemen Dragas | klemen.dragas@eles.si | +38614743510 | kdragas@entsoe.local | kdragas@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/318/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/318/download/Agreement
320 | Slovenia-Hungary/Croatia interconnection | The project consists of a new 80 km double circuit AC 400 kV overhead line Cirkovce-Pince and a new 400 kV Cirkovce substation (Slovenia) by which a new connection to one circuit of the existing double circuit interconnection line between Hungary and Croatia will be established. | 240 | 2017-11-21 11:45 | 2018-01-15 09:47 | TRUE | Slovenia - Hungary/Croatia | 2018 |  |  | 132.5 | 0.9 |  | ELES; MAVIR; HOPS | 1200 MW | 3.9.1 | Project included in Slovenian NDP 2017-2026 - investment no. I039-138, I039-139 |  | 173e4c59-6bc1-43b7-8361-686169084c0d.pdf | TRUE | FALSE |  |  |  |  | 5b4fd288-5a89-49dc-8537-283e1860cc1b.pdf | FALSE | The project will create a new border (Slovenia-Hungary) and establish new transfer capacities, which will contribute to market integration and market competition and also increase of the energy flows in east-west direction. | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Klemen Dragas; Zsolt Lengyel | klemen.dragas@eles.si; lengyelz@mavir.hu | +38614743510; | kdragas@entsoe.local | kdragas@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/320/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/320/download/Agreement
321 | Herbertingen - Tiengen | reinforcements of 380 kV lines between Herbertingen and Tiengen | 144 | 2017-11-21 14:05 | 2018-01-15 14:48 |  |  | 2025 |  |  | 221 | 1.77 |  | Amprion,TransnetBW | - |  | the project is part of the German NDP (project 206) |  |  | FALSE | FALSE |  |  |  |  | 1852622a-a5b0-443b-bbec-32030307b778.xlsx | TRUE | - | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Christian Neus | christian.neus@amprion.net | +49 231 5849 12305 | ezieschang@ENTSOE.local | mfranz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/321/download/Attachment
322 | Wullenstetten - Border Area (DE-AT) | - | 188 | 2017-11-21 14:11 | 2018-01-15 14:43 | TRUE | Germany - Austria | 2020 |  |  | 164 | 1.312 |  | Amprion,vuen,APG | - |  | The project is part of the german NDP. (Project 52) |  |  | FALSE | FALSE |  |  |  |  | 759ffbbd-a7f9-4cb5-acd0-37ed23f7688a.xlsx | TRUE | - | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Christian Neus | christian.neus@amprion.net | +49 231 5849 12305 | ezieschang@ENTSOE.local | mfranz@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/322/download/Attachment
323 | Dekani (SI) - Zaule (IT) interconnection | The Zaule (IT) - Dekani (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Zaule (IT) substation to Dekani (SI) substation, including a 110/135 kV Phase Shifter Transformer. | 107 | 2017-11-21 16:00 | 2017-11-29 14:46 | TRUE | Slovenia – Italy | 2020 | The Zaule (IT) - Dekani (SI) interconnection project (Project) has been implemented in the framework of the European Regulation that allows private enterprises to build and manage new electrical interconnections, in order to strengthen competitiveness of the European energy markets and to increase the cross-border capacity among Member Countries. The Project, that is design and in permitting phase, obtained exemptions from obligation on allocation of revenues resulting from auctions ex art. 16(6) Reg. 714/09/EC, with capacity allocated by TSOs and revenues transferred pro-rata to the merchant liner, and from obligation of art. 9 Dir. 2009/72/EC (unbundling). |  | 16 | 0.3 | Negligible | Adria Link Srl, E3 d.o.o., HSE d.o.o.. | 150 |  |  |  |  | FALSE | TRUE |  |  |  | 081ec1fe-67e7-471b-9844-000d15647b41.zip | 9f14decb-22a5-4bdb-b72f-89aef9b0cf08.jpg | FALSE | The Zaule (IT) - Dekani (SI) interconnection is a private project foreseen under the Reg (EC) 714/2009. The use of the transfer capacity has been defined by the exemption of the art. 17, Reg. (EU) 347/2013 issued by the EC February, Commission Decision C(2014) 9904 of 17 December 2014 and extended with the decision C(2017) 1209 final, February, 16th, 2017. The obtained exemptions relate to the obligation on allocation of revenues resulting from auctions ex art. 16(6) Reg. 714/09/EC, with capacity allocated by TSOs and revenues transferred pro-rata to the merchant liner, and relate to the obligation of art. 9 Dir. 2009/72/EC (unbundling). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 02bc8848-6827-4550-bc96-0828d0494085.kmz | TRUE | Fabrizio Scaramuzza | fabrizio.scaramuzza@enel.com | +393290184625 | fscaramuzza@ENTSOE.local | fscaramuzza@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/323/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/323/download/Attachment |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/323/download/ExemptionProcess
324 | Redipuglia (IT) - Vrtojba (SI) interconnection | The Redipuglia (IT) - Vrtojba (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Redipuglia (IT) substation to Vrtojba (SI) substation, including a 110/135 kV Phase Shifter Trasformer. | 107 | 2017-11-21 16:05 | 2017-11-29 14:45 | TRUE | Italy, Slovenia | 2020 | The Redipuglia (IT) - Vrtojba (SI) interconnection project (Project) has been implemented in the framework of the European Regulation that allows private enterprises to build and manage new electrical interconnections, in order to strengthen competitiveness of the European energy markets and to increase the cross-border capacity among Member Countries. The Project, that is design and in permitting phase, obtained exemptions from obligation on allocation of revenues resulting from auctions ex art. 16(6) Reg. 714/09/EC, with capacity allocated by TSOs and revenues transferred pro-rata to the merchant liner, and from obligation of art. 9 Dir. 2009/72/EC (unbundling). |  | 24 | 0.4 | NEGLIGIBLE | Adria Link Srl, E3 d.o.o., HSE d.o.o.. | 150 |  |  |  |  | FALSE | TRUE |  |  |  | 3ead681c-e0b4-4d44-8625-b3ec61fb3d40.zip | b1503fb4-6e87-4589-bed6-6f2dd543ab44.jpg | FALSE | The Redipuglia (IT) - Vrtojba (SI) interconnection is a private project foreseen under the Reg (EC) 714/2009. The use of the transfer capacity has been defined by the exemption of the art. 17, Reg. (EU) 347/2013 issued by the EC February, Commission Decision C(2014) 9904 of 17 December 2014 and extended with the decision C(2017) 1209 final, February, 16th, 2017. The obtained exemptions relate to the obligation on allocation of revenues resulting from auctions ex art. 16(6) Reg. 714/09/EC, with capacity allocated by TSOs and revenues transferred pro-rata to the merchant liner, and relate to the obligation of art. 9 Dir. 2009/72/EC (unbundling). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | b7274ced-bf0f-4e54-9c0d-a051817ff350.kmz | TRUE | Fabrizio Scaramuzza | fabrizio.scaramuzza@enel.com | +393290184625 | fscaramuzza@ENTSOE.local | fscaramuzza@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/324/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/324/download/Attachment |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/324/download/ExemptionProcess
325 | AT, SI, IT - South-East Alps Project | - Lienz - Obersielach (AT Internal, mandatory requirement for NTC increases on AT-IT and AT-SI border) - Obersielach - Podlog (AT-SI) (380kV +500MW NTC in both directions) - Lienz - Italy (AT - IT) (380kV +500MW IT-AT, + 600MW AT-IT) | 224 | 2017-11-22 07:45 | 2018-01-15 10:27 | TRUE | Austria-Italy; Austria-Slowenia | 2035 | The PCI 3.2.2 / investment 218 is part of the Austrian 380-kV ring and therefore a major basis for a secure and efficient connection of exiting generation and demand areas as well as a prerequisite for further connection of hydro storage power plants in the west/south part of APG further powerful interconnectors. Looking at the investment 218 itself without the context of the project 26, the increase of transmission capacity is not only given on the AT-IT and AT-SI border. Due to the fact, that this investment is the key for closing the important 380-kV-ring in Austria, an capacity increase on regional level and for wide area transports is achieved. | For the Investments: AT internal: Third PCI list (23.11.2017): https://ec.europa.eu/energy/sites/ener/files/documents/annex_to_pci_list_final_2017_en.pdf APG's NDP: http://www.apg.at/de/netz/netzausbau/Netzentwicklungsplan Link to last release of the Italian National Development Plan 2016 |  |  | Negligible or less than 15km | APG; TERNA; ELES | AT-IT 600 MW; IT-AT 500 MW; AT-SI & SI-AT 500 MW | AT internal (Lienz - Obersielach): 3.2.2 | AT internal (Lienz - Obersielach): 11-14 |  | a5afacd3-2832-40aa-86ed-d82dfae2e5b1.pdf | TRUE | FALSE |  |  |  |  | 85de301a-990c-4b3e-a7ba-31c227e0d046.pdf | TRUE | AT-SI: NTC increase as a result of the identification of system needs phase (market integration, socioeconomic welfare) | TRUE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | AGP: Stefan Führer / TERNA: Alessio Tonti / ELES: Klemen Dragas | APG: stefan.fuehrer@apg.at / TERNA: alessio.tonti@terna.it / ELES: klemen.dragas@eles.si | APG: +43 (1) 50 320 / 56361 / TERNA: +039 0683138020 / ELES: +386 1 474 3510 | sfuhrer@entsoe.local | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/325/download/Attachment | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/325/download/Agreement
328 | Interconnector DE-LUX | The project comprises the construction of two new 380-kV-substations in Germany (Aach) and Luxemburg (Bofferdange). The new substations will be connected via a new AC-link to allow a higher cross border capacity between Germany and Luxembourg. | 143 | 2017-11-22 13:16 | 2018-01-12 15:12 | TRUE | Luxembourg Germany | 2026 | The reinforcement is mainly driven by security of supply in Luxembourg especially due to load increase expected in Luxembourg and additional flows on the DE-LU border due to the new interconnection BE-LUX put in operation in 2017. The load and consumption of Luxembourg is expected to further increase until 2050 from currently 700MW to 1300MW (depending on the scenarios). The current available transfer capacity between Germany and Luxembourg is set to 980 MW and is not sufficient to cover the additional load increase expected in Luxembourg and the transit flows towards Belgium. The German-Luxemburgish border would be structurally congested and no transfer capacity would be available on the LU-BE border. In addition the reinforcement on the German border would ease the operational constraints I the German grid close to the Luxemburgish border due to the operation of the pump storage located in Vianden and additional wind parks expected in the region. |  | 158 | 1.26 | not defined | Amprion, Creos Luxembourg | 1000 MW |  |  | Included in the NDP of Luxembourg and Germany |  | FALSE | FALSE |  |  |  |  | e142f9f7-bce2-4379-9682-73c288edaffa.docx | FALSE | The capacity increase will primarily be used to ensure the security of supply of Luxembourg and secure transit flows to Belgium. | FALSE | FALSE | TRUE |  |  | FALSE | FALSE | e97c98dc-d384-4f1d-8801-ffe28538c29b.docx | TRUE | Louis Philippe | louis.philippe@creos.net | 00352 2624 8501 | lphilippe@entsoe.local | cstrotmann@entsoe.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/328/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/328/download/Attachment
329 | Stevin-Izegem/Avelgem (Kustlus): new corridor | The development of ~6 GW transport capacity through the elaboration of a new corridor in the western part of Belgium, between the Stevin axis and the Izegem/Avelgem substation. Should the corridor end in Izegem, it is to be complemented with an HTLS upgrade of the existing Izegem-Avelgem connection. Along this corridor a substation functioning as 'gateway' for the evacution of offshore potential (see for example project 120) is envisioned. This corridor is envisioned to be implemented in AC technology as per the example of the Stevin project. Timing, routing, scope, etc. subject to feasibility studies and subsequent spatial planning procedures. | 82 | 2017-11-23 17:27 | 2018-01-14 15:43 |  |  | 2028 | The capacity of the Stevin axis will be fully used by 2020 for the integration of the first wave of 2.3 GW offshore wind in the Belgian North Sea and Nemo Link. A further development of the 380 kV grid via a new corridor towards the coast creates the necessary perspective to unlock the energetic potential of the North Sea beyond 2020, including but not limited to the development of additional offshore wind in the Belgian part of the North sea. This new corridor will be linked to the Stevin corridor, creating a meshed 380 kV grid structure and thus considerably increasing the reliability and maintainability of the grid expansion to the coast, a crucial advantage considering the strategic role of the North Sea within the energy transition. The ‘Coast loop’ would also allow to connect Nautilus (the second interconnector between Belgium and Great-Britain) closer to the coast (as did the Stevin project with Nemo Link). Not only does this decrease the potential impact on the environment, it also lowers the investment cost. |  | 400 | 0.3 |  | ELIA | 6000 |  |  |  |  | FALSE | FALSE |  |  |  |  | 97dd33fa-6222-4152-9386-8d3ee4f20414.docx | TRUE | Integration of energetic potential in the North Sea: offshore wind and additional interconnectors | FALSE | FALSE | FALSE | TYNDP studies illustrating need to develop transport capacity between coast and center of Belgium |  | FALSE | TRUE |  | TRUE | Steve Van Campenhout | steve.vancampenhout@elia.be | 3225467226 | svcampenhout@entsoe.local | pjmarsboom@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/329/download/Attachment
330 | 4th 400kV CZ-SK interconnector | This new 400 kV cross-border overhead line between the substations Otrokovice (CZ) - Ladce (SK) will strenghten the transmission capacity between Slovak and Czech transmission systems, aiming to maintain secure operation of both transmission systems. | 195 | 2017-11-27 09:38 | 2018-01-15 14:58 | TRUE | Czech republic and Slovak republic | 2035 |  |  | 86.3 | 0.62 |  | CEPS,SEPS | 500 |  |  |  |  | FALSE | FALSE | Based on the bilateral study on 220 kV cross-border lines replacement |  |  |  | b2c3a8c1-49d7-45a0-a457-35ef57475026.pdf | FALSE | Market intergration and increasing security and reliability of the both transmission systems operation | FALSE | FALSE | FALSE | Based on the results of the Identification of system needs proces under the TYNDP2018 |  | FALSE | FALSE |  | TRUE | Lubos Samsely / Andrew Kasembe | lubos.samsely@sepsas.sk / kasembe@ceps.cz | +421 905 412 135 / +420 211 044 356 | lsamsely@entsoe.local | lsamsely@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/330/download/Attachment
331 | Dante | This | 87 | 2017-11-27 11:21 | 2017-11-27 11:23 | FALSE |  | 2022 |  |  | 3231 | 232 |  | none | 32 |  |  |  |  | FALSE | FALSE |  |  |  |  | d1839422-08a6-443f-b60c-1d700553b632.docx | TRUE | 32 | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | dante | tert | rrer | dpowell@entsoe.eu | dpowell@entsoe.eu |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/331/download/Attachment
332 | dante2 | ygtyy | 86 | 2017-11-27 11:28 | 2017-11-27 11:28 |  |  | 32 |  |  | 32 | 23 |  | y | 323 |  |  |  |  | FALSE | FALSE |  |  |  |  | 4802a895-88f9-418d-bddb-cf4cac64685f.docx | TRUE | 2332 | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | dante | dssd | sdds | dpowell@entsoe.eu | dpowell@entsoe.eu |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/332/download/Attachment
333 | PST Foretaille | Installation of two PSTs in Foretaille that control the flow on the Foretaille - Verbois 220 kV double line | 246 | 2017-11-27 13:10 | 2018-01-12 17:47 |  |  | 2031 |  |  | 35 | 0 |  | Swissgrid | FR > CH: +0.7 GW // CH > FR: + 0.1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | 8dfcb716-49e2-4ae8-9ab3-19f4415c32a0.xlsx | TRUE | partial covering of the CH-FR capacity increase yielded by the TYNDP 2018 Identification of System Needs | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Marc Emery | marc.emery@swissgrid.ch | +41 58 580 24 21 | memery@entsoe.local | memery@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/333/download/Attachment
335 | North Sea Wind Power Hub | This project is a building block in this modular hub-and-spoke concept connecting up to 12 GW future offshore wind Projects to the systems of Denmark, the Netherlands and Germany after 2035. On the offshore hub, interconnection capacity between these countries is created by connecting the transport capacity between the hub and countries in a "copper plate" type installation. TenneT Netherlands, TenneT Germany, Energinet and Gasunie joined forces to develop a large scale European electricity system for offshore wind in the North Sea. The North Sea Wind Power Hub (NSWPH) consortium partners consider the project to be an important possible alternative path of internationally coordinated roll-out towards accomplishing the green energy transition and achieving the Paris Agreement. By developing the North Sea Wind Power Hub project, the NSWPH consortium endeavours to make the energy transition both feasible and affordable. Central to the vision is the construction of one or more hubs at a suitable location in the North Sea with interconnectors to bordering North Sea countries. The whole system may function as a hub for transport of wind energy, an interconnection hub to the connected countries, a working hub for offshore wind developers and a location for possible Power to Gas solutions. As such the NSWPH infrastructure offers benefits by optimizing integration costs of offshore wind, increasing socio-economic welfare by further integrating energy markets, supporting security of supply at wider regional level, and providing potential for innovative power-to-gas concepts to optimize system energy costs. | 132 | 2017-11-28 06:59 | 2017-11-29 16:31 | TRUE | The Netherlands, Denmark, Germany | 2035-2040 |  |  | 0 | 0 |  | TenneT-NL, Energinet, TenneT-DE | Offshore hub connecting 12 GW of future offshore wind after 2035, and providing transfer capacity of 2000 MW to DKW, 6000 MW to DE, 4000 MW to NL. |  |  |  |  | FALSE | FALSE |  |  |  |  | 655aff54-95c5-4bbe-a3d8-a68940e38d81.docx | FALSE | The hybrid concept of the NSWPH allows for the transfer capacity to be used for cross-border trading and generation connection. The NSWPH is connected with HVDC cables to the three countries. On the offshore hub, a "copper plate" type electrical installation connects HVDC systems to shore and up to 12 GW of wind. The generated wind can be transported to all connected countries, remaining transport capacity is used for additional cross-border trade. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 458e5c69-55cb-424c-9058-9a8914e675af.jpg | TRUE | Henrik Thomsen (Energinet); Nils Schindzielorz (TenneT DE); Kedar Kolharkar (TenneT NL) | hth@energinet.dk; Nils.Schindzielorz@tennet.eu; Kedar.kolharkar@tennet.eu | +45 51677886; +49 (151) 44045759; +49 (151) 40267054 | hthomsen@entsoe.local | hthomsen@entsoe.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/335/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/335/download/Attachment
336 | Prati (IT) – Steinach (AT) | New Italy-Austria tie-line between the existing 110kV Steinach substation in Austria and 132 kV Brennero substation, including PST; and connection to 132 kV Prati di Vizze substation. | 238 | 2017-11-28 09:33 | 2018-01-15 10:27 | TRUE | ITALY-AUSTRIA | 2019 |  |  | 40 |  |  | Terna; Tinetz | IT-AT: 100 MW; AT-IT: 100 MW |  | http://download.terna.it/terna/0000/0109/45.pdf |  |  | FALSE | FALSE |  |  |  |  | 8f9a66f3-3af0-48ed-aefc-28dcacaa861e.pdf | FALSE | The project will allow the increase of the energy flows between Italy and Austria via the additional transfer capacity | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 | aconserva@ENTSOE.local | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/336/download/Attachment
337 | Conneforde-Merzen | The project consists of a new 380-kV overhead line between Merzen and Cloppenburg. North Germany is characterised by a high amount of RES, the feed-in exceeds the local load and therefore there is a high demand for transfer to the load centres in western and southern parts of Germany. With the further installation of additional offshore wind energy, the relevance of this projects increases. The project has a significant relation to the Project Ultranet (Project ID 254), which connects the western part of Germany to the south. | 183 | 2017-11-28 09:46 | 2018-01-12 15:13 |  |  | 2024 |  | Further information on the project, its investments and their necessity particularly for the German Energiewende can be found in the German grid development plan (in German): http://www.netzentwicklungsplan.de/content/der-netzentwicklungsplan-0 More detailed information can be found on the investment websites (in German): http://netzausbau.amprion.net/projekte/cloppenburg-merzen/projektbeschreibung http://www.tennet.eu/de/netz-und-projekte/onshore-projekte/conneforde-cloppenburg-merzen.html | 0 | 0 | NA | Amprion; TenneT-DE | tbd |  | it is part of the German NDP |  |  | FALSE | FALSE |  |  |  |  | 628e6c1b-0ca8-4d3a-925b-eb54893bb1f1.pdf | TRUE | Integration of RES; retain the security of supply in southern Germany at an acceptable level | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar; Christian Neus | kedar.kolharkar@tennet.eu; christian.neus@amprion.net | +49 (921) 50740 - 4166; +49 231 5849-12305 | nschindzielorz@entsoe.local | nschindzielorz@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/337/download/Attachment
338 | Adriatic HVDC link | new HVDC line between Villanova and Fano existing 400 kV substations | 238 | 2017-11-28 14:35 | 2018-01-15 10:30 |  |  | 2027 |  |  | 1150 |  |  | TERNA | 1000-1200 |  |  | Project to be included in next Terna's Network Development Plan |  | FALSE | FALSE |  |  |  |  | 2f1e817e-988d-436e-86d4-3c16aabbef17.pdf | TRUE | The project will allow the increase of the energy flows between Italy Central South and Italy Central North via 1000-1200 MW of additional capacity | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 | aconserva@ENTSOE.local | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/338/download/Attachment
339 | Italian HVDC tri-terminal link | Italian HVDC tri-terminal link | 238 | 2017-11-28 14:36 | 2018-01-15 10:30 |  |  | 2027 |  |  | 2600 |  |  | terna | 1000 MW |  |  | Project to be included in next Terna's Network Development Plan |  | FALSE | FALSE |  |  |  |  | 5790046f-8317-47c0-a5d4-9f1e561c6f49.pdf | TRUE | NA | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Terna | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 | aconserva@ENTSOE.local | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/339/download/Attachment
340 | Avelgem-Center: new corridor | The development of ~6 GW transport capacity through the elaboration of a new corridor between the Avelgem substation and the center of the Belgium (substation to be determined along the axis Bruegel-Courcelles). This corridor is envisioned to be implemented in AC technology as per the example of the Stevin project. Timing, routing, scope, etc. subject to feasibility studies and subsequent spatial planning procedures. | 82 | 2017-11-28 16:50 | 2018-01-14 15:45 |  |  | 2028 | Today, the west and the center of the country are connected on 380 kV via only one corridor between Mercator and Horta, which is currently being upgraded to HTLS. Additional capacity between the west and the center is, however, required to sustain price convergence within a European merit order increasingly characterized by RES. A new corridor between Avelgem and the center of the country would deliver around 6 GW of capacity and at the same time increases the maintainability and reliability of the grid, fulfilling the regulatory expectation that internal grids should be sufficiently strong so that society can fully reap the benefits from European market integration. Furthermore, the Avelgem – Center corridor is a pre-requisite for the integration of new offshore production capacity, for the connection of new large power plants west of Mercator, and for the integration of a second interconnector with Great-Britain (Nautilus). |  | 500 | 0.5 |  | ELIA | 6000 |  |  |  |  | FALSE | FALSE |  |  |  |  | 98679523-7b9b-40f5-a5c5-5d5d123861a9.docx | TRUE | Sustain price convergence within a European merit order increasingly characterized by RES, allow development of onshore/offshore capacity and interconnectors in the western part of Belgium | FALSE | FALSE | FALSE | TYNDP studies illustrating need to develop transport capacity between coast and center of Belgium |  | FALSE | TRUE |  | TRUE | Steve Van Campenhout | steve.vancampenhout@elia.be | +3225467226 | svcampenhout@entsoe.local | pjmarsboom@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/340/download/Attachment
341 | North CSE Corridor | This project will consists of three investments. The investments of this project are SS 400/110 Belgrade West, OHL 400 kV SS Belgrade West - WPP Cibuk and doubling existing OHL 400 kV Portile de Fier (RO) - Resica (RS). All investment from this project has significance cross-border impact on border between Romania and Serbia. | 93 | 2017-11-29 00:56 | 2018-01-15 09:20 | TRUE | Romania and Serbia | 2030 |  |  | 43.5 | 0.51 |  | EMS, Transelectrica | 700 |  | Yes |  |  | FALSE | FALSE |  |  |  |  | 6579d48a-71c4-4d8f-a323-c27ea41f0e61.xlsx | FALSE | Such level of capacity will be used mainly for exporting RES energy from Rumania towards West | FALSE | TRUE | FALSE | Resulting from an ENTSO - E system needs studies (Identification of system needs, Common planning studies) |  | FALSE | TRUE |  | TRUE | Nebojsa Vucinic | nebojsa.vucinic@ems.rs | 00381648029424 | nvucinic@entsoe.local | itrkulja@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/341/download/Attachment
342 | Central Balkan Corridor | This corridor will enable transmission energy from east to west on the border between Bulgaria and Serbia. It consists of several investments from SS Sofia West on the east to SS Bajina Basta. On that way this corridor will be directly connected with project Transbalkan corridor. | 92 | 2017-11-29 08:10 | 2018-01-15 09:24 | TRUE | Bulgaria and Serbia | 2034 |  |  | 156 | 2 |  | EMS, ESO | 550 |  | Yes |  |  | FALSE | FALSE |  |  |  |  | 5f895cc4-5761-47f0-bdbd-4518105d0776.xlsx | FALSE | Increasing capacity will be used mostly for exporting energy from Bulgaria and Turkay to west. | FALSE | TRUE | FALSE | Resulting from an ENTSO - E system needs studies (Identification of system needs, Common planning studies) |  | FALSE | TRUE |  | TRUE | Nebojsa Vucinic | nebojsa.vucinic@ems.rs | 00381648029424 | nvucinic@entsoe.local | itrkulja@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/342/download/Attachment
343 | CSE1 New | The project will contribute in strengthen Croatian transmission grid along its main north-south axis (in parallel with eastern Adriatic coast) allowing for additional long-distance power transfers (including cross border) from existing and new planned power plants (RES/wind/ and conventional/hydro and thermal/) in Croatia (coastal parts) and BiH to major consumption areas in Italy (through Slovenia) and north Croatia. The increased transfer capacity will support market integration (particularly between Croatia and Bosnia-Herzegovina) by improving security of supply (also for emergency situations), achieving higher diversity of supply&generation sources and routes, increasing resilience and flexibility of the transmission network | 120 | 2017-11-29 11:16 | 2017-11-30 09:37 | TRUE | Croatia, Bosnia and Herzegovina | 2030 |  |  | 155.7 | 0.2 | Negligible or less than 15km | HOPS, NOS BIH | 600 |  |  |  |  | FALSE | FALSE |  |  |  |  | fc745665-6728-41bb-a28f-d68260a6ad3e.xlsx | FALSE | GTC on the boundary considered will reach up to 500 MW (in predominant direction E->W) in 2030. | FALSE | FALSE | FALSE | Pre feasibility study is being contracted |  | FALSE | TRUE |  | TRUE | Ljupko Teklic | ljupko.teklic@hops.hr | +385998023261 | lteklic@entsoe.local | scazin@entsoe.local |  | FALSE | TRUE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/343/download/Attachment
344 | Reinforcements Ring NL phase II | Upgrade of existing 380kV circuits from 2,5 kA to 4 kA | 179 | 2017-11-29 15:02 | 2017-11-30 10:53 |  |  | 2035 | The project reinforces the Dutch 380kV grid to accommodate new conventional and renewable generation, to handle regional flow patterns and to facilitate the cross-border capacity increase with neighbouring countries. |  |  |  |  | TENNET-NL | 200 |  |  | Project is described in Dutch NDP (Kwaliteits- en Capaciteitsplan 2017) |  | FALSE | FALSE |  |  |  |  | 2d48985a-aa4b-490a-a9f0-2ccf67471f47.docx | TRUE | Expansion of onshore AC capacity to relieve internal congestions. | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (151) 40267054 | jbos@entsoe.local | jbos@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/344/download/Attachment
345 | Northern East-West connection NL | New double circuit 380 kV connection between the North East and Western part of the Netherlands. | 189 | 2017-11-29 15:13 | 2017-11-30 10:57 |  |  | 2040 | [5 empty] | TENNET-NL | tbd |  |  | possible congestion identified in NDP (Kwaliteits- en Capaciteitsplan 2017) after 2030, further investigation needed |  | FALSE | FALSE |  |  |  |  | b6969713-3e51-4718-9df7-8fe3ceba7723.docx | TRUE | Internal grid reinforcment to relieve internal congestions and facilitate cross-border exchanges | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (151) 40267054 | jbos@entsoe.local | jbos@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/345/download/Attachment
346 | ZuidWest380 NL | New 380 kV connection between Borssele and Tilburg, including new 380 kV substations Rilland and Tilburg. | 179 | 2017-11-29 15:28 | 2017-11-30 11:00 |  |  | 2025 | • Improve SoS • RES integration • Increase cross-border import capacity | http://www.zuid-west380kv.nl/ (in Dutch) |  |  |  | TENNET-NL | 1000 MW from BE to NL |  | Project is described in Dutch NDP (Kwaliteits- en Capaciteitsplan 2017) |  |  | FALSE | FALSE |  |  |  |  | 59251367-76fa-4563-b4d2-d785b53c6d4d.docx | TRUE | Project is being realised to facilitate large scale generation in the area of Borssele, this also includes the foreseen plans for at least 1400 MW offshore wind. Next to that, the project facilitates an increase of the import capability from Belgium. | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (151) 40267054 | jbos@entsoe.local | jbos@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/346/download/Attachment
347 | Maasvlakte – Noord Brabant connection NL | New double circuit 380 kV connection between the Maasvlakte and Noord-Brabant area within the Netherlands | 189 | 2017-11-29 15:34 | 2017-11-30 11:03 |  |  | 2040 | [5 empty] | TENNET-NL | tbd |  |  | possible congestion identified in NDP (Kwaliteits- en Capaciteitsplan 2017) after 2030, further investigation needed |  | FALSE | FALSE |  |  |  |  | d3456373-8514-4ccc-af01-169143665d54.docx | TRUE | Internal grid reinforcment to relieve internal congestions and facilitate cross-border exchanges | FALSE | FALSE | TRUE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (151) 40267054 | jbos@entsoe.local | jbos@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/347/download/Attachment
348 | NoordWest380 NL | Upgrade of existing 220kV circuits between Eemshaven and Vierverlaten to 2* 380kV – 2645MVA circuits | 179 | 2017-11-29 15:39 | 2017-11-30 11:06 |  |  | 2021 | To relieve internal congestion due to bulk transport of RES and conventional generation from Eemshaven region towards the main 380kV ring. | http://www.eemshaven-vierverlaten380kv.nl/ (in Dutch) |  |  |  | TENNET-NL | 0 |  | Project is described in Dutch NDP (Kwaliteits- en Capaciteitsplan 2017) |  |  | FALSE | FALSE |  |  |  |  | 637c7564-7c37-4dd9-a4cf-08da871bd302.docx | TRUE | Expansion onshore AC capacity | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Kedar Kolharkar | kedar.kolharkar@tennet.eu | +49 (151) 40267054 | jbos@entsoe.local | jbos@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/348/download/Attachment
349 | Organic Power Interconnector | 750MW HVDC VSC Interconnector between UK and Ireland. Three node connection. UK connection point Connah's Quay, Ireland Connection 1: Maynooth (Dublin area) Bellacorick (Mayo Area). Transmission wilol be directly between Bellacorick and Connah's Quay with a tapped connection at Maynooth. | 184 | 2017-11-30 11:21 | 2017-11-30 14:21 | TRUE | Republic of Ireland, United Kingdom | 2023 | Interconnect west of Ireland to UK via Dublin to increase penetration and availibility of renewable energy and energy storage capacity to Irish and UK markets. | This project will connect 6GWh of storage and 2GW of new wind generation to UK and Irish Transmission networks. | 1255 | 4 | underground and undersea HVDC with partial overhead in low impact areas | Organic Power International SL(Spain) via SPV OPIC Energy Ltd. (Irl) | 750MW |  |  |  |  | FALSE | FALSE |  |  |  |  | da6b5095-bf5c-4ec7-b9d3-36199bf3f54c.docx | FALSE | Increase in day ahead power trade and RE export from Ireland to UK | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | f088b6b2-f25f-4db1-8e23-3bc977da0cb6.jpg | TRUE | Maurice McCarthy | m.mccarthy@organicpowerinternational.com | 0034639577296 | mmccarthy1@ENTSOE.local | mmccarthy1@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/349/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/349/download/Attachment
350 | South Balkan Corridor | Тhis project consists of three investments: one 400 kV OHL Bitola(MK)- Elbasan(AL), and two 400 kV SS Ohrid and Kumanovo, in Macedonia. The interconnection contributes to increasing the transmission capacity in the East-West direction. Мentioned two SS-s will increase the security of supply in the SouthWest part of the FYR of Macedonia. Construction of 400 kV OHTL interconnection from SS Bitola 2 to Macedonian/Albanian border and SS 400/110 kV Ohrid 400 kV interconnection transmission line Bitola (Macedonia) - Elbasan (Albania) is the last part of the implementation of the Corridor 8 in the context of creating a corridor East-West power transmission corridor between Bulgaria, Macedonia, Albania and Italy. | 247 | 2017-11-30 11:52 | 2018-01-04 08:19 | TRUE | Macedonia - Albania | 2020 | [5 empty] | MEPSO | BTC = 500 MW | 2016 PECI/PMI Code, name El_13 | The project is included in the last NDP and validated by the corresponding NRA. |  | a1f64bee-aca1-45f9-ae64-cb43d0555b1a.PDF | TRUE | TRUE |  |  |  | fb24967f-9ded-4714-9bf4-16ad72284371.pdf |  | TRUE | Increase of the transfered energy in the east-west corridor in SEE, toward Italy. | TRUE | TRUE | FALSE | http://www.mepso.com.mk/en-us/Details.aspx?categoryID=230 |  | FALSE | TRUE | 4cbf1723-22a8-4f08-a990-df703e577cdc.zip | TRUE | Elena Achkoska | eackoska@mepso.com.mk | 00389023149096 | eackoska@entsoe.local | eackoska@entsoe.local |  | FALSE | TRUE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/350/download/Location |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/350/download/Agreement | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/350/download/ExemptionProcess
351 | Eastern HVDC Link | A new ~2GW submarine HVDC cable route from Peterhead to Hawthorn Pit with associated AC network reinforcement works at both ends | 173 | 2017-11-30 12:00 | 2018-01-15 12:42 |  |  | 2024 | Increase RES integration and SoS |  | 1460 |  |  | NGET; SHETL | 2000 |  |  |  |  | FALSE | FALSE |  |  |  |  | 9f6cc039-d2cf-4c78-b7c1-2fe8afcf32a4.docx | TRUE | Increase RES integration and SoS | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Le Fu; Richard Woodward | Le.Fu@nationalgrid.com; Richard.Woodward@nationalgrid.com | +44(0)1926656596 | aalikhanzadeh@ENTSOE.local | aalikhanzadeh@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/351/download/Attachment
353 | United Kingdom - Germany Interconnector | United Kingdom—Germany Interconnector is a new 2,000 MW high voltage direct current interconnection line to be built between the United Kingdom and Germany via a 730 km ±500 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:14 | 2018-01-15 14:00 | TRUE | United Kingdom, Germany | 2024 |  |  | 1952 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 2 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | bd7d441b-6450-4a47-bcde-cdf02a5dafbd.pdf | FALSE | United Kingdom—Germany Interconnection will better integrate Britain with the rest of continental Europe and put an end to its isolation from the rest of the internal energy market. It will enable the integration of a greater volume of renewable energy into the grid, especially wind energy. It will significantly contribute in helping both countries to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 4a5e8301-d7a5-456c-9fdf-b30b032b6f7b.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/353/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/353/download/Attachment
354 | Irish Sea Offshore Export Cable | Irish Sea Offshore Export Cable is a new 1,500 MW high voltage direct current interconnection line to be built between two substations in Ireland via a 243 km ±500 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:14 | 2018-01-15 14:00 | FALSE |  | 2024 |  |  | 906 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1.5 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | f2769b5c-377c-4636-ba88-189f944622d8.pdf | TRUE | Irish Sea Offshore Export Cable will enable the integration of a greater volume of renewable energy into the grid, especially the wind energy which is abundant in Ireland, while significantly increasing available capacity. It is a big driver to meet the renewable energy target and to reduce greenhouse gases by 20 % by 2020. The project will greatly help the Irish government to reach 40 % target of Ireland’s electricity consumption coming from renewable sources. These sources should be cost-effective, reliable and have minimal environmental impact. Subsea cable will secure delivering energy from potential offshore wind farms. Also, there is currently no 400 kV line connecting south of Ireland to the north. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 8b0d17c1-190a-442b-8001-72f245556b8c.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/354/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/354/download/Attachment
358 | Germany - Poland Interconnector | Germany—Poland Interconnector is a new 1,000 MW high voltage direct current interconnection line to be built between Germany and Poland via a 175 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:16 | 2018-01-15 14:00 | TRUE | Germany, Poland | 2025 |  |  | 608 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | 80153945-6935-488b-b31b-c56585d41f84.pdf | FALSE | Germany—Poland Interconnection will enable the integration of a greater volume of renewable energy into the grid, especially wind energy. It will significantly contribute in helping both countries to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 248393e0-aa2f-41d1-9884-429301c9888d.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/358/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/358/download/Attachment
359 | Poland - Lithuania Interconnector | Poland—Lithuania Interconnector is a new 400 MW high voltage direct current interconnection line to be built between Poland and Germany via a 258 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:17 | 2018-01-15 15:18 | TRUE | Poland, Lithuania | 2025 |  |  | 596 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 400 MW |  |  |  |  | FALSE | FALSE |  |  |  |  | ecb9a158-0848-4bee-bebb-8a01e9441fa3.pdf | FALSE | Poland—Lithuania Interconnection will enable the integration of a greater volume of renewable energy into the grid, especially wind and biomass energy. It will significantly contribute in helping both countries to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 32b7d99a-d8c2-4af8-b4fa-6940555d62d3.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/359/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/359/download/Attachment
362 | France - Spain East Interconnector | France—Spain East Interconnector is a new 400 MW high voltage direct current interconnection line to be built between France and Spain via a 113 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:17 | 2018-01-15 15:18 | TRUE | France, Spain | 2024 |  |  | 373 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 400 MW |  |  |  |  | FALSE | FALSE |  |  |  |  | 4674db99-ec34-4c68-809a-d9ce0955b775.pdf | FALSE | France—Spain East Interconnector will better integrate the Iberian Peninsula with the rest of Europe and put a definite end to its isolation from the rest of the internal energy market. It will enable the integration of a greater volume of renewable energy into the grid, especially wind and hydro energy. It will significantly contribute in helping both countries to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 8f465f37-3c99-4621-8e58-acef6e74aacd.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/362/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/362/download/Attachment
363 | Spain - Portugal North Interconnector | Spain—Portugal North Interconnector is a new 400 MW high voltage direct current interconnection line to be built between Spain and Portugal via a 159 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:17 | 2018-01-15 15:18 | TRUE | Spain, Portugal | 2024 |  |  | 432 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 400 MW |  |  |  |  | FALSE | FALSE |  |  |  |  | f38cd67e-8cc7-4af8-baba-66a534651240.pdf | FALSE | Spain—Portugal North Interconnector will better integrate Portugal with the rest of Europe. It will enable the integration of a greater volume of renewable energy into the grid, especially wind and solar energy. It will significantly contribute in helping both countries to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 00e1ec50-d74d-4e0c-850f-577a44d0a643.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/363/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/363/download/Attachment
365 | Italy - Croatia Interconnector | Italy—Croatia Interconnector is a new 1,000 MW high voltage direct current interconnection line to be built between Italy and Croatia via a 280 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:18 | 2018-01-15 15:19 | TRUE | Italy, Croatia | 2023 |  |  | 782 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | f933ecf0-7b3a-4ba6-94fc-5b16fd3f0b81.pdf | FALSE | Italy—Croatia Interconnector will enable the integration of a greater volume of renewable energy into the grid, especially solar and hydro energy. It will significantly contribute in helping both countries to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | d4426383-b4e8-4ae6-b4ca-f87388cf5072.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/365/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/365/download/Attachment
366 | Italy - Albania Interconnector | Italy—Albania Interconnector is a new 400 MW high voltage direct current interconnection line to be built between Italy and Croatia via a 127 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:18 | 2018-01-15 15:19 | TRUE | Italy, Albania | 2023 |  |  | 381 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 400 MW |  |  |  |  | FALSE | FALSE |  |  |  |  | eba34461-7da0-43a6-9594-f71c834aa745.pdf | FALSE | Italy—Albania Interconnector will enable the integration of a greater volume of renewable energy into the grid, especially solar and hydro energy. It will significantly contribute in helping Italy to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 40108fc1-e211-468c-adcc-c5029b30330a.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/366/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/366/download/Attachment
367 | Greece - Turkey Interconnector | Greece—Turkey Interconnector is a new 1,000 MW high voltage direct current interconnection line to be built between Greece and Turkey via a 393 km 400 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:19 | 2018-01-15 15:20 | TRUE | Greece, Turkey | 2024 |  |  | 890 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | e88747bf-eee3-43c5-8048-4a39c52cd4bb.pdf | FALSE | Greece—Turkey Interconnector will enable the integration of a greater volume of renewable energy into the grid. It will significantly contribute in helping Greece to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 42e49484-2685-4354-b08a-37da73e2c3c9.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/367/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/367/download/Attachment
369 | Ukraine - Poland Interconnector | Ukraine—Poland Interconnector is a new 1,000 MW high voltage direct current interconnection line to be built between Ukraine and Poland via a 205 km 400 kV land cable and with converter stations at both ending points. | 237 | 2017-11-30 12:19 | 2018-01-15 15:20 | TRUE | Ukraine, Poland | 2021 |  |  | 648 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | 244927e6-f212-4788-9ce0-ae11c23ddc91.pdf | FALSE | Ukraine—Poland Interconnector will enable the integration of a greater volume of renewable energy into the grid, especially hydro energy. It will significantly contribute in helping Poland to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 0086ddec-c5ac-4c8c-a697-6d59063f76fc.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/369/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/369/download/Attachment
370 | Ukraine - Hungary Interconnector | Ukraine—Hungary Interconnector is a new 1,000 MW high voltage direct current interconnection line to be built between Ukraine and Hungary via a 520 km 400 kV land cable and with converter stations at both ending points. | 237 | 2017-11-30 12:19 | 2018-01-15 15:21 | TRUE | Ukraine, Hungary | 2021 |  |  | 1052 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | e2f9e07b-ed3c-4335-9a0f-67956f271931.pdf | FALSE | Ukraine—Hungary Interconnector will enable the integration of a greater volume of renewable energy into the grid, especially hydro energy. It will significantly contribute in helping Hungary to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 31b2d7da-b9ca-4f40-9447-9e64ab263c9c.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/370/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/370/download/Attachment
371 | Cyprus - Turkey Interconnector | Cyprus—Turkey Interconnector is a new 2,000 MW high voltage direct current interconnection line to be built between Cyprus and Turkey via a 108 km ±500 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:20 | 2018-01-15 15:21 | TRUE | Cyprus, Turkey | 2024 |  |  | 772 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 2 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | 73bbb78b-6ed9-412b-b909-1ada8a987b46.pdf | FALSE | Cyprus—Turkey Interconnector will enable the integration of a greater volume of renewable energy into the grid, especially solar and hydro energy. It will significantly increase available capacity and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 9120984b-0089-4bf7-b931-6a02bc05c15b.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/371/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/371/download/Attachment
372 | Cyprus - Kingdom of Saudi Arabia Interconnector | Cyprus—Kingdom of Saudi Arabia Interconnector is a new 2,000 MW high voltage direct current interconnection line to be built between the south of Cyprus and the Kingdom of Saudi Arabia via a ±500 kV subsea cable and with converter stations at both ending points. | 237 | 2017-11-30 12:20 | 2018-01-15 15:22 | TRUE | Cyprus, Kingdom of Saudi Arabia | 2025 |  |  | 2749 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 2 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | 54ae1b5a-44be-4881-8450-e31fc84eb791.pdf | FALSE | Cyprus—Kingdom of Saudi Arabia Interconnector will enable the integration of a greater volume of renewable energy into the grid, especially solar energy. It will significantly increase available capacity and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). It will free up more crude oil for export from the Kingdom of Saudi Arabia. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 80538447-b856-436a-b127-f719b43bee1b.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/372/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/372/download/Attachment
374 | Germany - Russia Interconnector | Germany—Russia Interconnector is a new 2,000 MW high voltage direct current transcontinental multi-terminal interconnection line to be built between Germany and Russia via a 2,000 km ±500 kV subsea and land cable and with converter stations at each ending point. | 237 | 2017-11-30 12:20 | 2018-01-15 15:22 | TRUE | Germany, Russia | 2026 |  |  | 4060 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 2 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | 029a3630-a866-46cb-a3d2-2ef05014e7c4.pdf | FALSE | Germany—Russia Interconnection will enable the integration of a greater volume of renewable energy into the grid, especially wind and hydro energy. It will significantly contribute in helping Germany to reach politically agreed targets for interconnection (15 % by 2030), increase available capacity, and offer longer-term contracts than currently available (multi-year contracts instead of the currently prevailing daily-yearly contracts). | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 0262a158-cb6f-47ef-90c2-beb6c239382a.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/374/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/374/download/Attachment
375 | Lienz (AT) - Veneto region (IT) 220 kV | Reconstruction of the existing 220kV-interconnection line between Lienz and Veneto Region (IT) | 238 | 2017-11-30 12:57 | 2018-01-15 10:31 | TRUE | ITALY; AUSTRIA | 2024 | [5 empty] | TERNA; APG | 300 MW |  | http://download.terna.it/terna/0000/0109/45.pdf |  |  | FALSE | FALSE |  |  |  |  | 37a28b42-7cd6-43db-a04d-715c2e8a28d7.pdf | FALSE | The project will allow the increase of the energy flows between Italy and Austria via the additional transfer capacity | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | TERNA: Alessio Tonti | TERNA: alessio.tonti@terna.it | TERNA: +39 0683138020 | aconserva@ENTSOE.local | aconserva@ENTSOE.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/375/download/Attachment
376 | Refurbishment of the 400kV Meliti(GR)-Bitola(MK) interconnector | The project aims at the reconductoring of the already existing 400kV interconnector between Meliti(GR) and Bitola(MK), in order to increase transfer capacity of the interconnector. | 190 | 2017-11-30 13:28 | 2017-11-30 14:37 | TRUE | Greece-FYR of Macedonia | 2030 | [5 empty] | MEPSO(MK), IPTO(GR) | 500MW |  |  |  |  | FALSE | FALSE |  |  |  |  | ff00c3e3-cc48-4f47-9540-ac023db5a99f.xlsx | FALSE | The need of this transfer capacity increase has been identified during IOSN studies. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Aristomenis Neris | aneris@admie.gr | +302105192362 | aneris@entsoe.local | aneris@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/376/download/Attachment
377 | Upgrade BE-NL interconnector VanEyck-Maasbracht | This study envisions an upgrade of the existing interconnector VanEyck-Maasbracht between Belgium and the Netherlands making use of PSTs and/or HTLS technology. The study will determine the appropriate implementation option and timing, taking into account - The already planned upgrade of the Zandvliet-Rilland interconnector on the BE-NL border (see project 262) - The synchronisation with project study to upgrade interconnection DE-NL, also currently under consideration (see project 256) | 214 | 2017-11-30 14:13 | 2018-01-15 13:40 | TRUE | Belgium - The Netherlands | 2030 | A need has been identified to further develop interconnection capacity on the BE-NL border, hereby alleviating VanEyck-Maasbracht as bottleneck. |  |  |  |  | Elia, TENNET-NL | 500-1000 |  |  |  |  | FALSE | FALSE |  |  |  |  | 4e1a8447-4b73-4ece-933f-0dc1e6a3b94d.docx | FALSE | Capacity increase on the border available to the operational processes dealing with market coupling and system security | FALSE | FALSE | FALSE |  |  | FALSE | FALSE |  | TRUE | Steve Van Campenhout (ELIA); Kedar Kolharkar (TENNET-NL) | Steve.vancampenhout@elia.be; Kedar.kolharkar@tennet.eu (TENNET-NL) | Steve (+32 497 71 09 48) Kedar (+49 (151) 40267054) | wvdenakker@entsoe.local | jbos@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/377/download/Attachment
378 | Transformer Gatica | New transformer 400/220 kV in existing GATICA subestation | 225 | 2017-11-30 14:51 | 2017-11-30 16:52 |  |  | 2025 | Needed to solve certain congestions in certain situations in relation to the HVDC Biscay Gulf Project between Spain and France |  | 8.16 | 0.1224 |  | REE | 100 |  | Spain NDP Planificación Energética.2015-2020 (reference TI-2 Anexo II.1. Página 22) |  |  | FALSE | FALSE |  |  |  |  | 83a7bb24-7151-4de6-9a23-bef5c83d2553.docx | TRUE | cross-border impact, market Integration, RES integration | FALSE | TRUE | FALSE |  |  | FALSE | FALSE |  | TRUE | Laura López (REE) / Patricia Labra (REE) as substitute | laura.lopez@ree.es (plabra@ree.es) | 916508500 - Ext. 3192 | llopez@entsoe.local | plabra@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/378/download/Attachment
379 | Uprate Gatica lines | Uprate of the following 400kV lines that reach Gatica subestation : Gatica-Gueñes, Gatica-Amorebieta-Ichaso and Gatica-Azpeitia | 225 | 2017-11-30 15:23 | 2018-01-15 11:24 |  |  | 2025 | potential Project needed to solve posible congestions in certain situations associated to the HVDC Biscay Gulf Project between France and Spain |  | 2.18 | 0.0327 |  | REE | 100 |  |  |  |  | FALSE | FALSE | already available to ENTSOE |  |  |  | 19af8707-7569-4308-8e39-844af79b31f6.docx | TRUE | cross-border impact, market Integration, RES integration | FALSE | FALSE | FALSE | ENTSOE studies in the IoSN process and internal studies |  | FALSE | FALSE |  | TRUE | Laura López (REE) / Patricia Labra (REE) as substitute | laura.lopez@ree.es (plabra@ree.es) | 916508500 - Ext. 3192 | llopez@entsoe.local | llopez@entsoe.local |  | FALSE | FALSE |  | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/379/download/Attachment
380 | Tunisia - Italy Sardinia Interconnector | Tunisia—Italy Sardinia Interconnector is a new 1,000 MW high voltage direct current interconnection line connecting Tunisia with the Italian island of Sardinia via a 255 km 400 kV subsea cable and with a converter station at both ends. | 237 | 2017-11-30 15:40 | 2018-01-15 15:22 | TRUE | Tunisia, Sardinia | 2021 |  |  | 740 | 10 |  | Europagrid Infrastructure Holdings Designated Activity Company | 1 GW |  |  |  |  | FALSE | FALSE |  |  |  |  | e5844221-6cc7-45d1-97ac-318050157024.pdf | FALSE | The interconnection will allow the two continents to exchange power and increase the use of renewable energy, tapping into the vast solar energy sources of the North Africa. | FALSE | FALSE | FALSE |  |  | FALSE | FALSE | 1c130d7e-6766-41b0-9311-1ac25dd3d41a.pdf | TRUE | Bara Greplova | bara.greplova@europagrid.com | +353 87 464 8856 | bgreplova@ENTSOE.local | bgreplova@ENTSOE.local |  | FALSE | FALSE | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/380/download/Location | https://entsoe-projectsubscription.azurewebsites.net/api/transmission/project/380/download/Attachment

## GeoJson File (hidden)
cartodb_id | the_geom | id | project_id | name | _from | _to | elementstype | technology_type | total_route_length | voltage_level | expected_commissioning_year | status | tso_in_charge_from | tso_in_charge_to | third_party | country_1 | country_2 | country_3 | code | internal | regions
3 | 0105000020E61000000100000001020000000B000000FFFFFFFF870D1FC04CAAE04E70CA4440451A558F00981FC09884AC5DC4BC4440FFFFFFFF37A81FC070D4FDD9E0B7444000000000581F20C0AD1040CB67AC44403B02EC53254920C09CC5D18DF0A14440000000C0BF7E20C07D8953D68882444000000000097D20C062593770E5814440000000A0186420C0625EFA20017C4440FFFFFF3FD29120C0D5D82EF9CB74444000000080ECAF20C061DAF8B57F78444000000040E3BC20C04FBB7AB5087A4440 | 4 | 1 | V.Minho -R.Pena-FridÃ£o-Feira | V.Minho (by Ribeira de Pena and FridÃ£o) | Feira (by Ribeira de Pena and FridÃ£o) | Overhead Line | AC | 131 | 400 | 2022-2024 | In Permitting | REN | REN | FALSE | Portugal |  |  |  | TRUE | CSW
1 | 0104000020E6100000010000000101000000FFFFFFFF37A81FC08C4A811DBFB74440 | 474 | 1 | Substation Ribeira de Pena | Ribeira de Pena (PT) | - | Substation | AC | 0 | 400 | 2022-2024 | In Permitting | REN | - | FALSE | Portugal |  |  |  | TRUE | CSW
2 | 0105000020E610000001000000010200000003000000FFFFFFFF65A720C0D84E8BD925CC4440000000007CDC20C08A70915C0ABB444000000000F4EB20C0FAF071C65EA24440 | 2 | 1 | Pedralva-Sobrado | Pedralva (PT) | Sobrado (PT) | Overhead Line | AC | 67 | 400 | 2022-2023 | Planned but not yet permitting | REN | REN | FALSE | Portugal |  |  |  | TRUE | CSW
4 | 0104000020E6100000010000000101000000FFFFFFFFFB3E20C0E5967474DCA64440 | 941 | 1 | Switching station FridÃ£o | FridÃ£o | Fontefria (ES) | Substation | AC | 0 | 400 | 2026-2030 | In Permitting | REN | - | FALSE | Portugal |  |  |  | TRUE | CSW
9 | 0104000020E610000001000000010100000000000000D33921C05D5C6D6BA2D14440 | 500 | 4 | Ponte de Lima (PT) | Ponte de Lima (PT) | La Ribina (ES) | Substation | AC | 0 | 400 | 2021-01-01 | In Permitting | REN | REN | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
5 | 0104000020E61000000100000001010000000000000090D720C0F2F4CB8ADF134540 | 498 | 4 | SE Fontefria 400/220kV | Fontefria (ES) | Beariz (ES) | Substation | AC | 0 | 400 | 2021-01-01 | In Permitting | REE | REE | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
8 | 0105000020E6100000010000000102000000030000000000000094C420C03787F9E0D315454000000000E43721C017D74E75CCD1444000000000F94F21C0AE2022AE99BB4440 | 496 | 4 | Fontefria (ES) - Vila Nova de FamalicÃ†o (PT) | Fontefria (ES) | REE | Overhead Line | AC | 135 | 400 | 2021-01-01 | In Permitting | REE | REN | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
6 | 0105000020E61000000100000001020000000400000000000000E8CA20C0AF2AFAB0A71445400000000080C920C0663F80EE37164540FFFFFFFF5FAD20C026523E96EA27454000000000C07A20C009E654393B304540 | 18 | 4 | Beariz (ES) - Fontefria (ES) | Beariz (ES) | Vila Nova de FamalicÃ†o (PT) (By Ponte de Lima) | Overhead Line | AC | 32 | 400 | 2021-01-01 | In Permitting | REE | REE | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
7 | 0104000020E610000001000000010100000000000000D86220C0551CC5C5692E4540 | 499 | 4 | Beariz 400kV (ES) | Beariz (ES) | Ponte de Lima (PT) | Substation | AC | 0 | 400 | 2021-01-01 | In Permitting | REE | REE | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
12 | 0104000020E6100000010000000101000000000000008006FFBFF629F8D906AC4240 | 570 | 13 | New substation La Ribina | La Ribina (ES) | Cubnezais (FR) | Substation | AC | 0 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
10 | 0105000020E610000001000000010200000006000000FFFFFFFFDF2DFFBFD0EECA4960AC4240FFBBD60FD2CAFDBF2E8DCE0596AB4240FFFFFFFFEF3BFFBFAE95E30F84AC424049E20C304CE408C02F6A6173EDDD42400000000030740FC0CD79D3F753AB4240FFFFFFFF7FE70FC06722246AA49C4240 | 31 | 13 | Axis Caparacena-Baza-La Ribina | Caparacena (ES) | Baza (ES) | Overhead Line | AC | 177 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
11 | 0104000020E610000001000000010100000049E20C304CE408C02F6A6173EDDD4240 | 569 | 13 | New substation Baza | Baza (ES) | La Ribina (ES) | Substation | AC | 0 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
13 | 0105000020E610000001000000010200000003000000E37ED12F5BBCDFBF7FF324E1A97A46401CF7FFD4EC7FD9BF8EDBDC56027E46408ACEF06E7EE6D5BFEA064CD8E5834640 | 38 | 16 | HVDC Gatica-Cubnezais | Gatica (ES) | Piossasco (IT) | Subsea Cable | DC | 370 | 320 | 2025-01-01 | In Permitting | REE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS
14 | 0105000020E6100000010000000102000000080000000000E0C0043D1D40C998D495796B4640A9D30393D84F1A401F68B4F329774640A166B19E210719409F69AF55569846402ABF10C72FBA1840DD9D003736A246401D6BE992CF7E18407600B4BB29AC4640B629876B5D8718402DEE69ABC0BF4640E60F1650046F1840275905520FBF4640257DCCFFEE5D1840D6DF20FF50BE4640 | 55 | 21 | Savoie - PiÃ¨mont | Grande Ile (FR) | Horta (BE) | Underground Cable | DC | 190 | 320 | 2019 | Under Construction | RTE | TERNA | FALSE | France | Italy | 0 | FR - IT | FALSE | CSW,NS,CCS
15 | 0105000020E6100000010000000102000000040000008501CBB77EB90840D430F87423414940DF59D4B6D5360A406B7671F0A449494048812597836A0B400549ED28B95E494027422D9557980C4069802E1206824940 | 60 | 23 | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | Avelin/Mastaing (FR) | Chilling (GB) | Overhead Line | AC | 80 | 400 | 2022-01-01 | In Permitting | RTE | ELIA | FALSE | France | Belgium | 0 | FR - BE | FALSE | CSW,NS
16 | 0105000020E6100000010000000102000000030000000000001A937BF3BF823C268CB66E4940000000010DE8C8BF3BFDCEC984A448408C448D52A546C5BFC1454C26FC894840 | 62 | 25 | IFA2 | Tourbe (FR) | Glorenza (IT) | Subsea Cable | DC | 250 | 320 | 2020-01-01 | Under Construction | RTE | NGIHL | FALSE | France | Great Britain | 0 | FR - GB | FALSE | CSW,NS
17 | 0105000020E61000000100000001020000000200000001000000E80225400C78B159D36E474001000000461D2540C6C007A1D7554740 | 614 | 26 | Reschenpass Interconnector | Nauders (AT) | Lastva (ME) | Underground Cable | AC | 26 | 220 | 2021 | In Permitting | APG | Terna | FALSE | Austria | Italy | 0 | AT - IT | FALSE | CCS,CCE
18 | 0105000020E610000001000000010200000006000000BB17252EAC0E2C40F932FBF04C344540CF7DBD4BF1AA30404DFE758F1439454063E413095B4B314052B3210A9736454037F42B1717753240102320BC7D2445408A7CAE2261B632409DE6C3719B3045403705033689B33240270C74F65D4E4540 | 70 | 28 | First HVDC Module IT-ME | Villanova (IT) |  | Subsea Cable | DC | 445 | 500 | 2019 | Under Construction | TERNA | CGES | FALSE | Italy | Montenegro | 0 | IT - ME | FALSE | CSE,CCS
19 | 0104000020E610000001000000010100000085C43512B3B232405F1462DE724E4540 | 624 | 28 | SS 400/110 kV Lastva | Lastva (ME) | Lastva (ME) | Substation | AC | 0 | 400 | 2018-12-31 | Under Construction | CGES |  | FALSE | Italy | Montenegro | 0 | IT - ME | FALSE | CSE,CCS
20 | 0105000020E61000000100000001020000000200000001000000C0ED2540948AE5207381424001000000C09E29406831D2C7A6E24240 | 635 | 29 | Elmed Project | Sicily Area (IT) | Pallanzeno(IT)-Baggio(IT) | Subsea Cable | DC | 200 | 400 | 2022 | In Permitting | TERNA | STEG | FALSE | Italy | Tunisia | 0 | IT - TN | FALSE | CSE,CCS
21 | 0105000020E6100000010000000102000000020000000100000040DC1F406711DAA3DB1C4740960D0800D0B5204015BBE8F19CCD4640 | 642 | 31 | San Giacomo Project | All'Acqua (CH) | Colunga (IT) | Overhead Line | AC | 100 | 380 | 2025 | In Permitting | SWISSGRID | TERNA | FALSE | Switzerland | Italy | 0 | CH - IT | FALSE | CCS
23 | 0105000020E6100000010000000102000000020000000100000020E22B4034AAE6C99D2645400000000080A12A40051A54A496DB4540 | 1041 | 33 | Rem. lim. in Central Italy | Villanova (IT) |  | Overhead Line | AC | 350 | 220 | 2022-01-01 | Planned but not yet permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
22 | 0105000020E6100000010000000102000000020000006F76BA729A912640057FABF1423F46401F9C0EBF2C42264099D3AF5CD7E54540 | 90 | 33 | 90 | Calenzano (IT) | S. Barbara (IT) | Overhead Line | AC | 80 | 400 | 2022 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
24 | 0104000020E6100000010000000101000000DFFDA6AB19892C4058F9B7A4689B4840 | 311 | 35 | R Kocin | Kocin (CZ) | Mirovka (CZ) | Substation | AC | 0 | 400 | 2024-01-01 | Under Construction | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
25 | 0105000020E610000001000000010200000002000000DFFDA6AB19892C4058F9B7A4689B4840FC281368EB5F2F4000078C76F3C34840 | 313 | 35 | Kocin-Mirovka | Kocin (CZ) | Prestice (CZ) | Overhead Line | AC | 121 | 400 | 2024-01-01 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
26 | 0105000020E610000001000000010200000007000000DFFDA6AB19892C4058F9B7A4689B4840E9201B844EFD2B405FCF0AF41F9A4840BE391A0D413D2B408F72D4A2F4A74840DFC3C578970D2B400AA1A663FEBA4840262EC55319E62A4061156EFAAFCA484043A6865B20D32A405C8F1182B6D2484035DB7627FA902A40917A826BB7CD4840 | 315 | 35 | Kocin-Prestice | Kocin (CZ) | Bentwisch (DE) | Overhead Line | AC | 116 | 400 | 2028-01-01 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
27 | 0105000020E610000001000000010200000005000000ABC1242A8E9028404D37E4FAD20F4B409224085740FD29404E173976967D4B4033B1AF2B1CFD294067C64FA1427D4B400000000070A42840D6E074229ECB4B4099570100F8FC294092DC0ECBEE7C4B40 | 141 | 36 | Kriegers Flak CGS, TYNDP ID: 36.141 | IshÃ¸j / BjÃ¦verskov (DK) | Wilster (DE) | Subsea Cable | AC | 24 | 150 | 2018-12-31 | Under Construction | Energinet.dk | 50Hertz Transmission GmbH | FALSE | denmark | Germany | 0 | DK - DE | FALSE | BS,NS
30 | 0105000020E61000000100000001020000000300000007140387C4952240AE2636BC2C894B40F516ACC47E1F2340DAC95CF0542A4B402366F6798C8423402E00CFEEF7264B40 | 144 | 39 | Audorf - Kassoe | Audorf (DE) | LUX-DE (TBC) | Overhead Line | AC | 110 | 380 | 2020-12-31 | Under Construction | TenneT-DE | Energienet.dk | FALSE | denmark | Germany | 0 | DK - DE | FALSE | BS,NS
31 | 0105000020E610000001000000010200000002000000010000007D4D17401930062F6EC848400100000018A31740163BBA0C0BC94840 | 650 | 40 | BE-LUX-DE Long-Term perspective | Aubange (TBC) | St. Peter (AT) | Overhead Line | AC | 0 | 0 | 2035 | Under Consideration | ELIA | CREOS; AMPRION | FALSE | Belgium | Germany | Luxembourg | BE - DE | FALSE | BS,NS,CCS
35 | 0105000020E61000000100000001020000000200000088E52200306F25407E9F9A60729F4740EC43280010C92740384B0B8FE4AA4740 | 219 | 47 | 219: Westtirol - Zell/Ziller (AT internal) | Westtirol (AT) | Westtirol (AT) | Overhead Line | AC | 105 | 380 | 2024 | Planned but not yet permitting | APG | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
34 | 0105000020E6100000010000000102000000090000000D4106D94F202440BEC8BA6E801948407C6CA201826C2440FCD99785D90C48405A27B2FFCF272440710081F7A3F547400EBD83A7A9B22440045805E6F8DE47407A4E40346FB62440ADFE426E0AD34740D844EA661487254083A3E4D539C54740A43569C7CBC62540DCB22A5F23B54740195334FF7D762540A95E2B5F9FA14740A43569C7CBC62540DCB22A5F23B54740 | 689 | 47 | 689: VÃ¶hringen (DE) - Westtirol (AT) | VÃ¶hringen (DE) |  | Overhead Line | AC | 114 | 380 | 2024 | Planned but not yet permitting | Amprion | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
33 | 0105000020E610000001000000010200000008000000C174D67E9D5929406DCA91A5C1AB4740BF2AB4FF43A22940C38A8D580FA14740EE5DA4CCDDDF2940B778FC0726A44740E035BFCC3DE329404FEBF48BABA847407B0ACA7E27652A40269AB4679EAF4740D2C15D6A425A2A40396933B16DD4474001000000A8102A40B8417D8D9700484001000000C0252A40E772027960224840 | 216 | 47 | (is a single investment project, please consider only content of project 312) 216 | St. Peter (AT) | Zell-Ziller (AT) | Overhead Line | AC | 128 | 400 | 2022 | In Permitting | APG | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
32 | 0105000020E610000001000000010200000002000000000000C04793294037E64D5B2E32484000000000F04129402753DC6F7A194840 | 212 | 47 | (is a single investment project, please consider only content of project 313) 212 Isar/Altheim/Ottenhofen - St. Peter | Isar (DE) | Tauern (AT) | Overhead Line | AC | 90 | 400 | 2021 | In Permitting | TenneT-DE | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
37 | 0104000020E61000000100000001010000003E20BEC8738F3440ECEC912EA4214840 | 697 | 48 | Hunew 2 | SajÃ³ivÃ¡nka (HU) | Gonyu (HU) | Substation | AC | 0 | 400 | 2020 | In Permitting | MAVIR |  | FALSE | Slovakia | Hungary | 0 | SK - HU | FALSE | CCE
36 | 0104000020E61000000100000001010000003E20BEC8738F3440ECEC912EA4214840 | 696 | 48 | Hunew 1 | SajÃ³ivÃ¡nka (HU) |  | Compensation | AC | 0 | 400 | 2020 | In Permitting | MAVIR |  | FALSE | Slovakia | Hungary | 0 | SK - HU | FALSE | CCE
311 | 0102000020E610000005000000CB060400E8F433407A2B9EBCC030484069F60680A6013440379AD0E294274840EDE9F2FF0D383440DBE34358A63248408F23EF7FF4673440500C3D205830484057DCEAFF3D8F34402386FCB7BB214840 | 1501 | 48 | 2. SK-HU interconnection | RimavskaÂ Sobota (SK) | Sajoivanka (HU) | Overhead Line | AC | 48 | 400 | 2020 | In Permitting | MAVIR |  | FALSE | Slovakia | Hungary |  | SK - HU | FALSE | CCE
312 | 0102000020E6100000120000000839EFFFE3BE31409D36DBC3FBED4740E014F3FFECE231408A07CEF8C2F44740529A0F0003EB3140A3D7131BFBEC47404473F8FFCCF33140196B45BC71EA474038F00F00C1FF3140FB42865DADE94740A190F0FFDB1132407C3727405EE547404AB405009E133240D4426E2BE2E14740FD08ECFF561E32406029C39F7EDA474057DCEAFF3D19324042D1973938DE4740630CEEFFCA13324078A1D2EBC3E14740A190F0FFDB113240FB8867224FE5474087930B001B003240FB42865DADE947407ABE0B00FAF33140196B45BC71EA47401B4FFCFFD5EA3140B753C601ECEC4740C7BC0A00C0E23140C22708E4B3F44740CB060400E805324080DA45244CFB4740A190F0FFDB3E324085B80FCC930C48406FE1EDFFEB4C32401AFAE59B06224840 | 1500 | 48 | 1. SK-HU interconnection | Gabcikovo (SK) | Gonyu (HU) | Overhead Line | AC | 110 | 400 | 2020 | In Permitting | SEPS | MAVIR | FALSE | Slovakia | Hungary |  | SK - HU | FALSE | CCE
40 | 0105000020E61000000100000001020000000200000000000000431D38404B8E72E9BA7A4C40000000008BD53740BC18304E816A4C40 | 1062 | 62 | Riga CHP2 - Riga HPP | Riga CHP2 | Eemshaven (NL) | Overhead Line | AC | 15 | 330 | 2020-01-01 | In Permitting | AST | AST | FALSE | Estonia | Latvia | 0 | EE - LV | FALSE | BS
38 | 0105000020E610000001000000010200000005000000FFFFFFFF6F2B3940B08D1494E3174D4000000000705839401E4B73932FEE4C4000000000500F3940DCFCF8FB4FD74C40FFFFFFFF5F1D3940B758E87628C34C4000000000241E38409C4914B7DF7A4C40 | 386 | 62 | 3rd EE-LV interconnection | Kilingi-Nomme (EE) | Sindi (EE) | Overhead Line | AC | 205 | 330 | 2020 | Under Construction | Elering | AST | FALSE | Estonia | Latvia | 0 | EE - LV | FALSE | BS
39 | 0105000020E610000001000000010200000008000000000000003C6038402923E188E3B24D400000000088323840416DCC74398E4D400000000064FC37400F2560C1EC834D40FFFFFFFF7FFE3740A7B9A2016F714D40FFFFFFFFBBC237400AA5417E63594D4000000000A0473840FD2BF6E527344D40FFFFFFFFB39C38406FA3122649374D400000000064B03840630DD38978304D40 | 735 | 62 | Harku-Sindi 330kV OHL | Harku (EE) | Riga HPP | Overhead Line | AC | 175 | 330 | 2020-12-31 | Under Construction | Elering | Elering | FALSE | Estonia | Latvia | 0 | EE - LV | FALSE | BS
41 | 0105000020E6100000010000000102000000020000001E16AC69C5B2214042942F68A1BE4B4000000000701A1B4023BF19675EB94A40 | 427 | 71 | COBRA Cable | Endrup (DK) | Gezelle (BE) | Subsea Cable | DC | 325 | 320 | 2019 | Under Construction | Energinet | TENNET-NL | FALSE | denmark | Netherlands | 0 | DK - NL | FALSE | BS,NS
44 | 0105000020E610000001000000010200000002000000F8F112E516B5EE3F45DD281D848749408D380005C049ED3F07BD8497E0764940 | 450 | 74 | SELL - DUNG Reconductoring | Sellindge (GB) | Stevin (Zeebrugge) | Overhead Line | AC | 26 | 400 | 2016-11-30 | Under Construction | NGET | NGET | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
42 | 0105000020E61000000100000001020000000300000000000000F2A809406FAB36488FA34940000000008426094046F13F604DA949400000000060F3F53FD2DE5E5D35AA4940 | 443 | 74 | NEMO | Richborough (GB) | Canterbury (GB) | Subsea Cable | DC | 140 | 400 | 2019-01-01 | Under Construction | NGET | ELIA | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
43 | 0105000020E610000001000000010200000002000000A1A5EC591F58F23F14934DA7079F494072EBE6F1946EF43F4F9343A7C59D4940 | 449 | 74 | Richborough - Canterbury | Richborough (GB) | Dungeness (GB) | Overhead Line | AC | 20 | 400 | 2018 | In Permitting | NGET | NGET | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
45 | 0105000020E6100000010000000102000000020000000000000000C9084087B56D7EDDBB49400100000080390940D7D00B6732AB4940 | 752 | 75 | Modular Offshore Grid | Offshore platform | Deeside (GB) | Subsea Cable | AC | 50 | 220 | 2020-01-01 | In Permitting | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
46 | 0105000020E610000001000000010200000005000000C0A61AFF218C07C0330DAF16B39F4A40733686F4E18511C025CCD1AD094B4B400791164D1B8F14C07CBF6445724C4B40784AFFD8718315C0992449FE02954B408417AAA81B4813C05CAD7B981FD34B40 | 452 | 77 | Western HVDC Link | Hunterston (GB) | Seabank (GB) | Subsea Cable | DC | 360 | 500 | 2017 | Under Construction | SPT | NGET | FALSE | United Kingdom |  |  |  | TRUE | NS
47 | 0105000020E610000001000000010200000003000000A3CAC93F4E1205C02CC364F644C44940906769F7F66007C0BC288DB2769A4940A0FB0CCB5FAF09C0C1A0F35A4C914940 | 458 | 78 | HINP-SEAB New Double Circuit | Hinkley Point (GB) | Turleenan (NI) | Overhead Line | AC | 60 | 400 | 2024 | In Permitting | NGET | NGET | FALSE | United Kingdom |  |  |  | TRUE | NS
48 | 0105000020E61000000100000001020000000400000098D9CD88B0731AC089662E3670B84A40FEFFFFFFE7FC1AC02C0C9B19A8B94A4000000000A81E1BC09825C15292DB4A400000000075701AC01F07C5C50C3C4B40 | 462 | 81 | 462 | Woodland (IE) | New substation in South Donegal (IE) | Overhead Line | AC | 138 | 400 | 2020 | In Permitting | EirGrid | SONI | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
49 | 0105000020E61000000100000001020000000200000003F34C298ED620C0D575BBFEAA1A4B40FFFFFFFF67FF1FC00FAB5E3D10574B40 | 463 | 82 | Srananagh - South Donegal | Srananagh (IE) | Omagh South (NI) | Overhead Line | AC | 76 | 220 | 2029 | Planned but not yet permitting | EirGrid | EirGrid | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
50 | 0105000020E610000001000000010200000002000000FEFFFFBF89FF1FC0F4FDB14512574B40FFFFFFFFA0AA1DC0C75E6846C8434B40 | 896 | 82 | Omagh South to South Donegal | South Donegal (IE) | Turleenan | Overhead Line | AC | 58 | 275 | 2029 | Planned but not yet permitting | EirGrid | SONI | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
51 | 0105000020E610000001000000010200000002000000FFFFFFFF65A91DC0253358F4B7434B4000000000EE6F1AC0E7D13AF7023C4B40 | 897 | 82 | Omagh South to Turleenan | Omagh South | Tavira (by Ourique) | Overhead Line | AC | 63 | 275 | 2029 | Planned but not yet permitting | SONI | SONI | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
53 | 0104000020E6100000010000000101000000000000802C6120C07B9EFA225DD54240 | 780 | 85 | Extension of Ourique substation | Ourique (PT) | Lixhe (BE) | Substation | AC | 0 | 400 | 2024-2026 | Planned but not yet permitting | REN | - | FALSE | Portugal |  |  |  | TRUE | CSW
52 | 0105000020E61000000100000001020000000600000000000080581720C0975E7B9AF3064340000000603D6120C04A29D99661D5424000000000BCD81FC0B44F06B279B14240000000002C5A1FC046411FC81DB34240FFFFFFFF93011FC0267E4E130FB442400000000041EB1EC043A26074E1B24240 | 779 | 85 | F.Alentejo-Ourique-Tavira | F. Alentejo (by Ourique) | - | Overhead Line | AC | 122 | 400 | 2024-2026 | Planned but not yet permitting | REN | REN | FALSE | Portugal |  |  |  | TRUE | CSW
54 | 0105000020E610000001000000010200000013000000FFFFFFFFAFC01640C8D62210525D4940FFFFFFFFA7B9164069965260A35549400000000000DA164001E3F52FDA5249400000000044FF1640748AE6623C51494000000000D83D1740748AE6623C514940000000009C791740C78BA7E5F5514940000000004CBA17409B7867852153494000000000C4F6174042A7BE0D3E534940FFFFFFFF7B111840779945679454494000000000E02518400169B07415564940000000001050184058AE1949895949400000000094801840802E70AE515C494000000000CAA41840C1036699E75D4940FFFFFFFF2DB918409BE38A0B4C6149400000000058BC1840EE0EFB0577634940FFFFFFFF1FB81840AF61DA658C67494000000000BA1D1940C721213C5A6A494000000000A0551940BDA707064C6A49400000000054DD1940FEABF7EA446A4940 | 146 | 92 | ALEGrO | Oberzier (DE) | Krajnik (PL) | Underground Cable | DC | 100 | 320 | 2020-10-01 | In Permitting | AMPRION | ELIA | FALSE | Belgium | Germany | 0 | BE - DE | FALSE | BS,NS,CCS
55 | 0105000020E610000001000000010200000002000000D43E250062812C4002D437DD708B4A4050D9FA33CDE12C407F3AF5B31E954A40 | 139 | 94 | Krajnik-Vierraden | Vierraden (DE) | Krajnik (PL) | Overhead Line | AC | 26 | 400 | 2020-12-31 | Under Construction | 50Hertz | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
56 | 0106000020E610000001000000010300000001000000050000000000008037E02C407D2849EBF5944A400000008037E02C401146694E34954A40FFFFFFFF1DE32C401146694E34954A40FFFFFFFF1DE32C407D2849EBF5944A400000008037E02C407D2849EBF5944A40 | 796 | 94 | Krajnik | Krajnik (PL) | Mikulowa (PL) | Substation | AC | 0 | 400 | 2019 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
57 | 0105000020E6100000010000000102000000060000007B3331305B0F3A4001FCBF81CA3D5040ED223FDDB1D23940EC766032EA445040F4A13BC473923940C5C4B128BB5450409D6320BBCB913940E0C72084A46650404D365404BF393940F7B9775D0F7550405C1EBE0BC49C38401CDAC20026785040 | 801 | 96 | FI5 KI-PS | Keminmaa (FI) | Ens | Overhead Line | AC | 156 | 400 | 2024-01-01 | In Permitting | Fingrid | Fingrid | FALSE | Finland |  |  |  | TRUE | BS
335 | 0102000020E61000000400000056362000406F1440F6E93E21B72D4A40A6D84D0030041740E4C3471FCE534A40F96B0D00B0A11740544035B9F3524A408F79150080DF1840A03261A801414A40 | 1540 | 103 | Eindhoven-Maasbracht | Eindhoven | Maasbracht | Overhead Line | AC | 50 | 380 | 2023 | Planned but not yet permitting | TENNET - NL | TENNET - NL |  | Netherlands |  |  | NL | TRUE | NS
334 | 0102000020E6100000080000002B1B1000A09317405580B58B6597494056362000408B164044A31A7A34A049400000000000CC1540121B242B5CB84940C7BC0A00C02B1440A01CA25DC7D44940466BDAFFDFC01340DB0384415FE84940E5AF3500C0961240E3CA34F595ED4940E20CD5FFFFDC1340992A5AB126074A4056362000406F1440D6849B29802D4A40 | 1488 | 103 | Diemen-Lelystad-Ens | Diemen | Ens | Overhead Line | AC | 75 | 380 | 2020 | Under Construction | TENNEL - NL | TENNET - NL | FALSE | Netherlands |  |  | NL | TRUE | NS
333 | 0102000020E6100000030000000000004019AE8640D80B4A1FCE534A40010000C03DAF8640AD66008386524A40010000C0B3B18640155801366F414A40 | 1488 | 103 | Diemen-Lelystad-Ens | Diemen | Ens | Overhead Line | AC | 75 | 380 | 2020 | Under Construction | TENNET - NL | TENNET - NL | FALSE | Germany |  |  | DE | TRUE | CCE,BS,NS,CCS
58 | 0105000020E61000000100000001020000000300000000000000106710C025430256803B484000000000906618C05964CBE63F03494000000000C0301EC0EDD8424377FB4940 | 810 | 107 | France Ireland Interconnector | West Wexford or East Cork (IE) | Blythe (GB) | Subsea Cable | DC | 580 | 320 | 2026 | Under Consideration | EIRGRID | RTE | FALSE | France | Ireland | 0 | FR - IE | FALSE | NS
59 | 0105000020E610000001000000010200000004000000A41C05731AF71940450BE873F9BA4D40CC30D7A2CAC21440AA8ED47DD97E4D400EA799A2241EE7BFB2BB8E9496BB4B40BD3509A3B2A8FABFA56EE8DBE19A4B40 | 424 | 110 | Norway - Great Britain | Kvilldal (NO) | Messaure (Sweden, bidding area SE1) | Subsea Cable | DC | 720 | 500 | 2021 | Under Construction | Statnett | NHIGL | FALSE | United Kingdom | norway | 0 | GB - NO | FALSE | BS,NS
60 | 0105000020E610000001000000010200000004000000010000000091344021BFA7AE9995504001000000208E35404C87F144618F50408F791500801D37408B0A2816708350408F791500808538402A986BB0B4795040 | 396 | 111 | 3rd AC Finland-Sweden north | Keminmaa (Finland) | Doetinchem (NL) | Overhead Line | AC | 200 | 400 | 2025 | In Permitting | Fingrid | Svenska kraftnÃ¤t | FALSE | Finland | Sweden | 0 | FI - SE | FALSE | BS
61 | 0105000020E6100000010000000102000000040000005C1AE0FE33751A40C4C81672BAD049405BD52F64B71B1A401EE558C538D7494009833AFE6E9E1940075B2E132CD7494035E0E297B00C1940768D12CB18004A40 | 145 | 113 | Doetinchem-Niederrhein | Niederrhein (DE) | TBD (BE) | Overhead Line | AC | 57 | 380 | 2018 | Under Construction | AMPRION | TENNET-NL | FALSE | Netherlands | Germany | 0 | NL - DE | FALSE | NS,CCS
323 | 0102000020E61000000200000001000000C0850440E6247A81B9A3494001000000C0BD0840B09790AE5C9B4940 | 1625 | 120 | MOG II: connection of up to 2 GW additional offshore wind Belgium | Offshore (TBD) | Onshore (TBD) | Subsea Cable | DC | 50 | 400 | 2030 | Under Consideration | Elia | Elia | FALSE | Belgium |  |  | BE | TRUE | NS
62 | 0105000020E6100000010000000102000000030000009B9AFCFDFF6BEB3F5D8D26F6D4AD49400100000000B30040E4557D227EBE494001000000C0EA0840499608610A9A4940 | 934 | 121 | Nautilus: 2nd interco UK - BE | Leiston (UK) | Stanislawow (PL) | Subsea Cable | DC | 250 | 400 | 2028 | Under Consideration | NGHIL | ELIA | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
63 | 0105000020E61000000100000001020000000A000000000000DA51A035402A965A2D9F864A400000000094B03540BEA0DEAAD5804A4000000000309C3540050CB308626C4A4000000000208E3540450AEDB32D674A400000000006993540FF2A5332014F4A400000000016A73540995222A7964B4A400000000086AF3540CB68F26E673C4A4000000000BA9935407C25697A042D4A40000000009E6A35404A831CE71B224A40FFFFFF734A68354081CAA6DF451B4A40 | 373 | 123 | Ostroleka-Stanislawow | Ostroleka (PL) | Musa | Overhead Line | AC | 106 | 400 | 2023-12-31 | Planned but not yet permitting | PSE | PSE | FALSE | Poland | Lithuania | 0 | PL - LT | FALSE | BS
64 | 0105000020E610000001000000010200000002000000DFB34DCC586B38405303EAACBEE24B40026078BE0C603740A5F336BFB01A4C40 | 378 | 124 | 330 kV OHL Panevezys-Musa | Panevezys | Imanta (LV) | Overhead Line | AC | 80 | 330 | 2023-12-31 | Planned but not yet permitting | LITGRID | LITGRID | FALSE | Lithuania | Sweden | 0 | LT - SE | FALSE | BS
65 | 0105000020E610000001000000010200000005000000FFFFFFFFD7D53540DA20D92667C24C4000000000E86A3640828F3C161DBD4C400000000078E93640C3749E072F8A4C4000000000908537403235CB8930784C400000000098B93740B3CB18927D7A4C40 | 385 | 124 | Grobina (LV) - Imanta (LV) | Grobina (LV) | Nybro/Hemsjo (SE) | Overhead Line | AC | 380 | 330 | 2019 | Under Construction | AST | AST | FALSE | Lithuania | Sweden | 0 | LT - SE | FALSE | BS
66 | 0105000020E6100000010000000102000000040000006E595F9802A9304032FED9DEDFB74C40434B2915FC4430401FE8280BC58A4C408EE5779F10162F40BC3053AC1A534C402DA2A7AEA67F2D40BD3247DBB6294C40 | 733 | 124 | Ekhyddan-Nybro-Hemsjo | Ekhyddan (SE) | SE3 | Overhead Line | AC | 160 | 400 | 2023 | In Permitting | Svk | Svk | FALSE | Lithuania | Sweden | 0 | LT - SE | FALSE | BS
67 | 0105000020E6100000010000000102000000020000000100000000122B40AFD15B91479C4D400100000000B33040CD236FFF63035040 | 403 | 126 | Reinforcements SE2-SE3 in Sweden | SE2 | Villanova (IT) | Compensation | AC | 900 | 400 | 2030 | Under Consideration | Svk | Svk | FALSE | Sweden |  |  |  | TRUE | BS
71 | 0105000020E6100000010000000102000000020000000100000010DF2F40445CC8079ADB434001000000C0982F402565B6D76E174440 | 645 | 127 | ITA-3 | Laino (IT) | Isar (DE) | Overhead Line | AC | 50 | 400 | 2022-01-01 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
68 | 0105000020E6100000010000000102000000040000005469502EBE492F40E251F93AE6AD444087F2E2AC15D32D408D30BB8C74F04440B8E3487E42EF2C40A95FEE4E4E134540DC6A398F0A122C407822053744344540 | 86 | 127 | 86 | Foggia (IT) | Benevento II (IT) | Overhead Line | AC | 178 | 400 | 2022-01-01 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
69 | 0105000020E6100000010000000102000000020000002FE5593F71462F4044583167F2AD444047D69CB1ADEA2D40DD977A6C5C924440 | 91 | 127 | 91 | Foggia (IT) | Bisaccia (IT) | Overhead Line | AC | 85 | 400 | 2014-06-30 | Commissioned | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
70 | 0105000020E610000001000000010200000002000000A1958663AD1C2F40FBDC8EE2069544409FC3DF0A05CE2E40B23C4E8D86714440 | 96 | 127 | 96 | Deliceto (IT) | Altomonte (IT) | Overhead Line | AC | 30 | 400 | 2022-12-31 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
72 | 0105000020E6100000010000000102000000020000003943F5FF3F6C2740BC1A457BE11E4A40AAC9DFFFBF9028404A05BA9B4C5A4840 | 665 | 130 | Wolmirstedt-Isar | Wolmirstedt (DE) | Osterath (DE) | Underground Cable | DC | 540 | 0 | 2025 | In Permitting | 50Hertz | TenneT DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
73 | 0106000020E61000000100000001030000000100000004000000B74422849FAB1C40C1B876BE4BB34A4020B99BD53FC01C4092E0681FE0B24A405442EE7A009E1C40CA721A0F50B34A40B74422849FAB1C40C1B876BE4BB34A40 | 661 | 132 | HVDC Line A-North | Emden East (DE) | Eichstetten (DE) | Overhead Line | DC | 300 | 400 | 2025-01-01 | Under Consideration | Amprion | Amprion | FALSE | Germany |  | 0 | Internal | TRUE | CCE,BS,NS,CCS
308 | 0102000020E61000000500000050A22D00F07C1A40EC4879D683A2494000000000007A1C4098F192014C1C4A4001000000A0331D4064D5E6FBD26E4A4001000000002E1D402D8A24AAA29B4A4010CB450060CE1C40A6AEA51599AF4A40 | 661 | 132 | HVDC Line A-North | Emden East (DE) | Osterath (DE) | Overhead Line | DC | 300 | 400 | 2025 | Planned but not yet permitting | AMPRION | AMPRION | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
75 | 0105000020E61000000100000001020000000E0000000000000058A620402B26B19328814840F92C885F23E820408176DF6FF3874840CA11E2D83CEF2040DA2E7226B2964840EA9E4624C2F52040889DD28D2DA448400000000054132140DD025EEBE6A948402B5E2FE6EE162140687BED3BDEB0484000000000443221404670EEA460BA4840FFFFFFFF575A2140B7E72012CCC348406909D0E1584F214022CD14D7ECCF48407C8BD5318F212140500E5E0120E64840E8DC2325BF072140963D6DA768EF48400EC8C56CC60D214081CCF8FC28F148405C4263B6BF78214033E04492FCF04840CB4D63ADB69921409732F0CF4AF74840 | 680 | 134 | Urberach - Daxlanden | Urberach (DE) | WeiÃŸenthurm (DE) | Overhead Line | AC | 219 | 400 | 2022-01-01 | Under Consideration | Amprion | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
74 | 0105000020E610000001000000010200000005000000D171FE927DDA1E40DFABCDEF3A0D4840CC04D3E01A831F4008C7DC89E33F484000000000D808204014AAA693B551484000000000AC7F2040F7A41DC6D561484035EE697811A72040C051561D2D814840 | 176 | 134 | Daxlanden-Eichstetten | Daxlanden (DE) | Daxlanden (DE) | Overhead Line | AC | 120 | 380 | 2021-01-01 | Under Consideration | TransnetBW | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
76 | 0105000020E6100000010000000102000000020000002211F2B30ABA1A40D35237F4457F4940334514CF7C871D40D49887613C304940 | 179 | 135 | Rommerskirchen - WeiÃŸenthurm | Rommerskirchen (DE) | Dauersberg (DE) | Overhead Line | AC | 94 | 400 | 2019-01-01 | Under Construction | Amprion | Amprion | FALSE | Germany |  | 0 | Internal | TRUE | CCE,BS,NS,CCS
77 | 0105000020E610000001000000010200000002000000702AD40257941E40AC0121D85BBB49405765BB1469AF1F404555C7470F684940 | 188 | 135 | Kruckel - Dauersberg | Kruckel (DE) | Stalpu (RO) | Overhead Line | AC | 110 | 380 | 2021-01-01 | In Permitting | Amprion | Amprion | FALSE | Germany |  | 0 | Internal | TRUE | CCE,BS,NS,CCS
81 | 0105000020E610000001000000010200000002000000635D03B8C9CD3B40EFB098CD02D645401E42CA521DBD3B4048EC097CE2DD4540 | 800 | 138 | 400 kV OHL Varna-Burgas | Varna(BG) | N.Santa (GR) | Overhead Line | AC | 140 | 400 | 2021-03-31 | Planned but not yet permitting | ESO-EAD | ESO-EAD | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE
80 | 0104000020E6100000010000000101000000EBCB77A702EE3A4082953609859A4640 | 715 | 138 | 220kV Stalpu substation upgrade to 400 kV | Stalpu (RO) | Burgas(BG) | Substation | AC | 0 | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE
78 | 0105000020E610000001000000010200000004000000DBDC7790C7E93B40708F8C723CCE4640FDE71F3306C93B4093226C576CF34640BE1CD198A44C3B40F65D953414194740EAE5DAC487DF3A4095779B58DC214740 | 275 | 138 | 400 kV OHL Smardan-Gutinas | Smardan (RO) | Stalpu (RO) | Overhead Line | AC | 140 | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE,CCE
79 | 0105000020E6100000010000000102000000020000000100000008EC3A40A2491BE4C49A46400100000080363C40C5D4712487384640 | 273 | 138 | 400kV OHL Cernavoda-Stalpu | Cernavoda (RO) | Gutinas (RO) | Overhead Line | AC | 159 | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE
82 | 0105000020E6100000010000000102000000020000007767981BE9823940982B3ED1C39944409A77656B2A023A40349EDA1CB01A4540 | 256 | 142 | 256 | Maritsa East 1 (BG) | Plovdiv (BG) | Overhead Line | AC | 130 | 400 | 2023-01-30 | In Permitting | ESO-EAD | IPTO-SA | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
83 | 0105000020E6100000010000000102000000020000007F2221E7487C384037547D4BB30B4540A8AF8F05EFFF3940CE1226B3E3194540 | 257 | 142 | 257 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | Overhead Line | AC | 100 | 400 | 2020-12-30 | Under Consideration | ESO-EAD | ESO-EAD | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
84 | 0105000020E610000001000000010200000002000000833C504E45143A408CB381EFDA1245408D8F7199C1583A40A8C745EE95214540 | 258 | 142 | 258 | Maritsa East 1 (BG) | Burgas (BG) | Overhead Line | AC | 13 | 400 | 2019-06-30 | Under Consideration | ESO-EAD | ESO-EAD | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
85 | 0105000020E610000001000000010200000003000000F163EA1981FF39406A282DDE2319454018BF0D486EED3A4043895104724D45401307337C485C3B40354893B7FD494540 | 262 | 142 | 262 | Maritsa East 1 (BG) | Pancevo (RS) | Overhead Line | AC | 150 | 400 | 2021-06-01 | Under Consideration | ESO-EAD | ESO-EAD | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
90 | 0104000020E6100000010000000101000000A9F0E0B7225635407D86BC3C6BE04640 | 705 | 144 | 400 kV Substation Timisoara | Timisoara (RO) | Border IT-SI | Substation | AC | 0 | 400 | 2023 | Under Consideration | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
88 | 0105000020E610000001000000010200000002000000000000003A563540854A6DAB86E0464000000000425D35401ED27D9558F54640 | 270 | 144 | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz - Arad to 400kV double circuit line | Resita (RO) | Resita (RO) | Overhead Line | AC | 175 | 400 | 2023 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
89 | 0104000020E61000000100000001010000008AF6E0BBF6003640BDF53EB8A1A74640 | 701 | 144 | 400 kV Substation Resita | Resita (RO) | Timisoara (RO) | Substation | AC | 0 | 400 | 2019 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
86 | 0105000020E610000001000000010200000002000000290C670ADFB93440C99F1CC36B834640F392DEBBF6003640B99236B8A1A74640 | 238 | 144 | New_400 kV OHL RO-RS | Resita (RO) | Resita (RO) | Overhead Line | AC | 131 | 400 | 2017 | Under Construction | Transelectrica | EMS | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE,CCE
87 | 0105000020E610000001000000010200000002000000D25E8310E6983640FC80E387606146408AF6E0BBF6003640BDF53EB8A1A74640 | 269 | 144 | 400 kV OHL Portile de Fier-Resita | Portile de Fier (RO) | Arad (RO) | Overhead Line | AC | 116 | 400 | 2019 | Under Construction | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
91 | 0105000020E610000001000000010200000003000000C7BC0A00C08D2B40B83145D251C04640C7BC0A00C08D2B4032CCC7BD12C046400D28E5FF9F062D40190C853A72064740 | 616 | 150 | Salgareda - Border IT-SI | Salgareda (IT) | Border IT-SI | Underground Cable | DC | 0 | 500 | 2022 | Under Consideration | TERNA |  | FALSE | Slovenia | Italy | 0 | SI - IT | FALSE | CCE,CCS
320 | 0102000020E6100000030000006AF2F7FF2F202940B6AB255790D0464014BCD7FFEF8A2B40B83145D251C04640D82EE9FF87892B4032CCC7BD12C04640 | 1616 | 150 | BeriÄevo - Border IT-SI | BeriÄevo (SI) | Border IT-SI | Underground Cable | DC | 140 | 400 | 2022 | In Permitting | ELES | TERNA |  | Slovenia | Italy |  |  | FALSE | CCE,CCS
92 | 0105000020E6100000010000000102000000060000007F2D3C46A0D4FABFF9FDE82C00BE4840FFFFFF9E2991FEBF43B86557C2C14840000000EE8F7001C09A728F5455DC48400000000950DF02C019AAB97B6CF148408A950B3C51D109C012EF4A505A4F4940ACA978A534DC0AC0C74CA000975E4940 | 987 | 153 | France-Alderney-Britain | Menuel (FR) | Stade (DE) | Subsea Cable | DC | 210 | 320 | 2022-01-01 | In Permitting | RTE (FR) | NGIHL (UK) | FALSE | France | Great Britain | 0 | FR - GB | FALSE | CSW,NS
94 | 0105000020E610000001000000010200000004000000EFF6498315E82440FA7764490C214A40CCAB00007C7F23404792416A6AD0494099570100F802244065F238D2BAB54940A7206029A23F2340CC6B3E11386E4940 | 157 | 164 | Wahle - Mecklar | Wahle (DE) | Landesbergen (DE) | Overhead Line | AC | 210 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
96 | 0105000020E6100000010000000102000000070000006CCF4D17393E234036B98C59FE6D49402B1B1000A05B23401BC26B762861494060140C00B870234078EA7869965749405A80190068842340F62CC6C8AB4E494074D0E3FFA78F234076B6D318A54849400794F2FF4F9C23407C7B19BD81434940C89C8089EC292440F07F0DA99EF94840 | 685 | 164 | Mecklar - Grafenrheinfeld | Mecklar (DE) | Bicker Fen (GB) | Overhead Line | AC | 130 | 380 | 2027 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
93 | 0105000020E610000001000000010200000005000000689F9EA99DB2224020095EA1CDC84A40F908256119962240D896649164CB4A40CC9EC219158F22408FF1B43E5DC84A406E742909E4A922401371C67243C24A401AE7A9EDAA082340EC79AB6C27B54A40 | 149 | 164 | Dollern - Stade | Dollern (DE) | Mecklar (DE) | Overhead Line | AC | 14 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
95 | 0105000020E61000000100000001020000000A0000001AE7A9EDAA082340EC79AB6C27B54A4099522CF15FDC22402D18092B1DB24A40330B1FD7A7BC22400785181A95B34A4032177E914C5C22405FB10AC480934A403454FFFF8378224025A865947C854A40417CE4FF23F721402A1C834617694A40B64BFAFF61C82140F6536F4F085E4A40F96B0D00B0012240B3EB20A7964B4A404321E1FFB7352240B23B93ECC7464A40904C4532FD5522401340D6F8F1434A40 | 677 | 164 | Dollern - Landesbergen | Dollern (DE) | Grafenrheinfeld (DE) | Overhead Line | AC | 130 | 380 | 2023 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
97 | 0105000020E61000000100000001020000000400000000000000102922403420470249BF4B4000000000A05E20403739B342EFE84B40000000000048C23FBB8CCD8CF77B4A40000000000020BCBFC2837B016E844A40 | 998 | 167 | Viking Link DKW-GB, TYNDP ID 167.998 | Revsing (DKW) | Neris | Subsea Cable | DC | 770 | 515 | 2022-12-31 | In Permitting | Energinet.dk | National Grid | FALSE | Denmark | United Kingdom | 0 | DK - GB | FALSE | BS,NS
98 | 0105000020E6100000010000000102000000040000004E9274EEF22139409C79A487C24B4B4037CA558737463940318A2F24F1524B40BB80971936423940244A9420D05A4B40386C953F632139407750C396A2604B40 | 382 | 170 | 330 kV line Vilnius-Neris | Vilnius | Paide | Overhead Line | AC | 80 | 330 | 2024-01-01 | Planned but not yet permitting | LITGRID | LITGRID | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
100 | 0105000020E610000001000000010200000002000000ECEB3F4950013A40C72930DF26F64C4094473297BA4E39404976F2BBE5C34C40 | 1011 | 170 | Valmiera -Tsirguliina 330 kV | Tsirguliina | Tartu | Overhead Line | AC | 60 | 330 | 2025-01-01 | Planned but not yet permitting | Elering | AST | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
99 | 0105000020E6100000010000000102000000060000007A924C413B163C40C8618EE0B4A64D408C275B8A2DFF3A409288642B45974D40FBEBBC832CAF3A40AD7A84FB2B764D407503EBEC4F8F3A400934A9CF102E4D40B209B3DADC453940A834C831F7D24C4094473297BA4E39404976F2BBE5C34C40 | 1010 | 170 | 330 kV OHL Tartu-Valmiera | Tartu | Valmiera | Overhead Line | AC | 133 | 330 | 2025-01-01 | Planned but not yet permitting | Elering | AST | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
103 | 0105000020E6100000010000000102000000040000005DF546CE3E813740CAE15132D2544B4057A0ABE783623740A9D0ABC71E484B403272F5E7CB2C37400B6413EC81484B40F554FB3220FA36402EE983C025324B40 | 1034 | 170 | New 400 kV interconnection line from Lithuania to state border | Marijampole | - | Overhead Line | AC | 51 | 400 | 2031-01-01 | Under Consideration | LITGRID | LITGRID | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
102 | 0105000020E61000000100000001020000000200000042F0185E3733394092438B4CF1754D40BD71304D7EB03840FB2E633651304D40 | 1013 | 170 | Eesti-Tsirguliina 330kV OHL | Eesti | State border | Overhead Line | AC | 243 | 330 | 2025-01-01 | Under Consideration | ELERING | ELERING | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
104 | 0106000020E61000000100000001030000000100000005000000FFFFFFFF43183C40429D207FE1AB4D40FFFFFFFF46153C40AFB19DA19CA64D40FEFFFF7FD01A3C40937809AF6EA64D4000000000111E3C40294D35DEADAB4D40FFFFFFFF43183C40429D207FE1AB4D40 | 1117 | 170 | B2B at Narva | Eesti | - | Substation | DC | 0 | 330 | 2024-01-01 | Under Consideration | ELERING | - | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
101 | 0105000020E6100000010000000102000000070000007A924C413B163C40C8618EE0B4A64D40B9462E63AFE33B40C51FC90AAFA54D4079BD3EDDA2C13B40ACBB73AA2B934D40AF62615A3CF33A4082131CC823874D40D9DA71F030C53A4016B8D51D60744D400A96D2BDB8A53A40ABBC619FDD264D407503EBEC4F8F3A400934A9CF102E4D40 | 1012 | 170 | 330 kV OHL Tartu-Balti (L300) | Balti | Tsirguliina | Overhead Line | AC | 168 | 330 | 2024-01-01 | Under Consideration | ELERING | ELERING | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
318 | 0102000020E6100000020000000C8C82010077EF3F8702113D048F494077CCAB00006CFB3FEF0F08320A704940 | 1487 | 172 | Eleclink | Sellindge | Mandarins | Subsea Cable | DC | 69 | 400 | 2019 | Under Construction | National Grid | Reseau de Transport d'Electricite, the French TSO | FALSE | United Kingdom | France |  | GB - FR | FALSE | NS
105 | 0105000020E61000000100000001020000000400000024871D00504D17404534D32079C8484000000000184917406C113E5450C248400100000000611740C448B2CD75BF484001000000988C1740FA165390DCBD4840 | 1281 | 173 | Aubange-Moulaine: PSTs | Aubange (BE) | Sils i.D. | Phase Shift Transformer | AC | 0 | 220 | 2020-12-31 | Planned but not yet permitting | ELIA | RTE | FALSE | France | Belgium | 0 | FR - BE | FALSE | CSW,NS
106 | 0105000020E61000000100000001020000000A000000584E9A3C57A8224002762CD5E8584740F2B5DD6D3959224059AADC63205147402DE476D3D6C1224044D5FB5C6C224740B3DDF49F4BD622400B2B66697117474062E50F274D972240CD7D041F1D104740CCD802766A922240E05AAA285B06474094FE1850E8872240C9953B408D004740F694D0EC549522409FF9A1ACC6F846400D019C047AA02240ABE022AAA1F24640D9ADC0EF28AF224094A003CCADE04640 | 1014 | 174 | Greenconnector | Verderio | Not decided | Underground Cable | DC | 150 | 400 | 2022 | In Permitting | Terna | Swissgrid | TRUE | Italy | Switzerland | 0 | IT - CH | FALSE | CSE,CCS
107 | 0105000020E610000001000000010200000002000000A276AE0040F723409547253524144C407779DB0CA7C52740ADCBADC895E84B40 | 1000 | 175 | Great Belt II | Not decided | GueÂstrow (DE) | Subsea Cable | DC | 50 | 400 | 2030 | Under Consideration | Energinet | Energinet | FALSE | Denmark | Denmark | 0 | DK - DK | FALSE | BS
108 | 0105000020E61000000100000001020000000400000001000000C0EA284068EAA83AC8EE4A4001000000402E29409EA3EBCA7B4C4B4001000000C0BA2B4057B066F049954B4001000000C0BA2B40E60EF76B7CDB4B40 | 995 | 176 | Hansa PowerBridge | Hurva (SE4) | Bentwisch (DE) | Subsea Cable | DC | 300 | 300 | 2026 | In Permitting | Svk | 50Hertz | FALSE | Germany | Sweden | 0 | DE - SE | FALSE | BS,NS,CCE
109 | 0105000020E6100000010000000102000000020000003033DFB96C002840D96E39F109BA4B40F427022A8E902840A3BBEBFAD20F4B40 | 1016 | 179 | DKE-DE (Kontek 2) | BjÃ¦verskov (DK2) | Endrup (DKW) | Subsea Cable | DC | 170 | 400 | 2030 | Under Consideration | Energinet | 50Hertz | FALSE | Denmark | Germany | 0 | DK - DE | FALSE | BS,NS
110 | 0105000020E610000001000000010200000003000000F028D669C5B2214069E12D68A1BE4B4057D70F893ABB214047511CD785894B40CCEDC53A22BD214013FD0D9D2E6E4B40 | 1018 | 183 | DKW-DE, Westcoast, TYNDP ID 183.1018 | KlixbÃ¼ll (DE) | Neusiedl/Zaya | Overhead Line | AC | 92 | 380 | 2022-12-31 | In Permitting | TenneT-DE | Energinet.dk | FALSE | Denmark | Germany | 0 | DK - DE | FALSE | BS,NS
111 | 0105000020E61000000100000001020000000300000001000000A08B3040CEAD41B81E26484001000000A8BF30403C9F870BED284840A0EBF3FF47C53040EDE4FCE20C574840 | 886 | 186 | 886 | Seyring | St. Peter (AT) | Overhead Line | AC | 60 | 380 | 2021 | In Permitting | APG | APG | FALSE | Austria |  |  |  | TRUE | CCE,CCS,CCE
112 | 0105000020E6100000010000000102000000040000000000008053122A404014FC0896564840000000801E382A4028B3269C6A424840FFFFFFFF6A022A404CFB71D49C334840FFFFFFFFCA292A40A059B18EC4204840 | 997 | 187 | 997 Pleinting - St. Peter | Pleinting (DE) | Peterhead | Overhead Line | AC | 60 | 380 | 2024 | In Permitting | TenneT-DE | APG | FALSE | Austria | Germany | 0 | AT - DE | FALSE | CCE,CCS,CCE
113 | 0105000020E61000000100000001020000000300000062D4392FE3A01840D993C0E69C404E4045B4C29904D8154014D852F64CE24D4056069B5B9DD3FDBF05EB8BC6D2C34C40 | 1382 | 190 | NorthConnect | Sima | Emden/East (DE) | Subsea Cable | DC | 655 | 500 | 2022 | In Permitting | Statnett | National Grid (SSEN is TO) | TRUE | Great Britain | Norway | 0 | GB - NO | FALSE | BS,NS
116 | 0105000020E6100000010000000102000000020000005393BFFF7FBD1C40B6636EE710B14A40E5AF3500C0BA1B405E7A03E519FE4A40 | 953 | 191 | Cluster DolWin6 | Cluster DolWin 6 (NOR-3-3) | DÃ¶rpen/West (DE) | Subsea Cable | DC | 90 | 320 | 2023 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
115 | 0105000020E6100000010000000102000000030000003943F5FF3F0C1D40441283E158D34A40F3D71A0060471C40B89DCFE324E84A405393BFFF7FED19401ABE2ABC70F04A40 | 952 | 191 | Cluster DolWin 5 (NOR 1-1) | Cluster DolWin 5 (NOR-1-1) | Emden/East | Subsea Cable | DC | 130 | 320 | 2024 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
114 | 0105000020E6100000010000000102000000040000000000000000881D40D0EEB170698F4A403943F5FF3F0C1D40C89220F956DD4A40E5AF3500C0BA1B4058CEF7B60D264B400000000000B81A40200A24306F2D4B40 | 656 | 191 | BorWin3 | Cluster BorWin3 | Emden/East (DE) | Subsea Cable | DC | 160 | 320 | 2019 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
117 | 0105000020E610000001000000010200000002000000E20CD5FFFF1C1F40CCF6F8EF078A4B40F3D71A00606F2240A3CAEED134FB4A40 | 659 | 192 | SylWin2 | Cluster SylWin2 (DE) | area of Cloppenburg/East | Subsea Cable | DC | 205 | 320 | 2025 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
119 | 0105000020E610000001000000010200000002000000C1281800700720400C04E0238B7B4A4000000000006C1B40DEA306ECCDE94A40 | 211 | 192 | DolWin 4 (NOR-3-2) | Cluster DolWin 4 (NOR 3-2) | BÂÃ¼ttel (DE) | Subsea Cable | DC | 190 | 320 | 2028 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
118 | 0105000020E6100000010000000102000000030000003CE6550000FE1F404664D48CF77B4A408CD6B4FFBFD91A40B5A9150129E34A407186EAFF7F741A402C8E56F7402E4B40 | 954 | 192 | Cluster BorWin 5 (NOR-7-1) | Cluster BorWin 5 (NOR-7-1) | area of Cloppenburg/East | Subsea Cable | DC | 250 | 320 | 2025 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
120 | 0105000020E61000000100000001020000000600000000000000C066F5BF6F848C2317BB4340FFFFFFFFFFAFF3BF2A6134490FC14340000000004045F1BF67531A97DFC143400000000000A4EFBF3F528A339CFD4340FFFFFFFFFFEFDEBFBAC736BF362A44400000000000CFD2BFC4315C2B492B4440 | 927 | 193 | La Plana/Morella-Godelleta | La Plana/Morella | Cartuja (ES) | Overhead Line | AC | 207.5 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
121 | 0104000020E6100000010000000101000000FFFFFFFFC76A18C0D1CEF4B16C494240 | 561 | 194 | New substation Cartuja | Cartuja (ES) | Arcos | Substation | AC | 0 | 400 | 2029 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
122 | 0105000020E61000000100000001020000000200000000000000986D18C0ABD26D22DC484240FFFFFFFF0F1517C04BA755353F6B4240 | 929 | 194 | Cartuja-Arcos 400 kV | Cartuja | Petajavesi (FI) | Overhead Line | AC | 30 | 400 | 2029 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
123 | 0105000020E6100000010000000102000000030000007B3331305B0F3A4001FCBF81CA3D50409828BCB6C8973A40D3796BE3F1165040979C5A6826083A4029B4588F952B4F40 | 742 | 197 | Pyhanselka-Petajavesi | Pyhanselka (FI) | CHAVALON (CH) | Overhead Line | AC | 300 | 400 | 2022-07-01 | In Permitting | Fingrid | Fingrid | FALSE | Finland |  |  |  | TRUE | BS
124 | 0105000020E6100000010000000102000000040000005D3EA1955A441940E41B4F47C80F47400000509D79BA1A403E75F312A620474000008039FDF01B40B711D9F6FF2447408CE3F004E81C1C401F6318AC6F2A4740 | 1051 | 199 | Cornier - Chavalon 400 kV | CORNIER (FR) |  | Overhead Line | AC | 65 | 400 | 2035 | Under Consideration | RTE | SWISSGRID | FALSE | France | Switzerland | 0 | FR - CH | FALSE | CSW,NS,CCS
125 | 0104000020E610000001000000010100000049035F021B172A4089C9E458D0234940 | 306 | 200 | R Vitkov | Vitkov (CZ) | Vitkov (CZ) | Substation | AC | 0 | 400 | 2022-11-30 | In Permitting | CEPS |  | FALSE | Czech Republic |  |  |  | TRUE | CCE
127 | 0105000020E61000000100000001020000000500000016D6B86FA8972940583B8A1D62144940ED181DBA9E7A29403017E3967BFF48404852770595AC2940C8DFD2B543E948408A1CCF7F0C4A2A40E9D78BAD0DCB484035DB7627FA902A40917A826BB7CD4840 | 309 | 200 | Vitkov-Prestice | Vitkov (CZ) |  | Overhead Line | AC | 86 | 400 | 2022-11-30 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
126 | 0105000020E61000000100000001020000000400000049035F021B172A4089C9E458D02349404F23D38714512A4021AF9972851D49400CF9CE4C0B112A402B34C4C29718494016D6B86FA8972940583B8A1D62144940 | 308 | 200 | Vernerov-Vitkov | Vernerov (CZ) | Prestice (CZ) | Overhead Line | AC | 71 | 400 | 2025-07-30 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
128 | 0104000020E6100000010000000101000000FC281368EB5F2F4000078C76F3C34840 | 312 | 200 | R Mirovka | Mirovka (CZ) | V413 (CZ) | Substation | AC | 0 | 400 | 2025-09-30 | In Permitting | CEPS |  | FALSE | Czech Republic |  |  |  | TRUE | CCE
129 | 0105000020E610000001000000010200000002000000FC281368EB5F2F4000078C76F3C34840D179794113772F40A80313CC60E44840 | 314 | 200 | Mirkovka-V413 | Mirovka (CZ) | La Plana(ES) | Overhead Line | AC | 27 | 400 | 2019-05-30 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
130 | 0105000020E6100000010000000102000000030000005B28248F01DCCCBFBBC952BC131044400000000080B8D2BFB9172491042B444064CE2CAA16F0D4BFBC29C9202C474440 | 538 | 203 | Morella-La Plana | Morella (ES) | Endersbach (DE) | Overhead Line | AC | 78 | 400 | 2020 | In Permitting | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
132 | 0105000020E6100000010000000102000000070000004095E4CAEA5B26408388D4B48B1B4940D3A5FB10868F274059DACAC7C5224940E4991BFC921D28407080D39AEA0D4940D0A22D9DC555284009157F88CBEF484058DC87D582192840ADD371CA16D848401B59A61D06F627408145D9B683B94840621EC749401028407B1C61ACCAAC4840 | 687 | 206 | Redwitz - Schwandorf | Redwitz (DE) | Altheim (DE) | Overhead Line | AC | 185 | 380 | 2023 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
133 | 0105000020E610000001000000010200000008000000CCAB00007C9B254028C412C59AB44840CCAB00007C9B2540B80BC50452BA48407B07AA0C049D264031E509A52BBA484041E4A1AD52DD26405704FF5BC996484062CB5D111D3E2740800ACBC86E754840EF41848FF3AE2740D645E1E52F6F48403E801CFFCB582840BBAC70689D514840372E0C263884284094C0C50E534D4840 | 688 | 206 | Raitersaich-Altheim | Raitersaich (DE) | GroÃŸgartach (DE) | Overhead Line | AC | 160 | 380 | 2026 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
131 | 0105000020E610000001000000010200000008000000859B29000822224049EA0CA5599348407C6308008E5F22407C48D7D076834840B30101003AB322402152BA9185834840297613000CC322400A41F5AC777A48401F99F5FFFDC12240C44827F9AE6E4840C862D5FFBDB62240DB432D93826748407675E0FF3B0C224024F0879FFF6948400794F2FF4FDA2140A5ED88D81A674840 | 682 | 206 | GroÃŸgartach - Endersbach | GroÃŸgartach (DE) | Schwandorf (DE) | Overhead Line | AC | 0 | 380 | 2025 | Planned but not yet permitting | TransnetBW | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
134 | 0105000020E610000001000000010200000007000000C89C8089EC292440F07F0DA99EF9484000000000000A24400768957844F148402CC1DAFF9D022440168C84950ECE48409101A8FB63FA23406D79614237BB4840AA059BDFD51723408DD3CE38A6A14840EB44F6FF7991224026B79A33AA9E4840765B5CC2252022403AE1EB8CEB934840 | 990 | 206 | Grafenrheinfeld - GroÃŸgartach | Grafenrheinfeld (DE) | Elsfleht/West (DE) | Overhead Line | AC | 168 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
321 | 0102000020E610000006000000010000002026244059F38A6335FA4840010000006004244057A6A46B0FF248400100000050F623404E5B268276BB4840010000008012234055C7FBF5D1A1484001000000808B2240DC087D0AFC9F48400100000040262240D7EDA13B0A944840 | 990 | 206 | Grafenrheinfeld - GroÃŸgartach |  |  | Overhead Line | AC |  |  |  | Planned but not yet permitting
137 | 0105000020E610000001000000010200000002000000F3F2C7F652071D40E044BAC0E1AF4A40E5AF3500C0221D407F58E32A9ED24A40 | 940 | 207 | Emden - Halbemond | Emden/Ost | Wilhelmshaven (DE) | Overhead Line | AC | 30 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
135 | 0105000020E610000001000000010200000007000000AD13D9FFE7B9224090B423EE94B34A40C29ED92227012240496760E4E5BB4A40A74601058BB12140CDBFA78306AF4A40777FFE737F5A21408E5C169753964A408DD5E6FF554D2140768D54E76A924A40BF831B00DCD620406F0089686C974A40F033ECFF35D720406F0089686C974A40 | 676 | 207 | Dollern - Elsfleth/West | Dollern (DE) | Emden/Ost | Overhead Line | AC | 100 | 380 | 2026 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
136 | 0105000020E61000000100000001020000000200000097B204006440204006C1FC785CA64A40C128180070091D40F5CF78C7CEAF4A40 | 939 | 207 | Conneforde - Emden | Conneforde | Halbemond | Overhead Line | AC | 60 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
139 | 0105000020E610000001000000010200000004000000C6F2B6EB08EE204046EDC03132794A40FDB50600D8BC2040950BF8A9E84B4A40D789ECFFF3BE2040954B5FDF393B4A406F8E08006D912040EB807734062C4A40 | 151 | 208 | Ganderkesee - Wehrendorf | Wehrendorf (DE) | DÃ¶rpen/West (DE) | Overhead Line | AC | 95 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
140 | 0105000020E61000000100000001020000000600000068E04FA634771A40B29ACF35A3D049405EFA136C8E7D1A40E1B58D3760D84940E9A0C7FF4FDF1B4030AC4D2950F44940C7BC0A00C04F1D40C337A0E747194A40AB336BE7038B1C402E498E09EB484A400C6B32FC0AC61C40A3096F6A7B734A40 | 156 | 208 | Niederrhein-DÃ¶rpen | Niederrhein (DE) | GÃ¶hl/Siems | Overhead Line | AC | 182 | 380 | 2021 | In Permitting | Amprion | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
138 | 0105000020E610000001000000010200000003000000546096B0153E2040CB4BBC0BADA64A40A5DAE9FF03192040B7F3588EEBC14A407186EAFF7F4220402C5DA899C1C24A40 | 150 | 208 | Conneforde-Wilhelmshaven | Conneforde (DE) | Ganderkesee (DE) | Overhead Line | AC | 30 | 380 | 2020 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
141 | 0105000020E610000001000000010200000007000000A824E3FF2BDC25406CFC1574F3254B409E46F7FFB3722540CD07E32BAA094B40466BDAFFDF822540F3F77BF781EF4A4099570100F8C42540ED40212B8DF94A403855317470832540F119C37B92EF4A401F0CE13DAC182540F0B724A4C1EA4A40BDC227428FE5234077137CD3F4E74A40 | 935 | 209 | Kreis Segeberg - Siems | Kreis Segeberg | WURMLACH | Overhead Line | AC | 110 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
142 | 0105000020E6100000010000000102000000020000003B165FDD46E52940CDAFA4E46E2E474051472A0084072A407DB7F5AA00544740 | 1380 | 210 | Wurmlach (AT) - Somplago (IT) interconnection | SOMPLAGO | tbd | Underground Cable | AC | 51 | 220 | 2021 | In Permitting | TERNA SPA | Austrian Power Grid AG | TRUE | Austria | Italy | 0 | AT - IT | FALSE | CSE,CCE,CCE
143 | 0105000020E6100000010000000102000000020000000100000000B330C019A02BEF82F54F4000000000007215C0DD0E0EF11EEF4C40 | 1082 | 214 | Interco Iceland-UK | tbd | Kofinou Site | Subsea Cable | DC | 1000 | 500 | 2030 | Under Consideration | tbd | tbd | FALSE | Iceland | Great Britain | 0 | IS - GB | FALSE | NS
146 | 0105000020E6100000010000000102000000040000004EE1CC730DFC3740E6EB951B5FE042403C9CF862BEFF3740F6C8305F32B14240EE13EB00911C3840279117E94F7A4240072C63AF42EE38406D45858839AF4140 | 1410 | 219 | EuroAsia Interconnector | Korakia (Crete)Site | to be defined (DE) | Subsea Cable | DC | 0 | 500 | 2020 | In Permitting | ADMHE | ADMHE | FALSE | Cyprus | Greece | Isreal | CY - GR | FALSE | CSE
145 | 0105000020E610000001000000010200000006000000072C63AF42EE38406D45858839AF4140EC8CA442AF4D39407CB8D4C064BD414037DD116A88703A404DCE4DAE2BA741407300BD7A9DC53A405AB10EE7C07E41404B403AC287934040A35DDFE94D3B4140CDEFF2FDD7B040403E811F3C1C614140 | 1409 | 219 | EuroAsia Interconnector | Kofinou Site | Athens Site | Subsea Cable | DC | 0 | 0 | 2021 | In Permitting | TSO Cyprus | ADMHE | FALSE | Cyprus | Greece | Isreal | CY - GR | FALSE | CSE
144 | 0105000020E610000001000000010200000002000000CDEFF2FDD7B040403E811F3C1C61414043AAA5EFF0784140D03680BF7C514040 | 1407 | 219 | EuroAsia Interconnector | Hadera Site | Korakia (Crete)Site | Subsea Cable | DC | 0 | 500 | 2020 | In Permitting | IEC | TSO Cyprus | FALSE | Cyprus | Greece | Isreal | CY - GR | FALSE | CSE
147 | 0105000020E61000000100000001020000001200000000000080168E174014517940362C494074294B0040C617407DB9260F51204940C1281800701D1840E9B23D1F0A13494032AF0200F08D18408399BEF02D0D4940960D0800D025194056ADF9AFFB0E4940C128180070851940BA5EC3A171184940A335EDFF6FB21940C94A1FFC3C234940A6D84D0030D4194062DDD330572D49408542C2FF6FDF1940470D1AB88B3849403FD7E7FF8FCE19405709924E0F43494067A8FEFF07B119401ED19033C54B49409CA1FAFF1F6C19404AE23832075649404DFFCCFF2FF3184004711E4E605D494081513000E0521840F51B3FB744604940F034BAFF9FED17405D79A080B35849402B1B1000A09317401E019A108C4B4940B05DD2FF0F6F174038742796E33949403CE65500008E1740A281F50B382C4940 | 1107 | 225 | 2nd interconnecter between Belgium and Germany | to be defined (BE) | Visegrad (BA) | Underground Cable | DC | 0 | 0 | 2028 | Under Consideration | ELIA | AMPRION | FALSE | Belgium | Germany | 0 | BE - DE | FALSE | BS,NS,CCS
149 | 0105000020E610000001000000010200000005000000F91650F50BB03340C553015F14034640FFFFFFFF3BCE33401705F9913D0E4640000000008CE73340604BD850991A46400000000050233440072CC15CC6374640B2BE69CCBB203440CDA470AD934B4640 | 628 | 227 | 400kV OHL B.Basta-Obrenovac | SS Bajina Basta (RS) | Pljevlja (ME) | Overhead Line | AC | 115 | 400 | 2024 | In Permitting | EMS | EMS | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
151 | 0104000020E6100000010000000101000000F91650F50BB03340C553015F14034640 | 631 | 227 | 400kV SS B.Basta upgrade | Bajina Basta (RS) | SS Pljevlja | Substation | AC | 0 | 400 | 2024 | In Permitting | EMS | EMS | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
150 | 0105000020E610000001000000010200000004000000B8AE56F50BB0334061A2075F1403464001000000A88F334041CAAFB0F1D245400000000088733340091A64EAE59F454001000000B8BC3240433F16B11C504540 | 630 | 227 | 400kV interconnection RS-ME | Bajina Basta (RS) | Bajina Basta (RS) | Overhead Line | AC | 100 | 400 | 2024 | In Permitting | EMS | CGES | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
148 | 0105000020E610000001000000010200000002000000B8AE56F50BB0334061A2075F1403464001000000D08533404259103581D64540 | 627 | 227 | 400kV interconnection RS-BA | Bajina Basta (RS) | SS Obrenovac (RS) | Overhead Line | AC | 65 | 400 | 2024 | In Permitting | EMS | NOSBIH | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
326 | 0102000020E6100000020000000100000028E134400711CACBD3FE454001000000D4AD3440AA7F1D2225DF4540 | 1527 | 227 | 400 kV OHL Kragujevac-Kraljevo | SS Kragujevac | SS Kraljevo | Overhead Line | AC | 60 | 400 | 2020 | Under Construction | EMS | EMS | FALSE | Serbia | Montenegro |  | RS - MO | TRUE | CSE
152 | 0105000020E6100000010000000102000000020000000100000080711D403804911268F347400100000040CE1E40FE8B204EC00D4840 | 1231 | 228 | Muhlbach Eichstetten | Muhlbach | Zielona GÃ³ra | Overhead Line | AC | 32 | 400 | 2025 | Planned but not yet permitting | RTE | TransnetBW GmbH | FALSE | France | Germany | 0 | FR - DE | FALSE | CSW,NS,CCS
154 | 0105000020E610000001000000010200000003000000FFFFFFFF6B652F40C0D7F18C4B334A40FFFFFFFFD1592F40A4C218835C0E4A40000000E08E532F4080A1747BEA0B4A40 | 1271 | 229 | Zielona GÃ³ra - Plewiska | Zielona GÃ³ra | n.a. | Overhead Line | AC | 40 | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
155 | 0106000020E61000000100000001030000000100000005000000FFFFFFF71C532F40343E1769E10B4A40FFFFFFF71C532F402EDB371FF30B4A40FFFFFFD7E1532F402EDB371FF30B4A40FFFFFFD7E1532F40343E1769E10B4A40FFFFFFF71C532F40343E1769E10B4A40 | 1272 | 229 | Zielona GÃ³ra | Zielona GÃ³ra | Gubin | Substation | AC | 0 | 400 | >2030 | Under Consideration | PSE S.A. | n.a. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
156 | 0105000020E61000000100000001020000000500000000000000F2862D4009419680B2154A40FFFFFFFF8D9F2D406C4A2B37C2124A40FFFFFFFF2B4C2E406641804CEE0C4A40FFFFFFFF9B082F406FE23C52030C4A40FFFFFFF389532F40243FFC3CEB0B4A40 | 1273 | 229 | Zielona GÃ³ra-Gubin | Zielona GÃ³ra | n.a. | Overhead Line | AC | 60 | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
158 | 0105000020E61000000100000001020000000300000000000000F2862D40E73EF766B9154A40FFFFFFFFA16D2D40860F07F0F1134A4000000000783D2D401100ECB30F104A40 | 1275 | 229 | Gubin - Eisenhuettenstadt | Gubin (PL) | Baczyna (PL) | Overhead Line | AC | 20 | 400 | >2030 | Under Consideration | PSE S.A. | 50Hertz | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
157 | 0106000020E61000000100000001030000000100000005000000000000E0D5862D40088463BFB1154A40000000E0D5862D40F39CF9B4B6154A400000002815872D40F39CF9B4B6154A400000002815872D40088463BFB1154A40000000E0D5862D40088463BFB1154A40 | 1274 | 229 | Gubin | Gubin | Eisenhuettenstadt (DE) | Substation | AC | 0 | 400 | >2030 | Under Consideration | PSE S.A. | n.a. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
153 | 0105000020E610000001000000010200000003000000B428054089532F40B1236121EB0B4A4051472A00844D2F407F4AF852B60E4A40B450D77F425A2F40F60B13997B334A40 | 1270 | 229 | Baczyna-Zielona GÃ³ra | Baczyna-Plewiska indentation | Baczyna-Plewiska indentation | Overhead Line | AC | 40 | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
160 | 0105000020E6100000010000000102000000080000009307F90B032D2E40A47C7345CA88494045C50F00E2592E40C294D44B048649409BFCFDFF8B732E4068EBBF528684494067A8FEFF079D2E40DEEEFEDBD9854940D19AF6FF37033040CAABEFD323754940EF8EEFFFA1113040E1F01F5E996D49409CA1FAFF1F48304065CF965A0C6849402754EC3F9D5D3040464F80176C684940 | 355 | 230 | MikuÅ‚owa - Åšwiebodzice | MikuÅ‚owa (PL) | n.a. | Overhead Line | AC | 100 | 400 | 2023 | Planned but not yet permitting | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
159 | 0105000020E61000000100000001020000000700000031CC2AE8CDE12C402C1DFF471E954A40BDA81FCCD4052D4021BF0A327A864A40E652019C832C2D404966D400CE824A40831313CC7F692D40205FA52FC2684A400D98F2E7FCA22D406F53B084BD624A408BF91CCCE4C72D4034FB55E399584A404046E5CBB00A2E405365CEE9E8574A40 | 353 | 230 | Krajnik-Baczyna | Krajnik (PL) | Åšwiebodzice (PL) | Overhead Line | AC | 70 | 400 | 2021 | In Permitting | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
161 | 0106000020E61000000100000001030000000100000005000000FFFFFF676F0A2E405D78F0AAE1574A40FFFFFF676F0A2E408E99B63DEE574A40000000F0E60A2E408E99B63DEE574A40000000F0E60A2E405D78F0AAE1574A40FFFFFF676F0A2E405D78F0AAE1574A40 | 1035 | 230 | Baczyna | Baczyna | Plewiska | Substation | AC | 0 | 400 | 2020 | Under Construction | PSE S.A. | n.a. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
162 | 0105000020E6100000010000000102000000050000008466F8CBFEBA304041A8FF6A5D294A4048D30B0422BA30404FDECF4265294A406AF2F7FF2F1A2F402F01746FB0344A403C8DEEFF673D2E405DAE55ED60534A409A390B18B00A2E405365CEE9E8574A40 | 1232 | 230 | Baczyna-Plewiska | Baczyna | Tiengen (DE) | Overhead Line | AC | 142 | 400 | 2024 | Planned but not yet permitting | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
165 | 0105000020E610000001000000010200000002000000010000000064E4BF743ED1A126C244400100000000F0CE3F39B18AA70A004540 | 1235 | 233 | Conceptual project | - | Dunowo (PL) | Overhead Line | AC | 0 | 400 | 2027 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
166 | 0105000020E61000000100000001020000000400000000000000F0BA28403A8A534531CF4B40FFFFFFFF1F992940CDC839424F9B4B40FEFFFFFFAF602C40CDC839424F9B4B4000000000C0203040D3BF2CDF42104B40 | 1236 | 234 | DKE-PL-1 | AvedÃ¸re (DKE) | "GroÃŸgartach, Grafenrheinfeld" | Subsea Cable | DC | 330 | 400 | >2030 | Under Consideration | Energinet | PSE | FALSE | Denmark | Poland | 0 | DK - PL | FALSE | BS,NS
167 | 0105000020E6100000010000000102000000040000001EF32A00001B224070A7005A6B954840AAC9DFFFBF962240A03E1B1C19F24A403943F5FF3F26224000C098CA2EFF4840C7BC0A00C02B24406885B741CC024940 | 664 | 235 | HVDC Line C | "BrunsbÃ¼Âttel, Wilster" | Mercator (BE) | Overhead Line | DC | 700 | 520 | 2025 | In Permitting | TenneT-DE | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
168 | 0105000020E61000000100000001020000000500000000000000ECB71040663AF7139694494000000000A0B81040A1A0824CB2944940E858CF7C031E0E40D0BBC5B41D90494058F3602810F00C403F8109EDF48E4940EF6C5D3195940C4009CA73F6DF814940 | 608 | 236 | HTLS upgrade Horta-Mercator | Horta (BE) | Tuovila (FI) | Overhead Line | AC | 50 | 380 | 2019-12-31 | Under Construction | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
169 | 0105000020E610000001000000010200000002000000010000002056314035AA3CE9C1934F40C7BC0A00C0C03540458B225A617F4F40 | 1241 | 239 | Fenno-Skan 1 renewal | Hjalta (SE2) | Wolmirstedt (DE) | Subsea Cable | DC | 200 | 300 | 2029 | Under Consideration | SVK | FINGRID | FALSE | Finland | Sweden | 0 | FI - SE | FALSE | BS
307 | 0102000020E6100000020000003943F5FF3F6C2740B6C4E305051E4A400D28E5FF9F74284034419AD276EB4A40 |  | 240 | AC Enhancement GÃ¼strow-Wolmirstedt |  |  | Underground Cable | AC |  |  |  | In Permitting |  |  | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
170 | 0105000020E610000001000000010200000002000000000000285B4C32402A80927DE7A84640000000CC32673240C670238E5B484640 | 1276 | 241 | Upgrading of existing 220 kV line between SS Dakovo (HR) and TPP Tuzla (BA) to 400 kV line | Dakovo | Gradacac | Overhead Line | AC | 91 | 400 | 2032-12-31 | Under Consideration | HOPS | NOS BIH | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
171 | 0105000020E61000000100000001020000000400000000000000384C32401A877D94DFA84640000000C0FA413240F71FC5C0D1A0464000000070404C32400EF028A19B7A46400000001A7F183240CD4B5041F1754640 | 1277 | 241 | Upgrading of existing 220 kV line between SS Dakovo (HR) and Gradacac (BA) to 400 kV line | Dakovo | Dakovo | Overhead Line | AC | 46.2 | 400 | 2032-12-31 | Under Consideration | HOPS | NOS BIH | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
172 | 0106000020E610000001000000010300000001000000050000000000005E254C32404859A9ABEDA84640000000C4734C32406AC2DE49EEA84640FFFFFF93764C324066EE2A83DAA84640000000E8224C32405D908663DAA846400000005E254C32404859A9ABEDA84640 | 1278 | 241 | Upgrading existing 220 kV SS Dakovo to 400 kV | Dakovo | Razbojiste | Substation | AC | 0 | 400 | 2032-12-31 | Under Consideration | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
173 | 0105000020E610000001000000010200000002000000000000383C4C3240AB51540DE2A84640FFFFFF6F9F2932403EA9FC242ABA4640 | 1279 | 241 | New double 400 kV line between SS Dakovo and location Razbojiste | Dakovo | TPP Tuzla (BA) | Overhead Line | AC | 25 | 400 | 2032-12-31 | Under Consideration | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
174 | 0105000020E61000000100000001020000001300000001000000C0602B40D1075BE18A7F4B408F79150080092C402F368C0619794B401EF32A0000A72C40932400E6F76C4B402B1B1000A0332D402109B95AC05C4B400D28E5FF9F602D40F8F3B74EED4E4B40C7BC0A00C04F2D40EDFEA99F54444B407186EAFF7FEA2C40A3C7318ACC3D4B407186EAFF7F902C40856B41312A3C4B405636200040D12B406A0F20E88D454B400000000000122B4059D10FB8E8114B40CE50FDFF0FD42B400A8E3F0FBD444B4032AF0200F05D2B403EB53496B44D4B40A0EBF3FF47F72A405F671A7FE8594B40645E0500E0F52A406C9A3580505A4B4028D1160078F42A40EECEFB7B80594B40F621140088A82A408BA970DBA9644B401EF32A00008B2A4087578ACB0E754B409CA1FAFF1FD42A40702F611B8E7F4B40AAC9DFFFBF602B40702F611B8E7F4B40 | 194 | 242 | Offshore Connection Cluster 1 | OWF Cluster Baltic Sea East (DE) | Sombor | Subsea Cable | AC | 115 | 220 | 2018 | Under Construction | 50Hertz | 50Hertz | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
175 | 0105000020E610000001000000010200000004000000000000B4D99B324048FEAF568BB4464000000000341333405E8E791627C3464000000000AC4F3340535FD4C387D246400000004CA67233400FB1646E73FE4640 | 1269 | 243 | New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | Ernestinovo | Uchtelfangen (DE) | Overhead Line | AC | 70 | 400 | 2035-01-01 | Under Consideration | HOPS | EMS | FALSE | Croatia | Serbia | 0 | HR - RS | FALSE | CSE
176 | 0105000020E6100000010000000102000000040000000000A06644C61B400634554B93B148400000C0677ACA1A40D58C94D077A5484000003E33DB4D1A40A701E11D919F4840000020CC720019403E23CAF179974840 | 1245 | 244 | Vigy - Uchtelfangen (or beyond) | Vigy (FR) | Uchtelfangen (DE) | Overhead Line | AC | 65 | 400 | 2027 | Planned but not yet permitting | Rte | Amprion | FALSE | France | Germany | 0 | FR - DE | FALSE | CSW,NS,CCS
177 | 0105000020E6100000010000000102000000030000002A1DACFF73E81B40D9CC21A985814A40D19AF6FF37AB1C4044E9E2A135824A40379EF8FFAB811D40E40E1F0171874A40 | 1246 | 245 | Upgrade Meeden - Diele | Meeden [NL] | Barnabos (FR) | Overhead Line | AC | 27 | 380 | 2019 | Under Construction | TENNET-NL | TENNET-DE | FALSE | Netherlands | Germany | 0 | NL - DE | FALSE | NS,CCS
178 | 0105000020E610000001000000010200000002000000893354FFFFA3EFBF3C086C9496734940010000000099FB3F0AD42309C5384940 | 1381 | 247 | AQUIND Interconnector | Lovedean (GB) | Lubmin (DE) | Subsea Cable | DC | 250 | 320 | 2022 | In Permitting | National Grid plc | RÃ©seau de transport d'Ã©lectricitÃ© | TRUE | France | Great Britain | 0 | FR - GB | FALSE | CSW,NS
179 | 0105000020E6100000010000000102000000160000000FCDE1FF33CF2A40A7E8482EFF524B40466BDAFFDF142A40AAB89299622B4B407186EAFF7FCE2A40A7E8482EFF524B402B1B1000A0BD2A401028F62BF85D4B402B1B1000A0BD2A405032DEFBC06B4B409CA1FAFF1FD42A4060513A2645764B4056362000401D2B400882957DB67A4B40781ADDFFCF6E2B400882957DB67A4B40C7BC0A00C0E72B4087578ACB0E754B40781ADDFFCF222C40629A8EA534704B405636200040852C40F0190598E4664B402B1B1000A0D92C40003940B4FF5F4B40EC432800100F2D409FB7885AE0574B40AAC9DFFFBF222D4003BE4F13854E4B40C128180070092D40EDFEA99F54444B408F79150080BD2C40B59AE061FB3C4B400D28E5FF9F522C40FC2A2B131F3A4B406AF2F7FF2FF02B40856B41312A3C4B402B1B1000A0712B40F503CBCF15114B4001000000D6EF2B40007247312A3C4B4024871D00502B2B4065FBF3E197474B40D33FF3FFCBCD2A40A7E8482EFF524B40 | 1248 | 248 | Offshore Connection Cluster 2 | OWF Cluster Baltic Sea (DE) | SiedenbrÃ¼nzow/Alt Telin/Bartow (DE) | Subsea Cable | AC | 115 | 220 | 2022 | In Permitting | 50Hertz | 50Hertz | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
180 | 0105000020E610000001000000010200000002000000A335EDFF6FAA2240C257AE96BF204740CE50FDFF0F0A23407D435D7B512F4740 | 1384 | 250 | "Merchant line ""Castasegna (CH) - Mese (IT)""" | Castasegna | Hamburg/Nord (DE) | Underground Cable | AC | 0 | 220 | 2021 | In Permitting | swissgrid | Terna | TRUE | Italy | Switzerland | 0 | IT - CH | FALSE | CSE,CCS
181 | 0105000020E610000001000000010200000003000000BDC227428FE5234077137CD3F4E74A40A9CDEE7F362C23405BAF2B5E13C14A401AE7A9EDAA082340EC79AB6C27B54A40 | 147 | 251 | Dollern - Hamburg/Nord | Dollern (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 45 | 380 | 2018 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
182 | 0105000020E610000001000000010200000003000000BDC227428FE5234077137CD3F4E74A40F621140088A0234011A4D6240D224B403E132F899284234043062C98FC264B40 | 148 | 251 | Audorf - Hamburg/Nord | Audorf (DE) | Gramme | Overhead Line | AC | 65 | 380 | 2017 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
183 | 0105000020E61000000100000001020000000800000092C94FF275DF144046B7B3890B3B49400000000012E715407AB2F1CBB6694940FFFFFFFF9FDF1640905C4718ED8B494000000000A0A41540BBDCB8FA588F4940FFFFFFFFB3BE144002AE00DCD9854940000000000C5814405054C3D3288A4940FFFFFFFF3FBB13405C0A537EF2904940FFFFFFFFF76D12407CE1398AB39A4940 | 1050 | 252 | Van Eyck - Gramme: HTLS upgrade | Van Eyck | Van Eyck (BE) | Overhead Line | AC | 90 | 380 | 2029-12-31 | Under Consideration | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
322 | 0102000020E61000000500000001000000200715404661904E0F4349400100000060341140DBAC062F1245494001000000C00111400BCF2D635D5749400100000038B710400361BB68C094494001000000ACAC10404EFC12A1DC944940 |  | 252
184 | 0105000020E61000000100000001020000000300000000800DC0C03615401F2BD3CA9AE3464000003EB3AA6C154023DFEFECB6DA4640FFFFFFFF51C515407073F97B6DDE4640 | 1224 | 253 | Uprate of Creys-St Vulbas | Creys(FR) | Cornier (FR) | Overhead Line | AC | 21 | 400 | 2031 | Under Consideration | RTE | RTE | FALSE | France | Switzerland | 0 | FR - CH | FALSE | CSW,NS,CCS
185 | 0104000020E61000000100000001010000000000F0C566421940A69AFE79DE0F4740 | 1225 | 253 | PST in Cornier | Cornier (FR) | Philippsburg (DE) | Phase Shift Transformer | AC | 0 | 400 | 2031 | Under Consideration | RTE | RTE | FALSE | France | Switzerland | 0 | FR - CH | FALSE | CSW,NS,CCS
186 | 0105000020E61000000100000001020000001B00000000000000223621408B35B67D59A64840000000003C582140B5DE873C5AA748402B5E2FE6EE162140687BED3BDEB0484000000000443221403D16826443BA4840DA896ADEC52F2140BB2603CF04C44840BFA299A6FC2D2140548F6DD2C5CC484000000000B22D21404EB3DAA71FD34840888C1CF188122140177F2093B6D8484015A7B7E809F7204002FBA5918CEA484061168A0268C920406EA3F7D48BF34840D6B6FE8673B420406F88B80D0D054940D3B493E3116620407B0A84A3BC23494035415F5DB13F2040D23679902E27494098FF9CE47DE71F407060A036F82D49402E80C42911EF1E408B8AF7F762344940F760CA416FD61E4012016EC098324940FD024A9446561E40B6A850D34129494044A8FF217DC11D403244C557202C494038810E88A3861D40B6C4B776273049400F2F7F265AE81B40065294307D4C4940C924E8D6A5B71B4047215B85CE5649401F696CCF41B01B408A7139ACFF624940B5F911D629FF1A40494107921C71494006C4465017CC1A40D0036BA8297549404E0FFC415FB81A401DE890C5647F4940F0BA60CC389B1A40326A1799CF854940F539DA29E7571A406A1CFF58699F4940 | 660 | 254 | HVDC Line A South - Ultranet | Osterath (DE) | Ichaso | Overhead Line | DC | 340 | 400 | 2021-01-01 | In Permitting | Amprion | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
187 | 0105000020E61000000100000001020000000700000000000000400FFABFA77FDC3E1841454000000000C06EFCBFB9E821975A414540FFFFFFFFFF79FCBF432388E0F84B4540FFFFFFFF7FCBFDBF173286C3AE61454000000000807D01C077F3B3D17873454000000000A02E03C0A3E33CC8BC7C454000000000408E03C0702A0643C3864540 | 1251 | 255 | New line 400 kV Muruarte-Ichaso | Muruarte | Ichaso | Overhead Line | AC | 145 | 400 | 2023 | In Permitting | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
189 | 0105000020E6100000010000000102000000030000002F650900C8BC214032B08EE3076E4B400C83E8FF0B9622404A6F2CE66F0F4B40EF8D210038A62240A15D4BE995F74A40 | 667 | 258 | BrunsbÂttel - KlixbÃ¼ll | BrunsbÂÃ¼ttel (DE) | Oradea | Overhead Line | AC | 125 | 380 | 2019 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
190 | 0105000020E61000000100000001020000000200000001000000C06635404A5A584886E04740000000004031364052A7E7A0B6774740 | 1205 | 259 | HU-RO | JÃ³zsa | TBD | Overhead Line | AC | 0 | 400 | >2030 | Under Consideration | MAVIR | Transelectrica | FALSE | Hungary | romania | 0 | HU - RO | FALSE | CSE,CCE
191 | 0105000020E610000001000000010200000002000000DC31AF0200B0E3BF9440B587DEC2494001000000E00F1040F1D8424377FB4940 | 1255 | 260 | Interconnector GB-NL | TBD | Rilland (NL) | Subsea Cable | DC | 0 | 0 | 2030 | Under Consideration | National Grid | TENNET-NL | FALSE | Great Britain | Netherlands | 0 | GB - NL | FALSE | NS
192 | 0105000020E61000000100000001020000000200000001000000A0121140D6D56DDCB8AD494001000000582D1140EE7CCE3778B84940 | 1257 | 262 | Belgium-Netherlands: Zandvliet-Rilland | Zandvliet (BE) | Grynau & Bonaduz | Overhead Line | AC | 10 | 380 | 2022 | Planned but not yet permitting | ELIA | TENNET-NL | FALSE | Belgium | Netherlands | 0 | BE - NL | FALSE | NS
193 | 0105000020E610000001000000010200000007000000FFFF3FCDF5802240049F5B98F9684740FFFF6F3415AC2240583632DE246D47400000D09824C9224024C1FCC2087C47400000703425E722405135CB3EC49F474000007034B584224082FA211798AD4740FFFF6F3435142240E0AF33C3439C47400000703405172240E0AF33C3439C4740 | 1258 | 263 | RÃ¼Âthi - Bonaduz/Grynau | RÃ¼Âthi | xx | Overhead Line | AC | 0 | 380 | 2035 | Under Consideration | Swissgrid | Swissgrid | FALSE | Switzerland | austria | germany | CH - AT | FALSE | NS,CCS
310 | 0102000020E6100000020000000100000034E62240676A011D0BA047400100000068B12340D9240E4C18BD4740 | 1583 | 263 | Vorarlberg | Rüthi | Border area (DE-AT) | Overhead Line | AC | 1 | 380 | 2035 | Under Consideration | Swissgrid | VUEN | FALSE | Switzerland | austria |  | CH - AT | FALSE | CCS
195 | 0105000020E610000001000000010200000004000000FFFF4F9401BA2440236CD801606747400000F02F820D24408294D5B2D45F47400000F02F820D2440580C6CF5B95947400000F02F629723408D0A6D71B3474740 | 1284 | 264 | Pradella - La Punt | Pradella | MÂhleberg | Overhead Line | AC | 49 | 380 | 2021 | Under Construction | Swissgrid | Swissgrid | FALSE | Switzerland |  |  |  | TRUE | CCS
197 | 0105000020E6100000010000000102000000070000003857C502FC982040067E75D1E7924740057EE06C6B56204033A76838A7894740F2161FD1CA32204066AD152BF2824740EB57F802CC412040A1894DB72E6D4740D7C654D18A2720406AAA82AC025C4740FEE9ED6C1B6A20409390E5B0BD5547408EB819D1EAA82040C4F1B6B1DD434740 | 1288 | 264 | Mettlen - Ulrichen | Mettlen | Ulrichen | Overhead Line | AC | 0 | 220 | 2025-01-01 | Planned but not yet permitting | xx | xx | FALSE | Switzerland |  |  |  | TRUE | CCS
194 | 0105000020E6100000010000000102000000050000000000C09C718A20409C4C707474BD4740FFFFBF9C01552040A305007EE8B7474000009035926A2040120D787B06AF4740FFFFBF9C31AC2040AFEAB9C249A64740FFFF8F35629A2040503A405807934740 | 1259 | 264 | Beznau - Mettlen | Beznau | La Punt | Overhead Line | AC | 64 | 380 | 2025 | In Permitting | Swissgrid | Swissgrid | FALSE | Switzerland |  |  |  | TRUE | CCS
196 | 0105000020E610000001000000010200000005000000646E089FF7C41C409BAC3001E8AE47403294D1D058CE1C40759B0514C9A34740E21CD89E170E1D40119D12CEF698474069BB956756DD1C403D143FA5CE8D4740673466D0D8E41C40F51D4F0DAC814740 | 1287 | 264 | Bassecourt - MÂhleberg | Bassecourt | Ulrichen | Overhead Line | AC | 0 | 380 | 2025-01-01 | In Permitting | xx | xx | FALSE | Switzerland |  |  |  | TRUE | CCS
199 | 0105000020E61000000100000001020000000200000001000000F0FB234064A20FDEEB2B474001000000B01D2440DEBB158597364740 | 1289 | 265 | Lago Bianco connection | xx | xx | Overhead Line | AC | 0 | 380 | 2029-01-01 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
200 | 0105000020E610000001000000010200000002000000960D0800D00F214032E03496133747400100000030BE2140D9B8CBAE04174740 | 1290 | 265 | Magadino - Ulrichen | xx | Chamoson | Overhead Line | AC | 0 | 380 | 2029-01-01 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
198 | 0105000020E61000000100000001020000000300000001000000C020204094924564385E474001000000806F2040667FEB70785747400100000090AA2040E007CD2226444740 | 1260 | 265 | Grimsel connection | Innertkirchen | xx | Overhead Line | AC | 0 | 380 | 2029-01-01 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
203 | 0105000020E6100000010000000102000000020000000100000010A221405496DC5A1F13474001000000D0C32140FA0A0E670B164740 | 1285 | 266 | Magadino | xx | Lavorgo | Overhead Line | AC | 0 | 0 | 2019-01-01 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
202 | 0105000020E6100000010000000102000000080000000000509DCB371E40EA57DC82FE2A47400000C0D1ECCA1F40A3CA34B7BE2D47400000E06886202040E9B6B511893447400000E068B64A2040BEB906F8FE3A47400000E06886A720400C88DD71B54347400000E0FEA6E12040BEF695735A444740000040CD4532214023EED65A313F47400000E06896962140B0B6D04067334740 | 1286 | 266 | Chippis - Lavorgo | Chippis | GueÂstrow (DE) | Overhead Line | AC | 0 | 380 | 2024-01-01 | Under Consideration | xx | xx | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
201 | 0105000020E610000001000000010200000005000000FFFF5F03AE851D40E1B6F72028214740FFFF9F3ACF371E4017B9B9C3082B4740000060036E881E4092F90DA044564740FFFFBFD18C0E1E402F1EE74DFF614740FFFF7F9ACB911E40F9751813048A4740 | 1261 | 266 | Bickigen - Chippis - Chamoson | Bickigen | xx | Overhead Line | AC | 0 | 380 | 2021 | Under Consideration | Swissgrid | Swissgrid | FALSE | Switzerland | Switzerland | 0 | CH - CH | FALSE | CCS
204 | 0105000020E61000000100000001020000000400000001000000C036284025E431BC70F04A4001000000C09028404671BEB39F544B4001000000C0D92A4080C4E23380984B4001000000C0062B40A182D2993CE04B40 | 1262 | 267 | Hansa PowerBridge II | Hurva (SE4) | Aljarafe | Subsea Cable | DC | 300 | 300 | 2030 | Under Consideration | Svenska Kraftnat | 50Hertz | FALSE | Sweden | Germany | 0 | SE - DE | FALSE | BS,NS
206 | 0105000020E610000001000000010200000003000000FFFFFFFF31A618C09002613C8AA142400000000078F717C021D7DB6EBCA5424000000000CAF017C04C7E5FEC36AD4240 | 1229 | 269 | Uprate Aljarafe-Santiponce | Aljarafe | Marsillon | Overhead Line | AC | 13 | 220 | 2019 | In Permitting | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
205 | 0105000020E61000000100000001020000000B00000000000000BA7A16C0EBF3A7ADD7904240FFFFFFFFFE1617C088B6DBFD1B8E424000000000A18317C01CA1B5ECD9954240FFFFFFFFB5C817C0F16AA22F439A42400000000056FB17C0703AAD775DA1424000000000D2F717C09D4A57223FA542400000000008A318C0B41F58CA1EA142400000000040A718C056905228D7A042400000000008A318C03671D56B66A14240FFFFFFFF23A518C0499D2405F2A0424000000000D8A518C0B41F58CA1EA14240 | 1228 | 269 | Uprate D.Rodrigo-Aljarafe | "D.Rodrigo " | Santiponce | Overhead Line | AC | 33.7 | 220 | 2019 | Under Construction | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
208 | 0104000020E61000000100000001010000000000000000CCE5BF44A697E0B8444540 | 1215 | 270 | Aragon region subestation | Aragon region | 0 | Substation | AC | 0 | 400 | 2025-01-01 | Planned but not yet permitting | REE | REE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS,CCS
207 | 0104000020E6100000010000000101000000FFFFFFFFFF36F4BF36B18AA70A004540 | 1214 | 270 | Ejea de los Caballeros subestation | "Ejea de los Caballeros " | Aragon region | Substation | AC | 0 | 400 | 2025-01-01 | Planned but not yet permitting | REE | REE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS,CCS
209 | 0105000020E61000000100000001020000000200000001000000005EEABF7C10C1D0C6E34440010000000094D1BFD246FCBADA2C4540 | 1212 | 270 | New axis Ejea-Aragon region 400 kV | "Ejea de los Caballeros " | "Ejea de los Caballeros" | Overhead Line | AC | 110 | 400 | 2026-01-01 | Planned but not yet permitting | REE | REE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS
210 | 0105000020E6100000010000000102000000020000001267A8FEFF47D2BFDAED693DB22845400100000000B0E33F6157E3A718C04540 | 1211 | 270 | HVDC Aragon region -Marsillon | "Aragon region" | AragÂ¢n region | Underground Cable | DC | 230 | 320 | 2026-01-01 | Planned but not yet permitting | REE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS
214 | 0105000020E610000001000000010200000002000000B3B20101007AFCBFAE39B4865A3A4540010000004080E2BFF804EA092EAC4540 | 1206 | 276 | HVDC Pamplona area -Cantegrit | Pamplona area | Saucats | Underground Cable | DC | 225 | 320 | 2026-12-01 | Planned but not yet permitting | REE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW
212 | 0105000020E610000001000000010200000003000000000000AA3326EABFF5B1290590FD454000008039C33FE6BF6C10C21157C545400000002C736CE2BFF0DF0F9F0EAC4540 | 1208 | 276 | Upgrade Cantegrit-Marsillon | Cantegrit | "Pamplona area" | Overhead Line | AC | 80 | 400 | 2026 | Planned but not yet permitting | RTE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW
211 | 0105000020E610000001000000010200000004000000000000C2EC7BE1BF8A76A5F5AC47464000000058A60FE0BF186509E8AD3F464000000035E34FE0BFA20962D718314640FEFF7FFBAF05EABF228AED0679FD4540 | 1207 | 276 | Upgrade Cantegrit-Saucats | Cantegrit | Marsillon | Overhead Line | AC | 70 | 400 | 2026 | Planned but not yet permitting | RTE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW
213 | 0104000020E6100000010000000101000000FFFFFFFF7F9EFDBF978AFAE7195F4540 | 1210 | 276 | New substation Pamplona area | "Pamplona area " | Gramme (BE) | Substation | AC | 0 | 400 | 2025-01-01 | Planned but not yet permitting | REE | REE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW
215 | 0105000020E6100000010000000102000000070000000000E03325DF1440A3F65A84033B49400000D4CCFD881440AA441AB64C2D49400000249668321440AECCB18D541F49400000EC65CCCD1340640E273BD4064940000030329B3A134083946BC8720349400000F4989C5A1240ABB4BED1B9E74840FFFFDFFE81F61140DCDFAFAF8EE64840 | 1008 | 280 | Study Lonny-Achene-Gramme | Lonny (FR) | Exeter | Phase Shift Transformer | AC | 0 | 400 | 2025-2030 | Under Consideration | RTE | ELIA | FALSE | France | Belgium | 0 | FR - BE | FALSE | CSW,NS
218 | 0105000020E61000000100000001020000000E000000000000006CF52640C83820264531454000000000C0472640AF10D80500174540FFFFFFFFFF362440BEF74926C094444000000000C0FE2340570F8805571D4440FFFFFFFFFFAF23403A994EF99D78434000000000408E2340CC93D28F225C43400000000000FC2240E295A06B6FA642400000000040E82340CF9590A1874C424000000000C077234050256198FF1C424000000000C0A423408FECD69464E14040FFFFFFFFFFAF23400D80714792B94040000000000083234083EFA8E21B814040FFFFFFFF3FDA2240FDFE3A920A6040400000000000C12140EAF466F6AC5D4040 | 1378 | 283 | TuNur DC | Rejim Maatoug (TN) VSC HVDC - 400 kV AC +/- 500 kV DC â€“ 2x 1GW | Montalto di Castro (IT) Terna station 400 kV AC | Subsea Cable | DC | 1265 | 500 | 2025 | In Permitting | TuNur Limited | TuNur Limited | TRUE | Tunisia | Italy | 0 | TN - IT | FALSE | CSE,CCS
219 | 0105000020E61000000100000001020000000300000018AD69FF7F8B0240B2B43AD618814940EBF5F6004012F73F5C51105DCCB849407D126D018047EA3F4D8ED00900A94940 | 1383 | 285 | GridLink | Kingsnorth (UK) | Pembroke | Subsea Cable | DC | 156 | 0 | 2022 | In Permitting | National Grid | RTE | TRUE | United Kingdom | France | 0 | GB - FR | FALSE | NS
220 | 0105000020E61000000100000001020000000200000000000000B0F013C0BB68E40212D149400000000080DC1BC0826CD233F8224A40 | 1385 | 286 | Greenlink | Great Island | LEVITHA | Subsea Cable | DC | 195 | 320 | 2023 | Planned but not yet permitting | National Grid | EirGrid | TRUE | Ireland | United Kingdom | 0 | IE - GB | FALSE | NS
222 | 0105000020E610000001000000010200000002000000C5975D42B0763A40A6463CFD2D81424032916FA31DEB384074F41E1CB2B34140 | 1432 | 293 | Southern Aegean Interconnector | LEVITHA | Syrna | Subsea Cable | DC | 250 | 320 | 2026 | In Permitting | no | yes | TRUE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
223 | 0105000020E610000001000000010200000002000000C5975D42B0763A40A6463CFD2D8142407F05F0436EB23A405D7DD69DED2B4240 | 1433 | 293 | Southern Aegean Interconnector | Levitha | LEVITHA | Subsea Cable | AC | 81 | 220 | 2025 | In Permitting | no | no | TRUE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
221 | 0105000020E610000001000000010200000005000000D5EFDB730DFC37409463991B5FE04240FCEC787A4222384099D963F9A5E54240EEAEF53DD1C93840F8D8440384D74240252C22712C3E3940C0BCF88920A14240E78A5242B0763A40AD593EFD2D814240 | 1431 | 293 | Southern Aegean Interconnector | LAVRIO | KORAKIA CRETE | Subsea Cable | DC | 245 | 320 | 2024 | In Permitting | yes | no | FALSE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
224 | 0105000020E610000001000000010200000002000000C5975D42B0763A40A6463CFD2D81424056156579564E3A4089F61F83A27D4240 | 1434 | 293 | Southern Aegean Interconnector | KINAROS | Syrna | Subsea Cable | AC | 14 | 220 | 2024 | In Permitting | no | no | TRUE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
225 | 0105000020E610000001000000010200000002000000F75F00446EB23A404BB9D29DED2B424072A3C85A43113B405F16EA1B5E484240 | 1435 | 293 | Southern Aegean Interconnector | Kandeliousa | Pergousa | Subsea Cable | AC | 34 | 220 | 2025 | In Permitting | no | no | FALSE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
226 | 0105000020E61000000100000001020000000200000072A3C85A43113B405F16EA1B5E484240D0B0FFD70C243B40A0B8EBBE46564240 | 1436 | 293 | Southern Aegean Interconnector | Kandeliousa | tba near Bergen-Mongstad or Karsto- Blafalli | Subsea Cable | AC | 14 | 220 | 2025 | In Permitting | no | no | FALSE | Greece | Cyprus | 0 | GR - CY | FALSE | CSE
227 | 0106000020E61000000100000001030000000100000006000000EE98570100B8FA3F6A47F5C6DEFF4D406565030200D4ECBF16CC2DE731324E40EE9857010088FD3FFFC711840EFD4D4001000000008610408D47B71846D24D40AD6C400080E21540C771331E1DBB4D40EE98570100B8FA3F6A47F5C6DEFF4D40 | 1356 | 294 | Maali | Kergord Shetland | Gatica/Hernani, Cordemais and Langage/Indian Queens | Subsea Cable | DC | 400 | 320 | 2025 | Under Consideration | National Grid / Scottish Hydro Electric Transmission | Stattnett | TRUE | United Kingdom | Norway | 0 | GB - NO | FALSE | BS,NS
229 | 0105000020E61000000100000001020000000E0000000000000012281140554EC3A678AF4940000000000B3E1140EDD5AAAF37AF4940000000007A56114067663C4F37AE4940000000006E6211400913159660AC4940000000000E681140A35D6B7F69A94940000000003B681140987C4C56D2A8494000000000A15C1140E484CB0B59A849400000000012551140152AB200ABA74940FFFFFF7F8B4C11407B16878B48A749400000000040181140B03FC48CAAA24940000000004E1911401FE81A2FB4A14940FFFFFFFFFD2C11403E13D01AA6A14940FFFFFFFF1F291140E29C68A450A0494000000000E0F010404D168273689C4940 | 445 | 297 | BRABO II: Zandvliet - Lillo - Liefkenshoek | Zandvliet | Mercator (BE) | Overhead Line | AC | 18 | 380 | 2020-12-31 | In Permitting | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
231 | 0104000020E6100000010000000101000000FFFFFF7F97401140DA2CE81780A64940 | 605 | 297 | BRABO II: Lillo 380 | Lillo (BE) | Suvereto | Substation | AC | 0 | 380 | 2019-03-31 | Under Construction | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
230 | 0105000020E6100000010000000102000000030000000000000084B61040A1A0824CB2944940FFFFFFFF4BDF10401DDF39CD28994940FFFFFFFF93F11040A7CCE9B9929C4940 | 604 | 297 | BRABO III: Liefkenshoek - Mercator | Liefkenshoek (BE) | Lillo (BE) | Overhead Line | AC | 19 | 380 | 2023-01-01 | In Permitting | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
314 | 0102000020E6100000030000000100000040F6244014A595EE7A7C45400100000000482240D246FCBADA2C454001000000A07A22405FB97EE96D2D4440 | 1458 | 299 | SACOI3 | Codrongianos - Lucciana | Suvereto | Subsea Cable | DC | 300 | 200 | 2023 | In Permitting | TERNA | RTE | FALSE | Italy | France |  | IT - FR | FALSE | CCS
306 | 0102000020E610000002000000C419AAFFFF71F5BFCCA54454596B4B401EF32A00000D2140BC1468C1D5DF4A40 |  | 309 | Neuconnect |  |  | Subsea Cable | DC | 680 | 400 | 2023 | In Permitting |  |  | TRUE | United Kingdom | Germany |  | GB - DE | FALSE | NS,CCS
243 | 0105000020E61000000100000001020000000B00000001000000D859294066CD2B8D21AB47400100000028A029408F70C6EBE0A047400000000070DF2940C1424ED5FAA3474001000000F4E2294006991046B0A847400100000008652A40E0C33D3EB7AF474000000000F8562A40A2F2B93CE1D5474001000000400F2A404772B0716AFF4740010000C065292A40B2FF8DF0BE204840010000606B292A40C940EFCFC0204840010000C065292A407C9B2C11BD2048400100000071292A40A0A43EE0BF204840 | 1472 | 312 | St. Peter - Tauern (AT internal) | St. Peter | Tauern | Overhead Line | AC | 128 | 380 | 2022 | In Permitting | APG | APG | FALSE | Austria |  |  |  | TRUE | CCE,CCS,CCE
244 | 0105000020E6100000010000000102000000060000000100000017292A407C9B2C11BD20484001000000BCDE2940B9876456FA29484001000000349429405BDCC02C5432484000000000F0412940AC4C246F8919484001000000DA9329402875023C4532484001000000CC57284013EC1B50D3514840 | 1473 | 313 | Isar/Altheim/Ottenhofen - St. Peter | Isar/Altheim/Ottenhofen (DE) | St. Peter (AT) | Overhead Line | AC | 90 | 380 | 2021 | In Permitting | TenneT-DE | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CCE,NS,CCS
245 | 0105000020E6100000010000000102000000020000000100000000202C40A0CBDB356DD8464001000000A0332D400ED68659590A4740 | 1617 | 316 | Upgrade of 220 kV line Divaca-Bericevo to 400 kV | Divaca | Bericevo | Overhead Line | AC | 80 | 400 | 2030 | Under Consideration | ELES | ELES | FALSE | Slovenia | 0 | 0 |  | FALSE | CCE
246 | 0105000020E6100000010000000102000000020000000100000070362D40E598029F5F0947400100000040742E40074A0A2043204740 | 1615 | 317 | Upgrade of internal 220 kV line Podlog-Bericevo to 400 kV | Podlog | Bericevo | Overhead Line | AC | 63 | 400 | 2035 | Under Consideration | ELES | ELES | FALSE | Slovenia | 0 | 0 |  | FALSE | CCE
247 | 0105000020E61000000100000001020000000200000001000000D06B2E40074A0A20432047400100000030A12F409F6E5610592E4740 | 1614 | 318 | Upgrade of 220 kV line Podlog-Cirkovce to 400 kV | Podlog | Cirkovce | Overhead Line | AC | 50 | 400 | 2035 | Under Consideration | ELES | ELES | FALSE | Slovenia | 0 | 0 |  | FALSE | CCE
249 | 0105000020E61000000100000001020000000200000001000000C05B2140453CC5234EE4474001000000C0FE2340FE8B204EC00D4840 | 1475 | 321 | Herbertingen - Tiengen | Herbertingen | Tiengen | Overhead Line | AC | 138 | 380 | 2025 | Planned but not yet permitting | Amprion / TransnetBW | Amprion / TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
250 | 0105000020E61000000100000001020000000200000001000000C0FE2340BB41D4C1CB2A484001000000001825407E6671CFE5C74740 | 1476 | 322 | Wullenstetten - Border Area (DE-AT) | Wullenstetten (DE) | Austrian National border (AT) | Overhead Line | AC | 88 | 380 | 2020 | In Permitting | Amprion | Amprion / vuen/ APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CCE, CCS
251 | 0105000020E6100000010000000102000000020000000100000040C92440E8EB3698CBC947400100000020CC234026E3DF69A2EF4740 | 1477 | 322 | Herbertingen - Neuravensburg | Herbertingen | Neuravensburg | Overhead Line | AC | 56 | 380 | 2020 | Planned but not yet permitting | Amprion | Amprion | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CCE, CCS
252 | 0105000020E6100000010000000102000000020000005A801900689A2B4085334B44F0C84640859B290008A02B403AB24D85D3CF4640 | 1478 | 323 | Dekani (SI) - Zaule (IT) interconnection | DEKANI | ZAULE | Underground Cable | AC | 11 | 110 | 2020 | In Permitting | ELES D.O.O. | TERNA SPA | FALSE | Slovenia | Italy | 0 | SI - IT | FALSE | CCE
253 | 0105000020E6100000010000000102000000020000000100000080FB2A40FCBBA089C2ED464001000000B0522B400893733701EE4640 | 1482 | 324 | Redipuglia (IT) - Vrtojba (SI) Interconnection | REDIPUGLIA | VRTOJBA | Underground Cable | AC | 22.5 | 110 | 2020 | In Permitting | TERNA SPA | ELES D.O.O. | FALSE | Italy | Slovenia | 0 | IT - SI | FALSE | CSE,CCS
254 | 0105000020E6100000010000000102000000020000000100000030662E404D14AB96BF204740BA94250020772D40A2989BF3FC564740 | 1483 | 325 | Upgrade Obersielach (AT) - Podlog (SI) (finalisation after approval of APG's Board Members) | Obersielach (AT) | Podlog (SI) | Overhead Line | AC | 70 | 380 | 2035 | Under Consideration | APG | ELES | FALSE | Italy | Austria | 0 | IT - AT | FALSE | CCE, CCS,CCE
309 | 0102000020E610000002000000DC78E2FFAF6E2D408F000BECF357474001000000785F29405867135968664740 | 1800 | 325 | Lienz - Obersielach (AT Internal, mandatory requirement for NTC increases on AT-IT and AT-SI border) | Lienz (AT) | Obersielach (AT) |  | AC | 170 | 380 | 2027 | Planned but not yet permitting | APG | APG | FALSE | Austria |  |  | AT | TRUE | CCE, CCS,CCE
338 | 0102000020E610000004000000C7BC0A00C0712940C3610E27556847403FD7E7FF8F1A294077BE9F1A2F5F47403FD7E7FF8F662840E3B4B7C62D2347403FD7E7FF8F662840BD5941DB83ED4640 | 1631 | 325 | Lienz - Italy (AT - IT) | Lienz | Veneto Region | Overhead Line | AC | 140 | 380 | 2035 | Under Consideration | TERNA | APG | FALSE | ITALY | Austria |  | IT - AT | FALSE | CCE, CCS,CCE
319 | 0102000020E61000000200000001000000A0281940388647C918DE484000000000E0C81A40D34840CF5AEA4840 | 1630 | 328 | AC Overhead Line Aach-Bofferdange | Aach (DE) | Bofferdange (LU) | Overhead Line | AC | 38 | 400 | 2026 | Planned but not yet permitting | AMPRION | CREOS | FALSE | Germany | Switzerland |  | DE - CH | FALSE | CCS,CCE
255 | 0105000020E6100000010000000102000000050000000100000080390940699AD984AEA7494001000000009C0840790E1600B89849400100000000990B40CB09341DB766494001000000C0BA0B40CB09341DB76649400100000040D10B40BD0EBF5945664940 | 1518 | 329 | Stevin-Izegem/Avelgem: new corridor | Stevin | Avelgem | Overhead Line | AC | 60 | 380 | 2028 | Under Consideration | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
256 | 0105000020E6100000010000000102000000020000000100000010A231406EB0F8596B95484001000000F03932404012B0CAB0864840 | 1498 | 330 | New CZ-SK 400 kV interconnector | Otrokovice (CZ) | Ladce (SK) | Overhead Line | AC | 78 | 400 | 2035 | Under Consideration | CEPS | SEPS | FALSE | Czech Republic | slovakia | 0 | CZ - SK | FALSE | CCE
258 | 0105000020E6100000010000000102000000020000005393BFFF7F151040210B4DE9CBFF49401EF32A000007074087674B4E54AD4B40 | 1506 | 335 | Interconnection NL Maasvlakte to Power Link Island | Maasvlakte 380 kV | Power Link Island NL1 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT TSO NL | TenneT TSO NL | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
261 | 0105000020E6100000010000000102000000020000001EF32A0000592040F66351E0369B4A40C419AAFFFFD9064087674B4E54AD4B40 | 1509 | 335 | Interconnection DE (area of Oldenburg) to Power Link Island | German substation located in the area of Oldenburg | Power Link Island DE2 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT-DE | TenneT-DE | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
262 | 0105000020E6100000010000000102000000020000008F791500804D2440BA97C1391FBB4A401EF32A000007074087674B4E54AD4B40 | 1511 | 335 | Interconnection DE (area of KrÃ¼mmel) to Power Link Island | German substation located in the area of KrÃ¼mmel | Power Link Island DE3 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT-DE | TenneT-DE | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
260 | 0105000020E6100000010000000102000000020000008F79150080312240CBC80F4BB9F84A40C419AAFFFFD9064087674B4E54AD4B40 | 1508 | 335 | Interconnection DE (area of BrunsbÃ¼ttel) to Power Link Island | German substation located in the area of BrunsbÃ¼ttel (north of the Elbe) | Power Link Island DE1 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT-DE | TenneT-DE | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
257 | 0105000020E6100000010000000102000000020000001EF32A0000C121409224A52C857B4B401EF32A0000070740D66563EBBAAB4B40 | 1505 | 335 | Interconnection DKw to Power Link Island | Endrup, DKw | Power Link Island DKw | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | Energinet | Energinet | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
259 | 0105000020E6100000010000000102000000020000000100000062191B40C8D272CD6BB94A40000000000080064087674B4E54AD4B40 | 1507 | 335 | Interconnection NL Eemshaven to Power Link Island | Eemshaven 380 kV | Power Link Island NL2 | Subsea Cable | DC | 0 | 0 | 2035-2040 | Under Consideration | TenneT TSO NL | TenneT TSO NL | FALSE | Netherlands | denmark | Germany | NL - DK | FALSE | BS,NS
263 | 0105000020E610000001000000010200000002000000FFFFFFFFBFCE2640622FBB13E48A47400100000080C326402885F905D5744740 | 1556 | 336 | Prati (IT) Â– Steinach (AT) | Prati di Vizze (IT) | Steinach (AT) | Overhead Line | AC | 139 | 132 | 2019 | Under Construction | TERNA | TINETZ | FALSE | ITALY | austria | 0 | IT - AT | FALSE | CSE,CCS
265 | 0105000020E6100000010000000102000000020000000100000050182040C6A9936A73AC4A4001000000F01D2040DCD70530276A4A40 | 1512 | 337 | Conneforde - Cloppenburg | Conneforde (DE) | Cloppenburg (DE) | Overhead Line | AC | 60 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
264 | 0105000020E6100000010000000102000000020000000100000070072040EB3D889DA4724A4000000000C0C51F409E481FD200574A40 | 1510 | 337 | Cloppenburg East - Merzen | Cloppenburg East (DE) | Merzen (DE) | Overhead Line | AC | 55 | 380 | 2024 | Planned but not yet permitting | TenneT-DE | Amprion | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
266 | 0105000020E6100000010000000102000000020000000100000040A42B4081EC076ABC29454001000000A0632A4020254DD39ADC4540 | 1521 | 338 | new HVDC line between Villanova and Fano existing 400 kV substations | Villanova | Fano | Subsea Cable | DC | 0 | 500 | 2030 | Under Consideration | Terna | Terna | FALSE | Italy |  |  |  | FALSE | CSE,CCS
267 | 0102000020E6100000030000000100000060AF2D407B846584C761444001000000E0142A40A960C7307A094340D5E4EFFF5FF62240AB82E6AD19964340 | 1557 | 339 | Italian HVDC tri-terminal link | SARDINIA REGION | SICILY REGION - SOUTH OF ITALY | Subsea Cable | DC | 0 | 0 | 2025 | Under Consideration | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
268 | 0105000020E61000000100000001020000000200000001000000E0D60B4026CABE3B7E66494001000000600711408720284DB2564940 | 1519 | 340 | Avelgem-Center: new corridor | Avelgem | Center (TBD) | Overhead Line | AC | 100 | 380 | 2028 | Under Consideration | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
270 | 0105000020E6100000010000000102000000030000002B1B1000A03C34400CCB9F6F8B6F4640F6211400885434408E4E656AF5814640000000006EB934403A946F8033834640 | 1538 | 341 | New OHL 400 kV WPP Cibuk - SS Belgrade West | WPP Cibuk | Belgrade West | Overhead Line | AC | 60 | 400 | 2030 | Under Consideration | EMS | EMS | FALSE | Romania | serbia | 0 | RO - RS | FALSE | CSE,CCE
269 | 0105000020E6100000010000000102000000020000000000000042983640507B117014614640000000006854364040FA550610434640 | 1536 | 341 | Portile de Fier (RO) - Djerdap (RS) 2nd | Portile de Fier | Djerdap | Overhead Line | AC | 4 | 400 | 2030 | Under Consideration | Transelektrica | EMS | FALSE | Romania | serbia | 0 | RO - RS | FALSE | CSE,CCE
271 | 0105000020E6100000010000000102000000020000000100000010DA35408194F521ABAB454000000000E0443740572533436B594540 | 1520 | 342 | Sofia West (BG) - Nis 2 (RS) 2nd | SS Sofia West | SS Nis 2 | Overhead Line | AC | 80 | 40 | 2034 | Under Consideration | ESO | EMS | FALSE | Bulgaria | serbia | 0 | BG - RS | FALSE | CSE
272 | 0105000020E610000001000000010200000002000000010000000A59354029102DB37DCE45400000000002D935408194F521ABAB4540 | 1522 | 342 | Upgrade of exsisting OHL 220 kV to 400 kV SS Nis 2 - SS KruÂševac 1 | SS Nis 2 | SS Krusevac 1 | Overhead Line | AC | 40 | 400 | 2034 | Under Consideration | EMS | EMS | FALSE | Bulgaria | serbia | 0 | BG - RS | FALSE | CSE
273 | 0105000020E6100000010000000102000000030000000100000056583540D022BC479ECE45400100000026013540B47303D032D3454001000000D4AD34409C69CF99C3DE4540 | 1524 | 342 | Upgrading of exsisting OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | SS Krusevac 1 | SS Kraljevo 3 | Overhead Line | AC | 50 | 400 | 2034 | Under Consideration | EMS | EMS | FALSE | Bulgaria | serbia | 0 | BG - RS | FALSE | CSE
276 | 0105000020E6100000010000000102000000020000009CA1FAFF1F4A2D409E6230DA3E9D4640010000001CB530407BBA9D3B35B94540 | 1533 | 343 | New OHL 400 kV Lika Â Â– Melina | Lika (HR) | Melina (HR) | Overhead Line | AC | 68 | 400 | 2030 | Planned but not yet permitting | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
277 | 0105000020E610000001000000010200000002000000010000004CB2304060B708E4F3B84540010000000C7A3040D9BD93C053CC4540 | 1534 | 343 | New OHL 400 kV Lika Â Â– Konjsko | Lika (HR) | Konjsko (HR) | Overhead Line | AC | 200 | 400 | 2030 | Planned but not yet permitting | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
275 | 0105000020E610000001000000010200000002000000960D0800D00F3140CD7DEEDB7B7D464001000000A0B8304064C70D3FF9B94540 | 1532 | 343 | New OHL 400 kV Banja Luka - Lika | Banja Luka (BA) | Lika (HR) | Overhead Line | AC | 155 | 400 | 2030 | Planned but not yet permitting | NOS BIH | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
278 | 0105000020E6100000010000000102000000040000000100000020E518404BC7BDE0CA404A4001000000E04F1B40358311F2C3254A40D887500020121940210B4DE9CBFF4940F034BAFF9F3917408B0CDDB264024A40 | 1541 | 344 | Zwolle-Hengelo-Doetinchem-Dodewaard | Zwolle | Dodewaard | Overhead Line | AC | 165 | 380 | 2035 | Under Consideration | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
279 | 0102000020E6100000030000000100000020F913401E6E494C9A204A407FAECFFF1FF9134032E5013463204A408CD6B4FFBF711940959182C02D7C4A40 | 1542 | 345 | Northern East-West connection NL | tbd | tbd | Overhead Line | AC | 0 | 0 | 2040 | Under Consideration | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
281 | 0105000020E6100000010000000102000000020000000000000020CF10403290B12F63B6494001000000285A1440652AC925EAC64940 | 1544 | 346 | ZuidWest3808 Oost | Rilland | Tilburg | Overhead Line | AC | 80 | 380 | 2025 | In Permitting | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
280 | 0105000020E61000000100000001020000000500000001000000A0060D40B66EFFE51CBA49400000000000B50D40B04DBE4342BF494001000000E81610400A2CE975C1BB49400100000010941040CCCDA0A166B549400000000020CF1040ACC58C010FB64940 | 1543 | 346 | ZuidWest380 West | Borssele | Rilland | Overhead Line | AC | 40 | 380 | 2021 | Under Construction | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
282 | 0105000020E610000001000000010200000002000000010000007042114010A62E460CF649400000000080C61340F73BBB4994D34940 | 1545 | 347 | Maasvlakte Â– Noord Brabant connection | Krimpen | Geertruidenberg | Overhead Line | AC | 0 | 0 | 2040 | Under Consideration | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
283 | 0105000020E61000000100000001020000000200000072851C00161A1B4070076ECD6BB94A4000000000281919400DC9E82279944A40 | 1546 | 348 | NoordWest380 | Eemshaven Oude Schip | Vierverlaten | Overhead Line | AC | 40 | 380 | 2021 | Under Construction | TENNET-NL | TENNET-NL | FALSE | Netherlands |  |  |  | TRUE | NS
324 | 0102000020E6100000030000000000000008113440CC3619FDEC8E444001000000C8B9344030281CE2AF9C444001000000A851354044F39AEBF9864440 | 1622 | 350 | 400kV OHL SS Bitola - SS Elbasan | Bitola | Elbasan | Overhead Line | AC | 161 | 400 | 2020 | In Permitting | MEPSO | OST | FALSE | GREECE | Albania |  | GR - AL | FALSE | CSE
284 | 0105000020E6100000010000000102000000020000003CE65500002EFDBFE72D264FBCBC4C401EF32A00009FF5BF8B7227E070734B40 | 1547 | 351 | Eastern HVDC Link | Peterhead (GB) | Hawthorn Pit (GB) | Subsea Cable | DC | 365 | 500 | 2024 | Under Consideration | SHETL | NGET | FALSE | United Kingdom |  |  |  | TRUE | NS
299 | 0105000020E610000001000000010200000002000000010000003C52774052A7E7A0B677474001000000543A7740000DFCA84CDF4640 | 1555 | 375 | Lienz (AT) - Veneto region (IT) | Lienz (AT) | Veneto region (IT) | Overhead Line | AC | 140 | 220 | 2024 | In Permitting | APG | TERNA | FALSE | Italy | austria | 0 | IT - AT | FALSE | CSE,CCS
313 | 0102000020E61000000400000000000000107D28404C3F9C3DBDEE464000000000107D2840BFD61C5BB122474001000000D02529409E161CA5415D47405B26E4FF6571294073CD2E2908684740 | 1555 | 375 | Lienz (AT) - Veneto region (IT) | Lienz (AT) | Veneto region (IT) | Overhead Line | AC | 140 | 220 | 2024 | In Permitting | APG | TERNA | FALSE | Austria | Italy |  | AT - IT |  | CSE,CCE
300 | 0105000020E61000000100000001020000000200000035F9FBFF175A35402F47975024814440C3721100987035400B08EFA381654440 | 1559 | 376 | New investment | Bitola (MK) | Meliti (GR) | Overhead Line | AC | 35.512 | 400 | 2030 | Under Consideration | MEPSO | IPTO | FALSE | Greece | macedonia | 0 | GR - MK | FALSE | CSE
301 | 0105000020E61000000100000001020000000200000001000000A0DF16407181630A7C8B4940490E3B00A0661740C7363ECD28994940 | 1561 | 377 | BE-NL interconnector: upgrade VanEyck-Maasbracht | VanEyck | Maasbracht | Overhead Line | AC | 12 | 380 | 2030 | Under Consideration | Elia | TENNET-NL | FALSE | Belgium | netherlands | 0 | BE - NL | FALSE | NS
304 | 0105000020E610000001000000010200000002000000C419AAFFFFD906C068237423EEB14540CBAD9CFF4F0405C00C616F41BAA84540 | 1597 | 379 | Uprate Gatica-Azpeitia | Gatica | Azpeitia | Overhead Line | AC | 57 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
302 | 0105000020E6100000010000000102000000020000003C3487FFCFDC06C0431758F070B245406D955800F03308C0E0C91B1E4A964540 | 1593 | 379 | Uprate Gatica-Guenes | Gatica | Guenes | Overhead Line | AC | 38.8 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
303 | 0105000020E610000001000000010200000002000000C419AAFFFFD906C095285A3D50B2454084F49000A02002C0615BD46164954540 | 1595 | 379 | Uprate Gatica-Amorebieta-Ichaso | Gatica | Ichaso | Overhead Line | AC | 69.12 | 400 | 2021 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW

## Sheet5 (hidden)
name | _from | _to | elementstype | technology_type | total_route_length | voltage_level | expected_commissioning_year | status | tso_in_charge_from | tso_in_charge_to | third_party | country_1 | country_2 | country_3 | code | internal | regions
V.Minho -R.Pena-FridÃ£o-Feira | V.Minho (by Ribeira de Pena and FridÃ£o) | Feira (by Ribeira de Pena and FridÃ£o) | Overhead Line | AC | 131 | 400 | 2022-2024 | In Permitting | REN | REN | FALSE | Portugal |  |  |  | TRUE | CSW
Substation Ribeira de Pena | Ribeira de Pena (PT) | - | Substation | AC | 0 | 400 | 2022-2024 | In Permitting | REN | - | FALSE | Portugal |  |  |  | TRUE | CSW
Pedralva-Sobrado | Pedralva (PT) | Sobrado (PT) | Overhead Line | AC | 67 | 400 | 2022-2023 | Planned but not yet permitting | REN | REN | FALSE | Portugal |  |  |  | TRUE | CSW
Switching station FridÃ£o | FridÃ£o | Fontefria (ES) | Substation | AC | 0 | 400 | 2026-2030 | In Permitting | REN | - | FALSE | Portugal |  |  |  | TRUE | CSW
Ponte de Lima (PT) | Ponte de Lima (PT) | La Ribina (ES) | Substation | AC | 0 | 400 | 2021-01-01 | In Permitting | REN | REN | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
SE Fontefria 400/220kV | Fontefria (ES) | Beariz (ES) | Substation | AC | 0 | 400 | 2021-01-01 | In Permitting | REE | REE | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
Fontefria (ES) - Vila Nova de FamalicÃ†o (PT) | Fontefria (ES) | REE | Overhead Line | AC | 135 | 400 | 2021-01-01 | In Permitting | REE | REN | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
Beariz (ES) - Fontefria (ES) | Beariz (ES) | Vila Nova de FamalicÃ†o (PT) (By Ponte de Lima) | Overhead Line | AC | 32 | 400 | 2021-01-01 | In Permitting | REE | REE | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
Beariz 400kV (ES) | Beariz (ES) | Ponte de Lima (PT) | Substation | AC | 0 | 400 | 2021-01-01 | In Permitting | REE | REE | FALSE | Portugal | Spain | 0 | PT - ES | FALSE | CSW
New substation La Ribina | La Ribina (ES) | Cubnezais (FR) | Substation | AC | 0 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
Axis Caparacena-Baza-La Ribina | Caparacena (ES) | Baza (ES) | Overhead Line | AC | 177 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
New substation Baza | Baza (ES) | La Ribina (ES) | Substation | AC | 0 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
HVDC Gatica-Cubnezais | Gatica (ES) | Piossasco (IT) | Subsea Cable | DC | 370 | 320 | 2025-01-01 | In Permitting | REE | RTE | FALSE | Spain | France | 0 | ES - FR | FALSE | CSW,NS
Savoie - PiÃ¨mont | Grande Ile (FR) | Horta (BE) | Underground Cable | DC | 190 | 320 | 2019 | Under Construction | RTE | TERNA | FALSE | France | Italy | 0 | FR - IT | FALSE | CSW,NS,CCS
FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | Avelin/Mastaing (FR) | Chilling (GB) | Overhead Line | AC | 80 | 400 | 2022-01-01 | In Permitting | RTE | ELIA | FALSE | France | Belgium | 0 | FR - BE | FALSE | CSW,NS
IFA2 | Tourbe (FR) | Glorenza (IT) | Subsea Cable | DC | 250 | 320 | 2020-01-01 | Under Construction | RTE | NGIHL | FALSE | France | Great Britain | 0 | FR - GB | FALSE | CSW,NS
Reschenpass Interconnector | Nauders (AT) | Lastva (ME) | Underground Cable | AC | 26 | 220 | 2021 | In Permitting | APG | Terna | FALSE | Austria | Italy | 0 | AT - IT | FALSE | CCS,CCE
First HVDC Module IT-ME | Villanova (IT) |  | Subsea Cable | DC | 445 | 500 | 2019 | Under Construction | TERNA | CGES | FALSE | Italy | Montenegro | 0 | IT - ME | FALSE | CSE,CCS
SS 400/110 kV Lastva | Lastva (ME) | Lastva (ME) | Substation | AC | 0 | 400 | 2018-12-31 | Under Construction | CGES |  | FALSE | Italy | Montenegro | 0 | IT - ME | FALSE | CSE,CCS
Elmed Project | Sicily Area (IT) | Pallanzeno(IT)-Baggio(IT) | Subsea Cable | DC | 200 | 400 | 2022 | In Permitting | TERNA | STEG | FALSE | Italy | Tunisia | 0 | IT - TN | FALSE | CSE,CCS
San Giacomo Project | All'Acqua (CH) | Colunga (IT) | Overhead Line | AC | 100 | 380 | 2025 | In Permitting | SWISSGRID | TERNA | FALSE | Switzerland | Italy | 0 | CH - IT | FALSE | CCS
Rem. lim. in Central Italy | Villanova (IT) |  | Overhead Line | AC | 350 | 220 | 2022-01-01 | Planned but not yet permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
90 | Calenzano (IT) | S. Barbara (IT) | Overhead Line | AC | 80 | 400 | 2022 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
R Kocin | Kocin (CZ) | Mirovka (CZ) | Substation | AC | 0 | 400 | 2024-01-01 | Under Construction | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
Kocin-Mirovka | Kocin (CZ) | Prestice (CZ) | Overhead Line | AC | 121 | 400 | 2024-01-01 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
Kocin-Prestice | Kocin (CZ) | Bentwisch (DE) | Overhead Line | AC | 116 | 400 | 2028-01-01 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
Kriegers Flak CGS, TYNDP ID: 36.141 | IshÃ¸j / BjÃ¦verskov (DK) | Wilster (DE) | Subsea Cable | AC | 24 | 150 | 2018-12-31 | Under Construction | Energinet.dk | 50Hertz Transmission GmbH | FALSE | denmark | Germany | 0 | DK - DE | FALSE | BS,NS
Audorf - Kassoe | Audorf (DE) | LUX-DE (TBC) | Overhead Line | AC | 110 | 380 | 2020-12-31 | Under Construction | TenneT-DE | Energienet.dk | FALSE | denmark | Germany | 0 | DK - DE | FALSE | BS,NS
BE-LUX-DE Long-Term perspective | Aubange (TBC) | St. Peter (AT) | Overhead Line | AC | 0 | 0 | 2035 | Under Consideration | ELIA | CREOS; AMPRION | FALSE | Belgium | Germany | Luxembourg | BE - DE | FALSE | BS,NS,CCS
219: Westtirol - Zell/Ziller (AT internal) | Westtirol (AT) | Westtirol (AT) | Overhead Line | AC | 105 | 380 | 2024 | Planned but not yet permitting | APG | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
689: VÃ¶hringen (DE) - Westtirol (AT) | VÃ¶hringen (DE) |  | Overhead Line | AC | 114 | 380 | 2024 | Planned but not yet permitting | Amprion | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
(is a single investment project, please consider only content of project 312) 216 | St. Peter (AT) | Zell-Ziller (AT) | Overhead Line | AC | 128 | 400 | 2022 | In Permitting | APG | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
(is a single investment project, please consider only content of project 313) 212 Isar/Altheim/Ottenhofen - St. Peter | Isar (DE) | Tauern (AT) | Overhead Line | AC | 90 | 400 | 2021 | In Permitting | TenneT-DE | APG | FALSE | Germany | Austria | 0 | DE - AT | FALSE | CSE,CCE
Hunew 2 | SajÃ³ivÃ¡nka (HU) | Gonyu (HU) | Substation | AC | 0 | 400 | 2020 | In Permitting | MAVIR |  | FALSE | Slovakia | Hungary | 0 | SK - HU | FALSE | CCE
Hunew 1 | SajÃ³ivÃ¡nka (HU) |  | Compensation | AC | 0 | 400 | 2020 | In Permitting | MAVIR |  | FALSE | Slovakia | Hungary | 0 | SK - HU | FALSE | CCE
2. SK-HU interconnection | RimavskaÂ Sobota (SK) | Sajoivanka (HU) | Overhead Line | AC | 48 | 400 | 2020 | In Permitting | MAVIR |  | FALSE | Slovakia | Hungary |  | SK - HU | FALSE | CCE
1. SK-HU interconnection | Gabcikovo (SK) | Gonyu (HU) | Overhead Line | AC | 110 | 400 | 2020 | In Permitting | SEPS | MAVIR | FALSE | Slovakia | Hungary |  | SK - HU | FALSE | CCE
Riga CHP2 - Riga HPP | Riga CHP2 | Eemshaven (NL) | Overhead Line | AC | 15 | 330 | 2020-01-01 | In Permitting | AST | AST | FALSE | Estonia | Latvia | 0 | EE - LV | FALSE | BS
3rd EE-LV interconnection | Kilingi-Nomme (EE) | Sindi (EE) | Overhead Line | AC | 205 | 330 | 2020 | Under Construction | Elering | AST | FALSE | Estonia | Latvia | 0 | EE - LV | FALSE | BS
Harku-Sindi 330kV OHL | Harku (EE) | Riga HPP | Overhead Line | AC | 175 | 330 | 2020-12-31 | Under Construction | Elering | Elering | FALSE | Estonia | Latvia | 0 | EE - LV | FALSE | BS
COBRA Cable | Endrup (DK) | Gezelle (BE) | Subsea Cable | DC | 325 | 320 | 2019 | Under Construction | Energinet | TENNET-NL | FALSE | denmark | Netherlands | 0 | DK - NL | FALSE | BS,NS
SELL - DUNG Reconductoring | Sellindge (GB) | Stevin (Zeebrugge) | Overhead Line | AC | 26 | 400 | 2016-11-30 | Under Construction | NGET | NGET | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
NEMO | Richborough (GB) | Canterbury (GB) | Subsea Cable | DC | 140 | 400 | 2019-01-01 | Under Construction | NGET | ELIA | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
Richborough - Canterbury | Richborough (GB) | Dungeness (GB) | Overhead Line | AC | 20 | 400 | 2018 | In Permitting | NGET | NGET | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
Modular Offshore Grid | Offshore platform | Deeside (GB) | Subsea Cable | AC | 50 | 220 | 2020-01-01 | In Permitting | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
Western HVDC Link | Hunterston (GB) | Seabank (GB) | Subsea Cable | DC | 360 | 500 | 2017 | Under Construction | SPT | NGET | FALSE | United Kingdom |  |  |  | TRUE | NS
HINP-SEAB New Double Circuit | Hinkley Point (GB) | Turleenan (NI) | Overhead Line | AC | 60 | 400 | 2024 | In Permitting | NGET | NGET | FALSE | United Kingdom |  |  |  | TRUE | NS
462 | Woodland (IE) | New substation in South Donegal (IE) | Overhead Line | AC | 138 | 400 | 2020 | In Permitting | EirGrid | SONI | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
Srananagh - South Donegal | Srananagh (IE) | Omagh South (NI) | Overhead Line | AC | 76 | 220 | 2029 | Planned but not yet permitting | EirGrid | EirGrid | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
Omagh South to South Donegal | South Donegal (IE) | Turleenan | Overhead Line | AC | 58 | 275 | 2029 | Planned but not yet permitting | EirGrid | SONI | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
Omagh South to Turleenan | Omagh South | Tavira (by Ourique) | Overhead Line | AC | 63 | 275 | 2029 | Planned but not yet permitting | SONI | SONI | FALSE | Ireland | Northern Ireland | 0 | IE - NI | FALSE | NS
Extension of Ourique substation | Ourique (PT) | Lixhe (BE) | Substation | AC | 0 | 400 | 2024-2026 | Planned but not yet permitting | REN | - | FALSE | Portugal |  |  |  | TRUE | CSW
F.Alentejo-Ourique-Tavira | F. Alentejo (by Ourique) | - | Overhead Line | AC | 122 | 400 | 2024-2026 | Planned but not yet permitting | REN | REN | FALSE | Portugal |  |  |  | TRUE | CSW
ALEGrO | Oberzier (DE) | Krajnik (PL) | Underground Cable | DC | 100 | 320 | 2020-10-01 | In Permitting | AMPRION | ELIA | FALSE | Belgium | Germany | 0 | BE - DE | FALSE | BS,NS,CCS
Krajnik-Vierraden | Vierraden (DE) | Krajnik (PL) | Overhead Line | AC | 26 | 400 | 2020-12-31 | Under Construction | 50Hertz | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
Krajnik | Krajnik (PL) | Mikulowa (PL) | Substation | AC | 0 | 400 | 2019 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
FI5 KI-PS | Keminmaa (FI) | Ens | Overhead Line | AC | 156 | 400 | 2024-01-01 | In Permitting | Fingrid | Fingrid | FALSE | Finland |  |  |  | TRUE | BS
Eindhoven-Maasbracht | Eindhoven | Maasbracht | Overhead Line | AC | 50 | 380 | 2023 | Planned but not yet permitting | TENNET - NL | TENNET - NL |  | Netherlands |  |  | NL | TRUE | NS
Diemen-Lelystad-Ens | Diemen | Ens | Overhead Line | AC | 75 | 380 | 2020 | Under Construction | TENNEL - NL | TENNET - NL | FALSE | Netherlands |  |  | NL | TRUE | NS
Diemen-Lelystad-Ens | Diemen | Ens | Overhead Line | AC | 75 | 380 | 2020 | Under Construction | TENNET - NL | TENNET - NL | FALSE | Germany |  |  | DE | TRUE | CCE,BS,NS,CCS
France Ireland Interconnector | West Wexford or East Cork (IE) | Blythe (GB) | Subsea Cable | DC | 580 | 320 | 2026 | Under Consideration | EIRGRID | RTE | FALSE | France | Ireland | 0 | FR - IE | FALSE | NS
Norway - Great Britain | Kvilldal (NO) | Messaure (Sweden, bidding area SE1) | Subsea Cable | DC | 720 | 500 | 2021 | Under Construction | Statnett | NHIGL | FALSE | United Kingdom | norway | 0 | GB - NO | FALSE | BS,NS
3rd AC Finland-Sweden north | Keminmaa (Finland) | Doetinchem (NL) | Overhead Line | AC | 200 | 400 | 2025 | In Permitting | Fingrid | Svenska kraftnÃ¤t | FALSE | Finland | Sweden | 0 | FI - SE | FALSE | BS
Doetinchem-Niederrhein | Niederrhein (DE) | TBD (BE) | Overhead Line | AC | 57 | 380 | 2018 | Under Construction | AMPRION | TENNET-NL | FALSE | Netherlands | Germany | 0 | NL - DE | FALSE | NS,CCS
MOG II: connection of up to 2 GW additional offshore wind Belgium | Offshore (TBD) | Onshore (TBD) | Subsea Cable | DC | 50 | 400 | 2030 | Under Consideration | Elia | Elia | FALSE | Belgium |  |  | BE | TRUE | NS
Nautilus: 2nd interco UK - BE | Leiston (UK) | Stanislawow (PL) | Subsea Cable | DC | 250 | 400 | 2028 | Under Consideration | NGHIL | ELIA | FALSE | Belgium | Great Britain | 0 | BE - GB | FALSE | NS
Ostroleka-Stanislawow | Ostroleka (PL) | Musa | Overhead Line | AC | 106 | 400 | 2023-12-31 | Planned but not yet permitting | PSE | PSE | FALSE | Poland | Lithuania | 0 | PL - LT | FALSE | BS
330 kV OHL Panevezys-Musa | Panevezys | Imanta (LV) | Overhead Line | AC | 80 | 330 | 2023-12-31 | Planned but not yet permitting | LITGRID | LITGRID | FALSE | Lithuania | Sweden | 0 | LT - SE | FALSE | BS
Grobina (LV) - Imanta (LV) | Grobina (LV) | Nybro/Hemsjo (SE) | Overhead Line | AC | 380 | 330 | 2019 | Under Construction | AST | AST | FALSE | Lithuania | Sweden | 0 | LT - SE | FALSE | BS
Ekhyddan-Nybro-Hemsjo | Ekhyddan (SE) | SE3 | Overhead Line | AC | 160 | 400 | 2023 | In Permitting | Svk | Svk | FALSE | Lithuania | Sweden | 0 | LT - SE | FALSE | BS
Reinforcements SE2-SE3 in Sweden | SE2 | Villanova (IT) | Compensation | AC | 900 | 400 | 2030 | Under Consideration | Svk | Svk | FALSE | Sweden |  |  |  | TRUE | BS
ITA-3 | Laino (IT) | Isar (DE) | Overhead Line | AC | 50 | 400 | 2022-01-01 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
86 | Foggia (IT) | Benevento II (IT) | Overhead Line | AC | 178 | 400 | 2022-01-01 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
91 | Foggia (IT) | Bisaccia (IT) | Overhead Line | AC | 85 | 400 | 2014-06-30 | Commissioned | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
96 | Deliceto (IT) | Altomonte (IT) | Overhead Line | AC | 30 | 400 | 2022-12-31 | In Permitting | TERNA | TERNA | FALSE | Italy |  |  |  | TRUE | CSE,CCS
Wolmirstedt-Isar | Wolmirstedt (DE) | Osterath (DE) | Underground Cable | DC | 540 | 0 | 2025 | In Permitting | 50Hertz | TenneT DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
HVDC Line A-North | Emden East (DE) | Eichstetten (DE) | Overhead Line | DC | 300 | 400 | 2025-01-01 | Under Consideration | Amprion | Amprion | FALSE | Germany |  | 0 | Internal | TRUE | CCE,BS,NS,CCS
HVDC Line A-North | Emden East (DE) | Osterath (DE) | Overhead Line | DC | 300 | 400 | 2025 | Planned but not yet permitting | AMPRION | AMPRION | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Urberach - Daxlanden | Urberach (DE) | WeiÃŸenthurm (DE) | Overhead Line | AC | 219 | 400 | 2022-01-01 | Under Consideration | Amprion | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Daxlanden-Eichstetten | Daxlanden (DE) | Daxlanden (DE) | Overhead Line | AC | 120 | 380 | 2021-01-01 | Under Consideration | TransnetBW | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Rommerskirchen - WeiÃŸenthurm | Rommerskirchen (DE) | Dauersberg (DE) | Overhead Line | AC | 94 | 400 | 2019-01-01 | Under Construction | Amprion | Amprion | FALSE | Germany |  | 0 | Internal | TRUE | CCE,BS,NS,CCS
Kruckel - Dauersberg | Kruckel (DE) | Stalpu (RO) | Overhead Line | AC | 110 | 380 | 2021-01-01 | In Permitting | Amprion | Amprion | FALSE | Germany |  | 0 | Internal | TRUE | CCE,BS,NS,CCS
400 kV OHL Varna-Burgas | Varna(BG) | N.Santa (GR) | Overhead Line | AC | 140 | 400 | 2021-03-31 | Planned but not yet permitting | ESO-EAD | ESO-EAD | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE
220kV Stalpu substation upgrade to 400 kV | Stalpu (RO) | Burgas(BG) | Substation | AC | 0 | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE
400 kV OHL Smardan-Gutinas | Smardan (RO) | Stalpu (RO) | Overhead Line | AC | 140 | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE,CCE
400kV OHL Cernavoda-Stalpu | Cernavoda (RO) | Gutinas (RO) | Overhead Line | AC | 159 | 400 | 2020 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Bulgaria | 0 | RO - BG | FALSE | CSE
256 | Maritsa East 1 (BG) | Plovdiv (BG) | Overhead Line | AC | 130 | 400 | 2023-01-30 | In Permitting | ESO-EAD | IPTO-SA | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
257 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | Overhead Line | AC | 100 | 400 | 2020-12-30 | Under Consideration | ESO-EAD | ESO-EAD | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
258 | Maritsa East 1 (BG) | Burgas (BG) | Overhead Line | AC | 13 | 400 | 2019-06-30 | Under Consideration | ESO-EAD | ESO-EAD | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
262 | Maritsa East 1 (BG) | Pancevo (RS) | Overhead Line | AC | 150 | 400 | 2021-06-01 | Under Consideration | ESO-EAD | ESO-EAD | FALSE | Romania | Greece | 0 | RO - GR | FALSE | CSE
400 kV Substation Timisoara | Timisoara (RO) | Border IT-SI | Substation | AC | 0 | 400 | 2023 | Under Consideration | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz - Arad to 400kV double circuit line | Resita (RO) | Resita (RO) | Overhead Line | AC | 175 | 400 | 2023 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
400 kV Substation Resita | Resita (RO) | Timisoara (RO) | Substation | AC | 0 | 400 | 2019 | In Permitting | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
New_400 kV OHL RO-RS | Resita (RO) | Resita (RO) | Overhead Line | AC | 131 | 400 | 2017 | Under Construction | Transelectrica | EMS | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE,CCE
400 kV OHL Portile de Fier-Resita | Portile de Fier (RO) | Arad (RO) | Overhead Line | AC | 116 | 400 | 2019 | Under Construction | Transelectrica | Transelectrica | FALSE | Romania | Serbia | 0 | RO - RS | FALSE | CSE
Salgareda - Border IT-SI | Salgareda (IT) | Border IT-SI | Underground Cable | DC | 0 | 500 | 2022 | Under Consideration | TERNA |  | FALSE | Slovenia | Italy | 0 | SI - IT | FALSE | CCE,CCS
BeriÄevo - Border IT-SI | BeriÄevo (SI) | Border IT-SI | Underground Cable | DC | 140 | 400 | 2022 | In Permitting | ELES | TERNA |  | Slovenia | Italy |  |  | FALSE | CCE,CCS
France-Alderney-Britain | Menuel (FR) | Stade (DE) | Subsea Cable | DC | 210 | 320 | 2022-01-01 | In Permitting | RTE (FR) | NGIHL (UK) | FALSE | France | Great Britain | 0 | FR - GB | FALSE | CSW,NS
Wahle - Mecklar | Wahle (DE) | Landesbergen (DE) | Overhead Line | AC | 210 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Mecklar - Grafenrheinfeld | Mecklar (DE) | Bicker Fen (GB) | Overhead Line | AC | 130 | 380 | 2027 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Dollern - Stade | Dollern (DE) | Mecklar (DE) | Overhead Line | AC | 14 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Dollern - Landesbergen | Dollern (DE) | Grafenrheinfeld (DE) | Overhead Line | AC | 130 | 380 | 2023 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Viking Link DKW-GB, TYNDP ID 167.998 | Revsing (DKW) | Neris | Subsea Cable | DC | 770 | 515 | 2022-12-31 | In Permitting | Energinet.dk | National Grid | FALSE | Denmark | United Kingdom | 0 | DK - GB | FALSE | BS,NS
330 kV line Vilnius-Neris | Vilnius | Paide | Overhead Line | AC | 80 | 330 | 2024-01-01 | Planned but not yet permitting | LITGRID | LITGRID | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
Valmiera -Tsirguliina 330 kV | Tsirguliina | Tartu | Overhead Line | AC | 60 | 330 | 2025-01-01 | Planned but not yet permitting | Elering | AST | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
330 kV OHL Tartu-Valmiera | Tartu | Valmiera | Overhead Line | AC | 133 | 330 | 2025-01-01 | Planned but not yet permitting | Elering | AST | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
New 400 kV interconnection line from Lithuania to state border | Marijampole | - | Overhead Line | AC | 51 | 400 | 2031-01-01 | Under Consideration | LITGRID | LITGRID | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
Eesti-Tsirguliina 330kV OHL | Eesti | State border | Overhead Line | AC | 243 | 330 | 2025-01-01 | Under Consideration | ELERING | ELERING | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
B2B at Narva | Eesti | - | Substation | DC | 0 | 330 | 2024-01-01 | Under Consideration | ELERING | - | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
330 kV OHL Tartu-Balti (L300) | Balti | Tsirguliina | Overhead Line | AC | 168 | 330 | 2024-01-01 | Under Consideration | ELERING | ELERING | FALSE | Lithuania |  | 0 | Baltic | TRUE | BS
Eleclink | Sellindge | Mandarins | Subsea Cable | DC | 69 | 400 | 2019 | Under Construction | National Grid | Reseau de Transport d'Electricite, the French TSO | FALSE | United Kingdom | France |  | GB - FR | FALSE | NS
Aubange-Moulaine: PSTs | Aubange (BE) | Sils i.D. | Phase Shift Transformer | AC | 0 | 220 | 2020-12-31 | Planned but not yet permitting | ELIA | RTE | FALSE | France | Belgium | 0 | FR - BE | FALSE | CSW,NS
Greenconnector | Verderio | Not decided | Underground Cable | DC | 150 | 400 | 2022 | In Permitting | Terna | Swissgrid | TRUE | Italy | Switzerland | 0 | IT - CH | FALSE | CSE,CCS
Great Belt II | Not decided | GueÂstrow (DE) | Subsea Cable | DC | 50 | 400 | 2030 | Under Consideration | Energinet | Energinet | FALSE | Denmark | Denmark | 0 | DK - DK | FALSE | BS
Hansa PowerBridge | Hurva (SE4) | Bentwisch (DE) | Subsea Cable | DC | 300 | 300 | 2026 | In Permitting | Svk | 50Hertz | FALSE | Germany | Sweden | 0 | DE - SE | FALSE | BS,NS,CCE
DKE-DE (Kontek 2) | BjÃ¦verskov (DK2) | Endrup (DKW) | Subsea Cable | DC | 170 | 400 | 2030 | Under Consideration | Energinet | 50Hertz | FALSE | Denmark | Germany | 0 | DK - DE | FALSE | BS,NS
DKW-DE, Westcoast, TYNDP ID 183.1018 | KlixbÃ¼ll (DE) | Neusiedl/Zaya | Overhead Line | AC | 92 | 380 | 2022-12-31 | In Permitting | TenneT-DE | Energinet.dk | FALSE | Denmark | Germany | 0 | DK - DE | FALSE | BS,NS
886 | Seyring | St. Peter (AT) | Overhead Line | AC | 60 | 380 | 2021 | In Permitting | APG | APG | FALSE | Austria |  |  |  | TRUE | CCE,CCS,CCE
997 Pleinting - St. Peter | Pleinting (DE) | Peterhead | Overhead Line | AC | 60 | 380 | 2024 | In Permitting | TenneT-DE | APG | FALSE | Austria | Germany | 0 | AT - DE | FALSE | CCE,CCS,CCE
NorthConnect | Sima | Emden/East (DE) | Subsea Cable | DC | 655 | 500 | 2022 | In Permitting | Statnett | National Grid (SSEN is TO) | TRUE | Great Britain | Norway | 0 | GB - NO | FALSE | BS,NS
Cluster DolWin6 | Cluster DolWin 6 (NOR-3-3) | DÃ¶rpen/West (DE) | Subsea Cable | DC | 90 | 320 | 2023 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Cluster DolWin 5 (NOR 1-1) | Cluster DolWin 5 (NOR-1-1) | Emden/East | Subsea Cable | DC | 130 | 320 | 2024 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
BorWin3 | Cluster BorWin3 | Emden/East (DE) | Subsea Cable | DC | 160 | 320 | 2019 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
SylWin2 | Cluster SylWin2 (DE) | area of Cloppenburg/East | Subsea Cable | DC | 205 | 320 | 2025 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
DolWin 4 (NOR-3-2) | Cluster DolWin 4 (NOR 3-2) | BÂÃ¼ttel (DE) | Subsea Cable | DC | 190 | 320 | 2028 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Cluster BorWin 5 (NOR-7-1) | Cluster BorWin 5 (NOR-7-1) | area of Cloppenburg/East | Subsea Cable | DC | 250 | 320 | 2025 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
La Plana/Morella-Godelleta | La Plana/Morella | Cartuja (ES) | Overhead Line | AC | 207.5 | 400 | 2025 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
New substation Cartuja | Cartuja (ES) | Arcos | Substation | AC | 0 | 400 | 2029 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
Cartuja-Arcos 400 kV | Cartuja | Petajavesi (FI) | Overhead Line | AC | 30 | 400 | 2029 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
Pyhanselka-Petajavesi | Pyhanselka (FI) | CHAVALON (CH) | Overhead Line | AC | 300 | 400 | 2022-07-01 | In Permitting | Fingrid | Fingrid | FALSE | Finland |  |  |  | TRUE | BS
Cornier - Chavalon 400 kV | CORNIER (FR) |  | Overhead Line | AC | 65 | 400 | 2035 | Under Consideration | RTE | SWISSGRID | FALSE | France | Switzerland | 0 | FR - CH | FALSE | CSW,NS,CCS
R Vitkov | Vitkov (CZ) | Vitkov (CZ) | Substation | AC | 0 | 400 | 2022-11-30 | In Permitting | CEPS |  | FALSE | Czech Republic |  |  |  | TRUE | CCE
Vitkov-Prestice | Vitkov (CZ) |  | Overhead Line | AC | 86 | 400 | 2022-11-30 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
Vernerov-Vitkov | Vernerov (CZ) | Prestice (CZ) | Overhead Line | AC | 71 | 400 | 2025-07-30 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
R Mirovka | Mirovka (CZ) | V413 (CZ) | Substation | AC | 0 | 400 | 2025-09-30 | In Permitting | CEPS |  | FALSE | Czech Republic |  |  |  | TRUE | CCE
Mirkovka-V413 | Mirovka (CZ) | La Plana(ES) | Overhead Line | AC | 27 | 400 | 2019-05-30 | In Permitting | CEPS | CEPS | FALSE | Czech Republic |  |  |  | TRUE | CCE
Morella-La Plana | Morella (ES) | Endersbach (DE) | Overhead Line | AC | 78 | 400 | 2020 | In Permitting | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
Redwitz - Schwandorf | Redwitz (DE) | Altheim (DE) | Overhead Line | AC | 185 | 380 | 2023 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Raitersaich-Altheim | Raitersaich (DE) | GroÃŸgartach (DE) | Overhead Line | AC | 160 | 380 | 2026 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
GroÃŸgartach - Endersbach | GroÃŸgartach (DE) | Schwandorf (DE) | Overhead Line | AC | 0 | 380 | 2025 | Planned but not yet permitting | TransnetBW | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Grafenrheinfeld - GroÃŸgartach | Grafenrheinfeld (DE) | Elsfleht/West (DE) | Overhead Line | AC | 168 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Grafenrheinfeld - GroÃŸgartach |  |  | Overhead Line | AC |  |  |  | Planned but not yet permitting
Emden - Halbemond | Emden/Ost | Wilhelmshaven (DE) | Overhead Line | AC | 30 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Dollern - Elsfleth/West | Dollern (DE) | Emden/Ost | Overhead Line | AC | 100 | 380 | 2026 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Conneforde - Emden | Conneforde | Halbemond | Overhead Line | AC | 60 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Ganderkesee - Wehrendorf | Wehrendorf (DE) | DÃ¶rpen/West (DE) | Overhead Line | AC | 95 | 380 | 2021 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Niederrhein-DÃ¶rpen | Niederrhein (DE) | GÃ¶hl/Siems | Overhead Line | AC | 182 | 380 | 2021 | In Permitting | Amprion | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Conneforde-Wilhelmshaven | Conneforde (DE) | Ganderkesee (DE) | Overhead Line | AC | 30 | 380 | 2020 | In Permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Kreis Segeberg - Siems | Kreis Segeberg | WURMLACH | Overhead Line | AC | 110 | 380 | 2022 | Planned but not yet permitting | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Wurmlach (AT) - Somplago (IT) interconnection | SOMPLAGO | tbd | Underground Cable | AC | 51 | 220 | 2021 | In Permitting | TERNA SPA | Austrian Power Grid AG | TRUE | Austria | Italy | 0 | AT - IT | FALSE | CSE,CCE,CCE
Interco Iceland-UK | tbd | Kofinou Site | Subsea Cable | DC | 1000 | 500 | 2030 | Under Consideration | tbd | tbd | FALSE | Iceland | Great Britain | 0 | IS - GB | FALSE | NS
EuroAsia Interconnector | Korakia (Crete)Site | to be defined (DE) | Subsea Cable | DC | 0 | 500 | 2020 | In Permitting | ADMHE | ADMHE | FALSE | Cyprus | Greece | Isreal | CY - GR | FALSE | CSE
EuroAsia Interconnector | Kofinou Site | Athens Site | Subsea Cable | DC | 0 | 0 | 2021 | In Permitting | TSO Cyprus | ADMHE | FALSE | Cyprus | Greece | Isreal | CY - GR | FALSE | CSE
EuroAsia Interconnector | Hadera Site | Korakia (Crete)Site | Subsea Cable | DC | 0 | 500 | 2020 | In Permitting | IEC | TSO Cyprus | FALSE | Cyprus | Greece | Isreal | CY - GR | FALSE | CSE
2nd interconnecter between Belgium and Germany | to be defined (BE) | Visegrad (BA) | Underground Cable | DC | 0 | 0 | 2028 | Under Consideration | ELIA | AMPRION | FALSE | Belgium | Germany | 0 | BE - DE | FALSE | BS,NS,CCS
400kV OHL B.Basta-Obrenovac | SS Bajina Basta (RS) | Pljevlja (ME) | Overhead Line | AC | 115 | 400 | 2024 | In Permitting | EMS | EMS | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
400kV SS B.Basta upgrade | Bajina Basta (RS) | SS Pljevlja | Substation | AC | 0 | 400 | 2024 | In Permitting | EMS | EMS | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
400kV interconnection RS-ME | Bajina Basta (RS) | Bajina Basta (RS) | Overhead Line | AC | 100 | 400 | 2024 | In Permitting | EMS | CGES | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
400kV interconnection RS-BA | Bajina Basta (RS) | SS Obrenovac (RS) | Overhead Line | AC | 65 | 400 | 2024 | In Permitting | EMS | NOSBIH | FALSE | Serbia | Bosnia & Herzegovina | Montenegro | RS - BA | FALSE | CSE
400 kV OHL Kragujevac-Kraljevo | SS Kragujevac | SS Kraljevo | Overhead Line | AC | 60 | 400 | 2020 | Under Construction | EMS | EMS | FALSE | Serbia | Montenegro |  | RS - MO | TRUE | CSE
Muhlbach Eichstetten | Muhlbach | Zielona GÃ³ra | Overhead Line | AC | 32 | 400 | 2025 | Planned but not yet permitting | RTE | TransnetBW GmbH | FALSE | France | Germany | 0 | FR - DE | FALSE | CSW,NS,CCS
Zielona GÃ³ra - Plewiska | Zielona GÃ³ra | n.a. | Overhead Line | AC | 40 | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
Zielona GÃ³ra | Zielona GÃ³ra | Gubin | Substation | AC | 0 | 400 | >2030 | Under Consideration | PSE S.A. | n.a. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
Zielona GÃ³ra-Gubin | Zielona GÃ³ra | n.a. | Overhead Line | AC | 60 | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
Gubin - Eisenhuettenstadt | Gubin (PL) | Baczyna (PL) | Overhead Line | AC | 20 | 400 | >2030 | Under Consideration | PSE S.A. | 50Hertz | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
Gubin | Gubin | Eisenhuettenstadt (DE) | Substation | AC | 0 | 400 | >2030 | Under Consideration | PSE S.A. | n.a. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
Baczyna-Zielona GÃ³ra | Baczyna-Plewiska indentation | Baczyna-Plewiska indentation | Overhead Line | AC | 40 | 400 | >2030 | Under Consideration | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
MikuÅ‚owa - Åšwiebodzice | MikuÅ‚owa (PL) | n.a. | Overhead Line | AC | 100 | 400 | 2023 | Planned but not yet permitting | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
Krajnik-Baczyna | Krajnik (PL) | Åšwiebodzice (PL) | Overhead Line | AC | 70 | 400 | 2021 | In Permitting | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
Baczyna | Baczyna | Plewiska | Substation | AC | 0 | 400 | 2020 | Under Construction | PSE S.A. | n.a. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS
Baczyna-Plewiska | Baczyna | Tiengen (DE) | Overhead Line | AC | 142 | 400 | 2024 | Planned but not yet permitting | PSE S.A. | PSE S.A. | FALSE | Poland | Germany | 0 | PL - DE | FALSE | CCE,BS,NS,CCS
Conceptual project | - | Dunowo (PL) | Overhead Line | AC | 0 | 400 | 2027 | Under Consideration | REE | REE | FALSE | Spain |  |  |  | TRUE | CSW
DKE-PL-1 | AvedÃ¸re (DKE) | "GroÃŸgartach, Grafenrheinfeld" | Subsea Cable | DC | 330 | 400 | >2030 | Under Consideration | Energinet | PSE | FALSE | Denmark | Poland | 0 | DK - PL | FALSE | BS,NS
HVDC Line C | "BrunsbÃ¼Âttel, Wilster" | Mercator (BE) | Overhead Line | DC | 700 | 520 | 2025 | In Permitting | TenneT-DE | TransnetBW | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
HTLS upgrade Horta-Mercator | Horta (BE) | Tuovila (FI) | Overhead Line | AC | 50 | 380 | 2019-12-31 | Under Construction | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS
Fenno-Skan 1 renewal | Hjalta (SE2) | Wolmirstedt (DE) | Subsea Cable | DC | 200 | 300 | 2029 | Under Consideration | SVK | FINGRID | FALSE | Finland | Sweden | 0 | FI - SE | FALSE | BS
AC Enhancement GÃ¼strow-Wolmirstedt |  |  | Underground Cable | AC |  |  |  | In Permitting |  |  | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Upgrading of existing 220 kV line between SS Dakovo (HR) and TPP Tuzla (BA) to 400 kV line | Dakovo | Gradacac | Overhead Line | AC | 91 | 400 | 2032-12-31 | Under Consideration | HOPS | NOS BIH | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
Upgrading of existing 220 kV line between SS Dakovo (HR) and Gradacac (BA) to 400 kV line | Dakovo | Dakovo | Overhead Line | AC | 46.2 | 400 | 2032-12-31 | Under Consideration | HOPS | NOS BIH | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
Upgrading existing 220 kV SS Dakovo to 400 kV | Dakovo | Razbojiste | Substation | AC | 0 | 400 | 2032-12-31 | Under Consideration | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
New double 400 kV line between SS Dakovo and location Razbojiste | Dakovo | TPP Tuzla (BA) | Overhead Line | AC | 25 | 400 | 2032-12-31 | Under Consideration | HOPS | HOPS | FALSE | Croatia | Bosnia & Herzegovina | 0 | HR - BA | FALSE | CSE
Offshore Connection Cluster 1 | OWF Cluster Baltic Sea East (DE) | Sombor | Subsea Cable | AC | 115 | 220 | 2018 | Under Construction | 50Hertz | 50Hertz | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | Ernestinovo | Uchtelfangen (DE) | Overhead Line | AC | 70 | 400 | 2035-01-01 | Under Consideration | HOPS | EMS | FALSE | Croatia | Serbia | 0 | HR - RS | FALSE | CSE
Vigy - Uchtelfangen (or beyond) | Vigy (FR) | Uchtelfangen (DE) | Overhead Line | AC | 65 | 400 | 2027 | Planned but not yet permitting | Rte | Amprion | FALSE | France | Germany | 0 | FR - DE | FALSE | CSW,NS,CCS
Upgrade Meeden - Diele | Meeden [NL] | Barnabos (FR) | Overhead Line | AC | 27 | 380 | 2019 | Under Construction | TENNET-NL | TENNET-DE | FALSE | Netherlands | Germany | 0 | NL - DE | FALSE | NS,CCS
AQUIND Interconnector | Lovedean (GB) | Lubmin (DE) | Subsea Cable | DC | 250 | 320 | 2022 | In Permitting | National Grid plc | RÃ©seau de transport d'Ã©lectricitÃ© | TRUE | France | Great Britain | 0 | FR - GB | FALSE | CSW,NS
Offshore Connection Cluster 2 | OWF Cluster Baltic Sea (DE) | SiedenbrÃ¼nzow/Alt Telin/Bartow (DE) | Subsea Cable | AC | 115 | 220 | 2022 | In Permitting | 50Hertz | 50Hertz | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
"Merchant line ""Castasegna (CH) - Mese (IT)""" | Castasegna | Hamburg/Nord (DE) | Underground Cable | AC | 0 | 220 | 2021 | In Permitting | swissgrid | Terna | TRUE | Italy | Switzerland | 0 | IT - CH | FALSE | CSE,CCS
Dollern - Hamburg/Nord | Dollern (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 45 | 380 | 2018 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Audorf - Hamburg/Nord | Audorf (DE) | Gramme | Overhead Line | AC | 65 | 380 | 2017 | Under Construction | TenneT-DE | TenneT-DE | FALSE | Germany |  |  |  | TRUE | CCE,BS,NS,CCS
Van Eyck - Gramme: HTLS upgrade | Van Eyck | Van Eyck (BE) | Overhead Line | AC | 90 | 380 | 2029-12-31 | Under Consideration | ELIA | ELIA | FALSE | Belgium |  |  |  | TRUE | NS